## Sheet1
LAP 12SP-604A-06
[6 empty] | REPORT NUMBER: |  |  | 601 | SHEET: |  | 1 | OF | 1
CONCRETE QA CORRELATION
3031 W. Grand Blvd. Suite 228
Detroit, MI 48202
PROJECT NAME: | HMA Resurfacing 20 + Locations |  |  |  | DATE: |  |  |  |  | 2020-10-26
MDOT CONTROL SECTION: | 8200 |  |  |  | SOMAT JOB NUMBER: |  |  |  |  | 2019086C
MDOT JOB NUMBER: | 205935A,207914A |  |  |  | CLIENT: |  |  |  |  | HRC
PROJECT ENGINEER: | Kevin Surhigh |  |  |  | CONTRACTOR: |  |  |  |  | Merlo Construction
INSPECTOR: | Anthony Carrier |  |  |  | CITY:
QC TESTER: | Gilbert Guzman |  |  |  | QC COMPANY: |  |  |  |  | CTI
CONCRETE INFORMATION
CONCRETE COMPANY: | Superior Materials |  |  | TRUCK NUMBER: | [5 empty] | 9127
MIX DESIGN #: | P155E7CQA032 |  |  | PLANT LOCATION (CITY): | [5 empty] | Detroit
CONCRETE GRADE: | P1 |  |  | TOTAL QUANTITY (CYDS): | [5 empty] | 30
PWL/NON-PWL: | Non PWL |  |  | QUANTITY AT SAMPLE (CYDS): | [5 empty] | 10
POUR LOCATION (STATION, STRUCTURE, ETC…)
Used for curb at M-39/Southfield Road Service Drive NB from Paul Street to Joy Road.
TEST RESULTS
| QC (CONTRACTOR) |  | QA (SOMAT) |  |  |  | TOLERANCE |  |  |  | MEETS TOLERANCE (Y/N)
SAMPLE TIME (Hrs/Min): | 9:52AM |  | 9:52AM
AIR CONTENT (%): | 6.8 |  | 7 |  |  |  | +/- 0.8 PERCENT |  |  |  | Yes
CONCRETE TEMP. (°F): | 64 |  | 65 |  |  |  | +/- 2.0 DEGREES |  |  |  | Yes
AIR TEMP. (°F): | 44 |  | 44
REMARKS:
Both QA and QC field technicians performed correlation test and the results are within tolerance.
FIELD REPRESENTATIVE: | Jose M. Vinuya | [6 empty] | DATE: |  | 2020-10-26
PROJECT MANAGER(s): | Steve Drummond,P.E. | [6 empty] | DATE: |  | 2020-10-26
|  | Infrastructure Engineering Solutions | [10 empty] | 601 (01/18)