## RFIs
Bagley Streetscape_RFI Log
Contractor |  | Major Cement Company |  | Project Number | PW-7007 |  |  |  | Please do not delete this column. This is supporting information to choose Type of Submittal
Document Type
Item No. | Drawing/ Spec Reference | Description | Type of Submittal | Received from Contractor | Returned to Contractor | Action | Reviewed By | Notes
Bill Of Quantities
1 | Plan Sheet 5 + Concrete Pavers on Concrete and HMA Bed SP | Request to use sand in lieu of HMA for the concrete paver setting bed. | RFI | 2019-07-18 | AAN | NET | DPW | Warranty, credit, schedule savings. | Brief
2 | Specification for Tree Grate | Confirmation on tree grate size | RFI | 2019-08-05 | 2019-08-08 |  | WSP |  | Calculations
3 | Sheet UG-01 and IN-01 | Various lighting questions | RFI | 2019-08-06 | 2019-12-11 |  | PLA/CEA |  | Certificate
4 | Sheet 20 and 23 | Storm sewer revisions/utility conflict | RFI | 2019-08-30 | 2019-09-05 |  | WSP | Sewer Revisions provided 09/05, Grading Revisions provided 09/07. | Contracts
5 | Sheet 8 + Typical Joint Layout Detail | Cp Joints vs C3p Joints | RFI | 2019-09-05 | 2019-09-09 |  | WSP/AECOM | Direction given on site 09/16.
6 | Grading Sheet 28 | Grades at La Gloria parking lot tie in | RFI | 2019-09-24 | 2019-09-27 |  | WSP/AECOM
7 | Lighting Fixtures | Hapco questions | RFI | 2019-10-08 | 2019-10-15 |  | PLA/CEA
8 | Sheet 44 | ADA Paver Thickness | RFI | 2019-10-11 | 2019-10-15 |  | AECOM/DPW
9 | Sheet 20 | Storm sewer revisions 24th intersection | RFI | 2019-10-26 | 2019-11-04 |  | AECOM/WSP | Field direction provided 11/04. Work completed. Major Cement to prepare As-Builts to share with DWSD.
10 | DT-13.10 | Power Supply Pole Installation | RFI | 2019-11-15 | 2019-11-25 |  | PLA/CEA
Cost Estimate
Schedule
Scope Of Works
Shop Drawing
Sketch
Snag List