## Submittals
Bagley Streetscape_Submittal Log
Contractor |  | Major Cement Company |  | Project Number | PW-7007
Item No. | Drawing/ Spec Reference | Description | Type of Submittal | Action Code: NET = No exception taken; AAN = Approved as noted - Revise and resubmit for record; RAR = Revise and resubmit; REJ = Rejected; NA = Review not required; |  |  |  | Notes
|  |  |  | Received from Contractor | Returned to Contractor | Action | Action Required By
1 |  | Safety Program | Plan | 2019-07-19 | N/A | NET
2 |  | List of Subcontractors | Plan | 2019-07-19 | N/A | NET
3 |  | EEO Officer | Plan | 2019-07-19 | N/A | NET
4 |  | Damage Claim Program | Plan | 2019-07-19 | 2019-08-27 | RAR |  | needs resubmittal
5 |  | Concrete QC Plan | Plan | 2019-07-23 | 2019-08-02 | RAR
5.1 |  | Concrete QC Plan - R1 | Plan | 2019-08-14 | 2019-08-14 | RAR
5.2 |  | Concrete QC Plan - R2 | Plan | 2019-09-03 | 2019-09-05
6 |  | Vibration Monitoring Plan | Plan | 2019-08-06 | 2019-08-27 | RAR |  | needs resubmittal
7 |  | Concrete Mix Designs | Mix Design | 2019-08-13 | 2019-08-14 | RAR
7.1 |  | Concrete Mix Designs - R1 | Mix Design | 2019-08-16 | 2019-08-19 | AAN
8 |  | Bike Racks and Trash Receptacles | Shop Drawing/Product Data | 2019-08-13 | 2019-08-15 | AAN
9 |  | Silt Sack, Concrete Storm Manholes, HDPE Pipe, DI Water Main Fittings | Shop Drawing/Product Data | 2019-08-13 |  | NET
10 |  | Light Fdn Mix Design | Mix Design | 2019-08-23 | 2019-08-26 | RAR |  | Plant M-11 AAN; Plant M-40 RAR; needs resubmittal
11 |  | Light Fixtures | Shop Drawing/Product Data | 2019-08-16 | 2019-09-05 | NET
12 |  | Tree Grates | Shop Drawing/Product Data | 2019-08-24 | 2019-08-27 | NET
13 |  | Castings | Shop Drawing/Product Data | 2019-08-24 |  | NET
14 |  | Hydrant + Gate Valve | Shop Drawing/Product Data | 2019-08-24 |  | NET
15 |  | Polyurethane Sealant | Product Data | 2019-09-10 | 2019-10-15 | AAN
16 |  | Concrete Mix Designs - Updated | Mix Design | 2019-09-23 | 2019-09-26 | RAR |  | Plant M-40 AAN; Plant M-10 RAR; needs resubmittal
17 |  | Polymeric Sand Color | Product Data | 2019-09-23 | 2019-10-15 | AAN
18 |  | Landscape Product Data | Product Data | 2019-10-15 | 2019-10-18 | RAR
18.1 |  | Landscape Product Data - R1 | Product Data | 2019-10-23 | 2019-10-23 | AAN
19 |  | Plant Source List | Product Data | 2019-10-17 |  |  | AECOM/WSP | livingLAB tagged all trees; this submittal can be closed.
20 |  | Cold Weather Concrete | Mix Design | 2019-11-08 | 2019-11-11 | RAR
20.1 |  | Cold Weather Concrete - R1 | Mix Design | 2019-11-12 | 2019-11-14 | AAN |  | P1 mixes AAN; PNC mixes rejected;

## Submittal Type
Document Type | attachment
As-built Drawing | Please do not delete this column. This is supporting information to choose Type of Submittal
Bill Of Quantities
Brief
Calculations
Certificate | Document Type
Contracts | As-built Drawing
Cost Estimate | Bill Of Quantities
Data Sheets | Brief
Defect List | Calculations
Drawings | Certificate
Employers Instruction | Contracts
Engineer’s Instruction | Cost Estimate
Evaluation | Product Data
Form | Defect List
Guidelines | Drawings
Inspection Request | Employers Instruction
Invoice | Engineer’s Instruction
Manual | Evaluation
Master Plan | Form
Matrix | Guidelines
Method Statement | Inspection Request
Model | Invoice
Non-Conformance Report | Manual
No-Objection Certificate | Master Plan
Payment Certificates | Matrix
Performance Bond | Method Statement
Permit | Model
Photograph | Non-Conformance Report
Plan | No-Objection Certificate
Policy | Payment Certificates
Presentation | Performance Bond
Procedure | Permit
Proposal | Photograph
Register | Plan
Report | Policy
Request for Change | Presentation
Risk Register | Procedure
Sample | Register
Schedule | Report
Scope Of Works | Risk Register
Shop Drawing | Sample
Sketch | Schedule
Snag List | Scope Of Works
Specification | Shop Drawing
Standards | Sketch
Survey | Snag List
Tender
Variation Order
Work Instruction
Client Advice
Confirmation of Verbal Instruction
Notice to Proceed
Request for Information
Response to RFI
Transmittal