## Table 1
Contract ID: PW-7023 - Conner Ave HMA Resurfacing & Bike Trail in the City of Detroit
Cont. Mod. No. | Rev. No. | Cont. Mod. Date | Status | Approval Date | Short Description | Net Change Amount
1 |  | 2021-02-18 | Approved | 2021-03-23 | Adding Temporary Pavement Markings | 13290.19
2 |  | 2021-05-04 | Approved | 2021-05-06 | Balancing Original Items | 32733.13
3 |  | 2021-07-13 | Approved | 2021-07-20 | Budgeting Original Item increase and adding New Items | 39995
4 |  | 2021-10-18 | Approved | 2021-11-02 | Balancing Original Items and adding New Items | 106496.99
5 |  | 2022-02-03 | Approved | 2022-02-10 | Balancing Original Items and adding New Items | -14093.72
6 |  | 2022-07-12 | Approved | 2022-08-23 | Balancing items over authorized quantity | 27730.48
7 |  | 2022-12-13 | Approved | 2023-01-03 | Final balancing and one new item | -35862.94
8 |  | 2023-08-15 | Approved | 2023-08-16 | Final balancing | 17207.2
Total Net Change Amount | [5 empty] | 187496.34
|  | Awarded Contract Amount |  |  | 2682460.88
|  | Net Change Amount (Auth) |  |  | 187496.34 | ( + )
|  | Current Contract Amount |  |  | 2869957.22
|  | Amount Paid to Date (PE 001 - PE 013) |  |  | 2869957.22
|  | Current Contract Amount |  |  | 2869957.22 | ( - )
|  | Net Change Amount |  |  | 0