## Sheet1
| Somat Engineering, Inc. | [10 empty] | LAP 12SP-604A-09
[7 empty] | REPORT NUMBER: |  |  | 601 | SHEET: |  | 1 | OF | 1
CONCRETE QA CORRELATION
26445 Northline Rd, Taylor, MI 48180 Tel: 734-946-4966 Fax: 734-946-1147
DATE: |  | 2021-06-24 |  |  |  | CLIENT: |  |  |  |  | AECOM
MDOT CONTROL SECTION: |  | N/A |  |  |  | PROJECT ENGINEER: |  |  |  |  | Alan Ostrowski, P.E.
MDOT JOB NUMBER: |  | N/A |  |  |  | INSPECTOR: |  |  |  |  | Steve Szalkie
SOMAT JOB NUMBER: |  | 2019057D-002 (PW-7023) |  |  |  | CONTRACTOR: |  |  |  |  | Ajax
PROJECT NAME: |  | Conner Improvements |  |  |  | QC COMPANY: |  |  |  |  | CCT
CITY: |  | Detroit, MI |  |  |  | QC TESTER: |  |  |  |  | Mike
CONCRETE INFORMATION
CONCRETE COMPANY: |  | Titan Concrete |  |  | TRUCK NUMBER: | [5 empty] | 2101
MIX DESIGN #: |  | P1-DETM-1 |  |  | PLANT LOCATION (CITY): | [5 empty] | Plant #4
CONCRETE GRADE: |  | P1 |  |  | TOTAL QUANTITY (CYDS): | [5 empty] | 110
PWL/NON-PWL: |  | NON PWL |  |  | QUANTITY AT SAMPLE (CYDS): | [5 empty] | 1
POUR LOCATION (STATION, STRUCTURE, ETC…)
Sidewalk and bike path from 22+60 to 19+11, Kercheval bus stop/sidewalk.
TEST RESULTS
|  | QC (CONTRACTOR) |  | QA (SOMAT) |  |  |  | TOLERANCE |  |  |  | MEETS TOLERANCE (Y/N)
SAMPLE TIME (Hrs/Min): |  | 7:25am
AIR CONTENT (%): |  | 5.6 |  | 5.8 |  |  |  | +/- 0.8 PERCENT |  |  |  | YES
CONCRETE TEMP. (°F): |  | 76 |  | 76 |  |  |  | +/- 2.0 DEGREES |  |  |  | YES
AIR TEMP. (°F): |  | 68 |  | 68
REMARKS:
110 yards place, made two sets of two 4x8 clyinders thirds set was made by Brandon Smith.
FIELD REPRESENTATIVE: |  | Jaden Riley | [6 empty] | DATE: |  | 2021-06-24
PROJECT MANAGER(s): |  | Steve Drummond, P.E. | [6 empty] | DATE:
*All results noted in this report relate only to items inspected or tested by Somat Engineering, Inc. and/or Somat Engineering of Ohio, Inc. (Somat). This report shall not be reproduced, except in full, without the prior written approval of Somat.
|  |  | Infrastructure Engineering Solutions | [10 empty] | 601 (12/18)

## Sheet2 (hidden)
4039 40th St SE, Suite 4, Grand Rapids, MI 49512 Tel: 616-575-9230 Fax: 616-575-9236
26445 Northline Rd, Taylor, MI 48180 Tel: 734-946-4966 Fax: 734-946-1147
3031 W. Grand Blvd, Suite 228, Detroit, MI 48202 Tel: 313-963-2721 Fax: 313-963-2736
7125 Orchard Lake Rd, Suite 104, West Bloomfield, MI 48322 Tel: 248-562-7129 Fax: 248-562-7237
950 Keynote Circle, Unit 70, Brooklyn Heights, OH 44131 Tel: 216-479-0300 Fax: 216-479-0301
1100 Superior Avenue, Suite 2020, Cleveland, OH 44114 Tel: 216-706-6870 Fax: 216-479-0301
Somat Engineering, Inc.
Somat Engineering of Ohio, Inc.
YES
NO