## Sheet1
Contract ID: PW-7005 - Kercheval Streetscape in the City of Detroit
[9 empty] | AWARDED CONTRACT AMOUNT | 7523467.26
Item Description | Units | Item Code | Prop. Line | Quantity Placed | Quantity Paid | Authorized Quantity | Initial Quantity | Pending Changes | Unit Price | Auth. Amount | Placed Amount | % Cont. Amt. (awrd) | Item Cpt | Item Type | Cont. Mod. Number
Mobilization, Max 5% | LS | 1500001 | 10 | 1 | 1 | 1 | 1 | 0 | 350000 | 350000 | 350000 | 4.7% | Yes | Original
Tree, Rem, 6 inch to 18 inch | Ea | 2020004 | 20 | 6 | 6 | 6 | 6 | 0 | 500 | 3000 | 3000 | 0% | Yes | Original
Dr Structure, Rem | Ea | 2030011 | 30 | 5 | 5 | 5 | 1 | 0 | 800 | 4000 | 4000 | 0.1% | Yes | Original
Sewer, Rem, Less than 24 inch | Ft | 2030015 | 40 | 8 | 8 | 8 | 100 | 0 | 30 | 240 | 240 | 0% | Yes | Original
Fence, Rem | Ft | 2040025 | 50 | 0 | 0 | 0 | 10 | 0 | 40 | 0 | 0 | 0% | Yes | Original
Pavt, Rem | Syd | 2040050 | 60 | 4151.27 | 4151.27 | 4151.27 | 2647 | 0 | 28 | 116235.56 | 116235.56 | 1.5% | Yes | Original
Sidewalk, Rem | Syd | 2040055 | 70 | 8107.23 | 8107.23 | 8107.23 | 5828 | 0 | 18 | 145930.14 | 145930.14 | 1.9% | Yes | Original
Utility Pole, Rem | Ea | 2040070 | 80 | 0 | 0 | 0 | 10 | 0 | 1000 | 0 | 0 | 0% | Yes | Original
Curb, Rem Modified | Ft | 2040021 | 90 | 10349.33 | 10349.33 | 10349.33 | 5512 | 0 | 16 | 165589.28 | 165589.28 | 2.2% | Yes | Original
Non Haz Contam Mat'l Handling & Disp, LM | Cyd | 2050031 | 100 | 0 | 0 | 0 | 10 | 0 | 100 | 0 | 0 | 0% | Yes | Original
Excavation, Earth Modified | Cyd | 2050016 | 110 | 1598.02 | 1598.02 | 1598.02 | 10 | 0 | 52 | 83097.04 | 83097.04 | 1.1% | Yes | Original
Erosion Control, Sediment Trap | Ea | 2080034 | 120 | 60 | 60 | 60 | 34 | 0 | 140 | 8400 | 8400 | 0.1% | Yes | Original
Erosion Control, Silt Fence | Ft | 2080036 | 130 | 0 | 0 | 0 | 1396 | 0 | 2.75 | 0 | 0 | 0% | Yes | Original
Subbase, CIP | Cyd | 3010002 | 140 | 0 | 0 | 0 | 10 | 0 | 100 | 0 | 0 | 0% | Yes | Original
Aggregate Base | Ton | 3020001 | 150 | 964.52 | 964.52 | 964.52 | 450 | 0 | 52 | 50155.04 | 50155.04 | 0.7% | Yes | Original
Aggregate Base, 6 inch | Syd | 3020016 | 160 | 10126.55 | 10126.55 | 10126.55 | 5620 | 0 | 14 | 141771.7 | 141771.7 | 1.9% | Yes | Original
Sewer, Cl IV, 12 inch, Tr Det B | Ft | 4020987 | 170 | 355 | 355 | 355 | 120 | 0 | 100 | 35500 | 35500 | 0.5% | Yes | Original
Dr Structure, Tap, 12 inch | Ea | 4030312 | 180 | 3 | 3 | 3 | 4 | 0 | 1000 | 3000 | 3000 | 0% | Yes | Original
_ Dr Structure Lead, Cleaning, Modified | Ft | 4037001 | 190 | 480 | 480 | 480 | 3695 | 0 | 4.3 | 2064 | 2064 | 0% | Yes | Original
_ Dr Structure, Adj., Add Depth, Modified | Ft | 4037001 | 200 | 2 | 2 | 2 | 2 | 0 | 740 | 1480 | 1480 | 0% | Yes | Original
Dr Structure, 48 inch dia Streetscape | Ea | 4030210 | 210 | 6 | 6 | 6 | 3 | 0 | 4000 | 24000 | 24000 | 0.3% | Yes | Original
Dr Structure, Cleaning Modified | Ea | 4030290 | 220 | 50 | 50 | 50 | 50 | 0 | 200 | 10000 | 10000 | 0.1% | Yes | Original
Dr Structure Cover, Adj, Case 1 Modified | Ea | 4030005 | 230 | 357 | 357 | 357 | 309 | 0 | 800 | 285600 | 285600 | 3.8% | Yes | Original
_ Dr Structure Cover, Modified | Ea | 4037050 | 240 | 15 | 15 | 15 | 11 | 0 | 2000 | 30000 | 30000 | 0.4% | Yes | Original
Dr Structure, 48 inch dia | Ea | 4030210 | 250 | 2 | 2 | 2 | 1 | 0 | 7000 | 14000 | 14000 | 0.2% | Yes | Original
_ Reconstruct Dr Structure, Case 1, Modified | Ea | 4037050 | 260 | 23 | 23 | 23 | 28 | 0 | 1200 | 27600 | 27600 | 0.4% | Yes | Original
Underdrain, Pipe, Open-Graded, 4 inch | Ft | 4040041 | 270 | 0 | 0 | 0 | 340 | 0 | 21 | 0 | 0 | 0% | Yes | Original
Underdrain, Subbase, 4 inch | Ft | 4040061 | 280 | 2931 | 2931 | 2931 | 2126 | 0 | 21 | 61551 | 61551 | 0.8% | Yes | Original
HMA Surface, Rem | Syd | 5010005 | 290 | 2903.8 | 2903.8 | 2903.8 | 5347 | 0 | 7 | 20326.6 | 20326.6 | 0.3% | Yes | Original
Pavt for Butt Joints, Rem | Syd | 5010008 | 300 | 424.62 | 424.62 | 424.62 | 778 | 0 | 4 | 1698.48 | 1698.48 | 0% | Yes | Original
Hand Patching | Ton | 5010025 | 310 | 22 | 22 | 22 | 28 | 0 | 350 | 7700 | 7700 | 0.1% | Yes | Original
HMA, 4E3 | Ton | 5010051 | 320 | 8616.13 | 8616.13 | 8616.13 | 8672 | 0 | 118 | 1016703.34 | 1016703.34 | 13.5% | Yes | Original
HMA, 5E3 | Ton | 5010057 | 330 | 6441.53 | 6441.53 | 6441.53 | 6397 | 0 | 142 | 914697.26 | 914697.26 | 12.2% | Yes | Original
Cold Milling HMA Surface | Syd | 5010002 | 340 | 83409.58 | 83409.58 | 83409.58 | 80140 | 0 | 6 | 500457.48 | 500457.48 | 6.7% | Yes | Original
_ Conditioning Existing Pavement, Modified | Ton | 5017031 | 350 | 166.21 | 166.21 | 166.21 | 953 | 0 | 160 | 26593.6 | 26593.6 | 0.4% | Yes | Original
_ HMA Approach, Driveway, Modified | Ton | 5017031 | 360 | 144.86 | 144.86 | 144.86 | 643 | 0 | 240 | 34766.4 | 34766.4 | 0.5% | Yes | Original
_ HMA Approach, Modified | Ton | 5017031 | 370 | 689.34 | 689.34 | 689.34 | 736 | 0 | 165 | 113741.1 | 113741.1 | 1.5% | Yes | Original
Conc Pavt, Misc, Nonreinf, 8 inch | Syd | 6020054 | 380 | 528.34 | 528.34 | 528.34 | 801 | 0 | 82 | 43323.88 | 43323.88 | 0.6% | Yes | Original
Conc Base Cse, Nonreinf, 9 inch | Syd | 6020021 | 390 | 1217.13 | 1217.13 | 1217.13 | 1580 | 0 | 102 | 124147.26 | 124147.26 | 1.7% | Yes | Original
_ Concrete Repr, Nonreinf Conc, 10 inch, Modified | Syd | 6027011 | 400 | 401.43 | 401.43 | 401.43 | 200 | 0 | 117 | 46967.31 | 46967.31 | 0.6% | Yes | Original
Pavt Repr, Rem | Syd | 6030080 | 410 | 289.44 | 289.44 | 289.44 | 190 | 0 | 40 | 11577.6 | 11577.6 | 0.2% | Yes | Original
Driveway, Nonreinf Conc, 8 inch Modified | Syd | 8010007 | 420 | 857.23 | 857.23 | 857.23 | 523 | 0 | 84 | 72007.32 | 72007.32 | 1% | Yes | Original
Valley Gutter, Conc Modified | Ft | 8020060 | 430 | 194.5 | 194.5 | 194.5 | 231 | 0 | 48 | 9336 | 9336 | 0.1% | Yes | Original
_ Conc Curb, Detail CD, Modified | Ft | 8027001 | 440 | 1853.69 | 1853.69 | 1853.69 | 1816 | 0 | 40 | 74147.6 | 74147.6 | 1% | Yes | Original
_ Integral Curb and Sidewalk, 1.5 foot | Ft | 8027001 | 450 | 4933.66 | 4933.66 | 4933.66 | 3605 | 0 | 40 | 197346.4 | 197346.4 | 2.6% | Yes | Original
_ Integral Curb and Sidewalk, 2 foot | Ft | 8027001 | 460 | 72 | 72 | 72 | 1451 | 0 | 42 | 3024 | 3024 | 0% | Yes | Original
_ Curb Ramp Opening, Conc | Ft | 8027001 | 470 | 4128.5 | 4128.5 | 4128.5 | 2323 | 0 | 48 | 198168 | 198168 | 2.6% | Yes | Original
_ Detectable Warning Surface, Modified | Ft | 8037001 | 480 | 1028 | 1028 | 1028 | 1005 | 0 | 40 | 41120 | 41120 | 0.5% | Yes | Original
Sidewalk Ramp, Conc, 6 inch Modified | Sft | 8030036 | 490 | 15799.06 | 15799.06 | 15799.06 | 18111 | 0 | 11 | 173789.66 | 173789.66 | 2.3% | Yes | Original
Sidewalk, Conc, 4 inch Modified | Sft | 8030044 | 500 | 29024.93 | 29024.93 | 29024.93 | 18648 | 0 | 6 | 174149.58 | 174149.58 | 2.3% | Yes | Original
Sidewalk, Conc, 6 inch Modified | Sft | 8030046 | 510 | 34682.06 | 34682.06 | 34682.06 | 24634 | 0 | 8 | 277456.48 | 277456.48 | 3.7% | Yes | Original
_ Decorative Railing | Ft | 8037001 | 520 | 227 | 227 | 227 | 238 | 0 | 228.53 | 51876.31 | 51876.31 | 0.7% | Yes | Original
Band, Sign | Ea | 8100010 | 530 | 53 | 53 | 53 | 77 | 0 | 45 | 2385 | 2385 | 0% | Yes | Original
Post Hole Through Conc for Steel Post | Ea | 8100340 | 540 | 22 | 22 | 22 | 37 | 0 | 75 | 1650 | 1650 | 0% | Yes | Original
Post, Steel, 3 lb | Ft | 8100371 | 550 | 484 | 484 | 484 | 700 | 0 | 10 | 4840 | 4840 | 0.1% | Yes | Original
Sign, Type III, Erect, Salv | Ea | 8100402 | 560 | 34 | 34 | 34 | 30 | 0 | 50 | 1700 | 1700 | 0% | Yes | Original
Sign, Type III, Rem | Ea | 8100403 | 570 | 82 | 82 | 82 | 82 | 0 | 25 | 2050 | 2050 | 0% | Yes | Original
Sign, Type IIIA | Sft | 8100404 | 580 | 258.6 | 258.6 | 258.6 | 191 | 0 | 22 | 5689.2 | 5689.2 | 0.1% | Yes | Original
Sign, Type IIIB | Sft | 8100405 | 590 | 85.05 | 85.05 | 85.05 | 223 | 0 | 22 | 1871.1 | 1871.1 | 0% | Yes | Original
Mast Arm Pole, Cat II | Ea | 8100511 | 600 | 4 | 4 | 4 | 4 | 0 | 6407 | 25628 | 25628 | 0.3% | Yes | Original
Mast Arm, 25 foot, Cat II | Ea | 8100531 | 610 | 2 | 2 | 2 | 2 | 0 | 4511 | 9022 | 9022 | 0.1% | Yes | Original
Mast Arm, 30 foot, Cat II | Ea | 8100532 | 620 | 1 | 1 | 1 | 1 | 0 | 9971 | 9971 | 9971 | 0.1% | Yes | Original
Mast Arm, 40 foot, Cat II | Ea | 8100534 | 630 | 1 | 1 | 1 | 1 | 0 | 11646 | 11646 | 11646 | 0.2% | Yes | Original
Mast Arm, 45 foot, Cat II | Ea | 8100535 | 640 | 1 | 1 | 1 | 1 | 0 | 12022 | 12022 | 12022 | 0.2% | Yes | Original
Mast Arm Pole Fdn, 6 Bolt | Ft | 8100550 | 650 | 68 | 68 | 68 | 68 | 0 | 630 | 42840 | 42840 | 0.6% | Yes | Original
Rem Spec Mrkg | Sft | 8110343 | 660 | 114 | 114 | 114 | 460 | 0 | 4 | 456 | 456 | 0% | Yes | Original
_ Pavt Mrkg, Modified Urethane, 12 inch, Crosswalk | Ft | 8117001 | 670 | 13350 | 13350 | 13350 | 14410 | 0 | 5.95 | 79432.5 | 79432.5 | 1.1% | Yes | Original
_ Pavt Mrkg, Modified Urethane, 12 inch, Cross Hatching, White | Ft | 8117001 | 680 | 13959 | 13959 | 13959 | 13774 | 0 | 5.95 | 83056.05 | 83056.05 | 1.1% | Yes | Original
_ Pavt Mrkg, Modified Urethane, 4 inch, White | Ft | 8117001 | 690 | 7660 | 7660 | 7660 | 42985 | 0 | 0.75 | 5745 | 5745 | 0.1% | Yes | Original
_ Pavt Mrkg, Modified Urethane, 4 inch, Yellow | Ft | 8117001 | 700 | 184 | 184 | 184 | 25492 | 0 | 0.75 | 138 | 138 | 0% | Yes | Original
_ Pavt Mrkg, Modified Urethane, 18 inch, Stop Bar | Ft | 8117001 | 710 | 460 | 460 | 460 | 553 | 0 | 10 | 4600 | 4600 | 0.1% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, 12 inch, White | Ft | 8117001 | 720 | 1031 | 1031 | 1031 | 1222 | 0 | 9 | 9279 | 9279 | 0.1% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, 4 inch, Yellow | Ft | 8117001 | 730 | 3120 | 3120 | 3120 | 3221 | 0 | 3 | 9360 | 9360 | 0.1% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, 6 inch, White | Ft | 8117001 | 740 | 112 | 112 | 112 | 100 | 0 | 4 | 448 | 448 | 0% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacting, Green | Sft | 8117010 | 750 | 17771.4 | 17771.4 | 17771.4 | 16910 | 0 | 9 | 159942.6 | 159942.6 | 2.1% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacting, Red | Sft | 8117010 | 760 | 1654 | 1654 | 1654 | 1728 | 0 | 11 | 18194 | 18194 | 0.2% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Speed Table Sym | Ft | 8117001 | 770 | 13 | 13 | 13 | 10 | 0 | 100 | 1300 | 1300 | 0% | Yes | Original
_ Pavt Mrkg, Modified Urethane, Left Turn Arrow Symbol | Ft | 8117001 | 780 | 10 | 10 | 10 | 13 | 0 | 175 | 1750 | 1750 | 0% | Yes | Original
_ Pavt Mrkg, Modified Urethane, Only | Ft | 8117001 | 790 | 12 | 12 | 12 | 15 | 0 | 175 | 2100 | 2100 | 0% | Yes | Original
_ Pavt Mrkg, Modified Urethane, Rt Turn Arrow Symbol | Ft | 8117001 | 800 | 2 | 2 | 2 | 2 | 0 | 175 | 350 | 350 | 0% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Bike Left Turn Arrow | Ft | 8117001 | 810 | 5 | 5 | 5 | 5 | 0 | 200 | 1000 | 1000 | 0% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Bike Right Turn Arrow | Ft | 8117001 | 820 | 5 | 5 | 5 | 5 | 0 | 200 | 1000 | 1000 | 0% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Bike, Bike Turn Sym | Ft | 8117001 | 830 | 5 | 5 | 5 | 5 | 0 | 200 | 1000 | 1000 | 0% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Bike, Small Sym | Ft | 8117001 | 840 | 118 | 118 | 118 | 120 | 0 | 180 | 21240 | 21240 | 0.3% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Bus | Ft | 8117001 | 850 | 8 | 8 | 8 | 8 | 0 | 180 | 1440 | 1440 | 0% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Directional Arrow Sym, Bike | Ft | 8117001 | 860 | 118 | 118 | 118 | 120 | 0 | 180 | 21240 | 21240 | 0.3% | Yes | Original
_ Pavt Mrkg, Polymer Cement Surfacing, Stop | Ft | 8117001 | 870 | 8 | 8 | 8 | 8 | 0 | 200 | 1600 | 1600 | 0% | Yes | Original
_ Post, Delineator, 36 inch, Green | Ea | 8107050 | 880 | 680 | 680 | 680 | 768 | 0 | 110 | 74800 | 74800 | 1% | Yes | Original
Barr,TypeIII,HighInten,DblSided,Furn | Ea | 8120010 | 890 | 40 | 40 | 40 | 180 | 0 | 125 | 5000 | 5000 | 0.1% | Yes | Original
Barr,Type III,High Inten,Dbl Sided,Oper | Ea | 8120011 | 900 | 40 | 40 | 40 | 180 | 0 | 0.01 | 0.4 | 0.4 | 0% | Yes | Original
Lighted Arrow, Type C, Furn | Ea | 8120140 | 910 | 0 | 0 | 0 | 2 | 0 | 750 | 0 | 0 | 0% | Yes | Original
Lighted Arrow, Type C, Oper | Ea | 8120141 | 920 | 0 | 0 | 0 | 2 | 0 | 0.01 | 0 | 0 | 0% | Yes | Original
Pavt Mrkg, Longit, 6"or Less Width, Rem | Ft | 8120210 | 930 | 27984 | 27984 | 27984 | 16070 | 0 | 0.59 | 16510.56 | 16510.56 | 0.2% | Yes | Original
Pavt Mrkg,Type NR,Tape,4inch,White,Temp | Ft | 8120230 | 940 | 46709 | 46709 | 46709 | 9390 | 0 | 0.59 | 27558.31 | 27558.31 | 0.4% | Yes | Original
Pavt Mrkg,Type NR,Tape,4inch,Yellow,Temp | Ft | 8120231 | 950 | 55069 | 55069 | 55069 | 17560 | 0 | 0.59 | 32490.71 | 32490.71 | 0.4% | Yes | Original
PavtMrkg,WtRef,Type R, Tape,4 in,Wh,Temp | Ft | 8120245 | 960 | 1190 | 1190 | 1190 | 11880 | 0 | 1.85 | 2201.5 | 2201.5 | 0% | Yes | Original
PavtMrkg,WtRef,Type R, Tape,4 in,Ye,Temp | Ft | 8120246 | 970 | 0 | 0 | 0 | 21210 | 0 | 1.85 | 0 | 0 | 0% | Yes | Original
Plastic Drum, High Intensity, Furn | Ea | 8120250 | 980 | 410 | 410 | 410 | 510 | 0 | 30 | 12300 | 12300 | 0.2% | Yes | Original
Plastic Drum, High Intensity, Oper | Ea | 8120251 | 990 | 410 | 410 | 410 | 510 | 0 | 0.01 | 4.1 | 4.1 | 0% | Yes | Original
Sign, Portable, Changeable Message, Furn | Ea | 8120330 | 1000 | 2 | 2 | 2 | 2 | 0 | 6000 | 12000 | 12000 | 0.2% | Yes | Original
Sign, Portable, Changeable Message, Oper | Ea | 8120331 | 1010 | 2 | 2 | 2 | 2 | 0 | 0.01 | 0.02 | 0.02 | 0% | Yes | Original
Sign, Type B, Temp, Prismatic, Furn | Sft | 8120350 | 1020 | 416.75 | 416.75 | 416.75 | 2770 | 0 | 7 | 2917.25 | 2917.25 | 0% | Yes | Original
Sign, Type B, Temp, Prismatic, Oper | Sft | 8120351 | 1030 | 416.25 | 416.25 | 416.25 | 2770 | 0 | 0.01 | 4.16 | 4.1625 | 0% | Yes | Original
Sign,TypeB,Temp,Prismatic,Special, Furn | Sft | 8120352 | 1040 | 0 | 0 | 0 | 80 | 0 | 15 | 0 | 0 | 0% | Yes | Original
Sign,TypeB,Temp,Prismatic,Special, Oper | Sft | 8120353 | 1050 | 0 | 0 | 0 | 80 | 0 | 0.01 | 0 | 0 | 0% | Yes | Original
_ Planting MIx, Drainage Agg, Geotextile, Mulch & Perennials | Sft | 8157010 | 1060 | 4074.5 | 4074.5 | 4074.5 | 3362 | 0 | 12 | 48894 | 48894 | 0.6% | Yes | Original
_ Bike Racks | Ea | 8157050 | 1070 | 22 | 22 | 22 | 30 | 0 | 1200 | 26400 | 26400 | 0.4% | Yes | Original
_ Bus Stop Shelter, Rem and Replace | Ea | 8157050 | 1080 | 1 | 1 | 1 | 1 | 0 | 40000 | 40000 | 40000 | 0.5% | Yes | Original
_ Cleanout | Ea | 8157050 | 1090 | 5 | 5 | 5 | 5 | 0 | 1000 | 5000 | 5000 | 0.1% | No | Original
_ Overflow Inlet | Ea | 8157050 | 1100 | 5 | 5 | 5 | 5 | 0 | 1600 | 8000 | 8000 | 0.1% | No | Original
_ Street Tree, 3" Cal | Ea | 8157050 | 1110 | 49 | 49 | 49 | 50 | 0 | 700 | 34300 | 34300 | 0.5% | Yes | Original
_ Trash Receptacle | Ea | 8157050 | 1120 | 5 | 5 | 5 | 7 | 0 | 2700 | 13500 | 13500 | 0.2% | Yes | Original
_ Tree Grate amd Frame, 4 Foot x 12 Foot | Ea | 8157050 | 1130 | 50 | 50 | 50 | 50 | 0 | 3000 | 150000 | 150000 | 2% | Yes | Original
_ Tree Pit | Ea | 8157050 | 1140 | 49 | 49 | 49 | 50 | 0 | 1000 | 49000 | 49000 | 0.7% | Yes | Original
_ Low Maintenance Plater Watering and Cultivating, 2 Seasons | Ea | 8157050 | 1150 | 1 | 1 | 1 | 1 | 0 | 8000 | 8000 | 8000 | 0.1% | No | Original
Slope Restoration, Type B | Syd | 8160101 | 1160 | 1655.86 | 1655.86 | 1655.86 | 610 | 0 | 16 | 26493.76 | 26493.76 | 0.4% | Yes | Original
Seeding, Mixture THM Modified | Lb | 8160039 | 1170 | 0 | 0 | 0 | 100 | 0 | 12 | 0 | 0 | 0% | Yes | Original
Sodding | Syd | 8160055 | 1180 | 0 | 0 | 0 | 100 | 0 | 14 | 0 | 0 | 0% | Yes | Original
Topsoil Surface, Furn, LM Modified | Cyd | 8160071 | 1190 | 0 | 0 | 0 | 2 | 0 | 100 | 0 | 0 | 0% | Yes | Original
Cable Pole, TS and Sec, Disman | Ea | 8190009 | 1200 | 1 | 1 | 1 | 1 | 0 | 170 | 170 | 170 | 0% | Yes | Original
Cable Pole, TS, Disman | Ea | 8190010 | 1210 | 1 | 1 | 1 | 2 | 0 | 170 | 170 | 170 | 0% | Yes | Original
Cable, Rem | Ft | 8190016 | 1220 | 3066 | 3066 | 3066 | 3950 | 0 | 1.41 | 4323.06 | 4323.06 | 0.1% | Yes | Original
Cable, Sec, Rem | Ft | 8190017 | 1230 | 150 | 150 | 150 | 150 | 0 | 3.75 | 562.5 | 562.5 | 0% | Yes | Original
Conduit, DB, 2, 3 inch | Ft | 8190032 | 1240 | 4636 | 4636 | 4636 | 5285 | 0 | 21 | 97356 | 97356 | 1.3% | Yes | Original
Hh, Adj | Ea | 8190244 | 1250 | 4 | 4 | 4 | 34 | 0 | 700 | 2800 | 2800 | 0% | Yes | Original
Hh, Round | Ea | 8190260 | 1260 | 3 | 3 | 3 | 2 | 0 | 1400 | 4200 | 4200 | 0.1% | Yes | Original
Hh, Type S | Ea | 8190263 | 1270 | 3 | 3 | 3 | 3 | 0 | 4350 | 13050 | 13050 | 0.2% | Yes | Original
Light Std Arm, Install Salv | Ea | 8190276 | 1280 | 0 | 0 | 0 | 1 | 0 | 125 | 0 | 0 | 0% | Yes | Original
Light Std Arm, Rem and Salv | Ea | 8190278 | 1290 | 3 | 3 | 3 | 1 | 0 | 150 | 450 | 450 | 0% | Yes | Original
Light Std Fdn, Rem | Ea | 8190280 | 1300 | 1 | 1 | 1 | 1 | 0 | 800 | 800 | 800 | 0% | Yes | Original
Light Std Shaft, Install Salv | Ea | 8190301 | 1310 | 0 | 0 | 0 | 1 | 0 | 750 | 0 | 0 | 0% | Yes | Original
Light Std Shaft, Rem and Salv | Ea | 8190306 | 1320 | 1 | 1 | 1 | 1 | 0 | 880 | 880 | 880 | 0% | Yes | Original
Luminaire, Install Salv | Ea | 8190350 | 1330 | 0 | 0 | 0 | 1 | 0 | 125 | 0 | 0 | 0% | Yes | Original
Luminaire, Rem | Ea | 8190360 | 1340 | 22 | 22 | 22 | 23 | 0 | 80 | 1760 | 1760 | 0% | Yes | Original
Luminaire, Rem and Salv | Ea | 8190365 | 1350 | 1 | 1 | 1 | 1 | 0 | 125 | 125 | 125 | 0% | Yes | Original
Cable, Sec, 600V, 1, 3/C#6 | Ft | 8190399 | 1360 | 654 | 654 | 654 | 300 | 0 | 6.55 | 4283.7 | 4283.7 | 0.1% | Yes | Original
Wood Pole, Fit Up, Sec Cable Pole | Ea | 8190495 | 1370 | 3 | 3 | 3 | 3 | 0 | 750 | 2250 | 2250 | 0% | Yes | Original
Wood Pole, Rem | Ea | 8190505 | 1380 | 19 | 19 | 19 | 18 | 0 | 350 | 6650 | 6650 | 0.1% | Yes | Original
Conduit, Directional Bore, 2, 3 inch | Ft | 8190604 | 1390 | 1250 | 1250 | 1250 | 1120 | 0 | 28.9 | 36125 | 36125 | 0.5% | Yes | Original
Cable, Equipment Grounding Wire, 1/C#4 Modified | Ft | 8190234 | 1400 | 8137 | 8137 | 8137 | 6385 | 0 | 1.7 | 13832.9 | 13832.9 | 0.2% | Yes | Original
Cable, Sec, 600V, 2, 1/C#4 Modified | Ft | 8190404 | 1410 | 540 | 540 | 540 | 535 | 0 | 4.38 | 2365.2 | 2365.2 | 0% | Yes | Original
Cable, Sec, 600V, 3, 1/C#4 Modified | Ft | 8190405 | 1420 | 8137 | 8137 | 8137 | 6200 | 0 | 4.65 | 37837.05 | 37837.05 | 0.5% | Yes | Original
_ Cable, Sec, Quadplex, Aluminum, 4 AWG | Ft | 8197001 | 1430 | 578 | 578 | 578 | 700 | 0 | 4.88 | 2820.64 | 2820.64 | 0% | Yes | Original
Conduit, Encased, 1, 3 inch Modified | Ft | 8190058 | 1440 | 47.5 | 47.5 | 47.5 | 60 | 0 | 142 | 6745 | 6745 | 0.1% | Yes | Original
Conduit, Encased, 2, 3 inch Modified | Ft | 8190059 | 1450 | 106.5 | 106.5 | 106.5 | 50 | 0 | 149 | 15868.5 | 15868.5 | 0.2% | Yes | Original
Conduit, Encased, 2, 4 inch Modified | Ft | 8190071 | 1460 | 232 | 232 | 232 | 240 | 0 | 146 | 33872 | 33872 | 0.5% | Yes | Original
Conduit, Encased, 3, 4 inch Modified | Ft | 8190072 | 1470 | 39 | 39 | 39 | 20 | 0 | 156 | 6084 | 6084 | 0.1% | Yes | Original
_ Bracket Arm, Bolt On, Install | Ea | 8197050 | 1480 | 47 | 47 | 47 | 46 | 0 | 88 | 4136 | 4136 | 0.1% | Yes | Original
_ Bracket Arm, Bolt On, Rem | Ea | 8197050 | 1490 | 22 | 22 | 22 | 23 | 0 | 125 | 2750 | 2750 | 0% | Yes | Original
_ Bracket Arm, Clamp On, Install | Ea | 8197050 | 1500 | 47 | 47 | 47 | 46 | 0 | 90 | 4230 | 4230 | 0.1% | Yes | Original
_ Ground Rod, Install, Wood Pole | Ea | 8207050 | 1510 | 2 | 2 | 2 | 2 | 0 | 275 | 550 | 550 | 0% | Yes | Original
Hh, Polymer Conc Modified | Ea | 8190250 | 1520 | 60 | 60 | 60 | 65 | 0 | 1110 | 66600 | 66600 | 0.9% | Yes | Original
Hh, Round Modified | Ea | 8190260 | 1530 | 0 | 0 | 0 | 1 | 0 | 2100 | 0 | 0 | 0% | Yes | Original
Light Std Fdn Modified | Ea | 8190279 | 1540 | 47 | 47 | 47 | 47 | 0 | 1250 | 58750 | 58750 | 0.8% | Yes | Original
_ Light Std, Tapered Aluminum | Ea | 8197050 | 1550 | 4 | 4 | 4 | 5 | 0 | 1620 | 6480 | 6480 | 0.1% | Yes | Original
_ Light Std, Tapered Aluminum, Install | Ea | 8197050 | 1560 | 47 | 47 | 47 | 46 | 0 | 2400 | 112800 | 112800 | 1.5% | Yes | Original
_ Luminaire, 101W, Install | Ea | 8197050 | 1570 | 47 | 47 | 47 | 46 | 0 | 420 | 19740 | 19740 | 0.3% | Yes | Original
_ Luminaire, 139W, Install | Ea | 8197050 | 1580 | 47 | 47 | 47 | 46 | 0 | 444 | 20868 | 20868 | 0.3% | Yes | Original
_ Luminaire, 101W | Ea | 8197050 | 1590 | 4 | 4 | 4 | 5 | 0 | 365.22 | 1460.88 | 1460.88 | 0% | Yes | Original
_ Luminaire, 139W | Ea | 8197050 | 1600 | 4 | 4 | 4 | 5 | 0 | 399 | 1596 | 1596 | 0% | Yes | Original
_ Photo Control, Lighting | Ea | 8197050 | 1610 | 2 | 2 | 2 | 2 | 0 | 3019 | 6038 | 6038 | 0.1% | Yes | Original
Case Sign (LED), One Way, 12 in by 27 in | Ea | 8200019 | 1620 | 4 | 4 | 4 | 4 | 0 | 1036 | 4144 | 4144 | 0.1% | Yes | Original
Case Sign, Rem | Ea | 8200020 | 1630 | 2 | 2 | 2 | 2 | 0 | 88 | 176 | 176 | 0% | Yes | Original
Case Sign (LED), One Way, 24 in by 30 in | Ea | 8200029 | 1640 | 2 | 2 | 2 | 2 | 0 | 1447 | 2894 | 2894 | 0% | Yes | Original
Controller and Cabinet, Rem | Ea | 8200030 | 1650 | 2 | 2 | 2 | 2 | 0 | 250 | 500 | 500 | 0% | Yes | Original
Controller Fdn, Base Mount | Ea | 8200045 | 1660 | 2 | 2 | 2 | 2 | 0 | 1975 | 3950 | 3950 | 0.1% | Yes | Original
Controller Fdn, Rem | Ea | 8200046 | 1670 | 1 | 1 | 1 | 1 | 0 | 350 | 350 | 350 | 0% | Yes | Original
Fdn, Rem | Ea | 8200065 | 1680 | 2 | 2 | 2 | 2 | 0 | 500 | 1000 | 1000 | 0% | Yes | Original
Power Co. (Est. Cost to Contractor) | Dlr | 8200116 | 1690 | 8000 | 8000 | 8000 | 8000 | 0 | 1 | 8000 | 8000 | 0.1% | No | Original
Pushbutton and Sign | Ea | 8200121 | 1700 | 8 | 8 | 8 | 8 | 0 | 445 | 3560 | 3560 | 0% | Yes | Original
Serv Disconnect | Ea | 8200135 | 1710 | 3 | 3 | 3 | 2 | 0 | 1450 | 4350 | 4350 | 0.1% | Yes | Original
Serv Disconnect, Rem | Ea | 8200136 | 1720 | 2 | 2 | 2 | 2 | 0 | 89 | 178 | 178 | 0% | Yes | Original
Span Wire | Ea | 8200140 | 1730 | 4 | 4 | 4 | 4 | 0 | 809 | 3236 | 3236 | 0% | Yes | Original
Span Wire, Rem | Ea | 8200141 | 1740 | 2 | 2 | 2 | 2 | 0 | 175 | 350 | 350 | 0% | Yes | Original
Steel Pole, Rem | Ea | 8200145 | 1750 | 1 | 1 | 1 | 1 | 0 | 750 | 750 | 750 | 0% | Yes | Original
Strain Pole, Steel, Anchor Base, 30 foot | Ea | 8200155 | 1760 | 2 | 2 | 2 | 2 | 0 | 3570 | 7140 | 7140 | 0.1% | Yes | Original
Strain Pole, Steel, Anchor Fdn | Ea | 8200165 | 1770 | 2 | 2 | 2 | 2 | 0 | 7595 | 15190 | 15190 | 0.2% | Yes | Original
Guy, Rem | Ea | 8200167 | 1780 | 2 | 2 | 2 | 2 | 0 | 100 | 200 | 200 | 0% | Yes | Original
TS, Bracket Arm Mtd, Rem | Ea | 8200175 | 1790 | 2 | 2 | 2 | 2 | 0 | 88 | 176 | 176 | 0% | Yes | Original
TS, Pedestal Mtd, Rem | Ea | 8200179 | 1800 | 4 | 4 | 4 | 4 | 0 | 88 | 352 | 352 | 0% | Yes | Original
TS, Pedestrian, Bracket Arm Mtd, Rem | Ea | 8200180 | 1810 | 8 | 8 | 8 | 8 | 0 | 88 | 704 | 704 | 0% | Yes | Original
TS, Span Wire Mtd, Rem | Ea | 8200182 | 1820 | 4 | 4 | 4 | 4 | 0 | 88 | 352 | 352 | 0% | Yes | Original
TS, One Way Span Wire Mtd (LED) | Ea | 8200313 | 1830 | 10 | 10 | 10 | 10 | 0 | 880 | 8800 | 8800 | 0.1% | Yes | Original
TS, One Way Bracket Arm Mtd (LED) | Ea | 8200333 | 1840 | 3 | 3 | 3 | 2 | 0 | 1033 | 3099 | 3099 | 0% | Yes | Original
TS, Ped,Two Way Bracket Arm Mtd (LED) CD | Ea | 8200339 | 1850 | 6 | 6 | 6 | 6 | 0 | 1675 | 10050 | 10050 | 0.1% | Yes | Original
TS, One Way Pedestal Mtd (LED) | Ea | 8200340 | 1860 | 2 | 2 | 2 | 2 | 0 | 1320 | 2640 | 2640 | 0% | Yes | Original
TS, Ped, Two Way Pedestal Mtd (LED) CD | Ea | 8200347 | 1870 | 2 | 2 | 2 | 2 | 0 | 1735 | 3470 | 3470 | 0% | Yes | Original
TS, One Way Mast Arm Mtd (LED) | Ea | 8200359 | 1880 | 12 | 12 | 12 | 12 | 0 | 1055 | 12660 | 12660 | 0.2% | Yes | Original
Bracket, Truss, With 18 Foot Arm | Ea | 8200378 | 1890 | 2 | 2 | 2 | 1 | 0 | 2395 | 4790 | 4790 | 0.1% | Yes | Original
Casing | Ft | 8200153 | 1900 | 68 | 68 | 68 | 68 | 0 | 155 | 10540 | 10540 | 0.1% | Yes | Original
_ Cellular Data Service for 3 Years | Ea | 8207050 | 1910 | 2 | 2 | 2 | 1 | 0 | 1655 | 3310 | 3310 | 0% | Yes | Original
_ Cellular Data Streaming for 2 hours per month and for 3 Years | Ea | 8207050 | 1920 | 2 | 2 | 2 | 1 | 0 | 3310 | 6620 | 6620 | 0.1% | Yes | Original
Controller and Cabinet, Digital Type ITS | Ea | 8200031 | 1930 | 2 | 2 | 2 | 2 | 0 | 26350 | 52700 | 52700 | 0.7% | Yes | Original
_ Illuminated Street Name Sign, 6 ft | Ea | 8207050 | 1940 | 1 | 1 | 1 | 1 | 0 | 2339 | 2339 | 2339 | 0% | Yes | Original
_ Illuminated Street Name Sign, 8 ft | Ea | 8207050 | 1950 | 1 | 1 | 1 | 1 | 0 | 2755 | 2755 | 2755 | 0% | Yes | Original
_ Louvered Backplate | Ea | 8207050 | 1960 | 22 | 22 | 22 | 22 | 0 | 205 | 4510 | 4510 | 0.1% | Yes | Original
Pedestal, Alum Modified | Ea | 8200100 | 1970 | 5 | 5 | 5 | 5 | 0 | 565 | 2825 | 2825 | 0% | Yes | Original
Pedestal, Fdn Modified | Ea | 8200105 | 1980 | 5 | 5 | 5 | 5 | 0 | 1315 | 6575 | 6575 | 0.1% | Yes | Original
_ Video Capture and Streaming System | Ea | 8197050 | 1990 | 2 | 2 | 2 | 1 | 0 | 6120 | 12240 | 12240 | 0.2% | Yes | Original
_ Video Detection and Analytics System | Ea | 8197050 | 2000 | 2 | 2 | 2 | 1 | 0 | 11750 | 23500 | 23500 | 0.3% | Yes | Original
Monument Box Adjust Modified | Ea | 8210005 | 2010 | 0 | 0 | 0 | 1 | 0 | 258.43 | 0 | 0 | 0% | Yes | Original
Monument Preservation, Vertical Modified | Ea | 8210015 | 2020 | 0 | 0 | 0 | 1 | 0 | 3000 | 0 | 0 | 0% | Yes | Original
Water Shutoff, Adj, Case 1 Modified | Ea | 8230421 | 2030 | 81 | 81 | 81 | 64 | 0 | 500 | 40500 | 40500 | 0.5% | Yes | Original
Water Shutoff, Adj, Case 2 Modified | Ea | 8230422 | 2040 | 2 | 2 | 2 | 12 | 0 | 260 | 520 | 520 | 0% | Yes | Original
_ Audio-Visual Filming | LS | 1077051 | 2050 | 1 | 1 | 1 | 1 | 0 | 14000 | 14000 | 14000 | 0.2% | Yes | Original
_ Litter and Debris, Rem | Cyd | 2047021 | 2060 | 0 | 0 | 0 | 40 | 0 | 800 | 0 | 0 | 0% | Yes | Original
_ Wireless Data Acquisition, Alerts and Analytics System | Ea | 8197050 | 2065 | 2 | 2 | 2 | 2 | 0 | 5574 | 11148 | 11148 | 0.1% | Yes | Extra | 3
PavtMrkg,WetRetrflecPolyurea,4in,White | Ft | 8110500 | 2090 | 31378 | 31378 | 31378 | 42985 | 0 | 0.39 | 12237.42 | 12237.42 | 0.2% | Yes | Extra | 1
PavtMrkg,WetRetrflecPolyurea,4in,Yellow | Ft | 8110504 | 2095 | 20924 | 20924 | 20924 | 25492 | 0 | 0.39 | 8160.36 | 8160.36 | 0.1% | Yes | Extra | 1
Pavt Mrkg, Polyurea, 12 inch, Crosswalk | Ft | 8110110 | 2100 | 0 | 0 | 0 | 14410 | 0 | 5.95 | 0 | 0 | 0% | Yes | Extra | 1
Pavt Mrkg, Poly,12 in Cross Hatch,White | Ft | 8110108 | 2105 | 185 | 185 | 185 | 13774 | 0 | 5.95 | 1100.75 | 1100.75 | 0% | Yes | Extra | 1
Pavt Mrkg, Polyurea, 18 inch, Stop Bar | Ft | 8110113 | 2110 | 0 | 0 | 0 | 553 | 0 | 10 | 0 | 0 | 0% | Yes | Extra | 1
Pavt Mrkg, Polyurea, Lt Turn Arrow Sym 18 inch | Ea | 8110405 | 2115 | 0 | 0 | 0 | 13 | 0 | 175 | 0 | 0 | 0% | Yes | Extra | 1
Pavt Mrkg, Polyurea, Only 18 inch | Ea | 8110410 | 2120 | 0 | 0 | 0 | 15 | 0 | 175 | 0 | 0 | 0% | Yes | Extra | 1
Pavt Mrkg, Polyurea, Rt Turn Arrow Sym 18 inch | Ea | 8110412 | 2125 | 0 | 0 | 0 | 2 | 0 | 175 | 0 | 0 | 0% | Yes | Extra | 1
Recessing Pavt Mrkg, Transv | Sft | 8110451 | 2130 | 12238.5 | 12238.5 | 12238.5 | 14963 | 0 | 2.5 | 30596.25 | 30596.25 | 0.4% | Yes | Extra | 1
Rem Curing Compound, for Spec Mrkg | Sft | 8110321 | 2135 | 5630 | 5630 | 5630 | 5630 | 0 | 2.95 | 16608.5 | 16608.5 | 0.2% | Yes | Extra | 3
_ Cold Milling HMA Surface - 2021 Remobilization | LS | 5017051 | 2145 | 1 | 1 | 1 | 1 | 0 | 9200 | 9200 | 9200 | 0.1% | Yes | Extra | 3
_ HMA, 4E3 and 5E3 - 2021 Remobilization | Ton | 5017031 | 2150 | 200 | 200 | 200 | 200 | 0 | 200 | 40000 | 40000 | 0.5% | Yes | Extra | 3
_ Track, Rem - Modified | Ft | 2047001 | 2155 | 682 | 682 | 682 | 682 | 0 | 42 | 28644 | 28644 | 0.4% | Yes | Extra | 3
_ COD Martketing Signs | LS | 8107051 | 2160 | 1 | 1 | 1 | 1 | 0 | 3270.56 | 3270.56 | 3270.56 | 0% | Yes | Extra | 3
_ Cold Weather Costs | Dlr | 1077060 | 2165 | 20133.75 | 20133.75 | 20133.75 | 20133.75 | 0 | 1 | 20133.75 | 20133.75 | 0.3% | Yes | Extra | 3
_ Temporary Bus Stops | Ea | 8157050 | 2170 | 2 | 2 | 2 | 2 | 0 | 300 | 600 | 600 | 0% | Yes | Extra | 3
_ TS Face, Bag and Unbag | Ea | 8207050 | 2175 | 5 | 5 | 5 | 5 | 0 | 500 | 2500 | 2500 | 0% | Yes | Extra | 3
_ Traffic Control Price Adjustment | LS | 8127051 | 2180 | 1 | 1 | 1 | 1 | 0 | 121500 | 121500 | 121500 | 1.6% | Yes | Extra | 4
_ Pavt Mrkg, Rework | LS | 8107051 | 2185 | 1 | 1 | 1 | 1 | 0 | 2000 | 2000 | 2000 | 0% | Yes | Extra | 3
[10 empty] | 8044769.66 | 8044769.6625
[9 empty] | Balance | -521302.4 | -521302.4025
#REF!
[9 empty] | Balance | #REF!