## RFIs
Kercheval Streetscape_RFI Log
Contractor |  | Major Cement Company |  | Project Number | PW-7005 |  |  |  | Please do not delete this column. This is supporting information to choose Type of Submittal
Document Type
Item No. | Drawing/ Spec Reference | Description | Type of Submittal | Received from Contractor | Returned to Contractor | Action | Reviewed By | Notes
Bill Of Quantities
1 |  | General Lighting Plan Questions | RFI | 2020-01-29 | 2020-03-12 | NET | PLA |  | Brief
2 |  | General Signal Plan Questions | RFI | 2020-01-29 | 2020-04-08 |  | TED |  | Calculations
3 |  | Delineators | RFI | 2020-03-17 | 2020-04-07 |  | Fishbeck/DLZ |  | Certificate
4 |  | General Signal Plan Questions #2 | RFI | 2020-03-20 | 2020-04-08 |  | TED
5 |  | Street Name Signs | RFI | 2020-04-22 | 2020-04-23 |  | Fishbeck/DLZ
6 |  | Request for CAD Files | RFI | 2020-05-04 | 2020-05-05 |  | DLZ
7 |  | General Signal Plan Questions #3 | RFI | 2020-06-10 | 2020-06-15 |  | DLZ
8 |  | Underdrain Placement | RFI | 2020-06-17 | 2020-07-01 |  | Fishbeck/DLZ
9 |  | Lighting Power at E. Grand | RFI | 2020-07-01 | 2020-07-07 |  | PLA
10 |  | Direct Bury Conduits | RFI | 2020-07-06 | 2020-07-07 |  | PLA
11 |  | Directional Bore Conduits | RFI | 2020-07-15 | 2020-07-27 |  | AECOM
12 |  | Utility Conflicts | RFI | 2020-07-23 | 2020-07-24 |  | DPW/AECOM | Pam responded by email titled "Kercheval Streetscape" on 07/24/20
13 |  | Utility Conflicts #2 | RFI | 2020-08-13 | 2020-09-09 |  |  | Permit issued for utilities+ to remove conflicts; completing boxed out sidewalk will be completed in a later stage.
14 |  | Underground Standards for Signal Work | RFI | 2020-08-24 | 2020-08-26 |  | TED
15 |  | Underground Install vs Sidewalk Removal | RFI | 2020-09-21 | 2020-10-05 |  |  | Additional removal limits between E. Grand and Field, and in front of Butzel staked in the field. Balance of sidewalk from Baldwin to Van Dyke to be salvaged per plan with electrical undergroun installed between existing sidewalk and curb.
16 |  | Curb Height | RFI | 2020-10-13 | 2020-10-14 |  |  | Direction to remove additional sidewalk was given in the field on 10/14 which will allow replacement at a flatter slope and allow a curb raise.
17 |  | Planter Watering Device | RFI | 2020-10-28 | 2020-11-04 |  |  | Discussed at Progress Meeting 11
18 |  | Pavt Mrkg Substitution | RFI | 2020-11-18 | 2020-11-25
Cost Estimate
Schedule
Scope Of Works
Shop Drawing
Sketch
Snag List