## Submittals
Kercheval Streetscape_Submittal Log
Contractor |  | Major Cement Company |  | Project Number | PW-7005
Item No. | Drawing/ Spec Reference | Description | Type of Submittal | Action Code: NET = No exception taken; AAN = Approved as noted - Revise and resubmit for record; RAR = Revise and resubmit; REJ = Rejected; NA = Review not required; |  |  |  | Notes
|  |  |  | Received from Contractor | Returned to Contractor | Action | Action Required By
1 |  | Light Poles-Arms-Anchor Bolts | Shop Drawing/Product Data | 2019-10-25 | 2020-01-16 | AAN
2 |  | Mast Arm Poles-Arms-Signals | Shop Drawing/Product Data | 2019-10-25 | 2020-03-13 | AAN
3 |  | Light Fixtures | Shop Drawing/Product Data | 2019-10-25 | 2020-01-16 | AAN
4 |  | Concrete Mix Designs (Major) | Mix Design | 2020-03-16 | 2020-04-08 | AAN |  | Approved. Need to provide updated certs as required.
4.1 |  | Concrete Mix Designs (Major)_R1 | Mix Design | 2020-04-13 | 2020-04-16 | RAR |  | 1 of 4 mixes - P1-DETM-1 - was approved
4.2 |  | Concrete Mix Designs (Major)_R2 | Mix Design | 2020-04-17 | 2020-04-20 | AAN
4.3 |  | Concrete Mix Designs (Major)_R3 | Mix Design | 2020-04-29 | 2020-05-06 | NET |  | Agg source change
5 |  | Concrete QC Plan | Plan | 2020-03-16 | 2020-06-12 | RAR | Major
5.1 |  | Concrete QC Plan - R1 | Plan | 2020-08-14 | 2020-08-18 | NET |  | resubmitting to include liquid nitrogen
5.2 |  | Concrete QC Plan - R2 | Plan | 2020-09-16 | 2020-09-25 | NET
6 |  | Bus Shelter | Shop Drawing/Product Data | 2020-03-16 | 2020-05-08 | AAN
6.1 |  | Bus Shelter - R1 | Shop Drawing/Product Data | 2020-06-19 | 2020-07-01 | AAN
7 |  | Tree Grates and Frames | Shop Drawing/Product Data | 2020-03-16 | 2020-05-06 | AAN
7.1 |  | Tree Grates and Frames - R1 | Shop Drawing/Product Data | 2020-05-16 | 2020-06-18 | AAN
8 |  | Litter Receptacles and Plaque | Shop Drawing/Product Data | 2020-03-16 | 2020-05-07 | NET
9 |  | Bike Racks | Shop Drawing/Product Data | 2020-03-16 | 2020-05-06 | AAN
10 |  | Traffic Signal Street Name Sign | Shop Drawing/Product Data | 2020-03-20 | 2020-04-08 | NET
11 |  | Lighting Handholes | Shop Drawing/Product Data | 2020-03-20 | 2020-04-08 | NET
12 |  | PVC Conduit-Fittings-Grounding | Shop Drawing/Product Data | 2020-03-20 | 2020-04-08 | NET
13 |  | Concrete Mix Designs (MCE - Superior Plant 32) | Mix Design | 2020-03-20 | 2020-04-08 | RAR |  | Mix designs and certs were mostly in order, but they provided the wrong alkali-silica test for the pit listed on JMF.
13.1 |  | Concrete Mix Designs (MCE - Superior Plant 2) | Mix Design | 2020-03-20 | 2020-04-08 | AAN
13.2 |  | Concrete Mix Designs (MCE - Sup. Plant 2 +32) | Mix Design | 2020-06-18 | 2020-06-24 | RAR | MCE
13.3 |  | Concrete Mix Designs (MCE - Superior Plant 32) | Mix Design | 2020-07-31 | 2020-08-06 | RAR | MCE | S2 mix is AAN; M mix is RAR.
13.4 |  | Concrete Mix Designs (MCE - Superior Plant 32) | Mix Design | 2020-08-31 | 2020-09-09 | AAN |  | M mix is AAN; S2 mix was previously marked AAN and not reviewed again.
14 |  | Planter Rail | Shop Drawing/Product Data | 2020-04-15 | 2020-05-07 | AAN
15 |  | HMA QC Plan | Plan | 2020-04-16 | 2020-05-06 | NET
16 |  | Landscape Product Data | Product Data | 2020-05-16 | 2020-06-12 | RAR | WHC | Sod did not meet spec.
17 |  | HMA JMFs | Mix Design | 2020-06-15 | 2020-06-16 | RAR |  | Reduce air voids.
17.1 |  | HMA JMFs - R1 | Mix Design | 2020-06-17 | 2020-06-18 | AAN |  | JMFs check out, need to have stamped to formally respond.
17.2 |  | HMA JMFs - R2 | Mix Design | 2020-09-17 | 2020-10-14 | NET
18 |  | Concrete Mix Designs (Major - Alt Fly Ash) | Mix Design | 2020-06-19 | 2020-06-24 | AAN
19 |  | Miovision | Shop Drawing/Product Data | 2020-07-08 | 2020-08-06 | NET
20 |  | Concrete Hand Holes | Shop Drawing/Product Data | 2020-07-08 | 2020-08-06 | NET
21 |  | Lighting Controllers | Shop Drawing/Product Data | 2020-07-09 | 2020-07-14 | NET
22 |  | In-Line Fusing-Tagging-Terminations | Shop Drawing/Product Data | 2020-07-09 | 2020-07-14 | NET
23 |  | Lighting Cable | Shop Drawing/Product Data | 2020-07-09 | 2020-07-14 | NET
24 |  | Traffic Signal Cable | Shop Drawing/Product Data | 2020-07-09 | 2020-08-06 | RAR | TED
24.1 |  | Traffic Signal Cable | Shop Drawing/Product Data | 2020-09-23 |  |  | TED | Waiting on clairfication from Motor City
25 |  | Disconnect for T.S. | Shop Drawing/Product Data | 2020-07-09 | 2020-08-06 | NET
26 |  | Concrete Mix Designs (Major - P-NC0M-2) | Mix Design | 2020-08-06 | 2020-08-06 | NET
27 |  | Concrete Mix Designs (MCE - McCoig) | Mix Design | 2020-10-15 | 2020-10-26 | RAR | MCE
28 |  | Concrete Mix Designs (MCE - McCoig) (new cement) | Mix Design | 2020-10-23 | 2020-11-05 | AAN
29 |  | HMA JMF (Cadillac 5E10) | Mix Design | 2020-11-16 | 2020-11-17 | NET
29.1 |  | HMA JMF (Cadillac 5E3)_R1 | Mix Design | 2020-11-18 | 2020-11-18 | NET
30 |  | Major Alt. Conc Mix Design | Mix Design | 2020-11-23 | 2020-12-02 | RAR
30.1 |  | Major Alt. Conc Mix Design_R1 | Mix Design | 2020-12-03 | 2020-12-09 | AAN |  | Mix Design is acceptable for use with ambient temperatures above 59F based on the cement content.
31 |  | NitroCast K Accelerator Admixture | Mix Design | 2020-11-23 | 2020-12-02 | NET
32 |  | Concrete Mix Designs (Major for 2021) | Mix Design | 2021-06-10 | 2021-06-15 | NET
33 |  | HMA JMF (Cadillac 4E3 + 5E3) | Mix Design | 2021-07-07
34 |  | Concrete Mix Designs (Punch List) | Mix Design | 2022-05-04 | 2022-05-13 | NET

## Submittal Type
Document Type | attachment
As-built Drawing | Please do not delete this column. This is supporting information to choose Type of Submittal
Bill Of Quantities
Brief
Calculations
Certificate | Document Type
Contracts | As-built Drawing
Cost Estimate | Bill Of Quantities
Data Sheets | Brief
Defect List | Calculations
Drawings | Certificate
Employers Instruction | Contracts
Engineer’s Instruction | Cost Estimate
Evaluation | Product Data
Form | Defect List
Guidelines | Drawings
Inspection Request | Employers Instruction
Invoice | Engineer’s Instruction
Manual | Evaluation
Master Plan | Form
Matrix | Guidelines
Method Statement | Inspection Request
Model | Invoice
Non-Conformance Report | Manual
No-Objection Certificate | Master Plan
Payment Certificates | Matrix
Performance Bond | Method Statement
Permit | Model
Photograph | Non-Conformance Report
Plan | No-Objection Certificate
Policy | Payment Certificates
Presentation | Performance Bond
Procedure | Permit
Proposal | Photograph
Register | Plan
Report | Policy
Request for Change | Presentation
Risk Register | Procedure
Sample | Register
Schedule | Report
Scope Of Works | Risk Register
Shop Drawing | Sample
Sketch | Schedule
Snag List | Scope Of Works
Specification | Shop Drawing
Standards | Sketch
Survey | Snag List
Tender
Variation Order
Work Instruction
Client Advice
Confirmation of Verbal Instruction
Notice to Proceed
Request for Information
Response to RFI
Transmittal