## CM Summary
Contract ID: PW-7018 - Major Streets Resurfacing City of Detroit
Cont. Mod. No. | Rev. No. | Cont. Mod. Date | Status | Approval Date | Short Description | Net Change Amount
1 |  | 2020-07-21 | Approved | 2020-07-21 | Correct FM file to match unit prices from contract | 0
2 |  | 2020-10-19 | Approved | 2020-10-19 | adjustment for inspector OT | -3018.75
3 |  | 2020-10-19 | Approved | 2020-10-19 | adjustment for inspector OT | 1006.25
4 |  | 2020-10-27 | Approved | 2020-10-27 | adjustment for inspector OT | -7778.75
5 |  | 2020-11-12 | Approved | 2020-11-23 | Addition of type J and K drainage structure covers | 3750
6 | 1 | 2021-04-06 | Approved | 2021-10-06 | adjustment for inspector OT | -4856.25
7 |  | 2021-06-08 | Approved | 2021-06-14 | balancing contract items | -3524.2761
8 | 2 | 2021-10-01 | Approved | 2022-04-13 | addition of raised intersections on Clark and Scotten | 537750.95
9 |  | 2022-06-08 | Approved | 2022-06-10 | balancing contract items | -142232.05
10 |  | 2023-01-06 | Approved | 2023-02-01 | Final Balancing | 3061.15
Total Net Change Amount | [5 empty] | 384158.2739
|  | Awarded Contract Amount |  |  | 9988460.91
|  | Net Change Amount (Auth) |  |  | 384158.2739 | ( + )
|  | Current Contract Amount |  |  | 10372619.1839
|  | Amount Paid to Date (PE 001 - PE 027) |  |  | 10372619.23
|  | Current Contract Amount |  |  | 10372619.1839 | ( - )
|  | Net Change Amount |  |  | 0.04611