## Sheet1
Contract ID: PW-7018 - Major Resurfacing in the City of Detroit
[9 empty] | AWARDED CONTRACT AMOUNT | 9988460.91 | 523329.17 | 10511790.08 | 139170.85
Item Description | Units | Item Code | Prop. Line | Quantity Placed | Quantity Paid | Authorized Quantity | Initial Quantity | Pending Changes | Unit Price | Auth. Amount | Placed Amount | % Cont. Amt. (awrd) | Item Cpt | Item Type | Cont. Mod. Number
Dr Structure, Rem (Speed table) | Ea | 2030011 | 1035 | 0 | 0 | 0 | 2 | 0 | 945 | 0 | 0 | 0% | Yes | Extra | 8
Pavt, Rem (Speed table) | Syd | 2040050 | 1065 | 1244.97 | 1244.97 | 1244.97 | 992 | 0 | 33.6 | 41830.99 | 41830.99 | 0.4% | Yes | Adjustment | 8
Sidewalk, Rem (Speed Table) | Syd | 2040055 | 1055 | 513.9 | 513.9 | 513.9 | 364 | 0 | 21 | 10791.9 | 10791.9 | 0.1% | Yes | Adjustment | 8
Track, Rem | Ft | 2040065 | 1220 | 349 | 349 | 349 | 234 | 0 | 240 | 83760 | 83760 | 0.8% | Yes | Extra | 8
_ Curb, Rem, Modified (Speed Table) | Ft | 2047001 | 1060 | 501 | 501 | 501 | 550 | 0 | 23.1 | 11573.1 | 11573.1 | 0.1% | Yes | Adjustment | 8
_ Exploratory Trenching (Speed Table) | Ea | 2047050 | 1230 | 12 | 12 | 12 | 24 | 0 | 250 | 3000 | 3000 | 0% | Yes | Extra | 8
Aggregate Base, 8 inch (Speed Table) | Syd | 3020020 | 1185 | 1244.97 | 1244.97 | 1244.97 | 992 | 0 | 14.7 | 18301.06 | 18301.06 | 0.2% | Yes | Extra | 8
Sewer, Cl IV, 12 inch, Tr Det B (Speed table at Scotten) | Ft | 4020987 | 1190 | 246 | 246 | 246 | 56 | 0 | 52.5 | 12915 | 12915 | 0.1% | Yes | Adjustment | 8
Sewer, Cl IV, 12 inch, Tr Det B (Speed Table Clark) | Ft | 4020987 | 1040 | 59.5 | 59.5 | 59.5 | 331 | 0 | 131.25 | 7809.38 | 7809.38 | 0.1% | Yes | Extra | 8
Sewer Tap, 12 inch (Speed table at Scotten) | Ea | 4021204 | 1195 | 2 | 2 | 2 | 2 | 0 | 2100 | 4200 | 4200 | 0% | Yes | Adjustment | 8
Sewer Tap, 12 inch (Speed table) | Ea | 4021204 | 1045 | 5 | 5 | 5 | 5 | 0 | 1575 | 7875 | 7875 | 0.1% | Yes | Extra | 8
_ Sewer Trap, 12 inch | Ea | 4027050 | 1225 | 5 | 5 | 5 | 3 | 0 | 525 | 2625 | 2625 | 0% | Yes | Extra | 8
Dr Structure Cover, Type J | Ea | 4030045 | 1000 | 3 | 3 | 3 | 3 | 0 | 700 | 2100 | 2100 | 0% | Yes | Extra | 5
Dr Structure Cover, Type K | Ea | 4030050 | 1005 | 3 | 3 | 3 | 3 | 0 | 550 | 1650 | 1650 | 0% | Yes | Extra | 5
_ Dr Structure Lead, Cleaning, Modified (Speed Table) | Ft | 4037001 | 1070 | 170 | 170 | 170 | 50 | 0 | 7.88 | 1339.6 | 1339.6 | 0% | Yes | Adjustment | 8
_ Dr Structure Cleaning, Modified (Speed table) | Ea | 4037050 | 1205 | 17 | 17 | 17 | 5 | 0 | 525 | 8925 | 8925 | 0.1% | Yes | Adjustment | 8
_ Dr Structure 48 inch DIA, Modified (Speed table at Clark) | Ea | 4037050 | 1200 | 6 | 6 | 6 | 10 | 0 | 10500 | 63000 | 63000 | 0.6% | Yes | Adjustment | 8
_ Dr Structure 48 inch DIA, Modified (Speed Table Scotten) | Ea | 4037050 | 1050 | 7 | 7 | 7 | 4 | 0 | 7875 | 55125 | 55125 | 0.6% | Yes | Extra | 8
_ Dr Structure Cleaning, Modified, Adj | Ea | 4037050 | 925 | 290 | 290 | 290 | 832 | 0 | 100 | 29000 | 29000 | 0.3% | Yes | Adjustment | 1
_ Dr Structure Cover, Adj, Case 1, Mod (Speed Table) | Ea | 4037050 | 1075 | 25 | 25 | 25 | 12 | 0 | 577.5 | 14437.5 | 14437.5 | 0.1% | Yes | Adjustment | 8
_ Dr Structure Cover, Adj, Case 1, Modifie d, Adj | Ea | 4037050 | 930 | 807 | 807 | 807 | 722 | 0 | 400 | 322800 | 322800 | 3.2% | Yes | Adjustment | 1
_ Dr Structure Cover, Adj, Case 2, Modifie d, Adj | Ea | 4037050 | 935 | 3 | 3 | 3 | 8 | 0 | 400 | 1200 | 1200 | 0% | Yes | Adjustment | 1
_ Dr Structure Cover, Type CB, Modified, A dj | Ea | 4037050 | 940 | 362 | 362 | 362 | 353 | 0 | 300 | 108600 | 108600 | 1.1% | Yes | Adjustment | 1
_ Dr Structure Cover, Type PLD HH, Modifie d, Adj | Ea | 4037050 | 945 | 97 | 97 | 97 | 96 | 0 | 388.83 | 37716.51 | 37716.51 | 0.4% | Yes | Adjustment | 1
_ Dr Structure Cover, Type PLD MH, Modifie d, Adj | Ea | 4037050 | 950 | 79 | 79 | 79 | 89 | 0 | 609.5 | 48150.5 | 48150.5 | 0.5% | Yes | Adjustment | 1
_ Dr Structure Cover, Type Sewer MH, Modif ied, Adj | Ea | 4037050 | 960 | 156 | 156 | 156 | 196 | 0 | 400 | 62400 | 62400 | 0.6% | Yes | Adjustment | 1
_ Dr Structure Cover, Type Water MH, Modif ied, Adj | Ea | 4037050 | 965 | 120 | 120 | 120 | 75 | 0 | 400 | 48000 | 48000 | 0.5% | Yes | Adjustment | 1
_ Dr Structure Cover, Type Water Valve Box , Modified, Adj | Ea | 4037050 | 970 | 73 | 73 | 73 | 61 | 0 | 80.33 | 5864.09 | 5864.09 | 0.1% | Yes | Adjustment | 1
_ Drainage Structure Cover, Type CB, Mod (Speed table) | Ea | 4037050 | 1080 | 13 | 13 | 13 | 11 | 0 | 525 | 6825 | 6825 | 0.1% | Yes | Adjustment | 8
_ Drainage Structure Cover, Type Sewer MH, (Speed Table) | Ea | 4037050 | 1085 | 0 | 0 | 0 | 3 | 0 | 525 | 0 | 0 | 0% | Yes | Adjustment | 8
_ Drainage Structure Cover, Type Water MH (Speed Table) | Ea | 4037050 | 1090 | 0 | 0 | 0 | 4 | 0 | 525 | 0 | 0 | 0% | Yes | Adjustment | 8
_ Reconstructing Dr Structure, Case 1, Mod (Speed Table) | Ea | 4037050 | 1095 | 0 | 0 | 0 | 7 | 0 | 840 | 0 | 0 | 0% | Yes | Adjustment | 8
HMA Surface, Rem (Speed Table) | Syd | 5010005 | 1100 | 0 | 0 | 0 | 992 | 0 | 15.75 | 0 | 0 | 0% | Yes | Adjustment | 8
HMA, 5E3 (Speed Table) | Ton | 5010057 | 1105 | 36.04 | 36.04 | 36.04 | 24 | 0 | 787.5 | 28381.5 | 28381.5 | 0.3% | Yes | Adjustment | 8
_ Cold Milling HMA Surface, Mod (Speed Table) | Syd | 5017011 | 1110 | 0 | 0 | 0 | 276 | 0 | 15.75 | 0 | 0 | 0% | Yes | Adjustment | 8
_ Conditioning Existing Pavement, Modified (Speed Table) | Syd | 5017011 | 1115 | 0 | 0 | 0 | 1.68 | 0 | 787.5 | 0 | 0 | 0% | Yes | Adjustment | 8
_ HMA Approach, Modified, Adj | Ton | 5017031 | 975 | 2883.01 | 2883.01 | 2883.01 | 2511 | 0 | 160 | 461281.6 | 461281.6 | 4.6% | Yes | Adjustment | 1
_ HMA Shoulder, Modified, Adj | Ton | 5017031 | 980 | 318.82 | 318.82 | 318.82 | 251 | 0 | 360 | 114775.2 | 114775.2 | 1.1% | Yes | Adjustment | 1
Conc Pavt, Nonreinf, 8 inch (Speed Table) | Syd | 6020104 | 1125 | 1033.76 | 1033.76 | 1033.76 | 992 | 0 | 92.4 | 95519.42 | 95519.42 | 1% | Yes | Extra | 8
_ Concrete Quality Adjustment | Dlr | 6027060 | 1280 | -5569.81 | -5569.81 | -5569.81 | -5569.81 | 0 | 1 | -5569.81 | -5569.81 | -0.1% | Yes | Adjustment | 9
Lane Tie, Epoxy Anchored (Speed Table) | Ea | 6030030 | 1130 | 1822 | 1822 | 1822 | 825 | 0 | 7.35 | 13391.7 | 13391.7 | 0.1% | Yes | Extra | 8
Sawing and Sealing Longit Pavt Joints (Speed Table) | Ft | 6030095 | 1135 | 766 | 766 | 766 | 675 | 0 | 8.4 | 6434.4 | 6434.4 | 0.1% | Yes | Extra | 8
Sawing and Sealing Trans Pavt Joints (Speed Table) | Ft | 6030096 | 1140 | 1227 | 1227 | 1227 | 843 | 0 | 8.4 | 10306.8 | 10306.8 | 0.1% | Yes | Extra | 8
_ Curb, Conc, Detail CD, Modified (Speed Table) | Ft | 6037001 | 1145 | 331.8 | 331.8 | 331.8 | 551 | 0 | 26.25 | 8709.75 | 8709.75 | 0.1% | Yes | Adjustment | 8
_ Pavt Repr, Nonreinf Conc, 8 inch, Mod (Speed Table) | Syd | 6037011 | 1120 | 233.81 | 233.81 | 233.81 | 276 | 0 | 84 | 19640.04 | 19640.04 | 0.2% | Yes | Adjustment | 8
_ Detectable Warning Surface Tile, Mod (Speed Table) | Ft | 8027001 | 1150 | 115.2 | 115.2 | 115.2 | 135 | 0 | 94.5 | 10886.4 | 10886.4 | 0.1% | Yes | Adjustment | 8
_ Sidewalk, Conc, 4 inch, Modified (Speed Table) | Sft | 8027010 | 1155 | 3321.66 | 3321.66 | 3321.66 | 1621 | 0 | 6.3 | 20926.46 | 20926.46 | 0.2% | Yes | Adjustment | 8
_ Sidewalk, Conc, 6 inch, Modified (Speed Table) | Sft | 8027010 | 1160 | 272.9 | 272.9 | 272.9 | 1642 | 0 | 8.4 | 2292.36 | 2292.36 | 0% | Yes | Adjustment | 8
Curb Ramp Opening, Conc (Speed Table) | Ft | 8030030 | 1165 | 169.2 | 169.2 | 169.2 | 140 | 0 | 25.2 | 4263.84 | 4263.84 | 0% | Yes | Adjustment | 8
Pavt Mrkg, Polyurea, Yield | Ea | 8110103 | 1285 | 32 | 32 | 32 | 32 | 0 | 55 | 1760 | 1760 | 0% | Yes | Extra | 9
Rem Curing Compound, for Spec Mrkg | Sft | 8110321 | 1235 | 196 | 196 | 196 | 196 | 0 | 1.25 | 245 | 245 | 0% | Yes | Extra | 9
_ Pavt Mrkg, Polyuera, 4in Parking Mrkgs | Ft | 8117001 | 1295 | 416 | 416 | 416 | 416 | 0 | 3.95 | 1643.2 | 1643.2 | 0% | Yes | Extra | 9
_ Pavt Mrkg, Polyurea, 4 in Radius Mrkg | Ft | 8117001 | 1290 | 1063 | 1063 | 1063 | 1063 | 0 | 3.95 | 4198.85 | 4198.85 | 0% | Yes | Extra | 9
_ Pavt Mrkg, Polyurea, V Shaped Ramp SYM (Speed Table) | Ea | 8117050 | 1180 | 10 | 10 | 10 | 16 | 0 | 210 | 2100 | 2100 | 0% | Yes | Extra | 8
Minor Traf Devices (Speed table) | LS | 8120170 | 1175 | 1 | 1 | 1 | 1 | 0 | 5075 | 5075 | 5075 | 0.1% | Yes | Adjustment | 8
_ Idle Crew (Speed Table) | Hr | 8507040 | 1215 | 5 | 5 | 5 | 10 | 0 | 750 | 3750 | 3750 | 0% | Yes | Extra | 8
_ Inspector Overtime Hours April 2021 | Hr | 8507040 | 1240 | 18.5 | 18.5 | 18.5 | 18.5 | 0 | -52.5 | -971.25 | -971.25 | 0% | Yes | Extra | 9
_ Inspector Overtime Hours August 2020 | Hr | 8507040 | 995 | 129 | 129 | 129 | 129 | 0 | -52.5 | -6772.5 | -6772.5 | -0.1% | Yes | Extra | 4
_ Inspector Overtime Hours August 2021 | Hr | 8507040 | 1255 | 24.5 | 24.5 | 24.5 | 24.5 | 0 | -52.5 | -1286.25 | -1286.25 | 0% | Yes | Extra | 9
_ Inspector Overtime Hours December 2020 | Hr | 8507040 | 1025 | 0 | 0 | 0 | 2.5 | 0 | -52.5 | 0 | 0 | 0% | Yes | Extra | 6
_ Inspector Overtime Hours December 2021 | Hr | 8507040 | 1275 | 4 | 4 | 4 | 4 | 0 | -52.5 | -210 | -210 | 0% | Yes | Extra | 9
_ Inspector Overtime Hours July 2020 | Hr | 8507040 | 985 | 57.5 | 57.5 | 57.5 | 57.5 | 0 | -52.5 | -3018.75 | -3018.75 | 0% | Yes | Extra | 2
_ Inspector Overtime Hours July 2020 | Hr | 8507040 | 990 | 0 | 0 | 0 | 57.5 | 0 | -35 | 0 | 0 | 0% | Yes | Extra | 3
_ Inspector Overtime Hours July 2021 | Hr | 8507040 | 1250 | 8.5 | 8.5 | 8.5 | 8.5 | 0 | -52.5 | -446.25 | -446.25 | 0% | Yes | Extra | 9
_ Inspector Overtime Hours May 2021 | Hr | 8507040 | 1245 | 16.5 | 16.5 | 16.5 | 16.5 | 0 | -52.5 | -866.25 | -866.25 | 0% | Yes | Extra | 9
_ Inspector Overtime Hours November 2020 | Hr | 8507040 | 1020 | 0 | 0 | 0 | 23.5 | 0 | -52.5 | 0 | 0 | 0% | Yes | Extra | 6
_ Inspector Overtime Hours November 2021 | Hr | 8507040 | 1270 | 26.5 | 26.5 | 26.5 | 26.5 | 0 | -52.5 | -1391.25 | -1391.25 | 0% | Yes | Extra | 9
_ Inspector Overtime Hours October 2020 | Hr | 8507040 | 1015 | 0 | 0 | 0 | 34 | 0 | -52.5 | 0 | 0 | 0% | Yes | Extra | 6
_ Inspector Overtime Hours October 2021 | Hr | 8507040 | 1265 | 18 | 18 | 18 | 18 | 0 | -52.5 | -945 | -945 | 0% | Yes | Extra | 9
_ Inspector Overtime Hours September 2020 | Hr | 8507040 | 1010 | 0 | 0 | 0 | 32.5 | 0 | -52.5 | 0 | 0 | 0% | Yes | Extra | 6
_ Inspector Overtime Hours September 2021 | Hr | 8507040 | 1260 | 10 | 10 | 10 | 10 | 0 | -52.5 | -525 | -525 | 0% | Yes | Extra | 9
_ Bollard (Speed table) | Ea | 8507050 | 1170 | 18 | 18 | 18 | 14 | 0 | 1365 | 24570 | 24570 | 0.2% | Yes | Extra | 8
_ Pavt Mrkg, Polyurea, Bus Stop | Ea | 8507050 | 1030 | 10 | 10 | 10 | 6 | 0 | 331 | 3310 | 3310 | 0% | Yes | Extra | 7
Mobilization, Max 10% | LS | _1500001 | 10 | 1 | 1 | 1 | 1 | 0 | 453262.3 | 453262.3 | 453262.3 | 4.5% | Yes | Original
Pavt, Rem | Syd | _2040050 | 20 | 23.44 | 23.44 | 23.44 | 285.5 | 0 | 13 | 304.72 | 304.72 | 0% | Yes | Original
Sidewalk, Rem | Syd | _2040055 | 30 | 8996.86 | 8996.86 | 8996.86 | 8385 | 0 | 13 | 116959.18 | 116959.18 | 1.2% | Yes | Original
_Integral Curb and Sidewalk, 2 feet, Rem, Modified | Ft | _2047001 | 50 | 1133.2 | 1133.2 | 1133.2 | 1387 | 0 | 3 | 3399.6 | 3399.6 | 0% | Yes | Original
_ Curb, Rem, Modified | Ft | _2047002 | 40 | 8945.9 | 8945.9 | 8945.9 | 13579 | 0 | 14 | 125242.6 | 125242.6 | 1.3% | Yes | Original
Granular Material, Cl II | Cyd | _2050023 | 60 | 0 | 0 | 0 | 200 | 0 | 0.1 | 0 | 0 | 0% | Yes | Original
Subgrade Undercutting, Type II | Cyd | _2050041 | 70 | 0 | 0 | 0 | 50 | 0 | 0.1 | 0 | 0 | 0% | Yes | Original
_ Excavation, Earth, Modified | Cyd | _2057021 | 80 | 0 | 0 | 0 | 1000 | 0 | 0.1 | 0 | 0 | 0% | Yes | Original
Aggregate Base, 4 inch | Syd | _3020010 | 90 | 0 | 0 | 0 | 3000 | 0 | 0.1 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Lead, Cleaning, Modified | Ft | _4037001 | 100 | 2430 | 2430 | 2430 | 8320 | 0 | 2 | 4860 | 4860 | 0% | Yes | Original
_ Dr Structure Cleaning, Modified | Ea | _4037050 | 170 | 0 | 0 | 0 | 196 | 0 | 400 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Cover, Adj, Case 1, Modifie d | Ea | _4037051 | 180 | 0 | 0 | 0 | 75 | 0 | 400 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Cover, Adj, Case 2, Modifie d | Ea | _4037052 | 190 | 0 | 0 | 0 | 61 | 0 | 80.33 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Cover, Type CB, Modified | Ea | _4037053 | 110 | 1 | 1 | 1 | 832 | 0 | 100 | 100 | 100 | 0% | Yes | Original
_ Dr Structure Cover, Type PLD HH, Modified | Ea | _4037054 | 120 | 0 | 0 | 0 | 722 | 0 | 400 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Cover, Type PLD MH, Modified | Ea | _4037055 | 130 | 0 | 0 | 0 | 8 | 0 | 400 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Cover, Type Sewer MH, Modified | Ea | _4037056 | 140 | 0 | 0 | 0 | 353 | 0 | 300 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Cover, Type Water MH Modified | Ea | _4037057 | 150 | 0 | 0 | 0 | 96 | 0 | 388.83 | 0 | 0 | 0% | Yes | Original
_ Dr Structure Cover, Type Water Valve Box, Modified | Ea | _4037058 | 160 | 0 | 0 | 0 | 89 | 0 | 609.5 | 0 | 0 | 0% | Yes | Original
_ Reconstructing Dr Structure, Case 1, Mod ified | Ea | _4037059 | 200 | 20 | 20 | 20 | 82 | 0 | 400 | 8000 | 8000 | 0.1% | Yes | Original
_ Reconstructing Dr Structure, Case 2, Mod ified | Ea | _4037060 | 210 | 0 | 0 | 0 | 4 | 0 | 600 | 0 | 0 | 0% | Yes | Original
Pavt, Cleaning | LS | _5010001 | 220 | 1 | 1 | 1 | 1 | 0 | 150000 | 150000 | 150000 | 1.5% | Yes | Original
HMA Surface, Rem | Syd | _5010005 | 230 | 6167.91 | 6167.91 | 6167.91 | 13041 | 0 | 3.61 | 22266.16 | 22266.16 | 0.2% | Yes | Original
Pavt for Butt Joints, Rem | Syd | _5010008 | 240 | 905.78 | 905.78 | 905.78 | 3222 | 0 | 3.61 | 3269.87 | 3269.87 | 0% | Yes | Original
Hand Patching | Ton | _5010025 | 250 | 0 | 0 | 0 | 5 | 0 | 500 | 0 | 0 | 0% | Yes | Original
HMA, 4E3 | Ton | _5010051 | 260 | 30508.54 | 30508.54 | 30508.54 | 29047 | 0 | 77.6 | 2367462.7 | 2367462.7 | 23.7% | Yes | Original
HMA, 5E3 | Ton | _5010057 | 270 | 23173.25 | 23173.25 | 23173.25 | 21787 | 0 | 81.3 | 1883985.23 | 1883985.23 | 18.9% | Yes | Original
_ Cold Milling HMA Surface, Modified | Syd | _5017011 | 280 | 272129.38 | 272129.38 | 272129.38 | 264074 | 0 | 3.61 | 982387.06 | 982387.06 | 9.8% | Yes | Original
_ HMA Approach, Modified | Ton | _5017031 | 300 | 0 | 0 | 0 | 251 | 0 | 360 | 0 | 0 | 0% | Yes | Original
_ HMA Shoulder, Modified | Ton | _5017032 | 310 | 0 | 0 | 0 | 2511 | 0 | 160 | 0 | 0 | 0% | Yes | Original
_ Conditioning Existing Pavement, Modified | Ton | _5017033 | 290 | 0 | 0 | 0 | 1000 | 0 | 150 | 0 | 0 | 0% | Yes | Original
_ Pavt Repr, Nonreinf Conc, 10 inch, Modified | Syd | _6027011 | 320 | 7.56 | 7.56 | 7.56 | 2350 | 0 | 10 | 75.6 | 75.6 | 0% | Yes | Original
Cement | Ton | _6030005 | 350 | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 0% | Yes | Original
_ Curb, Conc, Detail CD, Modified | Ft | _6037001 | 360 | 7202.3 | 7202.3 | 7202.3 | 11351 | 0 | 14 | 100832.2 | 100832.2 | 1% | Yes | Original
_ Pavt Repr, Rem, Modified | Syd | _6037011 | 370 | 62.12 | 62.12 | 62.12 | 2350 | 0 | 10 | 621.2 | 621.2 | 0% | Yes | Original
_ Pavt Repr, Nonreinf Conc, 6 inch, Modified | Syd | _6037012 | 330 | 100.8 | 100.8 | 100.8 | 50 | 0 | 50 | 5040 | 5040 | 0.1% | Yes | Original
_ Pavt Repr, Nonreinf Conc, 8 inch, Modified | Syd | _6037013 | 340 | 0 | 0 | 0 | 100 | 0 | 60 | 0 | 0 | 0% | Yes | Original
_ Detectable Warning Surface Tile, Modifie d | Ft | _8027001 | 380 | 1285.8 | 1285.8 | 1285.8 | 1559 | 0 | 80 | 102864 | 102864 | 1% | Yes | Original
_ Sidewalk Ramp, ADA, Modified | Sft | _8027010 | 390 | 9503.85 | 9503.85 | 9503.85 | 13847 | 0 | 5 | 47519.25 | 47519.25 | 0.5% | Yes | Original
_ Sidewalk, Conc, 4 inch, Modified | Sft | _8027011 | 400 | 65309.07 | 65309.07 | 65309.07 | 43854 | 0 | 5 | 326545.35 | 326545.35 | 3.3% | Yes | Original
_ Sidewalk, Conc, 6 inch, Modified | Sft | _8027012 | 410 | 5620.46 | 5620.46 | 5620.46 | 4702 | 0 | 5 | 28102.3 | 28102.3 | 0.3% | Yes | Original
Curb Ramp Opening, Conc | Ft | _8030030 | 420 | 1673.57 | 1673.57 | 1673.57 | 2246 | 0 | 14 | 23429.98 | 23429.98 | 0.2% | Yes | Original
_Integral Curb and Sidewalk, 2 feet, Modified | Ft | _8037001 | 430 | 1160.2 | 1160.2 | 1160.2 | 1303 | 0 | 4 | 4640.8 | 4640.8 | 0% | Yes | Original
_ Sidewalk, Conc with Tree Roots, 4 inch, Modified | Sft | _8037010 | 440 | 7687.62 | 7687.62 | 7687.62 | 12665 | 0 | 5 | 38438.1 | 38438.1 | 0.4% | Yes | Original
_ Sidewalk, Conc with Tree Roots, 6 inch, Modified | Sft | _8037011 | 450 | 0 | 0 | 0 | 398 | 0 | 5 | 0 | 0 | 0% | Yes | Original
_ Delineator Post, 36 Inch, White | Ea | _8107050 | 460 | 0 | 0 | 0 | 12 | 0 | 85 | 0 | 0 | 0% | Yes | Original
Pavt Mrkg, Polyurea, 4 inch, White | Ft | _8110091 | 470 | 2357 | 2357 | 2357 | 4530 | 0 | 3.95 | 9310.15 | 9310.15 | 0.1% | Yes | Original
Pavt Mrkg, Polyurea, 6 inch, Crosswalk | Ft | _8110093 | 480 | 6197 | 6197 | 6197 | 11775 | 0 | 2.75 | 17041.75 | 17041.75 | 0.2% | Yes | Original
Pavt Mrkg, Polyurea, Bike, Small Symbol | Ea | _8110105 | 490 | 17 | 17 | 17 | 3 | 0 | 150 | 2550 | 2550 | 0% | Yes | Original
Pavt Mrkg, Polyurea, Directional Arrow Symbol, Bike | Ea | _8110106 | 500 | 2 | 2 | 2 | 3 | 0 | 150 | 300 | 300 | 0% | Yes | Original
Pavt Mrkg, Polyurea, 12 inch Cross Hatching, White | Ft | _8110108 | 510 | 2842 | 2842 | 2842 | 4970 | 0 | 5.95 | 16909.9 | 16909.9 | 0.2% | Yes | Original
Pavt Mrkg, Polyurea, 12 inch Cross Hatching, Yellow | Ft | _8110109 | 520 | 435 | 435 | 435 | 940 | 0 | 5.95 | 2588.25 | 2588.25 | 0% | Yes | Original
Pavt Mrkg, Polyurea, 12 inch, Crosswalk | Ft | _8110110 | 530 | 7092 | 7092 | 7092 | 9470 | 0 | 5.95 | 42197.4 | 42197.4 | 0.4% | Yes | Original
Pavt Mrkg, Polyurea, 12 inch, White | Ft | _8110111 | 540 | 712 | 712 | 712 | 100 | 0 | 5.95 | 4236.4 | 4236.4 | 0% | Yes | Original
Pavt Mrkg, Polyurea, 18 inch, Stop Bar | Ft | _8110113 | 550 | 1804 | 1804 | 1804 | 4115 | 0 | 9.5 | 17138 | 17138 | 0.2% | Yes | Original
Pavt Mrkg, Polyurea, 24 inch, Stop Bar | Ft | _8110114 | 560 | 75 | 75 | 75 | 50 | 0 | 12.95 | 971.25 | 971.25 | 0% | Yes | Original
Pavt Mrkg, Polyurea, Sharrow Symbol | Ea | _8110115 | 570 | 15 | 15 | 15 | 8 | 0 | 195 | 2925 | 2925 | 0% | Yes | Original
Pavt Mrkg, Sprayable Thermopl, 4 inch, White | Ft | _8110153 | 580 | 53149 | 53149 | 53149 | 91260 | 0 | 0.19 | 10098.31 | 10098.31 | 0.1% | Yes | Original
Pavt Mrkg, Sprayable Thermopl, 4 inch, Yellow | Ft | _8110154 | 590 | 61930 | 61930 | 61930 | 84650 | 0 | 0.19 | 11766.7 | 11766.7 | 0.1% | Yes | Original
Rem Spec Mrkg | Sft | _8110343 | 600 | 7 | 7 | 7 | 1750 | 0 | 2.95 | 20.65 | 20.65 | 0% | Yes | Original
Pavt Mrkg, Polyurea, Lt & Rt Turn Arrow Sym | Ea | _8110404 | 610 | 0 | 0 | 0 | 1 | 0 | 200 | 0 | 0 | 0% | Yes | Original
Pavt Mrkg, Polyurea, Lt Turn Arrow Sym | Ea | _8110405 | 620 | 31 | 31 | 31 | 46 | 0 | 175 | 5425 | 5425 | 0.1% | Yes | Original
Pavt Mrkg, Polyurea, Only | Ea | _8110410 | 630 | 48 | 48 | 48 | 69 | 0 | 175 | 8400 | 8400 | 0.1% | Yes | Original
Pavt Mrkg, Polyurea, Rt Turn Arrow Sym | Ea | _8110412 | 640 | 19 | 19 | 19 | 16 | 0 | 175 | 3325 | 3325 | 0% | Yes | Original
Pavt Mrkg, Polyurea, Thru & Lt Turn Arrow Sym | Ea | _8110416 | 650 | 4 | 4 | 4 | 3 | 0 | 215 | 860 | 860 | 0% | Yes | Original
Pavt Mrkg, Polyurea, Thru & Rt Turn Arrow Sym | Ea | _8110417 | 660 | 12 | 12 | 12 | 8 | 0 | 215 | 2580 | 2580 | 0% | Yes | Original
Pavt Mrkg, Polyurea, Thru Arrow Sym | Ea | _8110418 | 670 | 5 | 5 | 5 | 7 | 0 | 155 | 775 | 775 | 0% | Yes | Original
Recessing Pavt Mrkg, Transv | Sft | _8110451 | 680 | 11511.5 | 11511.5 | 11511.5 | 14246 | 0 | 2.85 | 32807.78 | 32807.78 | 0.3% | Yes | Original
Pavt Mrkg, Polymer Cement Surfacing, Green | Sft | _8117010 | 690 | 0 | 0 | 0 | 930 | 0 | 12.95 | 0 | 0 | 0% | Yes | Original
Pavt Mrkg, Polymer Cement Surfacing, Bike, Small Symbol | Ea | _8117050 | 700 | 0 | 0 | 0 | 2 | 0 | 200 | 0 | 0 | 0% | Yes | Original
Pavt Mrkg, Polymer Cement Surfacing, Directional Arrow Symb | Ea | _8117051 | 710 | 0 | 0 | 0 | 2 | 0 | 200 | 0 | 0 | 0% | Yes | Original
Barr,TypeIII,HighInten,DblSided,Ltd,Furn | Ea | _8120022 | 720 | 17 | 17 | 17 | 40 | 0 | 90 | 1530 | 1530 | 0% | Yes | Original
Barr,TypeIII,HighInten,DblSided,Ltd,Oper | Ea | _8120023 | 730 | 17 | 17 | 17 | 40 | 0 | 0.01 | 0.17 | 0.17 | 0% | Yes | Original
Lighted Arrow, Type C, Furn | Ea | _8120140 | 740 | 8 | 8 | 8 | 20 | 0 | 500 | 4000 | 4000 | 0% | Yes | Original
Lighted Arrow, Type C, Oper | Ea | _8120141 | 750 | 8 | 8 | 8 | 20 | 0 | 0.01 | 0.08 | 0.08 | 0% | Yes | Original
Minor Traf Devices | LS | _8120170 | 760 | 1 | 1 | 1 | 1 | 0 | 750000 | 750000 | 750000 | 7.5% | Yes | Original
PavtMrkg,WtRef,Type R, Tape,4 in,Wh,Temp | Ft | _8120245 | 770 | 4371 | 4371 | 4371 | 10000 | 0 | 1.15 | 5026.67 | 5026.67 | 0.1% | Yes | Original
PavtMrkg,WtRef,Type R, Tape,4 in,Ye,Temp | Ft | _8120246 | 780 | 6152 | 6152 | 6152 | 5000 | 0 | 1.15 | 7074.8 | 7074.8 | 0.1% | Yes | Original
Plastic Drum, High Intensity, Furn | Ea | _8120252 | 790 | 1071 | 1071 | 1071 | 800 | 0 | 25 | 26775 | 26775 | 0.3% | Yes | Original
Plastic Drum, High Intensity, Oper | Ea | _8120253 | 800 | 1071 | 1071 | 1071 | 800 | 0 | 0.01 | 10.71 | 10.71 | 0% | Yes | Original
Sign, Type B, Temp, Prismatic, Furn | Sft | _8120350 | 810 | 5089 | 5089 | 5089 | 5000 | 0 | 5.75 | 29261.75 | 29261.75 | 0.3% | Yes | Original
Sign, Type B, Temp, Prismatic, Oper | Sft | _8120351 | 820 | 5089 | 5089 | 5089 | 5000 | 0 | 0.01 | 50.89 | 50.89 | 0% | Yes | Original
Traf Regulator Control | LS | _8120370 | 830 | 1 | 1 | 1 | 1 | 0 | 675460.58 | 675460.58 | 675460.58 | 6.8% | Yes | Original
Sodding | Syd | _8160055 | 840 | 0 | 0 | 0 | 100 | 0 | 18 | 0 | 0 | 0% | Yes | Original
Water, Sodding/Seeding | Unit | _8160090 | 850 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0% | Yes | Original
_ Seeding, Mixture THM, Modified | Syd | _8167011 | 860 | 0 | 0 | 0 | 2000 | 0 | 6.33 | 0 | 0 | 0% | Yes | Original
_ Topsoil Surface, Furn, LM, Modified | Cyd | _8167021 | 870 | 40 | 40 | 40 | 1000 | 0 | 48 | 1920 | 1920 | 0% | Yes | Original
Monument Box | Ea | _8210001 | 880 | 7 | 7 | 7 | 3 | 0 | 400 | 2800 | 2800 | 0% | Yes | Original
Monument Preservation, Vertical | Ea | _8210015 | 890 | 0 | 0 | 0 | 2 | 0 | 1000 | 0 | 0 | 0% | Yes | Original
_ Water Shutoff, Adj, Modified | Ea | _8237050 | 900 | 84 | 84 | 84 | 61 | 0 | 400 | 33600 | 33600 | 0.3% | Yes | Original
_Door Hanger Notifications, Modified | LS | _8507051 | 910 | 0 | 0 | 0 | 1 | 0 | 1000 | 0 | 0 | 0% | Yes | Original
_Railroad Protection, at Grade Crossing | Dlr | _8507060 | 920 | 0 | 0 | 0 | 2000 | 0 | 1 | 0 | 0 | 0% | Yes | Original
[10 empty] | 10372619.23 | 10372619.23
[9 empty] | Balance | -384158.32 | -384158.32