CONTRACT CHANGE ORDER

   DPW-CITY ENGINEERING DIVISION

	
TO (Contractor's Name and Address)

Fort Wayne Contracting/Ajax Paving
320 E. Seven Mile Rd
Detroit, Mi 48203
	Contract Title
PW-7018

11 locations, HMA, Sidewalk, Drainage Structures
	

Change No.    002
	

SPO # 3045637

	
	
	
CED No.   
PW-7018
	CPA# 

	6002903

	
	
	
Date Approved by City Council:



	
	
	Date Issued: 



Type of Contract Change      Routine 	Emergency 		Confirming         X - Reconciling 

Reason for Change – improved pedestrian safety.

All other terms and conditions of the Contract Documents are to remain the same.
initials/contract adm initials    


        Cost of Change:

LUMP SUM INCREASE/DECREASE TO CONTRACT PRICE ....................... + $____-139,170.85

	
ADJUSTMENT IN CONTRACT PRICE
	
CONTRACTOR'S ACCEPTANCE
The signatures below reflect acceptance of the terms and conditions of this contract


	Original Contract Price:                     
	$9,988,460.91 
	Contractor:  Fort Wayne Contracting/Ajax Paving





	Changes-Pending Approval:                          
	$-139,170.85
	
Signature:


	Date


	Changes Approved:                          
	$523,329.17
	Title:   


	
Net Amount this Change:                                      $384,158.27                
	
Signature:



	
	Title:   


	
	
FOR THE CITY OF DETROIT

	Proposed Contract Price:                   
	 $10,372,619.23
	Approved-City Engineer
DPW -City Engineering Division
	
Date


	
	
	Approved-Director
DPW
                                                        
	
Date

	Approved-Law Department
	Date
	
Approved-Chief Procurement Officer
Office of Contracts & Procurement


	Date








REASON FOR CHANGE


This change order serves to close the contract and reconcile any difference between the estimated contract bid quantities and the change orders with actual placed quantities for the project.

	CM
	Net Change

	10
	$3,061.15

	9
	$-142,232.05

	8
	$537,750.95

	7
	$-3,524.28

	6
	$-4,856.25

	5
	$3,750.00

	4
	$-7,778.75

	3
	$1,006.25

	2
	$-3,018.75

	1
	$0.00

	Initial Authorized Amount
	$9,988,460.91

	Final Contract Amount
	$10,372,619.18



