PW-7035A Pre-Con Talking Points:

General Information:

- 7035A will cover Districts 3, 4, 5, 6.

- The contract length is 180 Days.

- 1600 Installations City Wide of both Speed Humps and Speed Cushions

  - The City plans to install 4500 Speed Humps and 500 Speed Cushions by the end of 2021.

- The project will be run on FieldManager (built by HRC)

- Century Cement is the prime contractor for PW7035A (Giorgi/Major have PW7035B)

Project Management:

- Chart As-Built Productivity as the project progresses. (Excel/Graphs/Charts)

- Work must be completed in each district prior to moving to the next.

  - Work around schools will be delayed until 2021 Summer Break.

- Follow Special Provision for Speed Hump, HMA – Mitigate Dust in the Air

- Ahmad from TED will be available to assist HRC with locating exact locations for the Speed Humps.

  - HRC needs training on how to use the GIS phone application and the Collector phone application. (Talk with Tyler City of Detroit IT)

  - HRC needs access to GIS data.

  - Locations may vary based on site conditions.

Inspection/IDRs:

- Include all installation locations (use street addresses) in the general comments of each IDR.

- Only 2 Pay Items (Speed Humps and Pavt Mrkgs)

- Inspectors must mark locations, use the collector app once permanent pavement markings have been installed.

- Flyers must be posted 2-3 days before installation of the speed hump.

Items of Work:

- Each hump placed daily must have temporary pavement markings installed by the end of the day.

- Permanent pavement markings must be placed within 10 days of the Speed Hump installation.

- Template for Hump? Check compliance after installation.

- Do test sections to verify hump looks correct prior to installation.

Coordination:

- DTE has locations to coordinate against

- DWSD has locations to coordinate against (maps provided by CED)

- SMD Residential Milling contract has locations to coordinate against (Get with Pam for list of streets, SMD must pave prior to the Speed Hump Installation)

Questions:

- When will IT be able to provide training on the GIS and Collector Apps?

- Where can we get DTE map of work for coordination?

- Are the Speed Humps being tested? (HMA Sampling, density test)