## Muni comments
Activity ID | WBS | Project Name | Activity Name | Footage | Main Start | Main Finish | Service Start | Service Finish | Restoration Start | Restoration Finish | Comments
Muni9510 | PROJ-0951-MUN-2.24.1.2 | 2021 GRP - Municipality | Install Main - Abington Ave (1) (ANO W Warren Ave & W Warren Ave) | 100 | 2021-10-20 | 2021-10-20 |  |  | 2021-10-22 | 2021-10-22 | No Services in this segement
Muni9590 | PROJ-0951-MUN-2.25.1.2 | 2021 GRP - Municipality | Install Main - Abington Ave (2) (W Warren Ave & ASO W Warren Ave) | 110 | 2021-10-27 | 2021-10-27 |  |  | 2021-11-01 | 2021-11-01 | No Services in this segement
Muni7430 | PROJ-0951-MUN-2.4.1.2 | 2021 GRP - Municipality | Install Main - ANO Chicago (Griggs & Wyoming) | 968 | 06-24-21 A | 06-30-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni9670 | PROJ-0951-MUN-2.26.1.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (26' WWPL Archdale St & Archdale St) | 75 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-19 | 2021-11-19 | No Services in this segement
Muni11590 | PROJ-0951-MUN-2.26.2.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Archdale St & Clayburn St) | 850 | 2021-09-22 | 2021-09-27 | 2021-09-29 | 2021-10-12 | 2021-10-14 | 2021-10-14
Muni11750 | PROJ-0951-MUN-2.26.4.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Asbury Park & St Marys St) | 540 | 2021-10-07 | 2021-10-12 | 2021-10-14 | 2021-10-27 | 2021-10-29 | 2021-10-29
Muni11670 | PROJ-0951-MUN-2.26.3.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Clayburn St & Woodmont Ave) | 1305 | 2021-09-29 | 2021-10-05 | 2021-10-07 | 2021-10-20 | 2021-10-22 | 2021-10-22
Muni11830 | PROJ-0951-MUN-2.26.5.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Southfield Rd & 18' WWPL Archdale St) | 185 | 11-12-21* | 2021-11-12 |  |  | 2021-11-17 | 2021-11-17 | No Services in this segement
Muni11910 | PROJ-0951-MUN-2.27.2.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (4) (EOM Penrod St & Rosemont Ave) | 280 | 11-08-21* | 2021-11-10 |  |  | 2021-11-15 | 2021-11-15 | No Services in this segement
Muni9750 | PROJ-0951-MUN-2.27.1.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (4) (Rosemont Ave & 25' EEPL Ashton Ave) | 395 | 2021-11-12 | 2021-11-17 |  |  | 2021-11-22 | 2021-11-22 | No Services in this segement
Muni9830 | PROJ-0951-MUN-2.28.1.2 | 2021 GRP - Municipality | Install Main - Archdale St (2) (ANO W Warren Ave & W Warren Ave) | 105 | 2021-11-18 | 2021-11-18 |  |  | 2021-11-24 | 2021-11-24 | No Services in this segement
Muni9910 | PROJ-0951-MUN-2.29.1.2 | 2021 GRP - Municipality | Install Main - Archdale St (3) (W Warren Ave & ASO W Warren Ave) | 105 | 2021-11-24 | 2021-11-24 |  |  | 2021-11-30 | 2021-11-30 | No Services in this segement
Muni9990 | PROJ-0951-MUN-2.30.1.2 | 2021 GRP - Municipality | Install Main - Asbury Park (2) (ANO W Warren Ave & W Warren Ave) | 105 | 2021-11-23 | 2021-11-23 |  |  | 2021-11-29 | 2021-11-29 | No Services in this segement
Muni10070 | PROJ-0951-MUN-2.31.1.2 | 2021 GRP - Municipality | Install Main - Asbury Park (3) (W Waren Ave & ASO W Warren Ave) | 115 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-18 | 2021-11-18 | No Services in this segement
Muni8150 | PROJ-0951-MUN-2.7.1.2 | 2021 GRP - Municipality | Install Main - Ash (Vinewood & Roosevelt) | 715 | 05-17-21 A | 05-24-21 A | 08-30-21 A | 09-01-21 A | 2021-09-22 | 2021-09-22
Muni7990 | PROJ-0951-MUN-2.11.1.2 | 2021 GRP - Municipality | Install Main - ASO Chicago (Pinehurst & Birwood) | 665 | 07-12-21 A | 07-19-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni8470 | PROJ-0951-MUN-2.16.1.2 | 2021 GRP - Municipality | Install Main - ASO Michigan (At Vinewood) | 5 | 06-08-21 A | 06-08-21 A |  |  | 2021-09-21 | 2021-09-21 | No Services in this segement
Muni12070 | PROJ-0951-MUN-2.32.3.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (24' EWPL Archdale St & 4' WEPL Archdale St) | 40 | 09-20-21* | 2021-09-20 |  |  | 2021-09-23 | 2021-09-23 | No Services in this segement
Muni11990 | PROJ-0951-MUN-2.32.2.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (Archdale St & St Marys St) | 2950 | 2021-10-14 | 2021-11-02 | 2021-11-04 | 2021-11-17 | 2021-11-19 | 2021-11-19
Muni10150 | PROJ-0951-MUN-2.32.1.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (Southfield Rd & Archdale St) | 275 | 2021-11-04 | 2021-11-04 | 2021-11-08 | 2021-11-19 | 2021-11-23 | 2021-11-23
Muni7910 | PROJ-0951-MUN-2.10.1.2 | 2021 GRP - Municipality | Install Main - Birwood (Chicago & ASO Chicago) | 118 | 07-12-21 A | 07-12-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni7270 | PROJ-0951-MUN-2.2.1.2 | 2021 GRP - Municipality | Install Main - Chicago 2 (Wyoming & EOM) | 210 | 07-09-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni10230 | PROJ-0951-MUN-2.33.1.2 | 2021 GRP - Municipality | Install Main - Clayburn St (1) (23' NNPL ANO W Warren Ave & 5' NSPL ANO W Warren Ave) | 45 | [6 empty] | No Services in this segement
Muni12150 | PROJ-0951-MUN-2.33.2.2 | 2021 GRP - Municipality | Install Main - Clayburn St (1) (ANO W Warren Ave & W Warren Ave) | 110 | [6 empty] | No Services in this segement
Muni10470 | PROJ-0951-MUN-2.36.1.2 | 2021 GRP - Municipality | Install Main - Grandmont Ave (2) (W Warren Ave & ASO W Warren Ave) | 110 | 2021-11-02 | 2021-11-02 |  |  | 2021-11-05 | 2021-11-05 | No Services in this segement
Muni7510 | PROJ-0951-MUN-2.5.1.2 | 2021 GRP - Municipality | Install Main - Griggs (ANO Chicago & Chicago) | 95 | 06-24-21 A | 06-30-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni8550 | PROJ-0951-MUN-2.17.1.2 | 2021 GRP - Municipality | Install Main - Hubbard (West Grand Blvd & Michigan) | 701 | 06-10-21 A | 06-16-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni8790 | PROJ-0951-MUN-2.20.1.2 | 2021 GRP - Municipality | Install Main - Lahser (Santa Clara & Mcnichols) | 725 | 05-31-21 A | 06-17-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni12230 | PROJ-0951-MUN-2.37.2.2 | 2021 GRP - Municipality | Install Main - Longacre St (2) (ANO W Warren Ave & W Warren Ave) | 115 | [6 empty] | No Services in this segement
Muni10550 | PROJ-0951-MUN-2.37.1.2 | 2021 GRP - Municipality | Install Main - Longacre St (2) (EOM & ANO W Warren Ave) | 290
Muni10630 | PROJ-0951-MUN-2.38.1.2 | 2021 GRP - Municipality | Install Main - Longacre St (3) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-10-11 | 2021-10-11 |  |  | 2021-10-14 | 2021-10-14 | No Services in this segement
Muni8950 | PROJ-0951-MUN-2.13.2.2 | 2021 GRP - Municipality | Install Main - Magnolia (Mckinley & Roosevelt) | 328 | 06-25-21 A | 06-30-21 A |  |  | 2021-09-21 | 2021-09-21 | No Services in this segement
Muni8230 | PROJ-0951-MUN-2.13.1.2 | 2021 GRP - Municipality | Install Main - Magnolia (Vinewood & Mckinley) | 424 | 06-29-21 A | 06-30-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni9350 | PROJ-0951-MUN-2.18.2.2 | 2021 GRP - Municipality | Install Main - Mckinley (Magnolia & West Grand Blvd) | 606 | 06-22-21 A | 06-24-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni8630 | PROJ-0951-MUN-2.18.1.2 | 2021 GRP - Municipality | Install Main - Mckinley (NO Magnolia & Magnolia) | 234 | 06-23-21 A | 06-28-21 A | 2021-09-20 | 2021-10-01 | 2021-10-05 | 2021-10-05
Muni10710 | PROJ-0951-MUN-2.39.1.2 | 2021 GRP - Municipality | Install Main - Memorial St (1) (ANO W Warren Ave & W Warren Ave) | 100 |  |  |  |  | 2021-10-05 | 2021-10-05 | Schedule show no main in this segement just Resto may be this is carryover or so.
Muni10790 | PROJ-0951-MUN-2.40.1.2 | 2021 GRP - Municipality | Install Main - Memorial St (2) (W Warren Ave & ASO W Warren Ave) | 110 |  |  |  |  | 2021-10-05 | 2021-10-05 | Schedule show no main in this segement just Resto may be this is carryover or so.
Muni7830 | PROJ-0951-MUN-2.9.1.2 | 2021 GRP - Municipality | Install Main - Mendota (Chicago & ASO Chicago) | 118 | 07-13-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni10870 | PROJ-0951-MUN-2.41.1.2 | 2021 GRP - Municipality | Install Main - Mettetal St (3) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-18 | 2021-11-18 | No Services in this segement
Muni9030 | PROJ-0951-MUN-2.14.2.2 | 2021 GRP - Municipality | Install Main - Michigan (At Vinewood) | 223 | 06-01-21 A | 06-08-21 A |  |  | 2021-09-21 | 2021-09-21 | No Services in this segement
Muni8310 | PROJ-0951-MUN-2.14.1.2 | 2021 GRP - Municipality | Install Main - Michigan (Hubbard & Vinewood) | 427 | 05-24-21 A | 06-08-21 A |  |  | 2021-09-22 | 2021-09-22 | No Services in this segement
Muni8870 | PROJ-0951-MUN-2.21.1.2 | 2021 GRP - Municipality | Install Main - Orchard (At Lahser) | 24 | 06-17-21 A | 06-17-21 A |  |  | 2021-09-21 | 2021-09-21 | No Services in this segement
Muni8070 | PROJ-0951-MUN-2.12.1.2 | 2021 GRP - Municipality | Install Main - Pinehurst (Chicago & Joy) | 2722 | 05-10-21 A | 06-30-21 A | 08-30-21 A | 09-01-21 A | 2021-09-21 | 2021-09-21
Muni10950 | PROJ-0951-MUN-2.42.1.2 | 2021 GRP - Municipality | Install Main - Rutland St (1) (ANO W Warren Ave & W Warren Ave) | 110 | 2021-10-13 | 2021-10-13 |  |  | 2021-10-18 | 2021-10-18 | No Services in this segement
Muni11030 | PROJ-0951-MUN-2.43.1.2 | 2021 GRP - Municipality | Install Main - Rutland St (2) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-10-19 | 2021-10-19 |  |  | 2021-10-22 | 2021-10-22 | No Services in this segement
Muni11110 | PROJ-0951-MUN-2.44.1.2 | 2021 GRP - Municipality | Install Main - Southfield Fwy (M-39) (66' EEPL Ashton Ave & 112' WWPL Archdale St) | 545 | 10-29-21* | 2021-11-08 |  |  | 06-16-21 A | 2021-11-10 | No Services in this segement
Muni11190 | PROJ-0951-MUN-2.45.1.2 | 2021 GRP - Municipality | Install Main - St Marys St (2) (ANO W Warren Ave & W Warren Ave) | 95 | [6 empty] | No Services in this segement
Muni11270 | PROJ-0951-MUN-2.46.1.2 | 2021 GRP - Municipality | Install Main - St Marys St (3) (W Warren Ave & ASO W Warren Ave) | 105 | [6 empty] | No Services in this segement
Muni8710 | PROJ-0951-MUN-2.19.1.2 | 2021 GRP - Municipality | Install Main - Vinewood (Magnolia & Michigan) | 1562 | 05-06-21 A | 05-24-21 A | 2021-09-20 | 2021-10-01 | 2021-10-05 | 2021-10-05 | No Services in this segement
Muni9430 | PROJ-0951-MUN-2.19.2.2 | 2021 GRP - Municipality | Install Main - Vinewood (Michigan & ASO Michigan) | 70 | 05-06-21 A | 06-08-21 A |  |  | 2021-09-21 | 2021-09-21 | No Services in this segement
Muni7750 | PROJ-0951-MUN-2.6.2.2 | 2021 GRP - Municipality | Install Main - W Chicago 1 (Pinehurst & Birwood) | 664 | 07-13-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni7590 | PROJ-0951-MUN-2.6.1.2 | 2021 GRP - Municipality | Install Main - W Chicago 1 (Pinehurst & Griggs) | 1160 | 06-14-21 A | 06-30-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni11350 | PROJ-0951-MUN-2.47.1.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (0' SNPL W Warren Ave & 0' NSPL W Warren Ave) | 100 | 2021-11-22 | 2021-11-22 |  |  | 2021-11-26 | 2021-11-26 | No Services in this segement
Muni13270 | PROJ-0951-MUN-2.47.14.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (0' SNPL W Warren Ave & 0' Sspl W Warren Ave) | 110 | 2021-11-29 | 2021-11-29 |  |  | 2021-12-02 | 2021-12-02 | No Services in this segement
Muni13030 | PROJ-0951-MUN-2.47.11.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (108' WWPL Asbury Park & Asbury Park) | 200 | 2021-11-10 | 2021-11-10 |  |  | 2021-11-15 | 2021-11-15 | No Services in this segement
Muni12630 | PROJ-0951-MUN-2.47.6.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (114' WWPL Abington Ave & 160' EEPL Abington Ave) | 335 | 2021-10-25 | 2021-10-25 |  |  | 2021-10-28 | 2021-10-28 | No Services in this segement
Muni12390 | PROJ-0951-MUN-2.47.3.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (150' WWPL Longacre St & 215' Longacre St) | 430 | 2021-10-06 | 2021-10-07 |  |  | 2021-10-12 | 2021-10-12 | No Services in this segement
Muni12550 | PROJ-0951-MUN-2.47.5.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (189' WWPL Abington Ave & Abington Ave) | 195 | 2021-10-21 | 2021-10-21 |  |  | 2021-10-26 | 2021-10-26 | No Services in this segement
Muni12310 | PROJ-0951-MUN-2.47.2.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (201' WWPL Longacre St & 13' EEPL Clayburn St) | 840 | 2021-09-29 | 2021-10-01 |  |  | 2021-10-07 | 2021-10-07 | No Services in this segement
Muni12790 | PROJ-0951-MUN-2.47.8.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (213' WWPL Woodmont Ave & 4' EWPL Woodmont Ave) | 220 | 2021-11-04 | 2021-11-04 |  |  | 2021-11-09 | 2021-11-09 | No Services in this segement
Muni12870 | PROJ-0951-MUN-2.47.9.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' EWPL Woodmont Ave & 4' WEPL Asbury Park) | 385 | 2021-11-17 | 2021-11-19 |  |  | 2021-11-24 | 2021-11-24 | No Services in this segement
Muni12950 | PROJ-0951-MUN-2.47.10.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' WEPL Asbury Park & 95' EEPL Asbury Park) | 100 | 2021-11-08 | 2021-11-08 |  |  | 2021-11-11 | 2021-11-11 | No Services in this segement
Muni12470 | PROJ-0951-MUN-2.47.4.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' WEPL Ruthland St & 158' EEPL Ruthland St) | 165 | 2021-10-15 | 2021-10-15 |  |  | 2021-10-20 | 2021-10-20 | No Services in this segement
Muni13110 | PROJ-0951-MUN-2.47.12.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Asbury Park & 209' EEPL Asbury Park) | 215 | 2021-11-12 | 2021-11-12 |  |  | 2021-11-17 | 2021-11-17 | No Services in this segement
Muni12710 | PROJ-0951-MUN-2.47.7.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Grandmont Ave & 149' EEPL Grandmont Ave) | 155 | 2021-10-29 | 2021-10-29 |  |  | 2021-11-03 | 2021-11-03 | No Services in this segement
Muni13190 | PROJ-0951-MUN-2.47.13.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Mettetal St & 266' EEPL Mettetal St) | 270 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-18 | 2021-11-18 | No Services in this segement
Muni9190 | PROJ-0951-MUN-2.15.3.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (EOM & Mckinley) | 82 | 06-23-21 A | 06-24-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni8390 | PROJ-0951-MUN-2.15.1.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (West Grand Blvd & EOM) | 109 | 06-15-21 A | 06-16-21 A | 2021-09-20 | 2021-10-01 | 2021-10-05 | 2021-10-05
Muni9110 | PROJ-0951-MUN-2.15.2.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (West Grand Blvd & Vinewood) | 336 | 06-15-21 A | 06-16-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni9270 | PROJ-0951-MUN-2.22.4.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (2) (Mckinley & Ash) | 589 | 06-17-21 A | 06-22-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni11430 | PROJ-0951-MUN-2.48.1.2 | 2021 GRP - Municipality | Install Main - Woodmont Ave (1) (ANO W Warren Ave & W Warren Ave) | 115 | [6 empty] | No Services in this segement
Muni11510 | PROJ-0951-MUN-2.49.1.2 | 2021 GRP - Municipality | Install Main - Woodmont Ave (2) (W Warren Ave & ASO W Warren Ave) | 100 |  |  |  |  | 2021-11-24 | 2021-11-24 | Restoration only Could be carryover
Muni7350 | PROJ-0951-MUN-2.3.1.2 | 2021 GRP - Municipality | Install Main - Wyoming (ANO Chicago & Chicago) | 167 | 07-02-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-23 |  | No Services in this segement
RR1 11181 | GRP-2021-FR.55.1.2 | 2021 GRP - Field Recommendation | Install Main - 18th (9'WEPL 18th & 3' WWPL 18th) | 18 | 2021-10-13 | 2021-10-14 |  |  | 2021-12-10 | 2021-09-23 | Fixed no services
Formulas:
Main Start = IFERROR(VLOOKUP([WBS],Main!$B:$G,5,FALSE),"")
Main Finish = IFERROR(VLOOKUP([WBS],Main!$B:$G,6,FALSE),"")
Restoration Start = IFERROR(VLOOKUP([WBS],Rest!$B:$F,5,FALSE),"")
Restoration Finish = IFERROR(VLOOKUP([WBS],Rest!$B:$G,6,FALSE),"")
Restoration Finish = IFERROR(VLOOKUP([WBS, row above],Rest!$B:$G,6,FALSE),"")
Service Start = IFERROR(VLOOKUP([WBS],Service!$B:$G,5,FALSE),"")
Service Finish = IFERROR(VLOOKUP([WBS],Service!$B:$G,6,FALSE),"")

## Residential Paving
Activity ID | WBS | Project Name | Activity Name | Footage | Main Start | Main Finish | Service Start | Service Finish | Resto Start | Resto Finish
EDET1 50657 | GRP-2021-ED1.37.1.2 | 2021 GRP - East Detroit 1 | Install Main - Yorkshire Rd (2) (Waveney St & Mack Ave) | 2610 | 01-04-21 A | 01-12-21 A | 01-19-21 A | 02-22-21 A | 05-18-21 A | 05-26-21 A
EDET1 50643 | GRP-2021-ED1.22.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bishop St (2) (Waveney St & Mack Ave) | 1400 | 01-04-21 A | 01-07-21 A | 02-01-21 A | 03-09-21 A | 05-04-21 A | 05-26-21 A
EDET1 50640 | GRP-2021-ED1.19.1.2 | 2021 GRP - East Detroit 1 | Install Main - Audubon Rd (2) (E Warrern Ave & Waveney St) | 1765 | 02-01-21 A | 03-09-21 A | 03-29-21 A | 05-03-21 A | 05-27-21 A | 05-28-21 A
NCDET - 5220 | NEWPROJ-6.3.2.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - Birwood (ANO Fenkell & Fenkell) - "Only to be installed if services cannot be moved to the alley" | 104 | 02-02-21 A | 02-02-21 A |  |  | 2021-09-23 | 2021-09-29
CDET2-1535 | GRP-2021-CDet2.2.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Glynn 1 (Dexter & Linwood) | 2624 | 02-02-21 A | 02-23-21 A | 03-11-21 A | 04-12-21 A | 06-22-21 A | 07-21-21 A
EDET1 50656 | GRP-2021-ED1.36.1.2 | 2021 GRP - East Detroit 1 | Install Main - Yorkshire Rd (1) (E Warrern Ave & Waveney St) | 1775 | 02-22-21 A | 02-26-21 A | 03-24-21 A | 03-31-21 A | 05-26-21 A | 05-26-21 A
EDET1 504716 | GRP-2021-ED1.18.5.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (Cadieux Dr & ASO E Warren Ave) | 110 | 03-05-21 A | 03-05-21 A | 2021-09-20 | 2021-09-20 | 2021-09-24 | 2021-09-29
EDET1 505196 | GRP-2021-ED1.18.11.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) S (Bishop St & Grayton St) | 315 | 03-08-21 A | 03-09-21 A | 2021-09-20 | 2021-09-20 | 2021-09-23 | 2021-09-28
EDET1 501120 | GRP-2021-ED1.74.1.2 | 2021 GRP - East Detroit 1 | Install Main - Buckingham Ave (2) (Waveney St & Mack Ave) | 2600 | 03-11-21 A | 03-17-21 A | 06-18-21 A | 06-21-21 A | 06-02-21 A | 2021-09-28
EDET1 503756 | GRP-2021-ED1.69.3.2 | 2021 GRP - East Detroit 1 | Install Main - Bedford St (1) (E Warren Ave & Waveney St) East | 1820 | 03-18-21 A | 03-23-21 A | 04-12-21 A | 05-19-21 A | 05-27-21 A | 06-07-21 A
EDET1 507396 | GRP-2021-ED1.69.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bedford St (1) (E Warren Ave & Waveney St) West | 1820 | 03-22-21 A | 03-30-21 A |  |  | 05-27-21 A | 06-07-21 A
EDET1 50469 | GRP-2021-ED1.18.1.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) S (Bishop St & Grayton St) | 315 | 04-12-21 A | 04-28-21 A | 2021-09-20 | 2021-09-20 | 2021-09-27 | 2021-09-30
EDET1 501045 | GRP-2021-ED1.53.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bremen St (2) (Balfour Rd & Buckingham Ave) | 885 | 03-25-21 A | 03-26-21 A | 06-18-21 A | 06-21-21 A | 2021-09-23 | 2021-09-28
EDET1 503906 | GRP-2021-ED1.75.3.2 | 2021 GRP - East Detroit 1 | Install Main - Devonshire Rd (1) (ASO E Warren Ave & Waveney Ave) | 1820 | 04-01-21 A | 04-07-21 A | 04-26-21 A | 05-19-21 A | 06-07-21 A | 07-08-21 A
EDET1 501054 | GRP-2021-ED1.62.1.2 | 2021 GRP - East Detroit 1 | Install Main - Somerset Ave (2) (Waveney St & Mack Ave) | 2335 | 03-30-21 A | 04-07-21 A | 04-26-21 A | 05-19-21 A | 06-07-21 A | 07-12-21 A
EDET1 501117 | GRP-2021-ED1.71.1.2 | 2021 GRP - East Detroit 1 | Install Main - Berkshire St (1) (ASO E Warrern Ave & Waveney St) | 1820 | 04-14-21 A | 04-16-21 A | 05-23-21 A | 05-23-21 A | 05-28-21 A | 2021-09-28
EDET1 506796 | GRP-2021-ED1.62.1.2 | 2021 GRP - East Detroit 1 | Install Main - Somerset Ave (2) (ANO Mack & Mack) | 160 | 03-30-21 A | 04-07-21 A | 04-26-21 A | 05-19-21 A | 06-07-21 A | 07-12-21 A
Muni8310 | PROJ-0951-MUN-2.14.1.2 | 2021 GRP - Municipality | Install Main - Michigan (Hubbard & Vinewood) | 427 | 05-24-21 A | 06-08-21 A |  |  | 2021-09-22 | 2021-09-22
Muni8070 | PROJ-0951-MUN-2.12.1.2 | 2021 GRP - Municipality | Install Main - Pinehurst (Chicago & Joy) | 2722 | 05-10-21 A | 06-30-21 A | 08-30-21 A | 09-01-21 A | 2021-09-21 | 2021-09-21
EDET1 501121 | GRP-2021-ED1.75.1.2 | 2021 GRP - East Detroit 1 | Install Main - Devonshire Rd (1) (ANO E Warren Ave & ASO E Warren Ave) | 315 | 05-10-21 A | 05-10-21 A |  |  | 2021-09-23 | 2021-09-28
Muni9030 | PROJ-0951-MUN-2.14.2.2 | 2021 GRP - Municipality | Install Main - Michigan (At Vinewood) | 223 | 06-01-21 A | 06-08-21 A |  |  | 2021-09-21 | 2021-09-21
Muni9430 | PROJ-0951-MUN-2.19.2.2 | 2021 GRP - Municipality | Install Main - Vinewood (Michigan & ASO Michigan) | 70 | 05-06-21 A | 06-08-21 A |  |  | 2021-09-21 | 2021-09-21
Muni8470 | PROJ-0951-MUN-2.16.1.2 | 2021 GRP - Municipality | Install Main - ASO Michigan (At Vinewood) | 5 | 06-08-21 A | 06-08-21 A |  |  | 2021-09-21 | 2021-09-21
Muni8550 | PROJ-0951-MUN-2.17.1.2 | 2021 GRP - Municipality | Install Main - Hubbard (West Grand Blvd & Michigan) | 701 | 06-10-21 A | 06-16-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni8790 | PROJ-0951-MUN-2.20.1.2 | 2021 GRP - Municipality | Install Main - Lahser (Santa Clara & Mcnichols) | 725 | 05-31-21 A | 06-17-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
NDET3-325 | GRP-2021-ND3.59.3.2 | 2021 GRP - North Detroit 3 | Install Main - Keystone St (1) (Hamlet St & E Outer Dr) | 1935 | 04-20-21 A | 04-23-21 A | 08-30-21 A | 09-01-21 A | 08-27-21 A | 2021-09-28
Muni8710 | PROJ-0951-MUN-2.19.1.2 | 2021 GRP - Municipality | Install Main - Vinewood (Magnolia & Michigan) | 1562 | 05-06-21 A | 05-24-21 A | 2021-09-20 | 2021-10-01 | 2021-10-05 | 2021-10-05
NDET3-6605 | GRP-2021-ND3.60.1.2 | 2021 GRP - North Detroit 3 | Install Main - Moenart St (1) (8 Mile Rd (M102) & Hamlet St) | 455 | 04-26-21 A | 04-26-21 A | 08-30-21 A | 09-01-21 A | 2021-09-23 | 2021-09-28
NDET3-6665 | GRP-2021-ND3.60.3.2 | 2021 GRP - North Detroit 3 | Install Main - Moenart St (1) (Hamlet St & E Outer Dr) | 1935 | 04-26-21 A | 05-04-21 A | 08-16-21 A | 08-19-21 A | 2021-09-23 | 2021-09-28
EDET1 504556 | GRP-2021-ED1.18.3.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Cadieux Rd) | 105 | 05-13-21 A | 05-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-23 | 2021-09-28
EDET1 504636 | GRP-2021-ED1.18.4.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (Cadieux Rd & ANO E Warren Ave) | 100 | 05-13-21 A | 05-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-24 | 2021-09-29
NDET3-6540 | GRP-2021-ND3.49.1.2 | 2021 GRP - North Detroit 3 | Install Main - Bloom St (1) (8 Mile Rd (M102) & Hamlet St) | 455 | 05-11-21 A | 05-12-21 A | 08-16-21 A | 08-16-21 A | 09-13-21 A | 09-13-21 A
Muni7590 | PROJ-0951-MUN-2.6.1.2 | 2021 GRP - Municipality | Install Main - W Chicago 1 (Pinehurst & Griggs) | 1160 | 06-14-21 A | 06-30-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
NDET3-6365 | GRP-2021-ND3.49.3.2 | 2021 GRP - North Detroit 3 | Install Main - Bloom St (1) (Hamlet St & E Outer Dr) | 1925 | 05-06-21 A | 05-11-21 A | 08-10-21 A | 08-16-21 A | 09-07-21 A | 2021-09-28
Muni8870 | PROJ-0951-MUN-2.21.1.2 | 2021 GRP - Municipality | Install Main - Orchard (At Lahser) | 24 | 06-17-21 A | 06-17-21 A |  |  | 2021-09-21 | 2021-09-21
Muni9270 | PROJ-0951-MUN-2.22.4.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (2) (Mckinley & Ash) | 589 | 06-17-21 A | 06-22-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni7910 | PROJ-0951-MUN-2.10.1.2 | 2021 GRP - Municipality | Install Main - Birwood (Chicago & ASO Chicago) | 118 | 07-12-21 A | 07-12-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni7990 | PROJ-0951-MUN-2.11.1.2 | 2021 GRP - Municipality | Install Main - ASO Chicago (Pinehurst & Birwood) | 665 | 07-12-21 A | 07-19-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni8390 | PROJ-0951-MUN-2.15.1.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (West Grand Blvd & EOM) | 109 | 06-15-21 A | 06-16-21 A | 2021-09-20 | 2021-10-01 | 2021-10-05 | 2021-10-05
Muni9110 | PROJ-0951-MUN-2.15.2.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (West Grand Blvd & Vinewood) | 336 | 06-15-21 A | 06-16-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
SWDET2-9945 | PROJ-0951-SWDET2.12.5.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor 4 (Tie-in & Dix) | 84 | 2021-10-21 | 2021-10-22 |  |  | 2021-11-03 | 2021-11-08
Muni7750 | PROJ-0951-MUN-2.6.2.2 | 2021 GRP - Municipality | Install Main - W Chicago 1 (Pinehurst & Birwood) | 664 | 07-13-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni9190 | PROJ-0951-MUN-2.15.3.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (EOM & Mckinley) | 82 | 06-23-21 A | 06-24-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni7510 | PROJ-0951-MUN-2.5.1.2 | 2021 GRP - Municipality | Install Main - Griggs (ANO Chicago & Chicago) | 95 | 06-24-21 A | 06-30-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni8630 | PROJ-0951-MUN-2.18.1.2 | 2021 GRP - Municipality | Install Main - Mckinley (NO Magnolia & Magnolia) | 234 | 06-23-21 A | 06-28-21 A | 2021-09-20 | 2021-10-01 | 2021-10-05 | 2021-10-05
Muni7430 | PROJ-0951-MUN-2.4.1.2 | 2021 GRP - Municipality | Install Main - ANO Chicago (Griggs & Wyoming) | 968 | 06-24-21 A | 06-30-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
RR1 8921 | GRP-2021-RR.46.1.2 | 2021 GRP - Risk Rank | Install Main - College (Conner & Gunston) | 3729 | 05-06-21 A | 05-25-21 A | 08-30-21 A | 09-01-21 A | 2021-09-23 | 2021-09-28
Muni7830 | PROJ-0951-MUN-2.9.1.2 | 2021 GRP - Municipality | Install Main - Mendota (Chicago & ASO Chicago) | 118 | 07-13-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni9350 | PROJ-0951-MUN-2.18.2.2 | 2021 GRP - Municipality | Install Main - Mckinley (Magnolia & West Grand Blvd) | 606 | 06-22-21 A | 06-24-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni8230 | PROJ-0951-MUN-2.13.1.2 | 2021 GRP - Municipality | Install Main - Magnolia (Vinewood & Mckinley) | 424 | 06-29-21 A | 06-30-21 A | 2021-09-20 | 2021-10-01 | 2021-10-06 | 2021-10-06
Muni8950 | PROJ-0951-MUN-2.13.2.2 | 2021 GRP - Municipality | Install Main - Magnolia (Mckinley & Roosevelt) | 328 | 06-25-21 A | 06-30-21 A |  |  | 2021-09-21 | 2021-09-21
Muni10150 | PROJ-0951-MUN-2.32.1.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (Southfield Rd & Archdale St) | 275 | 2021-11-04 | 2021-11-04 | 2021-11-08 | 2021-11-19 | 2021-11-23 | 2021-11-23
Muni7350 | PROJ-0951-MUN-2.3.1.2 | 2021 GRP - Municipality | Install Main - Wyoming (ANO Chicago & Chicago) | 167 | 07-02-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-23 | 2021-09-23
Muni10550 | PROJ-0951-MUN-2.37.1.2 | 2021 GRP - Municipality | Install Main - Longacre St (2) (EOM & ANO W Warren Ave) | 290
EDET1 50845 | GRP-2021-ED1.47.1.2 | 2021 GRP - East Detroit 1 | Install Main - Wayburn Ave (1) (E Warrern Ave & Waveney St) | 1790 | 04-22-21 A | 04-28-21 A | 07-15-21 A | 07-20-21 A | 07-12-21 A | 07-21-21 A
Muni8150 | PROJ-0951-MUN-2.7.1.2 | 2021 GRP - Municipality | Install Main - Ash (Vinewood & Roosevelt) | 715 | 05-17-21 A | 05-24-21 A | 08-30-21 A | 09-01-21 A | 2021-09-22 | 2021-09-22
Muni12230 | PROJ-0951-MUN-2.37.2.2 | 2021 GRP - Municipality | Install Main - Longacre St (2) (ANO W Warren Ave & W Warren Ave) | 115
Muni12310 | PROJ-0951-MUN-2.47.2.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (201' WWPL Longacre St & 13' EEPL Clayburn St) | 840 | 2021-09-29 | 2021-10-01 |  |  | 2021-10-07 | 2021-10-07
Muni7270 | PROJ-0951-MUN-2.2.1.2 | 2021 GRP - Municipality | Install Main - Chicago 2 (Wyoming & EOM) | 210 | 07-09-21 A | 07-13-21 A | 2021-09-20 | 2021-09-20 | 2021-09-22 | 2021-09-22
Muni12390 | PROJ-0951-MUN-2.47.3.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (150' WWPL Longacre St & 215' Longacre St) | 430 | 2021-10-06 | 2021-10-07 |  |  | 2021-10-12 | 2021-10-12
Muni10630 | PROJ-0951-MUN-2.38.1.2 | 2021 GRP - Municipality | Install Main - Longacre St (3) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-10-11 | 2021-10-11 |  |  | 2021-10-14 | 2021-10-14
Muni10950 | PROJ-0951-MUN-2.42.1.2 | 2021 GRP - Municipality | Install Main - Rutland St (1) (ANO W Warren Ave & W Warren Ave) | 110 | 2021-10-13 | 2021-10-13 |  |  | 2021-10-18 | 2021-10-18
Muni12470 | PROJ-0951-MUN-2.47.4.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' WEPL Ruthland St & 158' EEPL Ruthland St) | 165 | 2021-10-15 | 2021-10-15 |  |  | 2021-10-20 | 2021-10-20
Muni11030 | PROJ-0951-MUN-2.43.1.2 | 2021 GRP - Municipality | Install Main - Rutland St (2) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-10-19 | 2021-10-19 |  |  | 2021-10-22 | 2021-10-22
Muni10230 | PROJ-0951-MUN-2.33.1.2 | 2021 GRP - Municipality | Install Main - Clayburn St (1) (23' NNPL ANO W Warren Ave & 5' NSPL ANO W Warren Ave) | 45
Muni12150 | PROJ-0951-MUN-2.33.2.2 | 2021 GRP - Municipality | Install Main - Clayburn St (1) (ANO W Warren Ave & W Warren Ave) | 110
Muni10310 | PROJ-0951-MUN-2.34.1.2 | 2021 GRP - Municipality | Install Main - Clayburn St (2) (W Warren Ave & ASO W Warren Ave) | 100 |  |  |  |  | 2021-10-05 | 2021-10-05
Muni10710 | PROJ-0951-MUN-2.39.1.2 | 2021 GRP - Municipality | Install Main - Memorial St (1) (ANO W Warren Ave & W Warren Ave) | 100 |  |  |  |  | 2021-10-05 | 2021-10-05
Muni10790 | PROJ-0951-MUN-2.40.1.2 | 2021 GRP - Municipality | Install Main - Memorial St (2) (W Warren Ave & ASO W Warren Ave) | 110 |  |  |  |  | 2021-10-05 | 2021-10-05
Muni9510 | PROJ-0951-MUN-2.24.1.2 | 2021 GRP - Municipality | Install Main - Abington Ave (1) (ANO W Warren Ave & W Warren Ave) | 100 | 2021-10-20 | 2021-10-20 |  |  | 2021-10-22 | 2021-10-22
Muni12550 | PROJ-0951-MUN-2.47.5.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (189' WWPL Abington Ave & Abington Ave) | 195 | 2021-10-21 | 2021-10-21 |  |  | 2021-10-26 | 2021-10-26
Muni12630 | PROJ-0951-MUN-2.47.6.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (114' WWPL Abington Ave & 160' EEPL Abington Ave) | 335 | 2021-10-25 | 2021-10-25 |  |  | 2021-10-28 | 2021-10-28
Muni11910 | PROJ-0951-MUN-2.27.2.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (4) (EOM Penrod St & Rosemont Ave) | 280 | 11-08-21* | 2021-11-10 |  |  | 2021-11-15 | 2021-11-15
Muni9590 | PROJ-0951-MUN-2.25.1.2 | 2021 GRP - Municipality | Install Main - Abington Ave (2) (W Warren Ave & ASO W Warren Ave) | 110 | 2021-10-27 | 2021-10-27 |  |  | 2021-11-01 | 2021-11-01
Muni10390 | PROJ-0951-MUN-2.35.1.2 | 2021 GRP - Municipality | Install Main - Grandmont Ave (1) (ANO W Warren Ave & W Warren Ave) | 100 |  |  |  |  | 2021-11-01 | 2021-11-01
Muni9750 | PROJ-0951-MUN-2.27.1.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (4) (Rosemont Ave & 25' EEPL Ashton Ave) | 395 | 2021-11-12 | 2021-11-17 |  |  | 2021-11-22 | 2021-11-22
Muni12710 | PROJ-0951-MUN-2.47.7.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Grandmont Ave & 149' EEPL Grandmont Ave) | 155 | 2021-10-29 | 2021-10-29 |  |  | 2021-11-03 | 2021-11-03
Muni10470 | PROJ-0951-MUN-2.36.1.2 | 2021 GRP - Municipality | Install Main - Grandmont Ave (2) (W Warren Ave & ASO W Warren Ave) | 110 | 2021-11-02 | 2021-11-02 |  |  | 2021-11-05 | 2021-11-05
Muni11430 | PROJ-0951-MUN-2.48.1.2 | 2021 GRP - Municipality | Install Main - Woodmont Ave (1) (ANO W Warren Ave & W Warren Ave) | 115
Muni11110 | PROJ-0951-MUN-2.44.1.2 | 2021 GRP - Municipality | Install Main - Southfield Fwy (M-39) (66' EEPL Ashton Ave & 112' WWPL Archdale St) | 545 | 10-29-21* | 2021-11-08 |  |  | 06-16-21 A | 2021-11-10
Muni12790 | PROJ-0951-MUN-2.47.8.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (213' WWPL Woodmont Ave & 4' EWPL Woodmont Ave) | 220 | 2021-11-04 | 2021-11-04 |  |  | 2021-11-09 | 2021-11-09
Muni12870 | PROJ-0951-MUN-2.47.9.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' EWPL Woodmont Ave & 4' WEPL Asbury Park) | 385 | 2021-11-17 | 2021-11-19 |  |  | 2021-11-24 | 2021-11-24
Muni11510 | PROJ-0951-MUN-2.49.1.2 | 2021 GRP - Municipality | Install Main - Woodmont Ave (2) (W Warren Ave & ASO W Warren Ave) | 100 |  |  |  |  | 2021-11-24 | 2021-11-24
Muni9990 | PROJ-0951-MUN-2.30.1.2 | 2021 GRP - Municipality | Install Main - Asbury Park (2) (ANO W Warren Ave & W Warren Ave) | 105 | 2021-11-23 | 2021-11-23 |  |  | 2021-11-29 | 2021-11-29
Muni11830 | PROJ-0951-MUN-2.26.5.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Southfield Rd & 18' WWPL Archdale St) | 185 | 11-12-21* | 2021-11-12 |  |  | 2021-11-17 | 2021-11-17
Muni9670 | PROJ-0951-MUN-2.26.1.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (26' WWPL Archdale St & Archdale St) | 75 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-19 | 2021-11-19
Muni12950 | PROJ-0951-MUN-2.47.10.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' WEPL Asbury Park & 95' EEPL Asbury Park) | 100 | 2021-11-08 | 2021-11-08 |  |  | 2021-11-11 | 2021-11-11
Muni9830 | PROJ-0951-MUN-2.28.1.2 | 2021 GRP - Municipality | Install Main - Archdale St (2) (ANO W Warren Ave & W Warren Ave) | 105 | 2021-11-18 | 2021-11-18 |  |  | 2021-11-24 | 2021-11-24
Muni13030 | PROJ-0951-MUN-2.47.11.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (108' WWPL Asbury Park & Asbury Park) | 200 | 2021-11-10 | 2021-11-10 |  |  | 2021-11-15 | 2021-11-15
Muni11350 | PROJ-0951-MUN-2.47.1.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (0' SNPL W Warren Ave & 0' NSPL W Warren Ave) | 100 | 2021-11-22 | 2021-11-22 |  |  | 2021-11-26 | 2021-11-26
Muni13110 | PROJ-0951-MUN-2.47.12.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Asbury Park & 209' EEPL Asbury Park) | 215 | 2021-11-12 | 2021-11-12 |  |  | 2021-11-17 | 2021-11-17
Muni10070 | PROJ-0951-MUN-2.31.1.2 | 2021 GRP - Municipality | Install Main - Asbury Park (3) (W Waren Ave & ASO W Warren Ave) | 115 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-18 | 2021-11-18
Muni9910 | PROJ-0951-MUN-2.29.1.2 | 2021 GRP - Municipality | Install Main - Archdale St (3) (W Warren Ave & ASO W Warren Ave) | 105 | 2021-11-24 | 2021-11-24 |  |  | 2021-11-30 | 2021-11-30
Muni10870 | PROJ-0951-MUN-2.41.1.2 | 2021 GRP - Municipality | Install Main - Mettetal St (3) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-18 | 2021-11-18
Muni12070 | PROJ-0951-MUN-2.32.3.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (24' EWPL Archdale St & 4' WEPL Archdale St) | 40 | 09-20-21* | 2021-09-20 |  |  | 2021-09-23 | 2021-09-23
Muni13190 | PROJ-0951-MUN-2.47.13.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Mettetal St & 266' EEPL Mettetal St) | 270 | 2021-11-16 | 2021-11-16 |  |  | 2021-11-18 | 2021-11-18
Muni11590 | PROJ-0951-MUN-2.26.2.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Archdale St & Clayburn St) | 850 | 2021-09-22 | 2021-09-27 | 2021-09-29 | 2021-10-12 | 2021-10-14 | 2021-10-14
Muni11190 | PROJ-0951-MUN-2.45.1.2 | 2021 GRP - Municipality | Install Main - St Marys St (2) (ANO W Warren Ave & W Warren Ave) | 95
Muni13270 | PROJ-0951-MUN-2.47.14.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (0' SNPL W Warren Ave & 0' Sspl W Warren Ave) | 110 | 2021-11-29 | 2021-11-29 |  |  | 2021-12-02 | 2021-12-02
Muni11270 | PROJ-0951-MUN-2.46.1.2 | 2021 GRP - Municipality | Install Main - St Marys St (3) (W Warren Ave & ASO W Warren Ave) | 105
Muni11670 | PROJ-0951-MUN-2.26.3.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Clayburn St & Woodmont Ave) | 1305 | 2021-09-29 | 2021-10-05 | 2021-10-07 | 2021-10-20 | 2021-10-22 | 2021-10-22
Muni11990 | PROJ-0951-MUN-2.32.2.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (Archdale St & St Marys St) | 2950 | 2021-10-14 | 2021-11-02 | 2021-11-04 | 2021-11-17 | 2021-11-19 | 2021-11-19
Muni11750 | PROJ-0951-MUN-2.26.4.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Asbury Park & St Marys St) | 540 | 2021-10-07 | 2021-10-12 | 2021-10-14 | 2021-10-27 | 2021-10-29 | 2021-10-29
RR1 11371 | GRP-2021-FR.65.1.2 | 2021 GRP - Field Recommendation | Install Main - Rohns (Mack & Goethe) | 891 | 06-22-21 A | 06-24-21 A | 2021-09-20 | 2021-09-20 | 2021-09-24 | 2021-09-29
Formulas:
Resto Start = IFERROR(VLOOKUP([WBS],Rest!$B:$F,5,FALSE),"")
Resto Finish = IFERROR(VLOOKUP([WBS],Rest!$B:$G,6,FALSE),"")
Service Start = IFERROR(VLOOKUP([WBS],Service!$B:$F,5,FALSE),"")
Service Finish = IFERROR(VLOOKUP([WBS],Service!$B:$G,6,FALSE),"")
Main Start = IFERROR(VLOOKUP([WBS],Main!$B:$F,5,FALSE),"")
Main Finish = IFERROR(VLOOKUP([WBS],Main!$B:$G,6,FALSE),"")

## Speed Hump
OBJECTID1 | Join_Count | TARGET_FID | OBJECTID | RDNAME | FROMDESC | TODESC | Activity ID | WBS | Activity Name | Main Start | Main Finish | Selected_Blocks | COUNT | site_status | Id | Agency | Phase | Activity | Project_ID | Length | Contract | Proj_Type | Street | From_ | To | Start_Date | End_Date | Contact | Phone | Email | Pub_Contac | Pub_Phone | Pub_Web | Last_Updat | Datum | Municipali | Name | Name_1 | Shape__Area | Shape__Length | Shape_Length | Service Start | Service Finish | Restoration Start | Restoration Finish
1 | 1 | 2 | 2329 | Binder St | E Lantz St | E Outer Dr | NDET3-7515 | GRP-2021-ND3.63.1.2 | Elevate Main - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 06-21-21 A | 06-29-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.3396 | 06-18-21 A | 06-21-21 A | 2021-09-24 | 2021-09-29
2 | 1 | 11 | 3965 | Mitchell St | E 7 Mile Rd | Emery St | NDET3-6795 | GRP-2021-ND3.79.1.2 | Elevate Main - Mitchell St (2) (E Outer Dr & ANO 7 Mile Rd) | 10-06-21* | 2021-10-14 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 394.7284 | 2021-09-23 | 2021-10-05 | 2021-10-21 | 2021-10-26
5 | 1 | 25 | 962 | Binder St | E Remington St | E Winchester Ave | NDET3-7515 | GRP-2021-ND3.63.1.2 | Elevate Main - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 06-21-21 A | 06-29-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 373.641 | 06-18-21 A | 06-21-21 A | 2021-09-24 | 2021-09-29
10 | 1 | 62 | 2310 | Sunset St | E Lantz St | E Outer Dr | NDET3-6790 | GRP-2021-ND3.61.1.2 | Elevate Main - Sunset St (1) (8 Mile Rd (M102) & E Outer Dr) | 06-03-21 A | 06-04-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.6497 | 05-11-21 A | 05-11-21 A | 06-16-21 A | 2021-09-29
21 | 1 | 108 | 4655 | Spring Garden St | Queen St | Hayes St | RR1 6101 | GRP-2021-RR.9.1.2 | Install Main - Spring Garden 1 (Chalmers & Hayes) | 2021-11-01 | 2021-11-18 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Springarden | Kelly | Chalmers | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Springarden (Kelly-Chalmers) |  | 181497.5556 | 4059.3786 | 273.1732 | 2021-09-20 | 2021-09-29 | 2021-10-05 | 2021-10-08
26 | 1 | 139 | 955 | Conley St | Cordova St | Amrad St | NDET3-6830 | GRP-2021-ND3.52.1.2 | Install Main - Conley Ave (1) (8 Mile Rd (M102) & Hamlet St) | 04-15-21 A | 04-15-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 273.7408 | 09-13-21 A | 09-14-21 A | 2021-09-23 | 2021-09-28
27 | 1 | 140 | 2834 | Buffalo St | Emery St | E Lantz St | NDET3-6825 | GRP-2021-ND3.50.1.2 | Install Main - Buffalo St (1) (8 Mile Rd (M102) & Hamlet St) | 05-12-21 A | 05-14-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 357.7843 | 08-16-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
48 | 1 | 309 | 3974 | Harned St | E 7 Mile Rd | Emery St | NDET3-190 | GRP-2021-ND3.3.2.2 | Install Main - E Outer Dr (South) - (Crossing At Harned St) | 06-08-21 A | 06-08-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 392.3396 |  |  | 2021-09-24 | 2021-09-29
49 | 1 | 328 | 1975 | E Lantz St | Syracuse St | Albany St | NDET3-7025 | GRP-2021-ND3.97.1.2 | Install Main - E Lantz Ave (1) (Keystone & Bloom) | 06-28-21 A | 06-28-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 117.052 |  |  | 2021-09-24 | 2021-09-29
51 | 1 | 350 | 3561 | Keystone St | E 7 Mile Rd | Emery St | NDET3-7125 | GRP-2021-ND3.37.1.2 | Install Main - Keystone St (2) (E Lantz St & ANO 7 Mile Rd) | 06-30-21 A | 07-07-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 383.5396 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
54 | 1 | 366 | 2029 | E Lantz St | Fenelon St | Conley St | NDET3-7070 | GRP-2021-ND3.97.3.2 | Install Main - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) - Bloom Crossing | 06-22-21 A | 06-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 133.2495 |  |  | 2021-09-23 | 2021-09-28
62 | 1 | 477 | 1479 | Revere St | E Outer Dr | E Remington St | NDET3-6945 | GRP-2021-ND3.83.1.2 | Elevate Main - Revere Ave (2) (E Outer Dr & 7 Mile Rd) | 2021-10-05 | 2021-10-08 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 335.0111 | 2021-09-21 | 2021-10-04 | 2021-10-15 | 2021-10-20
68 | 1 | 506 | 2844 | E Lantz St | Andover St | Irvington St | NDET3-7070 | GRP-2021-ND3.97.3.2 | Install Main - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) - Bloom Crossing | 06-22-21 A | 06-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Irvington | State Fair | 7 Mile | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Irvington (State Fair-7 Mile) |  | 107646.3173 | 2321.9092 | 120.8312 |  |  | 2021-09-23 | 2021-09-28
69 | 1 | 508 | 2317 | E Lantz St | Dean St | Sunset St | NDET3-7070 | GRP-2021-ND3.97.3.2 | Install Main - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) - Bloom Crossing | 06-22-21 A | 06-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 128.2256 |  |  | 2021-09-23 | 2021-09-28
72 | 1 | 524 | 1830 | Saint Louis St | E Lantz St | E Outer Dr | NDET3-4825 | GRP-2021-ND3.22.1.2 | Install Main - St Louis Ave (E Outer Dr & ANO 7 Mile Rd) | 05-18-21 A | 05-20-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 253.4171 | 07-26-21 A | 09-01-21 A | 2021-09-24 | 2021-09-29
88 | 1 | 753 | 2871 | Keystone St | Emery St | E Lantz St | NDET3-7125 | GRP-2021-ND3.37.1.2 | Install Main - Keystone St (2) (E Lantz St & ANO 7 Mile Rd) | 06-30-21 A | 07-07-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 356.185 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
104 | 1 | 882 | 557 | Amrad St | Moenart St | Bloom St | NDET3-6920 | GRP-2021-ND3.50.4.2 | Install Main - Buffalo St (1) (Hamlet St & Amrad St) | 05-14-21 A | 05-14-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 113.8037 | 08-12-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
119 | 1 | 998 | 2982 | Dean St | Emery St | E Lantz St | NDET3-6235 | GRP-2021-ND3.29.1.2 | Install Main - Dean Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 08-04-21 A | 08-10-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 355.9629 | 2021-09-20 | 2021-10-05 | 2021-10-11 | 2021-10-14
122 | 1 | 1022 | 2999 | Binder St | Emery St | E Lantz St | NDET3-7295 | GRP-2021-ND3.64.1.2 | Elevate Main - Binder St (2) (E Outer Dr & ANO 7 Mile Rd) | 2021-10-27 | 2021-11-01 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 355.947 | 2021-10-12 | 2021-10-26 | 2021-11-05 | 2021-11-10
132 | 1 | 1096 | 1956 | Gable St | E Lantz St | E Outer Dr | NDET3-5010 | GRP-2021-ND3.19.1.2 | Install Main - Gable Ave (E Outer Dr & ANO 7 Mile Rd) | 05-24-21 A | 06-02-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.9869 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
150 | 1 | 1189 | 545 | Amrad St | Buffalo St | Caldwell St | NDET3-6920 | GRP-2021-ND3.50.4.2 | Install Main - Buffalo St (1) (Hamlet St & Amrad St) | 05-14-21 A | 05-14-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 121.3953 | 08-12-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
159 | 1 | 1258 | 1379 | Keystone St | E Outer Dr | Cordova St | NDET3-325 | GRP-2021-ND3.59.3.2 | Install Main - Keystone St (1) (Hamlet St & E Outer Dr) | 04-20-21 A | 04-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 257.5286 | 08-30-21 A | 09-01-21 A | 08-27-21 A | 2021-09-28
170 | 1 | 1334 | 950 | Keystone St | Cordova St | Amrad St | NDET3-325 | GRP-2021-ND3.59.3.2 | Install Main - Keystone St (1) (Hamlet St & E Outer Dr) | 04-20-21 A | 04-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 273.8971 | 08-30-21 A | 09-01-21 A | 08-27-21 A | 2021-09-28
171 | 1 | 1341 | 3826 | Dean St | E 7 Mile Rd | Emery St | NDET3-6235 | GRP-2021-ND3.29.1.2 | Install Main - Dean Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 08-04-21 A | 08-10-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 387.6559 | 2021-09-20 | 2021-10-05 | 2021-10-11 | 2021-10-14
173 | 1 | 1346 | 3516 | Buffalo St | E 7 Mile Rd | Emery St | NDET3-6825 | GRP-2021-ND3.50.1.2 | Install Main - Buffalo St (1) (8 Mile Rd (M102) & Hamlet St) | 05-12-21 A | 05-14-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 381.4329 | 08-16-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
189 | 1 | 1486 | 1002 | E Remington St | Anglin St | Harned St | NDET3-7800 | GRP-2021-ND3.8.1.2 | Elevate Main - E Remington St (Norwood & Yonka) | 08-16-21 A | 08-16-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 136.5973 | 07-20-21 A | 07-20-21 A | 2021-09-23 | 2021-09-28
193 | 1 | 1510 | 994 | E Remington St | Mitchell St | Charest St | NDET3-7800 | GRP-2021-ND3.8.1.2 | Elevate Main - E Remington St (Norwood & Yonka) | 08-16-21 A | 08-16-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 110.9091 | 07-20-21 A | 07-20-21 A | 2021-09-23 | 2021-09-28
201 | 1 | 1547 | 532 | Syracuse St | Amrad St | Hamlet St | NDET3-6390 | GRP-2021-ND3.62.3.2 | Install Main - Syracuse Ave (1) (Hamlet St & Amrad St) | 05-12-21 A | 05-13-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 273.495 | 07-16-21 A | 07-20-21 A | 2021-09-23 | 2021-09-28
204 | 1 | 1558 | 518 | Klinger St | E Winchester Ave | 8 Mile Rd | NDET3-4255 | GRP-2021-ND3.74.1.2 | Elevate Main - Klinger St (1) (8 Mile Rd (M102) & E Outer Dr) | 07-29-21 A | 08-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 312.5249 | 07-27-21 A | 08-03-21 A | 08-26-21 A | 08-30-21 A
215 | 1 | 1673 | 404 | Albany St | Hamlet St | 8 Mile Rd | NDET3-6270 | GRP-2021-ND3.46.1.2 | Install Main - Albany Ave (1) (Hamlet & Amrad St) | 05-10-21 A | 05-11-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 226.1796 | 08-16-21 A | 08-16-21 A | 2021-09-23 | 2021-09-28
232 | 1 | 1795 | 3811 | Sunset St | E 7 Mile Rd | Emery St | NDET3-6790 | GRP-2021-ND3.61.1.2 | Elevate Main - Sunset St (1) (8 Mile Rd (M102) & E Outer Dr) | 06-03-21 A | 06-04-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 387.5504 | 05-11-21 A | 05-11-21 A | 06-16-21 A | 2021-09-29
251 | 1 | 1922 | 1017 | Dean St | Cordova St | Amrad St | NDET3-7510 | GRP-2021-ND3.55.1.2 | Elevate Main - Dean Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 06-07-21 A | 06-11-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 273.006 | 05-17-21 A | 05-26-21 A | 07-28-21 A | 2021-09-29
260 | 1 | 2009 | 2076 | Justine St | E Lantz St | E Outer Dr | NDET3-5740 | GRP-2021-ND3.36.1.2 | Install Main - Justine Ave (E Outer Dr & 7 Mile Rd) | 07-19-21 A | 07-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.9883 | 2021-09-20 | 2021-10-05 | 2021-10-11 | 2021-10-14
261 | 1 | 2011 | 2840 | Bloom St | Emery St | E Lantz St | NDET3-6685 | GRP-2021-ND3.25.1.2 | Install Main - Bloom St (2) (E Outer Dr & E Lantz Ave) | 06-21-21 A | 06-21-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 357.0665 | 2021-09-20 | 2021-09-20 | 2021-11-30 | 2021-12-03
266 | 1 | 2043 | 546 | Buffalo St | Amrad St | Hamlet St | NDET3-6920 | GRP-2021-ND3.50.4.2 | Install Main - Buffalo St (1) (Hamlet St & Amrad St) | 05-14-21 A | 05-14-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 272.5933 | 08-12-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
271 | 1 | 2066 | 2355 | Norwood St | E Lantz St | E Outer Dr | NDET3-175 | GRP-2021-ND3.80.1.2 | Install Main - Tie-ins - Norwood At E Outer | 08-16-21 A | 08-17-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.4872 | 07-08-21 A | 07-20-21 A | 2021-09-24 | 2021-09-29
281 | 1 | 2149 | 1989 | E Lantz St | Buffalo St | Caldwell St | NDET3-7025 | GRP-2021-ND3.97.1.2 | Install Main - E Lantz Ave (1) (Keystone & Bloom) | 06-28-21 A | 06-28-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 117.264 |  |  | 2021-09-24 | 2021-09-29
287 | 1 | 2223 | 526 | Albany St | Amrad St | Hamlet St | NDET3-6270 | GRP-2021-ND3.46.1.2 | Install Main - Albany Ave (1) (Hamlet & Amrad St) | 05-10-21 A | 05-11-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 273.1509 | 08-16-21 A | 08-16-21 A | 2021-09-23 | 2021-09-28
293 | 1 | 2247 | 1485 | Klinger St | E Outer Dr | E Remington St | NDET3-7150 | GRP-2021-ND3.77.1.2 | Elevate Main - Klinger St (2) (E Outer Dr& 7 Mile Rd) | 09-16-21 A | 2021-10-05 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 337.0043 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
303 | 1 | 2307 | 1910 | Chippewa St | Santa Rosa Dr | Stoepel St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Stoepel | 8 Mile | Pembroke | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Stoepel (8 Mile-Pembroke) |  | 90202.9323 | 2296.9196 | 109.45
312 | 1 | 2348 | 2629 | Gable St | Emery St | E Lantz St | NDET3-5010 | GRP-2021-ND3.19.1.2 | Install Main - Gable Ave (E Outer Dr & ANO 7 Mile Rd) | 05-24-21 A | 06-02-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 356.7281 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
318 | 1 | 2402 | 3049 | Gallagher St | Emery St | E Lantz St | NDET3-4235 | GRP-2021-ND3.70.1.2 | Elevate Main - Gallagher (1) (8 Mile Rd (M102) & E Outer Dr) | 08-05-21 A | 08-10-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 355.9586 | 07-27-21 A | 08-10-21 A | 08-26-21 A | 08-26-21 A
338 | 1 | 2579 | 1511 | Mitchell St | E Outer Dr | E Remington St | NDET3-7400 | GRP-2021-ND3.78.1.2 | Elevate Main - Mitchell St (1) (8 Mile Rd (M102) & E Outer Dr) | 08-19-21 A | 08-24-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 341.6813 | 08-04-21 A | 09-01-21 A | 2021-09-24 | 2021-09-29
340 | 1 | 2590 | 1459 | Binder St | E Outer Dr | E Remington St | NDET3-7515 | GRP-2021-ND3.63.1.2 | Elevate Main - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 06-21-21 A | 06-29-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 328.8742 | 06-18-21 A | 06-21-21 A | 2021-09-24 | 2021-09-29
346 | 1 | 2680 | 2862 | Saint Louis St | Emery St | E Lantz St | NDET3-4825 | GRP-2021-ND3.22.1.2 | Install Main - St Louis Ave (E Outer Dr & ANO 7 Mile Rd) | 05-18-21 A | 05-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 428.7579 | 07-26-21 A | 09-01-21 A | 2021-09-24 | 2021-09-29
353 | 1 | 2739 | 2661 | Albany St | Emery St | E Lantz St | NDET3-6270 | GRP-2021-ND3.46.1.2 | Install Main - Albany Ave (1) (Hamlet & Amrad St) | 05-10-21 A | 05-11-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 356.2537 | 08-16-21 A | 08-16-21 A | 2021-09-23 | 2021-09-28
359 | 1 | 2787 | 498 | Binder St | E Winchester Ave | 8 Mile Rd | NDET3-7515 | GRP-2021-ND3.63.1.2 | Elevate Main - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 06-21-21 A | 06-29-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 313.3751 | 06-18-21 A | 06-21-21 A | 2021-09-24 | 2021-09-29
372 | 1 | 2915 | 2914 | Healy St | Emery St | E Lantz St | NDET3-5200 | GRP-2021-ND3.35.1.2 | Install Main - Healy St (E Outer Dr & ANO 7 Mile Rd) | 07-08-21 A | 07-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 355.7239 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
377 | 1 | 2934 | 3323 | Eastwood St | Goulburn St | Westphalia St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Westphalia | 7 Mile | Greiner | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Westphalia (7 Mile-Greiner) |  | 101051.7035 | 2387.8145 | 134.5302
379 | 1 | 2941 | 2089 | Shields St | E Lantz St | E Outer Dr | NDET3-5950 | GRP-2021-ND3.42.1.2 | Install Main - Shields St (E Outer Dr & ANO 7 Mile Rd) | 07-28-21 A | 08-03-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.6391 | 2021-09-20 | 2021-10-05 | 2021-10-12 | 2021-10-15
382 | 1 | 2949 | 431 | Keystone St | Hamlet St | 8 Mile Rd | NDET3-6780 | GRP-2021-ND3.59.1.2 | Install Main - Keystone St (1) (8 Mile Rd (M102) & Hamlet St) | 04-26-21 A | 04-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 221.2928 | 08-30-21 A | 09-01-21 A | 08-27-21 A | 08-27-21 A
383 | 1 | 2975 | 3554 | Moenart St | E 7 Mile Rd | Emery St | NDET3-7245 | GRP-2021-ND3.39.3.2 | Install Main - Moenart St (2) (E Outer Dr & ANO 7 Mile Rd) | 06-22-21 A | 06-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 383.9623 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-07
387 | 1 | 2994 | 2030 | Fenelon St | E Lantz St | E Outer Dr | NDET3-4840 | GRP-2021-ND3.33.1.2 | Install Main - Fenelon Ave (2) (E Outer Dr & 7 Mile Rd) | 07-01-21 A | 07-14-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 341.5125 | 2021-09-20 | 2021-10-01 | 2021-10-07 | 2021-10-12
389 | 1 | 3007 | 236 | Bringard Dr | Anvil St | Regent Dr | RR1 5781 | GRP-2021-RR.5.1.2 | Install Main - Bringard (Reno & Regent) | 04-14-21 A | 04-29-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Bringard | Regent | Reno | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Bringard (Regent-Reno) |  | 77579.4379 | 1714.8368 | 273.6348 | 07-07-21 A | 07-20-21 A | 08-26-21 A | 2021-09-28
393 | 1 | 3028 | 2067 | Eureka St | E Lantz St | E Outer Dr | NDET3-5550 | GRP-2021-ND3.32.1.2 | Install Main - Eureka St (E Outer Dr & ANO 7 Mile Rd) | 07-15-21 A | 07-21-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.5967 | 2021-09-20 | 2021-09-30 | 2021-10-07 | 2021-10-12
406 | 1 | 3142 | 3004 | Emery St | Wexford St | Binder St | NDET3-5930 | GRP-2021-ND3.102.1.2 | Install Main - Emery St (Buffalo St & Caldwell St) | 06-16-21 A | 06-16-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 109.3516 |  |  | 2021-09-24 | 2021-09-29
407 | 1 | 3143 | 531 | Amrad St | Syracuse St | Albany St | NDET3-6920 | GRP-2021-ND3.50.4.2 | Install Main - Buffalo St (1) (Hamlet St & Amrad St) | 05-14-21 A | 05-14-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 119.5679 | 08-12-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
427 | 1 | 3311 | 1494 | Gallagher St | E Outer Dr | E Remington St | NDET3-4235 | GRP-2021-ND3.70.1.2 | Elevate Main - Gallagher (1) (8 Mile Rd (M102) & E Outer Dr) | 08-05-21 A | 08-10-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 338.8217 | 07-27-21 A | 08-10-21 A | 08-26-21 A | 08-26-21 A
437 | 1 | 3362 | 240 | Bringard Dr | Hoyt St | Anvil St | RR1 5781 | GRP-2021-RR.5.1.2 | Install Main - Bringard (Reno & Regent) | 04-14-21 A | 04-29-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Bringard | Regent | Reno | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Bringard (Regent-Reno) |  | 77579.4379 | 1714.8368 | 273.6122 | 07-07-21 A | 07-20-21 A | 08-26-21 A | 2021-09-28
448 | 1 | 3500 | 2049 | E Lantz St | Healy St | Lamont St | NDET3-7070 | GRP-2021-ND3.97.3.2 | Install Main - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) - Bloom Crossing | 06-22-21 A | 06-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 110.1029 |  |  | 2021-09-23 | 2021-09-28
449 | 1 | 3502 | 2050 | Healy St | E Lantz St | E Outer Dr | NDET3-5200 | GRP-2021-ND3.35.1.2 | Install Main - Healy St (E Outer Dr & ANO 7 Mile Rd) | 07-08-21 A | 07-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.4915 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
450 | 1 | 3503 | 2039 | Lamont St | E Lantz St | E Outer Dr | NDET3-5030 | GRP-2021-ND3.38.1.2 | Install Main - Lamont Ave (E Outer Dr & 7 Mile Rd) | 07-08-21 A | 07-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 341.7158 | 2021-09-20 | 2021-10-04 | 2021-10-08 | 2021-10-13
482 | 1 | 3717 | 1990 | Buffalo St | E Lantz St | E Outer Dr | NDET3-6115 | GRP-2021-ND3.26.1.2 | Install Main - Buffalo St (2) (E Outer Dr & ANO 7 Mile Rd) | 06-09-21 A | 06-15-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 341.3272 | 2021-09-20 | 2021-10-05 | 2021-10-12 | 2021-10-15
484 | 1 | 3719 | 979 | Revere St | E Remington St | E Winchester Ave | NDET3-6945 | GRP-2021-ND3.83.1.2 | Elevate Main - Revere Ave (2) (E Outer Dr & 7 Mile Rd) | 2021-10-05 | 2021-10-08 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 371.2853 | 2021-09-21 | 2021-10-04 | 2021-10-15 | 2021-10-20
486 | 1 | 3758 | 411 | Syracuse St | Hamlet St | 8 Mile Rd | NDET3-6385 | GRP-2021-ND3.62.1.2 | Install Main - Syracuse Ave (1) (8 Mile Rd (M102) & Hamlet St) | 05-13-21 A | 05-13-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 223.8143 | 07-19-21 A | 07-20-21 A | 2021-09-23 | 2021-09-28
492 | 1 | 3806 | 3989 | Filer St | E Robinwood St | E 7 Mile Rd | NDET3-6505 | GRP-2021-ND3.18.1.2 | Install Main - Filer Ave (2) (Emery St & ANO 7 Mile Rd) | 06-03-21 A | 06-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 273.1008 | 2021-09-20 | 2021-09-21 | 2021-09-28 | 2021-10-01
500 | 1 | 3862 | 2088 | E Lantz St | Shields St | Justine St | NDET3-7070 | GRP-2021-ND3.97.3.2 | Install Main - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) - Bloom Crossing | 06-22-21 A | 06-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 114.7039 |  |  | 2021-09-23 | 2021-09-28
506 | 1 | 3893 | 3455 | Gable St | E 7 Mile Rd | Emery St | NDET3-5010 | GRP-2021-ND3.19.1.2 | Install Main - Gable Ave (E Outer Dr & ANO 7 Mile Rd) | 05-24-21 A | 06-02-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 379.2473 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
509 | 1 | 3907 | 3533 | Bloom St | E 7 Mile Rd | Emery St | NDET3-6365 | GRP-2021-ND3.49.3.2 | Install Main - Bloom St (1) (Hamlet St & E Outer Dr) | 05-06-21 A | 05-11-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 382.3614 | 08-10-21 A | 08-16-21 A | 09-07-21 A | 2021-09-28
514 | 1 | 3978 | 3617 | Healy St | E 7 Mile Rd | Emery St | NDET3-5200 | GRP-2021-ND3.35.1.2 | Install Main - Healy St (E Outer Dr & ANO 7 Mile Rd) | 07-08-21 A | 07-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 386.5537 | 2021-09-20 | 2021-10-04 | 2021-10-11 | 2021-10-14
518 | 1 | 3990 | 515 | Revere St | E Winchester Ave | 8 Mile Rd | NDET3-7275 | GRP-2021-ND3.82.1.2 | Elevate Main - Revere Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 07-21-21 A | 07-27-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 312.3949 | 07-26-21 A | 07-27-21 A | 07-23-21 A | 08-13-21 A
540 | 1 | 4139 | 2904 | Lamont St | Emery St | E Lantz St | NDET3-5030 | GRP-2021-ND3.38.1.2 | Install Main - Lamont Ave (E Outer Dr & 7 Mile Rd) | 07-08-21 A | 07-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 355.6702 | 2021-09-20 | 2021-10-04 | 2021-10-08 | 2021-10-13
542 | 1 | 4145 | 3941 | Gallagher St | E 7 Mile Rd | Emery St | NDET3-4240 | GRP-2021-ND3.71.1.2 | Elevate Main - Gallagher St (2) (E Outer Dr & ANO 7 Mile Rd) | 09-10-21 A | 09-14-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 393.8356 | 2021-09-29 | 2021-10-14 | 2021-10-20 | 2021-10-25
545 | 1 | 4181 | 2386 | Gallagher St | E Lantz St | E Outer Dr | NDET3-4240 | GRP-2021-ND3.71.1.2 | Elevate Main - Gallagher St (2) (E Outer Dr & ANO 7 Mile Rd) | 09-10-21 A | 09-14-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 342.329 | 2021-09-29 | 2021-10-14 | 2021-10-20 | 2021-10-25
559 | 1 | 4295 | 3850 | Binder St | E 7 Mile Rd | Emery St | NDET3-7515 | GRP-2021-ND3.63.1.2 | Elevate Main - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 06-21-21 A | 06-29-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 390.2735 | 06-18-21 A | 06-21-21 A | 2021-09-24 | 2021-09-29
568 | 1 | 4359 | 3602 | Lamont St | E 7 Mile Rd | Emery St | NDET3-5030 | GRP-2021-ND3.38.1.2 | Install Main - Lamont Ave (E Outer Dr & 7 Mile Rd) | 07-08-21 A | 07-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 386.0367 | 2021-09-20 | 2021-10-04 | 2021-10-08 | 2021-10-13
572 | 1 | 4380 | 1388 | Conley St | E Outer Dr | Cordova St | NDET3-6925 | GRP-2021-ND3.52.3.2 | Install Main - Conley Ave (1) (Hamlet St & E Outer Dr) | 04-16-21 A | 04-16-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 257.3631 | 09-13-21 A | 09-14-21 A | 2021-09-23 | 2021-09-28
573 | 1 | 4388 | 988 | E Remington St | Gallagher St | Klinger St | NDET3-7800 | GRP-2021-ND3.8.1.2 | Elevate Main - E Remington St (Norwood & Yonka) | 08-16-21 A | 08-16-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 110.9371 | 07-20-21 A | 07-20-21 A | 2021-09-23 | 2021-09-28
587 | 1 | 4462 | 3023 | Emery St | Norwood St | Yonka St | NDET3-5930 | GRP-2021-ND3.102.1.2 | Install Main - Emery St (Buffalo St & Caldwell St) | 06-16-21 A | 06-16-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 115.5533 |  |  | 2021-09-24 | 2021-09-29
617 | 1 | 4685 | 2066 | E Lantz St | Eureka St | Hasse St | NDET3-7070 | GRP-2021-ND3.97.3.2 | Install Main - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) - Bloom Crossing | 06-22-21 A | 06-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 109.5766 |  |  | 2021-09-23 | 2021-09-28
620 | 1 | 4691 | 2318 | Dean St | E Lantz St | E Outer Dr | NDET3-7510 | GRP-2021-ND3.55.1.2 | Elevate Main - Dean Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 06-07-21 A | 06-11-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 341.8485 | 05-17-21 A | 05-26-21 A | 07-28-21 A | 2021-09-29
623 | 1 | 4702 | 3437 | Saint Louis St | E 7 Mile Rd | Emery St | NDET3-4825 | GRP-2021-ND3.22.1.2 | Install Main - St Louis Ave (E Outer Dr & ANO 7 Mile Rd) | 05-18-21 A | 05-20-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021NDet3 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 5/5/2020 | NAD 1983 | Detroit | North Detroit 3 (NDet3) | NDet3 | 9178519.1101 | 14104.4149 | 305.8174 | 07-26-21 A | 09-01-21 A | 2021-09-24 | 2021-09-29
803 | 1 | 6166 | 9396 | Elmo St | Nashville St | Engleside St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Engleside | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Engleside (Connor-Gunston) |  | 97941.264 | 1888.7879 | 138.4616
830 | 1 | 6419 | 9039 | Kenmoor St | Algonac St | Elmo St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Kenmoor | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Kenmoor (Conner-Gunston) |  | 82696.7225 | 1879.512 | 272.4062
840 | 1 | 6481 | 6608 | Mayfield St | Hayes St | Kelly Rd | RR1 5941 | GRP-2021-RR.7.1.2 | Install Main - Mayfield (Chalmers & Kelly) | 2021-09-20 | 2021-10-12 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Mayfield | Kelly | Chalmers | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Mayfield (Kelly-Chalmers) |  | 150630.0996 | 2971.3446 | 304.9183 | 2021-10-13 | 2021-10-20 | 2021-10-26 | 2021-10-29
851 | 1 | 6582 | 9404 | Engleside St | Algonac St | Elmo St | RR1 8841 | GRP-2021-RR.45.1.2 | Install Main - Engleside (Conner & Gunston) | 04-23-21 A | 04-30-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Engleside | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Engleside (Connor-Gunston) |  | 97941.264 | 1888.7879 | 272.4224 | 08-30-21 A | 09-01-21 A | 09-16-21 A | 09-16-21 A
863 | 1 | 6701 | 9040 | Algonac St | Kenmoor St | Kennebec St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Kenmoor | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Kenmoor (Conner-Gunston) |  | 82696.7225 | 1879.512 | 130.1934
987 | 1 | 7801 | 6399 | Iowa St | Sherwood St | Carrie St | RR1 5861 | GRP-2021-RR.6.1.2 | Install Main - Iowa (Sherwood & School) | 05-17-21 A | 06-14-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Iowa | Sherwood | School | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Iowa (Sherwood-School) |  | 78154.3255 | 1921.2982 | 386.0901 | 08-02-21 A | 08-16-21 A | 09-14-21 A | 09-14-21 A
1047 | 1 | 8276 | 6593 | Mayfield St | Queen St | Hayes St | RR1 5941 | GRP-2021-RR.7.1.2 | Install Main - Mayfield (Chalmers & Kelly) | 2021-09-20 | 2021-10-12 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Mayfield | Kelly | Chalmers | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Mayfield (Kelly-Chalmers) |  | 150630.0996 | 2971.3446 | 272.8539 | 2021-10-13 | 2021-10-20 | 2021-10-26 | 2021-10-29
1076 | 1 | 8513 | 9442 | Kenmoor St | Conner St | Algonac St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Kenmoor | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Kenmoor (Conner-Gunston) |  | 82696.7225 | 1879.512 | 292.7361
1103 | 1 | 8700 | 8833 | Elmo St | Kenmoor St | Kennebec St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Kenmoor | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Kenmoor (Conner-Gunston) |  | 82696.7225 | 1879.512 | 131.6971
1145 | 1 | 9080 | 8832 | Kenmoor St | Elmo St | Gunston St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Kenmoor | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Kenmoor (Conner-Gunston) |  | 82696.7225 | 1879.512 | 413.4797
1148 | 1 | 9092 | 9113 | College St | Gunston St | Bradford St | RR1 10231 | GRP-2021-RR.46.2.2 | Install Main - College (Gunston & Devon) | 05-25-21 A | 05-25-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | College | Connor | Devon | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | College (Connor-Devon) |  | 172995.4632 | 3346.8888 | 400.2982 | 08-30-21 A | 09-01-21 A | 09-07-21 A | 2021-09-28
1182 | 1 | 9351 | 9024 | Engleside St | Elmo St | Gunston St | RR1 8841 | GRP-2021-RR.45.1.2 | Install Main - Engleside (Conner & Gunston) | 04-23-21 A | 04-30-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Engleside | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Engleside (Connor-Gunston) |  | 97941.264 | 1888.7879 | 413.2861 | 08-30-21 A | 09-01-21 A | 09-16-21 A | 09-16-21 A
1221 | 1 | 9815 | 13588 | Courville St | Cornwall St | E Warren Ave | EDET1 50644 | GRP-2021-ED1.24.1.2 | Install Main - Courville St (1) (E Warrern Ave & Waveney St) | 03-11-21 A | 03-12-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 282.6582 | 04-05-21 A | 06-15-21 A | 05-28-21 A | 06-07-21 A
1230 | 1 | 9906 | 9918 | Minden St | Elmo St | Gunston St | RR1 9001 | GRP-2021-RR.47.1.2 | Install Main - Minden (Conner & Gunston) | 08-02-21 A | 08-17-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Minden | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Minden (Conner-Gunston) |  | 81192.7953 | 1809.223 | 413.3763 | 2021-09-20 | 2021-10-06 | 2021-10-12 | 2021-10-15
1231 | 1 | 9913 | 13054 | Courville St | E Warren Ave | Frankfort St | EDET1 50644 | GRP-2021-ED1.24.1.2 | Install Main - Courville St (1) (E Warrern Ave & Waveney St) | 03-11-21 A | 03-12-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 281.4387 | 04-05-21 A | 06-15-21 A | 05-28-21 A | 06-07-21 A
1237 | 1 | 9967 | 13087 | Cornwall St | Kensington Ave | Yorkshire Rd | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 140.0791
1244 | 1 | 10032 | 12987 | Yorkshire Rd | Cornwall St | E Warren Ave | EDET1 50656 | GRP-2021-ED1.36.1.2 | Install Main - Yorkshire Rd (1) (E Warrern Ave & Waveney St) | 02-22-21 A | 02-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 282.0042 | 03-24-21 A | 03-31-21 A | 05-26-21 A | 05-26-21 A
1247 | 1 | 10065 | 12418 | Yorkshire Rd | E Warren Ave | Frankfort St | EDET1 50656 | GRP-2021-ED1.36.1.2 | Install Main - Yorkshire Rd (1) (E Warrern Ave & Waveney St) | 02-22-21 A | 02-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 282.1132 | 03-24-21 A | 03-31-21 A | 05-26-21 A | 05-26-21 A
1262 | 1 | 10225 | 12860 | Corbett Ave | Annsbury Ave | Park Dr | RR1 551 | GRP-2021-RR.17.1.2 | Install Main - Corbett 1 (Annsbury & Coplin) | 09-28-21* | 2021-10-15 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Corbett | Chalmers | Annsbury | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Corbett (Chalmers-Annsbury) |  | 171623.4659 | 3537.4533 | 333.493 | 2021-10-19 | 2021-11-05 | 2021-11-11 | 2021-11-16
1287 | 1 | 10495 | 10963 | Hereford St | E Warren Ave | Southampton St | EDET1 502806 | GRP-2021-ED1.80.2.2 | Install Main - ANO E Warren Ave (2) (Neff Ave & Hereford St) | 05-24-21 A | 05-27-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 562.5107 | 2021-09-20 | 2021-09-20 | 2021-09-24 | 2021-09-29
1295 | 1 | 10541 | 11955 | Harvard Rd | E Warren Ave | Frankfort St | EDET1 507796 | GRP-2021-ED1.6.3.2 | Install Main - Harvard Rd (1) (ASO Warren & Waveney) | 01-25-21 A | 02-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 281.8527 |  |  | 05-10-21 A | 05-27-21 A
1316 | 1 | 10722 | 14089 | Haverhill St | Cornwall St | E Warren Ave | EDET1 50649 | GRP-2021-ED1.29.1.2 | Install Main - Haverhill St (1) (E Warrern Ave & Waveney St) | 04-05-21 A | 04-13-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 281.9931 | 05-23-21 A | 05-23-21 A | 06-10-21 A | 2021-09-28
1318 | 1 | 10739 | 11988 | Guilford St | Cornwall St | E Warren Ave | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 280.8421
1339 | 1 | 10967 | 13088 | Kensington Ave | Cornwall St | E Warren Ave | EDET1 507256 | GRP-2021-ED1.5.1.2 | Install Main - Kensington Ave (ASO E Warren & Waveney) | 03-01-21 A | 03-04-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 282.1037 | 04-26-21 A | 04-27-21 A | 05-27-21 A | 05-27-21 A
1354 | 1 | 11100 | 14107 | Waveney St | Kensington Ave | Yorkshire Rd | EDET1 506916 | GRP-2021-ED1.65.3.2 | Install Main - Waveney Ave (2) (Courville & E Outer Dr) | 01-28-21 A | 01-29-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 140.3474 |  |  | 2021-09-23 | 2021-09-28
1377 | 1 | 11319 | 12851 | Fielding St | Verne St | Grove St | RR1 7561 | GRP-2021-RR.29.1.2 | Install Main - Fielding (McNichols & Grand River) | 03-01-21 A | 03-10-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Fielding | Grand River | McNichols | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Fielding (Grand River-McNichols) |  | 66966.4348 | 1426.558 | 271.0239 | 03-29-21 A | 04-27-21 A | 06-08-21 A | 2021-09-28
1379 | 1 | 11335 | 11959 | Dwyer St | Casmere St | Sobieski St | RR1 6981 | GRP-2021-RR.21.1.2 | Install Main - Dwyer (Charles & Casemere) | 03-24-21 A | 04-02-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Dwyer | Charles | Casmere | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Dwyer (Charles-Casmere) |  | 48317.6626 | 1187.3566 | 282.2692 | 2021-09-20 | 2021-09-22 | 2021-09-28 | 2021-10-01
1380 | 1 | 11339 | 13666 | Waveney St | Grayton St | Harvard Rd | EDET1 50846 | GRP-2021-ED1.48.1.2 | Install Main - Wayburn Ave (2) (Waveney St & Mack Ave) | 03-17-21 A | 03-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 145.1316 | 05-12-21 A | 05-19-21 A | 06-10-21 A | 06-14-21 A
1392 | 1 | 11450 | 12093 | Hereford St | Munich St | E Warren Ave | EDET1 502806 | GRP-2021-ED1.80.2.2 | Install Main - ANO E Warren Ave (2) (Neff Ave & Hereford St) | 05-24-21 A | 05-27-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 575.5601 | 2021-09-20 | 2021-09-20 | 2021-09-24 | 2021-09-29
1394 | 1 | 11473 | 12498 | Harvard Rd | Cornwall St | E Warren Ave | EDET1 507796 | GRP-2021-ED1.6.3.2 | Install Main - Harvard Rd (1) (ASO Warren & Waveney) | 01-25-21 A | 02-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 282.2716 |  |  | 05-10-21 A | 05-27-21 A
1428 | 1 | 11832 | 9603 | Engleside St | Conner St | Algonac St | RR1 8841 | GRP-2021-RR.45.1.2 | Install Main - Engleside (Conner & Gunston) | 04-23-21 A | 04-30-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Engleside | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Engleside (Connor-Gunston) |  | 97941.264 | 1888.7879 | 276.5293 | 08-30-21 A | 09-01-21 A | 09-16-21 A | 09-16-21 A
1462 | 1 | 12185 | 12088 | Fielding St | Grove St | W McNichols Rd | RR1 7561 | GRP-2021-RR.29.1.2 | Install Main - Fielding (McNichols & Grand River) | 03-01-21 A | 03-10-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Fielding | Grand River | McNichols | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Fielding (Grand River-McNichols) |  | 66966.4348 | 1426.558 | 249.9997 | 03-29-21 A | 04-27-21 A | 06-08-21 A | 2021-09-28
1466 | 1 | 12209 | 12890 | Bishop St | Cornwall St | E Warren Ave | EDET1 501526 | GRP-2021-ED1.21.3.2 | Install Main - Bishop St (1) (ASO E Warrern Ave & Waveney St) | 02-02-21 A | 02-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 281.7734 | 03-22-21 A | 03-24-21 A | 2021-09-24 | 2021-09-29
1469 | 1 | 12218 | 11369 | Dwyer St | Sobieski St | Charles St | RR1 6981 | GRP-2021-RR.21.1.2 | Install Main - Dwyer (Charles & Casemere) | 03-24-21 A | 04-02-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Dwyer | Charles | Casmere | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Dwyer (Charles-Casmere) |  | 48317.6626 | 1187.3566 | 225.0955 | 2021-09-20 | 2021-09-22 | 2021-09-28 | 2021-10-01
1475 | 1 | 12278 | 13381 | Bedford St | E Warren Ave | Frankfort St | EDET1 503756 | GRP-2021-ED1.69.3.2 | Install Main - Bedford St (1) (E Warren Ave & Waveney St) East | 03-18-21 A | 03-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 282.2588 | 04-12-21 A | 05-19-21 A | 05-27-21 A | 06-07-21 A
1490 | 1 | 12389 | 13929 | Bedford St | Cornwall St | E Warren Ave | EDET1 501116 | GRP-2021-ED1.70.1.2 | Install Main - Bedford St (2) West (Waveney St & Mack Ave) West | 02-03-21 A | 03-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 282.0161 | 03-08-21 A | 03-24-21 A | 2021-09-20 | 2021-09-23
1495 | 1 | 12445 | 13472 | Audubon Rd | Cornwall St | E Warren Ave | EDET1 50640 | GRP-2021-ED1.19.1.2 | Install Main - Audubon Rd (2) (E Warrern Ave & Waveney St) | 02-01-21 A | 03-09-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 281.8641 | 03-29-21 A | 05-03-21 A | 05-27-21 A | 05-28-21 A
1512 | 1 | 12598 | 12571 | Cornwall St | Grayton St | Harvard Rd | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 145.5421
1521 | 1 | 12654 | 11833 | Wayburn St | Evanston St | Wade St | RR1 5621 | GRP-2021-RR.3.1.2 | Install Main - Wayburn (Berkshire & Evanston) | 08-13-21 A | 08-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Wayburn | Evanston | Berkshire | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Wayburn (Evanston-Berkshire) |  | 90814.1646 | 1790.2966 | 253.7903 | 2021-09-20 | 2021-10-04 | 2021-10-08 | 2021-10-13
1535 | 1 | 12773 | 11080 | Wayburn St | Wade St | Elmdale St | RR1 5621 | GRP-2021-RR.3.1.2 | Install Main - Wayburn (Berkshire & Evanston) | 08-13-21 A | 08-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Wayburn | Evanston | Berkshire | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Wayburn (Evanston-Berkshire) |  | 90814.1646 | 1790.2966 | 273.0921 | 2021-09-20 | 2021-10-04 | 2021-10-08 | 2021-10-13
1548 | 1 | 12890 | 10604 | Wayburn St | Elmdale St | Berkshire St | RR1 5621 | GRP-2021-RR.3.1.2 | Install Main - Wayburn (Berkshire & Evanston) | 08-13-21 A | 08-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Wayburn | Evanston | Berkshire | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Wayburn (Evanston-Berkshire) |  | 90814.1646 | 1790.2966 | 307.8752 | 2021-09-20 | 2021-10-04 | 2021-10-08 | 2021-10-13
1573 | 1 | 13193 | 9595 | Algonac St | Nashville St | Engleside St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Engleside | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Engleside (Connor-Gunston) |  | 97941.264 | 1888.7879 | 138.4937
1577 | 1 | 13218 | 14108 | Kensington Ave | Waveney St | Cornwall St | EDET1 507256 | GRP-2021-ED1.5.1.2 | Install Main - Kensington Ave (ASO E Warren & Waveney) | 03-01-21 A | 03-04-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 522.0326 | 04-26-21 A | 04-27-21 A | 05-27-21 A | 05-27-21 A
1599 | 1 | 13382 | 13554 | Harvard Rd | Waveney St | Cornwall St | EDET1 50648 | GRP-2021-ED1.28.1.2 | Install Main - Harvard Rd (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-20-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 524.6072 | 02-08-21 A | 03-18-21 A | 05-10-21 A | 05-10-21 A
1625 | 1 | 13589 | 10103 | Minden St | Algonac St | Elmo St | RR1 9001 | GRP-2021-RR.47.1.2 | Install Main - Minden (Conner & Gunston) | 08-02-21 A | 08-17-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Minden | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Minden (Conner-Gunston) |  | 81192.7953 | 1809.223 | 271.8246 | 2021-09-20 | 2021-10-06 | 2021-10-12 | 2021-10-15
1659 | 1 | 13818 | 9933 | College St | Algonac St | Elmo St | RR1 8921 | GRP-2021-RR.46.1.2 | Install Main - College (Conner & Gunston) | 05-06-21 A | 05-25-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | College | Connor | Devon | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | College (Connor-Devon) |  | 172995.4632 | 3346.8888 | 272.1671 | 08-30-21 A | 09-01-21 A | 2021-09-23 | 2021-09-28
1663 | 1 | 13846 | 12510 | Kensington Ave | E Warren Ave | Frankfort St | EDET1 507256 | GRP-2021-ED1.5.1.2 | Install Main - Kensington Ave (ASO E Warren & Waveney) | 03-01-21 A | 03-04-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 281.9188 | 04-26-21 A | 04-27-21 A | 05-27-21 A | 05-27-21 A
1676 | 2 | 14006 | 9919 | Elmo St | Minden St | College St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Minden | Conner | Gunston | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Minden (Conner-Gunston) |  | 81192.7953 | 1809.223 | 136.1148
1710 | 1 | 14301 | 19015 | Petoskey Ave | Tyler St | Waverly | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 117.8142
1728 | 1 | 14427 | 15962 | Yorkshire Rd | Mack Ave | Rosewood St | EDET1 50657 | GRP-2021-ED1.37.1.2 | Install Main - Yorkshire Rd (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 355.7829 | 01-19-21 A | 02-22-21 A | 05-18-21 A | 05-26-21 A
1729 | 1 | 14455 | 14617 | Yorkshire Rd | Wallingford St | Waveney St | EDET1 50657 | GRP-2021-ED1.37.1.2 | Install Main - Yorkshire Rd (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.7594 | 01-19-21 A | 02-22-21 A | 05-18-21 A | 05-26-21 A
1733 | 1 | 14490 | 16629 | Lakepointe St | Lozier St | Waveney St | EDET1 50838 | GRP-2021-ED1.40.1.2 | Install Main - Lakepointe Sr (2) (Waveney St & Mack Ave) | 04-22-21 A | 04-27-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 419.4808 | 06-07-21 A | 06-08-21 A | 07-07-21 A | 07-07-21 A
1736 | 1 | 14555 | 17552 | Maryland St | Maryland Ave & Mack Ave | Lozier St | EDET1 50842 | GRP-2021-ED1.44.1.2 | Install Main - Maryland St (2) (Waveney St & ANO Mack Ave) | 04-27-21 A | 05-06-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 474.5731 | 06-07-21 A | 06-18-21 A | 07-12-21 A | 07-21-21 A
1746 | 1 | 14682 | 14385 | Harvard Rd | Wallingford St | Waveney St | EDET1 50648 | GRP-2021-ED1.28.1.2 | Install Main - Harvard Rd (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.6765 | 02-08-21 A | 03-18-21 A | 05-10-21 A | 05-10-21 A
1752 | 1 | 14739 | 15163 | Bishop St | Rosewood St | Wallingford St | EDET1 50643 | GRP-2021-ED1.22.1.2 | Install Main - Bishop St (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-07-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.6274 | 02-01-21 A | 03-09-21 A | 05-04-21 A | 05-26-21 A
1753 | 1 | 14759 | 15417 | Bremen St | Bedford St | 3 Mile Dr | EDET1 501045 | GRP-2021-ED1.53.1.2 | Install Main - Bremen St (2) (Balfour Rd & Buckingham Ave) | 03-25-21 A | 03-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 123.8797 | 06-18-21 A | 06-21-21 A | 2021-09-23 | 2021-09-28
1766 | 1 | 14921 | 14986 | Harvard Rd | Rosewood St | Wallingford St | EDET1 50648 | GRP-2021-ED1.28.1.2 | Install Main - Harvard Rd (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 368.0391 | 02-08-21 A | 03-18-21 A | 05-10-21 A | 05-10-21 A
1774 | 1 | 14997 | 15489 | Rosewood St | Kensington Ave | Yorkshire Rd | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 141.7678
1778 | 1 | 15084 | 15077 | Rosewood St | Grayton St | Harvard Rd | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 145.414
1783 | 1 | 15144 | 16493 | Courville St | Mack Ave | Brunswick St | EDET1 50645 | GRP-2021-ED1.25.1.2 | Install Main - Courville St (2) (Waveney St & Mack Ave) | 01-14-21 A | 01-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 276.9232 | 03-01-21 A | 03-08-21 A | 05-27-21 A | 05-27-21 A
1803 | 1 | 15329 | 14472 | Chatsworth St | Cornwall St | E Warren Ave | EDET1 501047 | GRP-2021-ED1.55.1.2 | Install Main - Chatsworth St (1) (E Warrern Ave & Waveney St) | 04-19-21 A | 04-21-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 281.8069 | 2021-09-20 | 2021-09-28 | 06-22-21 A | 07-07-21 A
1829 | 1 | 15718 | 16023 | Bremen St | Balfour Rd | Chatsworth St | EDET1 501045 | GRP-2021-ED1.53.1.2 | Install Main - Bremen St (2) (Balfour Rd & Buckingham Ave) | 03-25-21 A | 03-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 126.2177 | 06-18-21 A | 06-21-21 A | 2021-09-23 | 2021-09-28
1845 | 1 | 15910 | 14525 | Bishop St | Wallingford St | Waveney St | EDET1 50642 | GRP-2021-ED1.21.1.2 | Install Main - Bishop St (1) (E Warrern Ave & Waveney St) | 03-08-21 A | 03-08-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.7537 | 03-22-21 A | 03-30-21 A | 05-26-21 A | 05-26-21 A
1860 | 1 | 16074 | 15097 | Audubon Rd | Wallingford St | Waveney St | EDET1 50641 | GRP-2021-ED1.20.1.2 | Install Main - Audubon Rd (1) (Waveney St & Mack Ave) | 01-11-21 A | 01-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.708 | 03-01-21 A | 03-15-21 A | 05-27-21 A | 05-27-21 A
1865 | 1 | 16196 | 15684 | Audubon Rd | Rosewood St | Wallingford St | EDET1 50641 | GRP-2021-ED1.20.1.2 | Install Main - Audubon Rd (1) (Waveney St & Mack Ave) | 01-11-21 A | 01-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.6834 | 03-01-21 A | 03-15-21 A | 05-27-21 A | 05-27-21 A
1866 | 1 | 16249 | 16039 | Lakepointe St | Waveney St | Voight St | EDET1 50839 | GRP-2021-ED1.41.1.2 | Install Main - Lakepointe St (1) (ASO E Warrern Ave & Waveney St) | 04-13-21 A | 05-17-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 405.5853 | 06-07-21 A | 06-08-21 A | 07-21-21 A | 07-21-21 A
1870 | 1 | 16278 | 14422 | Bedford St | Munich St | Cornwall St | EDET1 506266 | GRP-2021-ED1.70.3.2 | Install Main - Bedford St East (2) (Waveney St & Mack Ave) East | 02-23-21 A | 03-01-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.9214 |  |  | 05-27-21 A | 05-27-21 A
1877 | 1 | 16345 | 16376 | Bedford St | Brunswick St | Windsor St | EDET1 501116 | GRP-2021-ED1.70.1.2 | Install Main - Bedford St (2) West (Waveney St & Mack Ave) West | 02-03-21 A | 03-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.7659 | 03-08-21 A | 03-24-21 A | 2021-09-20 | 2021-09-23
1879 | 1 | 16382 | 15481 | Chatsworth St | Waveney St | Munich St | EDET1 501047 | GRP-2021-ED1.55.1.2 | Install Main - Chatsworth St (1) (E Warrern Ave & Waveney St) | 04-19-21 A | 04-21-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.6037 | 2021-09-20 | 2021-09-28 | 06-22-21 A | 07-07-21 A
1887 | 1 | 16470 | 15542 | Harvard Rd | Mack Ave | Rosewood St | EDET1 50648 | GRP-2021-ED1.28.1.2 | Install Main - Harvard Rd (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 344.5719 | 02-08-21 A | 03-18-21 A | 05-10-21 A | 05-10-21 A
1891 | 1 | 16545 | 15490 | Kensington Ave | Rosewood St | Wallingford St | EDET1 50651 | GRP-2021-ED1.31.1.2 | Install Main - Kensington Ave (2) (Waveney St & Mack Ave)- Grosse pointe CL | 01-07-21 A | 01-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 368.1671 | 01-25-21 A | 03-16-21 A | 05-27-21 A | 05-27-21 A
1908 | 1 | 16722 | 15863 | Bremen St | Berkshire St | Buckingham Ave | EDET1 501045 | GRP-2021-ED1.53.1.2 | Install Main - Bremen St (2) (Balfour Rd & Buckingham Ave) | 03-25-21 A | 03-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 117.5039 | 06-18-21 A | 06-21-21 A | 2021-09-23 | 2021-09-28
1941 | 1 | 17046 | 16432 | Audubon Rd | Mack Ave | Rosewood St | EDET1 50641 | GRP-2021-ED1.20.1.2 | Install Main - Audubon Rd (1) (Waveney St & Mack Ave) | 01-11-21 A | 01-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 381.047 | 03-01-21 A | 03-15-21 A | 05-27-21 A | 05-27-21 A
1943 | 1 | 17067 | 17390 | Somerset Ave | Mack Ave | Brunswick St | EDET1 506796 | GRP-2021-ED1.62.1.2 | Install Main - Somerset Ave (2) (ANO Mack & Mack) | 04-22-21 A | 04-22-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 188.8965 | 04-26-21 A | 05-19-21 A | 06-07-21 A | 07-12-21 A
1963 | 1 | 17409 | 15391 | Yorkshire Rd | Rosewood St | Wallingford St | EDET1 50657 | GRP-2021-ED1.37.1.2 | Install Main - Yorkshire Rd (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.908 | 01-19-21 A | 02-22-21 A | 05-18-21 A | 05-26-21 A
1970 | 1 | 17448 | 17578 | Wayburn St | Mack Ave | Lozier St | EDET1 50846 | GRP-2021-ED1.48.1.2 | Install Main - Wayburn Ave (2) (Waveney St & Mack Ave) | 03-17-21 A | 03-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 447.2263 | 05-12-21 A | 05-19-21 A | 06-10-21 A | 06-14-21 A
1980 | 1 | 17641 | 14937 | Bedford St | Waveney St | Munich St | EDET1 503756 | GRP-2021-ED1.69.3.2 | Install Main - Bedford St (1) (E Warren Ave & Waveney St) East | 03-18-21 A | 03-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.6596 | 04-12-21 A | 05-19-21 A | 05-27-21 A | 06-07-21 A
1987 | 1 | 17711 | 14460 | Audubon Rd | Waveney St | Cornwall St | EDET1 50640 | GRP-2021-ED1.19.1.2 | Install Main - Audubon Rd (2) (E Warrern Ave & Waveney St) | 02-01-21 A | 03-09-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 519.4026 | 03-29-21 A | 05-03-21 A | 05-27-21 A | 05-28-21 A
1991 | 1 | 17754 | 16956 | Wayburn St | Lozier St | Waveney St | EDET1 50846 | GRP-2021-ED1.48.1.2 | Install Main - Wayburn Ave (2) (Waveney St & Mack Ave) | 03-17-21 A | 03-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 419.6648 | 05-12-21 A | 05-19-21 A | 06-10-21 A | 06-14-21 A
1995 | 1 | 17813 | 16348 | Bremen St | Nottingham Rd | Somerset Ave | EDET1 501045 | GRP-2021-ED1.53.1.2 | Install Main - Bremen St (2) (Balfour Rd & Buckingham Ave) | 03-25-21 A | 03-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 123.6561 | 06-18-21 A | 06-21-21 A | 2021-09-23 | 2021-09-28
1996 | 1 | 17906 | 16524 | Somerset Ave | Windsor St | Bremen St | EDET1 501054 | GRP-2021-ED1.62.1.2 | Install Main - Somerset Ave (2) (Waveney St & Mack Ave) | 03-30-21 A | 04-07-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.9568 | 04-26-21 A | 05-19-21 A | 06-07-21 A | 07-12-21 A
2009 | 1 | 18182 | 15418 | Bedford St | Bremen St | Waveney St | EDET1 507396 | GRP-2021-ED1.69.1.2 | Install Main - Bedford St (1) (E Warren Ave & Waveney St) West | 03-22-21 A | 03-30-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.5373 |  |  | 05-27-21 A | 06-07-21 A
2011 | 1 | 18190 | 15583 | Wayburn St | Voight St | E Warren Ave | EDET1 50845 | GRP-2021-ED1.47.1.2 | Install Main - Wayburn Ave (1) (E Warrern Ave & Waveney St) | 04-22-21 A | 04-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 405.8881 | 07-15-21 A | 07-20-21 A | 07-12-21 A | 07-21-21 A
2027 | 1 | 18377 | 15569 | Bremen St | Haverhill St | Devonshire Rd | EDET1 501045 | GRP-2021-ED1.53.1.2 | Install Main - Bremen St (2) (Balfour Rd & Buckingham Ave) | 03-25-21 A | 03-26-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 118.7318 | 06-18-21 A | 06-21-21 A | 2021-09-23 | 2021-09-28
2030 | 1 | 18397 | 17527 | Lakepointe St | Mack Ave | Lozier St | EDET1 50838 | GRP-2021-ED1.40.1.2 | Install Main - Lakepointe Sr (2) (Waveney St & Mack Ave) | 04-22-21 A | 04-27-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 503.7461 | 06-07-21 A | 06-08-21 A | 07-07-21 A | 07-07-21 A
2031 | 1 | 18407 | 16883 | Maryland St | Lozier St | Waveney St | EDET1 50842 | GRP-2021-ED1.44.1.2 | Install Main - Maryland St (2) (Waveney St & ANO Mack Ave) | 04-27-21 A | 05-06-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 419.7345 | 06-07-21 A | 06-18-21 A | 07-12-21 A | 07-21-21 A
2035 | 1 | 18503 | 14896 | Kensington Ave | Wallingford St | Waveney St | EDET1 50651 | GRP-2021-ED1.31.1.2 | Install Main - Kensington Ave (2) (Waveney St & Mack Ave)- Grosse pointe CL | 01-07-21 A | 01-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 367.1729 | 01-25-21 A | 03-16-21 A | 05-27-21 A | 05-27-21 A
2040 | 1 | 18544 | 16049 | Kensington Ave | Kensington Rd & Mack Ave | Rosewood St | EDET1 50651 | GRP-2021-ED1.31.1.2 | Install Main - Kensington Ave (2) (Waveney St & Mack Ave)- Grosse pointe CL | 01-07-21 A | 01-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 362.8419 | 01-25-21 A | 03-16-21 A | 05-27-21 A | 05-27-21 A
2046 | 1 | 18577 | 16366 | Wayburn St | Waveney St | Voight St | EDET1 50845 | GRP-2021-ED1.47.1.2 | Install Main - Wayburn Ave (1) (E Warrern Ave & Waveney St) | 04-22-21 A | 04-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 405.3289 | 07-15-21 A | 07-20-21 A | 07-12-21 A | 07-21-21 A
2056 | 1 | 18648 | 15875 | Bishop St | Mack Ave | Rosewood St | EDET1 50643 | GRP-2021-ED1.22.1.2 | Install Main - Bishop St (2) (Waveney St & Mack Ave) | 01-04-21 A | 01-07-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 352.1541 | 02-01-21 A | 03-09-21 A | 05-04-21 A | 05-26-21 A
2061 | 1 | 18769 | 16110 | Maryland St | Waveney St | Voight St | EDET1 50841 | GRP-2021-ED1.43.1.2 | Install Main - Maryland St (1) (E Warrern Ave & Waveney St) | 05-07-21 A | 05-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 405.5002 | 06-14-21 A | 06-17-21 A | 07-26-21 A | 07-26-21 A
2062 | 1 | 18790 | 16420 | Chatsworth St | Windsor St | Bremen St | EDET1 501048 | GRP-2021-ED1.56.1.2 | Install Main - Chatsworth St (2) (Bremen St & Mack Ave) | 03-19-21 A | 03-24-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.4618 | 04-26-21 A | 06-15-21 A | 05-27-21 A | 06-22-21 A
2068 | 1 | 18864 | 16994 | Somerset Ave | Brunswick St | Windsor St | EDET1 501054 | GRP-2021-ED1.62.1.2 | Install Main - Somerset Ave (2) (Waveney St & Mack Ave) | 03-30-21 A | 04-07-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021EDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 1/29/2020 | NAD 1983 | Detroit | East Detroit 1 (EDet1) | EDet1 | 5670348.3014 | 11251.905 | 272.3553 | 04-26-21 A | 05-19-21 A | 06-07-21 A | 07-12-21 A
2082 | 1 | 19118 | 21519 | Longfellow St | 14th St | Rosa Parks Blvd | CDET2-2255 | GRP-2021-CDet2.12.1.2 | Install Main - Longfellow 1 (Dexter & Lawton) | 01-19-21 A | 01-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 415.345 | 03-15-21 A | 03-15-21 A | 2021-09-23 | 2021-09-28
2085 | 1 | 19162 | 23602 | Rohns St | Goethe Ave | Mack Ave | RR1 11371 | GRP-2021-FR.65.1.2 | Install Main - Rohns (Mack & Goethe) | 06-22-21 A | 06-24-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Field Recommendation | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 9/29/2020 | NAD 1983 | Detroit | Mack (Crane-McClellan) |  | 193770.0008 | 3812.1791 | 371.462 | 2021-09-20 | 2021-09-20 | 2021-09-24 | 2021-09-29
2088 | 1 | 19210 | 19898 | Monica St | W Buena Vista St | W Davison St | WCDET1-8660 | GRP-2021-WCDet1.26.3.2 | Install Main - Monica West 1 (Oakman & Buena Vista) | 2021-10-04 | 2021-10-06 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 353.117 | 2021-10-07 | 2021-10-21 | 2021-09-23 | 2021-09-28
2094 | 1 | 19397 | 22020 | Atkinson St | 14th St | Rosa Parks Blvd | CDET2-2735 | GRP-2021-CDet2.18.1.2 | Install Main - Atkinson 2 (Linwood & Rosa Parks) | 01-11-21 A | 01-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 419.8612 | 03-22-21 A | 05-19-21 A | 05-26-21 A | 05-26-21 A
2100 | 1 | 19455 | 21067 | Longfellow St | Rosa Parks Blvd | Woodrow Wilson St | CDET2-2255 | GRP-2021-CDet2.12.1.2 | Install Main - Longfellow 1 (Dexter & Lawton) | 01-19-21 A | 01-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 364.2885 | 03-15-21 A | 03-15-21 A | 2021-09-23 | 2021-09-28
2121 | 1 | 19764 | 20511 | Fairview St | Mack Ave | E Canfield St | RR1 5541 | GRP-2021-RR.2.1.2 | Install Main - Fairview (E Warren & E Canfield) | 2021-11-19 | 2021-12-03 | Yes | 4 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Fairview | Warren | ANO Mack | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Fairview (Warren-ANO Mack) |  | 112573.9506 | 1840.1149 | 694.907 | 2021-12-07 | 2021-12-15 | 2021-12-21 | 2021-12-28
2126 | 1 | 19879 | 21563 | Lawton St | Glynn Ct | Calvert St | 0 |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 119.4554
2131 | 1 | 19955 | 23391 | Hazelwood St | La Salle Blvd | 14th St | CDET2-6470 | GRP-2021-CDet2.26.3.2 | Install Main - Hazelwood 2 (La Salle & Rosa Parks) | 02-24-21 A | 03-01-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 335.9456 | 04-12-21 A | 05-11-21 A | 07-06-21 A | 07-15-21 A
2133 | 1 | 19988 | 22571 | Edison St | Linwood St | La Salle Blvd | CDET2-2495 | GRP-2021-CDet2.15.1.2 | Install Main - Edison 2 (Linwood & Rosa Parks) | 01-04-21 A | 01-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 364.768 | 03-08-21 A | 04-15-21 A | 05-26-21 A | 07-21-21 A
2141 | 1 | 20102 | 20489 | Alger St | John R St | Brush St | RR1 7301 | GRP-2021-RR.26.1.2 | Install Main - Alger (Woodward & Beaubien) | 06-23-21 A | 07-19-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Alger | Woodward | Beaubien | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Alger (Woodward-Beaubien) |  | 71394.0943 | 1537.5737 | 303.0066 | 2021-09-20 | 2021-09-23 | 2021-09-29 | 2021-10-04
2161 | 1 | 20540 | 22351 | Edison St | La Salle Blvd | 14th St | CDET2-2495 | GRP-2021-CDet2.15.1.2 | Install Main - Edison 2 (Linwood & Rosa Parks) | 01-04-21 A | 01-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 335.8289 | 03-08-21 A | 04-15-21 A | 05-26-21 A | 07-21-21 A
2165 | 1 | 20675 | 21944 | Longfellow St | La Salle Blvd | 14th St | CDET2-2255 | GRP-2021-CDet2.12.1.2 | Install Main - Longfellow 1 (Dexter & Lawton) | 01-19-21 A | 01-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 335.8877 | 03-15-21 A | 03-15-21 A | 2021-09-23 | 2021-09-28
2171 | 1 | 20775 | 23534 | Gladstone St | La Salle Blvd | 14th St | CDET2-3455 | GRP-2021-CDet2.28.1.2 | Install Main - Gladstone 2 (Linwood & Linwood) | 05-03-21 A | 05-03-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 335.5418 |  |  | 06-23-21 A | 06-23-21 A
2185 | 1 | 21013 | 23022 | Hazelwood St | 14th St | Rosa Parks Blvd | CDET2-6470 | GRP-2021-CDet2.26.3.2 | Install Main - Hazelwood 2 (La Salle & Rosa Parks) | 02-24-21 A | 03-01-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 441.1391 | 04-12-21 A | 05-11-21 A | 07-06-21 A | 07-15-21 A
2188 | 1 | 21068 | 23054 | Monica St | Webb St | Tuxedo St | WCDET1-8980 | GRP-2021-WCDet1.12.3.2 | Install Main - Monica East 3 (Grand River & EOM) | 2021-10-25 | 2021-10-26 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 138.7471 | 2021-10-27 | 2021-10-27 | 2021-11-02 | 2021-11-05
2190 | 1 | 21078 | 19472 | Petoskey Ave | Glendale St | W Buena Vista St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 130.5663
2217 | 1 | 21629 | 23535 | La Salle Blvd | Gladstone St | Hazelwood St | CDET2-5215 | GRP-2021-CDet2.50.1.2 | Install Main - LaSalle 1 (Clairmount & Gladstone) | 03-03-21 A | 03-05-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 134.0666 | 04-11-21 A | 04-15-21 A | 2021-09-23 | 2021-09-28
2244 | 1 | 22341 | 21902 | Edison St | 14th St | Rosa Parks Blvd | CDET2-2495 | GRP-2021-CDet2.15.1.2 | Install Main - Edison 2 (Linwood & Rosa Parks) | 01-04-21 A | 01-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 417.4217 | 03-08-21 A | 04-15-21 A | 05-26-21 A | 07-21-21 A
2248 | 1 | 22381 | 22520 | Atkinson St | La Salle Blvd | 14th St | CDET2-2735 | GRP-2021-CDet2.18.1.2 | Install Main - Atkinson 2 (Linwood & Rosa Parks) | 01-11-21 A | 01-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 336.0745 | 03-22-21 A | 05-19-21 A | 05-26-21 A | 05-26-21 A
2268 | 1 | 22790 | 22412 | Longfellow St | Linwood St | La Salle Blvd | CDET2-2255 | GRP-2021-CDet2.12.1.2 | Install Main - Longfellow 1 (Dexter & Lawton) | 01-19-21 A | 01-20-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 364.4937 | 03-15-21 A | 03-15-21 A | 2021-09-23 | 2021-09-28
2272 | 1 | 22826 | 21423 | Edison St | Rosa Parks Blvd | Woodrow Wilson St | CDET2-2495 | GRP-2021-CDet2.15.1.2 | Install Main - Edison 2 (Linwood & Rosa Parks) | 01-04-21 A | 01-12-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 364.508 | 03-08-21 A | 04-15-21 A | 05-26-21 A | 07-21-21 A
2276 | 1 | 22911 | 23056 | Taylor St | La Salle Blvd | 14th St | CDET2-6310 | GRP-2021-CDet2.24.57.2 | Install Main - Taylor 2 (Linwood & La Salle) | 02-22-21 A | 02-23-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 335.8936 | 04-12-21 A | 04-15-21 A | 07-15-21 A | 07-15-21 A
2283 | 1 | 23038 | 22989 | Atkinson St | Linwood St | La Salle Blvd | CDET2-2735 | GRP-2021-CDet2.18.1.2 | Install Main - Atkinson 2 (Linwood & Rosa Parks) | 01-11-21 A | 01-22-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 364.5785 | 03-22-21 A | 05-19-21 A | 05-26-21 A | 05-26-21 A
2298 | 1 | 23288 | 22880 | Taylor St | 14th St | Rosa Parks Blvd | CDET2-10830 | GRP-2021-CDet2.24.1.2 | Install Main - Taylor 2 (La Salle & Rosa Parks) | 02-03-21 A | 02-19-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 440.1224 | 04-12-21 A | 05-11-21 A | 07-13-21 A | 07-21-21 A
2305 | 1 | 23501 | 23057 | La Salle Blvd | Taylor St | Clairmount St | CDET2-5215 | GRP-2021-CDet2.50.1.2 | Install Main - LaSalle 1 (Clairmount & Gladstone) | 03-03-21 A | 03-05-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 132.0209 | 04-11-21 A | 04-15-21 A | 2021-09-23 | 2021-09-28
2314 | 1 | 23700 | 23152 | Gladstone St | 14th St | Rosa Parks Blvd | CDET2-6530 | GRP-2021-CDet2.28.1.2 | Install Main - Gladstone 2 (Rosa Parks & Rosa Parks) | 05-03-21 A | 05-03-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 442.4046 |  |  | 06-23-21 A | 06-23-21 A
2337 | 1 | 24055 | 25116 | Carter St | Dexter Ave | Wildemere St | CDET2-3535 | GRP-2021-CDet2.29.1.2 | Install Main - Carter (Dexter & Linwood) | 03-22-21 A | 03-29-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 408.5675 | 07-09-21 A | 07-20-21 A | 07-28-21 A | 2021-09-28
2344 | 1 | 24103 | 27893 | Ohio St | Joy Rd | Stawell St | SCDet-8530 | GRP-2021-SCDet1.33.3.2 | Install Main - Ohio (12' SSPL Joy & 25' SSPL Joy) | 04-09-21 A | 04-09-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 266.5238
2358 | 1 | 24265 | 24406 | Stoepel St | Barr St | Georgeland St | WCDET1-4905 | GRP-2021-WCDet1.47.1.2 | Install Main - Stoepel 3 (Burlingame & Grand River) | 2021-10-27 | 2021-11-02 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 121.6058 | 2021-11-05 | 2021-11-10 | 2021-11-17 | 2021-11-22
2379 | 1 | 24637 | 24996 | Gladstone St | Dexter Ave | Wildemere St | CDET2-3455 | GRP-2021-CDet2.28.1.2 | Install Main - Gladstone 2 (Linwood & Linwood) | 05-03-21 A | 05-03-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 408.5675 |  |  | 06-23-21 A | 06-23-21 A
2380 | 1 | 24638 | 23906 | Stoepel St | Annland St | Stearns St | WCDET1-4905 | GRP-2021-WCDet1.47.1.2 | Install Main - Stoepel 3 (Burlingame & Grand River) | 2021-10-27 | 2021-11-02 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 133.7619 | 2021-11-05 | 2021-11-10 | 2021-11-17 | 2021-11-22
2385 | 1 | 24672 | 23924 | Gladstone St | Linwood St | La Salle Blvd | CDET2-3455 | GRP-2021-CDet2.28.1.2 | Install Main - Gladstone 2 (Linwood & Linwood) | 05-03-21 A | 05-03-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 361.1832 |  |  | 06-23-21 A | 06-23-21 A
2392 | 1 | 24744 | 25513 | Carter St | Holmur St | Dexter Ave | CDET2-3535 | GRP-2021-CDet2.29.1.2 | Install Main - Carter (Dexter & Linwood) | 03-22-21 A | 03-29-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 287.1313 | 07-09-21 A | 07-20-21 A | 07-28-21 A | 2021-09-28
2397 | 1 | 24812 | 27973 | Burt Rd | Cathedral St | Westfield St | RR1 7381 | GRP-2021-RR.27.1.2 | Install Main - Burt (Westfield & Joy) East | 03-30-21 A | 04-20-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Burt | Joy | Westfield | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Burt (Joy-Westfield) |  | 64370.9106 | 1646.6544 | 269.1296 | 06-02-21 A | 06-23-21 A | 07-07-21 A | 2021-09-28
2401 | 1 | 24954 | 28550 | Littlefield St | Mackenzie St | Joy Rd | SCDet-2615 | GRP-2021-SCDet1.9.1.2 | Install Main - Littlefield 1 (Joy & Sorrento) | 01-04-21 A | 01-19-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 316.2632 | 03-02-21 A | 03-10-21 A | 06-02-21 A | 06-02-21 A
2403 | 1 | 24966 | 23996 | Pingree St | La Salle Blvd | 14th St | CDET2-6990 | GRP-2021-CDet2.33.3.2 | Install Main - Pingree 2 (La Salle & 14th) | 03-18-21 A | 03-18-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 313.3588 | 07-20-21 A | 07-20-21 A | 09-13-21 A | 09-13-21 A
2407 | 1 | 25012 | 28513 | Mackenzie St | Esper St | Freda St | SCDet-9670 | GRP-2021-SCDet1.55.1.2 | Install Main - Mackenzie 2 (Oakman Blvd & Morrow Circle) | 01-22-21 A | 02-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 110.3782 | 05-03-21 A | 05-03-21 A | 06-23-21 A | 06-23-21 A
2414 | 1 | 25116 | 25625 | W Euclid St | Wildemere St | Lawton St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 339.3969
2415 | 1 | 25117 | 24374 | W Philadelphia St | La Salle Blvd | 14th St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 312.2397
2419 | 1 | 25211 | 24864 | Hazelwood St | Dexter Ave | Wildemere St | CDET2-3295 | GRP-2021-CDet2.26.1.2 | Install Main - Hazelwood 2 (Linwood & La Salle) | 03-01-21 A | 03-03-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 409.4366 | 05-10-21 A | 05-19-21 A | 07-06-21 A | 07-06-21 A
2435 | 1 | 25440 | 27884 | Northlawn St | Joy Rd | Stawell St | SCDet-4615 | GRP-2021-SCDet1.34.1.2 | Install Main - Northlawn (Joy & Tireman) | 11-24-20 A | 12-07-20 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 264.6681 | 01-11-21 A | 02-08-21 A | 05-26-21 A | 05-26-21 A
2438 | 1 | 25508 | 23997 | La Salle Blvd | Pingree St | Blaine St | CDET2-8510 | GRP-2021-CDet2.50.3.2 | Install Main - LaSalle 1 (Gladstone & W Euclid) | 03-05-21 A | 03-10-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 137.954 | 04-04-21 A | 04-08-21 A | 2021-09-23 | 2021-09-28
2452 | 1 | 25815 | 23864 | Blaine St | La Salle Blvd | 14th St | CDET2-3695 | GRP-2021-CDet2.31.1.2 | Install Main - Blaine 2 (Linwood & La Salle) | 03-22-21 A | 03-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 315.0035 | 05-03-21 A | 05-10-21 A | 07-22-21 A | 07-23-21 A
2455 | 1 | 25828 | 23935 | Clairmount St | Wildemere St | Lawton St | CDET2-2975 | GRP-2021-CDet2.21.1.2 | Install Main - Clairmount 2 (Linwood & La Salle) | 01-25-21 A | 02-02-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 344.1492 | 03-15-21 A | 07-27-21 A | 2021-09-23 | 2021-09-28
2456 | 1 | 25861 | 24878 | Carter St | Wildemere St | Lawton St | CDET2-3535 | GRP-2021-CDet2.29.1.2 | Install Main - Carter (Dexter & Linwood) | 03-22-21 A | 03-29-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 341.7841 | 07-09-21 A | 07-20-21 A | 07-28-21 A | 2021-09-28
2459 | 1 | 25892 | 24454 | Pingree St | Linwood St | La Salle Blvd | CDET2-3855 | GRP-2021-CDet2.33.1.2 | Install Main - Pingree 2 (Linwood & La Salle) | 03-19-21 A | 03-19-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 378.9534 | 07-19-21 A | 07-20-21 A | 07-29-21 A | 07-30-21 A
2469 | 1 | 26025 | 24072 | Blaine St | Linwood St | La Salle Blvd | CDET2-3695 | GRP-2021-CDet2.31.1.2 | Install Main - Blaine 2 (Linwood & La Salle) | 03-22-21 A | 03-23-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 379.2954 | 05-03-21 A | 05-10-21 A | 07-22-21 A | 07-23-21 A
2482 | 1 | 26249 | 24483 | Monica St | Grand River Ave | Burlingame St | WCDET1-8820 | GRP-2021-WCDet1.12.1.2 | Install Main - Monica (East) 3 (Burlingame & Grand River) | 2021-10-29 | 2021-11-02 | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 559.3389 | 2021-11-03 | 2021-11-11 | 2021-11-16 | 2021-11-22
2489 | 1 | 26409 | 28498 | Normile St | Mackenzie St | Esper St | SCDet-7800 | GRP-2021-SCDet1.28.3.2 | Install Main - Normile (Esper & Belton) | 02-01-21 A | 02-25-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 202.6755 | 03-08-21 A | 04-09-21 A | 06-02-21 A | 06-02-21 A
2497 | 1 | 26565 | 26434 | W Euclid St | Holmur St | Dexter Ave | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 287.5505
2522 | 1 | 26876 | 24399 | Clairmount St | Dexter Ave | Wildemere St | CDET2-2975 | GRP-2021-CDet2.21.1.2 | Install Main - Clairmount 2 (Linwood & La Salle) | 01-25-21 A | 02-02-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 409.7373 | 03-15-21 A | 07-27-21 A | 2021-09-23 | 2021-09-28
2531 | 1 | 27018 | 24600 | W Philadelphia St | Linwood St | La Salle Blvd | DNE IN P6 LAYOUT |  |  |  |  | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 378.715
2539 | 1 | 27207 | 24522 | La Salle Blvd | W Euclid St | W Philadelphia St | CDET2-8510 | GRP-2021-CDet2.50.3.2 | Install Main - LaSalle 1 (Gladstone & W Euclid) | 03-05-21 A | 03-10-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 138.2055 | 04-04-21 A | 04-08-21 A | 2021-09-23 | 2021-09-28
2553 | 1 | 27411 | 28438 | Roselawn St | Mackenzie St | Joy Rd | SCDet-4775 | GRP-2021-SCDet1.36.1.2 | Install Main - Roselawn (Joy & Tireman) | 11-17-20 A | 12-09-20 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 360.4361 | 02-24-21 A | 03-08-21 A | 06-02-21 A | 06-08-21 A
2561 | 1 | 27486 | 28569 | Sorrento St | Mackenzie St | Joy Rd | SCDet-3415 | GRP-2021-SCDet1.19.1.2 | Install Main - Sorrento (Joy & Mackenzie) | 03-01-21 A | 03-04-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 356.8404 | 04-13-21 A | 04-20-21 A | 06-02-21 A | 06-02-21 A
2565 | 1 | 27535 | 28497 | Mackenzie St | Normile St | Wyoming St | SCDet-9670 | GRP-2021-SCDet1.55.1.2 | Install Main - Mackenzie 2 (Oakman Blvd & Morrow Circle) | 01-22-21 A | 02-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 128.1469 | 05-03-21 A | 05-03-21 A | 06-23-21 A | 06-23-21 A
2573 | 1 | 27644 | 25367 | Gladstone St | Holmur St | Dexter Ave | CDET2-3455 | GRP-2021-CDet2.28.1.2 | Install Main - Gladstone 2 (Linwood & Linwood) | 05-03-21 A | 05-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 287.2153 |  |  | 06-23-21 A | 06-23-21 A
2595 | 1 | 27876 | 28435 | Burt Rd | Dover St | Cathedral St | RR1 7381 | GRP-2021-RR.27.1.2 | Install Main - Burt (Westfield & Joy) East | 03-30-21 A | 04-20-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Burt | Joy | Westfield | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Burt (Joy-Westfield) |  | 64370.9106 | 1646.6544 | 268.3953 | 06-02-21 A | 06-23-21 A | 07-07-21 A | 2021-09-28
2597 | 1 | 27895 | 25406 | W Euclid St | Lawton St | Linwood St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 352.3331
2599 | 1 | 27940 | 27479 | Holmur St | Whitney St | Columbus St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Whitney | Grand River | Dexter | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Whitney (Grand River-Dexter) |  | 52026.9138 | 1092.9953 | 120.263
2625 | 1 | 28189 | 26060 | W Euclid St | Dexter Ave | Wildemere St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 408.0202
2627 | 1 | 28276 | 24455 | Carter St | Lawton St | Linwood St | CDET2-6550 | GRP-2021-CDet2.29.1.2 | Install Main - Carter (Linwood & Linwood) | 04-19-21 A | 04-19-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021CDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/14/2020 | NAD 1983 | Detroit | Central Detroit 2 (CDet2) | CDet2 | 4459164.8898 | 8871.7151 | 349.5167 | 07-09-21 A | 07-20-21 A | 07-28-21 A | 2021-09-28
2638 | 1 | 28450 | 28485 | Kentucky St | Mackenzie St | Joy Rd | SCDet-4295 | GRP-2021-SCDet1.30.1.2 | Install Main - Kentucky (Joy & Tireman) | 01-04-21 A | 01-27-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 352.8962 | 03-29-21 A | 03-30-21 A | 05-26-21 A | 05-28-21 A
2648 | 1 | 28571 | 26451 | Saint Marys St | W Chicago St | Orangelawn St | RR1 6741 | GRP-2021-RR.18.1.2 | Install Main - St Marys (Chicago & Plymouth) | 03-05-21 A | 03-15-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | St Marys | Chicago | Plymouth | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | St. Marys (Chicago-Plymouth) |  | 126041.898 | 2377.5019 | 369.9794 | 07-13-21 A | 07-20-21 A | 2021-09-23 | 2021-09-28
2676 | 1 | 29119 | 29899 | Normile St | Normile Ave & Tireman Ave | Belton St | SCDet-7960 | GRP-2021-SCDet1.28.2.2 | Install Main - Normile (6' NNPL Tireman & Tireman) | 03-29-21 A | 03-30-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 361.4555 |  |  | 06-02-21 A | 2021-09-28
2684 | 1 | 29358 | 29140 | Middlepoint St | Belton St | Esper St | SCDet-7480 | GRP-2021-SCDet1.26.3.2 | Install Main - Middlepointe (Esper & Tireman) | 01-27-21 A | 02-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 195.1595 | 05-11-21 A | 05-17-21 A | 07-22-21 A | 07-23-21 A
2687 | 1 | 29421 | 29364 | Belton St | Mendota St | Middlepoint St | SCDet-5575 | GRP-2021-SCDet1.46.1.2 | Install Main - Belton 2 (Mendota & Middlepointe) | 02-03-21 A | 02-24-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 199.9745 | 06-15-21 A | 06-15-21 A | 2021-09-23 | 2021-09-28
2691 | 1 | 29472 | 29864 | Northlawn St | Tireman Ave | Belton St | SCDet-4615 | GRP-2021-SCDet1.34.1.2 | Install Main - Northlawn (Joy & Tireman) | 11-24-20 A | 12-07-20 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 362.4077 | 01-11-21 A | 02-08-21 A | 05-26-21 A | 05-26-21 A
2697 | 1 | 29597 | 30032 | Carlin St | Neckel Ave & Tireman Ave | Belton St | SCDet-2855 | GRP-2021-SCDet1.12.1.2 | Install Main - Carlin (Joy & Tireman) | 01-04-21 A | 01-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 361.5783 | 02-01-21 A | 02-25-21 A | 03-25-21 A | 03-25-21 A
2729 | 1 | 30213 | 29445 | Belton St | Cheyenne St | Ward St | SCDet-5495 | GRP-2021-SCDet1.45.1.2 | Install Main - Belton 1 (Decatur & Carlin) | 01-19-21 A | 01-28-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 129.2282 |  |  | 2021-09-23 | 2021-09-28
2736 | 1 | 30409 | 29105 | Normile St | Belton St | Mackenzie St | SCDet-7800 | GRP-2021-SCDet1.28.3.2 | Install Main - Normile (Esper & Belton) | 02-01-21 A | 02-25-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 367.8451 | 03-08-21 A | 04-09-21 A | 06-02-21 A | 06-02-21 A
2746 | 1 | 30594 | 29461 | Hartwell St | Belton St | Mackenzie St | SCDet-3095 | GRP-2021-SCDet1.15.1.2 | Install Main - Hartwell (Joy & Tireman) | 01-19-21 A | 01-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 372.238 | 03-15-21 A | 03-16-21 A | 04-29-21 A | 04-30-21 A
2759 | 1 | 30811 | 30014 | Hartwell St | Tireman Ave & Calhoun Ave | Belton St | SCDet-3095 | GRP-2021-SCDet1.15.1.2 | Install Main - Hartwell (Joy & Tireman) | 01-19-21 A | 01-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 361.4264 | 03-15-21 A | 03-16-21 A | 04-29-21 A | 04-30-21 A
2760 | 1 | 30826 | 29071 | Indiana St | Belton St | Mackenzie St | SCDet-4375 | GRP-2021-SCDet1.31.1.2 | Install Main - Indiana (Joy & Tireman) | 01-04-21 A | 01-25-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 368.1904 | 02-01-21 A | 02-24-21 A | 05-27-21 A | 05-28-21 A
2797 | 1 | 31462 | 28863 | Hartwell St | Mackenzie St | Joy Rd | SCDet-3095 | GRP-2021-SCDet1.15.1.2 | Install Main - Hartwell (Joy & Tireman) | 01-19-21 A | 01-28-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 361.4945 | 03-15-21 A | 03-16-21 A | 04-29-21 A | 04-30-21 A
2810 | 1 | 31789 | 29385 | Belton St | Manor | Pinehurst St | SCDet-8850 | GRP-2021-SCDet1.54.1.2 | Install Main - Belton 3 (Sorrento & Littlefield) | 03-12-21 A | 03-17-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 122.1662 |  |  | 2021-09-23 | 2021-09-28
2820 | 1 | 31929 | 29119 | Belton St | Freda St | Normile St | SCDet-5575 | GRP-2021-SCDet1.46.1.2 | Install Main - Belton 2 (Mendota & Middlepointe) | 02-03-21 A | 02-24-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 123.5766 | 06-15-21 A | 06-15-21 A | 2021-09-23 | 2021-09-28
2822 | 1 | 31937 | 29409 | Belton St | Appoline Ave | Meyers Rd | SCDet-8850 | GRP-2021-SCDet1.54.1.2 | Install Main - Belton 3 (Sorrento & Littlefield) | 03-12-21 A | 03-17-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 123.4768 |  |  | 2021-09-23 | 2021-09-28
2851 | 1 | 32489 | 28937 | Burt Rd | Joy Rd | Dover St | RR1 10151 | GRP-2021-RR.27.2.2 | Install Main - Burt (Westfield & Joy) West | 03-22-21 A | 03-31-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Burt | Joy | Westfield | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Burt (Joy-Westfield) |  | 64370.9106 | 1646.6544 | 265.5392 | 06-02-21 A | 06-23-21 A | 07-07-21 A | 2021-09-28
2852 | 1 | 32586 | 29129 | E Morrow Cir | Belton St | E Morrow Cir | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 279.6115
2875 | 1 | 33002 | 29460 | Belton St | Hartwell St | Bingham Ave | SCDet-5495 | GRP-2021-SCDet1.45.1.2 | Install Main - Belton 1 (Decatur & Carlin) | 01-19-21 A | 01-28-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 123.6312 |  |  | 2021-09-23 | 2021-09-28
2884 | 1 | 33213 | 29478 | Carlin St | Belton St | Van Buren St | SCDet-2855 | GRP-2021-SCDet1.12.1.2 | Install Main - Carlin (Joy & Tireman) | 01-04-21 A | 01-28-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 458.8783 | 02-01-21 A | 02-25-21 A | 03-25-21 A | 03-25-21 A
2899 | 1 | 33575 | 36999 | Rathbone St | Elsmere St | Lawndale St | SWDET2-4510 | PROJ-0951-SWDET2.37.1.2 | Install Main - Rathbone (Woodmere & Lawndale) | 08-02-21 A | 08-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 381.2679 | 2021-09-20 | 2021-10-01 | 2021-10-07 | 2021-10-12
2902 | 1 | 33582 | 36996 | Longworth St | Woodmere St | Elsmere St | SWDET2-4430 | PROJ-0951-SWDET2.36.1.2 | Install Main - Longworth (Woodmere & Lawndale) | 06-28-21 A | 07-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 381.7971 | 2021-09-20 | 2021-10-01 | 2021-09-23 | 2021-09-28
2906 | 1 | 33641 | 36971 | Longworth St | Elsmere St | Lawndale St | SWDET2-4430 | PROJ-0951-SWDET2.36.1.2 | Install Main - Longworth (Woodmere & Lawndale) | 06-28-21 A | 07-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 381.4218 | 2021-09-20 | 2021-10-01 | 2021-09-23 | 2021-09-28
2911 | 1 | 33722 | 36398 | Norman St | Belle St | Woodmere St | SWDET2-21635 | PROJ-0951-SWDET2.75.4.2 | Install Main - Norman (ANO Vernor & ANO Vernor) | 03-15-21 A | 03-18-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 214.1481 | 2021-09-20 | 2021-09-20 | 2021-11-12 | 2021-11-17
2915 | 1 | 33811 | 36586 | Oakdale St | W Vernor Hwy | Woodmere St | SWDET2-21795 | PROJ-0951-SWDET2.76.3.2 | Install Main - Oakdale (Woodmere & ANO W Vernor) | 04-12-21 A | 04-16-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 354.8835 | 08-09-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
2924 | 1 | 33921 | 36516 | Navy St | Central St | N Green St | SWDET2-21075 | PROJ-0951-SWDET2.59.3.2 | Install Main - Navy 2 (Central & Green) | 2021-10-26 | 2021-10-29 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 384.3428 | 2021-11-02 | 2021-11-09 | 2021-11-15 | 2021-11-18
2928 | 1 | 33984 | 36467 | Whittaker St | Central St | N Green St | SWDET2-14875 | PROJ-0951-SWDET2.64.3.2 | Install Main - Whitaker 2 (Central & Green) | 08-23-21 A | 08-25-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 382.6267 | 2021-09-20 | 2021-09-27 | 2021-10-01 | 2021-10-06
2930 | 1 | 34054 | 36973 | Rathbone St | Lawndale St | Springwells St | SWDET2-18675 | PROJ-0951-SWDET2.37.3.2 | Install Main - Rathbone (Lawndale & Springwells) | 04-15-21 A | 05-13-21 A | Yes | 4 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 704.7407 | 2021-09-20 | 2021-09-30 | 2021-10-06 | 2021-10-11
2937 | 1 | 34156 | 36932 | Mandale St | Woodmere St | Elsmere St | SWDET2-4990 | PROJ-0951-SWDET2.43.1.2 | Install Main - Mandale (Woodmere & Elsemere) | 03-22-21 A | 03-24-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 265.999 | 2021-09-20 | 2021-09-21 | 08-10-21 A | 08-10-21 A
2941 | 1 | 34230 | 36461 | Casper St | W Vernor Hwy | Pitt St | SWDET2-15645 | PROJ-0951-SWDET2.66.3.2 | Install Main - Casper (Tie-In & W Vernor) | 06-09-21 A | 06-10-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 319.7626 | 2021-09-20 | 2021-09-27 | 2021-10-01 | 2021-10-06
2946 | 1 | 34272 | 36497 | Pitt St | Ferris St | Wendell St | SWDET2-22995 | PROJ-0951-SWDET2.69.4.2 | Install Main - Pitt (Honorah & EOM) | 04-09-21 A | 04-09-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 109.0549 | 08-16-21 A | 08-16-21 A | 2021-09-23 | 2021-09-28
2947 | 1 | 34274 | 36590 | Casgrain St | W Lafayette Blvd | Army St | RR1 6341 | GRP-2021-FR.12.1.2 | Install Main - Casgrain (40' NNPL Lafayette & 131' NNPL Lafayette) | 06-14-21 A | 06-23-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Risk Rank | Lafayette | Rademacher | Campbell | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/11/2020 | NAD 1983 | Detroit | Lafayette (Rademacher-Campbell) |  | 60665.8992 | 2568.2209 | 297.3347
2948 | 1 | 34317 | 36566 | Lawndale St | W Vernor Hwy | Pitt St | SWDET2-7550 | PROJ-0951-SWDET2.74.1.2 | Install Main - Lawndale 2 (NO Woodmere & Woodmere) | 01-25-21 A | 02-03-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 324.9052 | 2021-09-20 | 2021-09-20 | 2021-09-27 | 2021-09-30
2950 | 1 | 34330 | 36569 | Gartner St | Springwells St | Evans St | SWDET2-6110 | PROJ-0951-SWDET2.57.1.2 | Install Main - Gartner 2 (Springwells & Central) | 2021-11-18 | 2021-11-23 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 121.1959 | 2021-11-26 | 2021-12-02 | 2021-12-08 | 2021-12-13
2956 | 1 | 34443 | 37017 | Rathbone St | Woodmere St | Elsmere St | SWDET2-4510 | PROJ-0951-SWDET2.37.1.2 | Install Main - Rathbone (Woodmere & Lawndale) | 08-02-21 A | 08-13-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 380.8635 | 2021-09-20 | 2021-10-01 | 2021-10-07 | 2021-10-12
2961 | 1 | 34471 | 36960 | Homer St | Lawndale St | Mullane St | SWDET2-18245 | PROJ-0951-SWDET2.34.3.2 | Install Main - Homer (Lawndale & Springwells) | 09-07-21 A | 2021-09-27 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 366.7284 | 2021-09-29 | 2021-10-13 | 2021-10-19 | 2021-10-22
2962 | 1 | 34474 | 36479 | Springwells St | W Vernor Hwy | Pitt St | SWDET2-10585 | PROJ-0951-SWDET2.9.2.2 | Install Main - Springwells 1 (W Vernor & ASO Vernor) | 2021-10-29 | 2021-11-01 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 320.6047 |  |  | 2021-11-05 | 2021-11-10
2975 | 1 | 34743 | 36615 | Navy St | Lawndale St | Mullane St | SWDET2-5710 | PROJ-0951-SWDET2.52.1.2 | Install Main - Navy 1 (Lawndale & Springwells) | 2021-10-06 | 2021-10-15 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 367.1597 | 2021-10-19 | 2021-11-02 | 2021-11-08 | 2021-11-11
2986 | 1 | 34882 | 36529 | Pearl St | W Vernor Hwy | Pitt St | SWDET2-22355 | PROJ-0951-SWDET2.77.3.2 | Install Main - Pearl (ANO W Vernor & EOM) | 06-17-21 A | 06-17-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 323.9576 |  |  | 2021-09-27 | 2021-09-30
2990 | 1 | 34915 | 36464 | Navy St | N Green St | Beard St | SWDET2-21155 | PROJ-0951-SWDET2.59.2.2 | Install Main - Navy 2 (Green & Beard) | 2021-11-02 | 2021-11-04 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 303.473 | 2021-11-08 | 2021-11-11 | 2021-11-17 | 2021-11-22
2992 | 1 | 34953 | 36553 | Cahalan St | N Green St | Central St | SWDET2-15245 | PROJ-0951-SWDET2.46.3.2 | Install Main - Cahalan 2 (Central & Green) | 2021-10-11 | 2021-10-14 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 386.5311 | 2021-10-19 | 2021-10-22 | 2021-10-28 | 2021-11-02
3002 | 1 | 35133 | 36603 | Gartner St | Mullane St | Springwells St | SWDET2-5390 | PROJ-0951-SWDET2.48.1.2 | Install Main - Gartner 1 (Lawndale & Springwells) | 2021-11-08 | 2021-11-16 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 320.6815 | 2021-11-18 | 2021-12-03 | 2021-12-09 | 2021-12-14
3003 | 1 | 35140 | 36571 | Lane St | Central St | N Green St | SWDET2-24535 | PROJ-0951-SWDET2.50.3.2 | Install Main - Lane 2 (Central & Green) | 2021-10-29 | 2021-11-03 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 387.2361 | 2021-11-05 | 2021-11-10 | 2021-11-16 | 2021-11-19
3013 | 1 | 35366 | 36561 | Gartner St | Evans St | Central St | SWDET2-6110 | PROJ-0951-SWDET2.57.1.2 | Install Main - Gartner 2 (Springwells & Central) | 2021-11-18 | 2021-11-23 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 247.6871 | 2021-11-26 | 2021-12-02 | 2021-12-08 | 2021-12-13
3015 | 1 | 35447 | 36471 | Pearl St | Pitt St | Woodmere St | SWDET2-22355 | PROJ-0951-SWDET2.77.3.2 | Install Main - Pearl (ANO W Vernor & EOM) | 06-17-21 A | 06-17-21 A | Yes | 3 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 463.0014 |  |  | 2021-09-27 | 2021-09-30
3016 | 1 | 35457 | 36421 | Stair St | W Vernor Hwy | Pitt St | SWDET2-7150 | PROJ-0951-SWDET2.71.1.2 | Install Main - Stair (Dix & W Vernor) | 04-27-21 A | 05-06-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 317.5576 | 08-10-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
3028 | 1 | 35579 | 36407 | Casper St | Pitt St | Belle St | SWDET2-6830 | PROJ-0951-SWDET2.66.1.2 | Install Main - Casper (Dix & Tie-In) | 02-22-21 A | 02-24-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 347.2782 | 2021-09-20 | 2021-09-23 | 2021-09-29 | 2021-10-04
3041 | 1 | 35736 | 36455 | Norman St | Pitt St | Belle St | SWDET2-21475 | PROJ-0951-SWDET2.75.2.2 | Install Main - Norman (Tie-In & ANO Vernor) | 2021-11-12 | 2021-11-12 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 346.2309 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-17
3047 | 1 | 35846 | 37008 | Homer St | Woodmere St | Elsmere St | SWDET2-4270 | PROJ-0951-SWDET2.34.1.2 | Install Main - Homer (Woodmere & Lawndale) | 07-12-21 A | 08-02-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 381.4316 | 2021-09-20 | 2021-10-04 | 2021-10-08 | 2021-10-13
3050 | 1 | 35913 | 36424 | Whittaker St | N Green St | Beard St | SWDET2-15035 | PROJ-0951-SWDET2.64.2.2 | Install Main - Whitaker 2 (Green & Beard) | 08-27-21 A | 08-30-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 304.0331 | 2021-09-20 | 2021-09-24 | 2021-09-30 | 2021-10-05
3060 | 1 | 36060 | 36492 | Senator St | Central St | N Green St | SWDET2-6430 | PROJ-0951-SWDET2.61.1.2 | Install Main - Senator 2 (Central & Green) | 09-10-21 A | 09-14-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 383.3691 | 2021-09-20 | 2021-09-28 | 2021-10-05 | 2021-10-08
3065 | 1 | 36105 | 36583 | Navy St | Mullane St | Springwells St | SWDET2-5710 | PROJ-0951-SWDET2.52.1.2 | Install Main - Navy 1 (Lawndale & Springwells) | 2021-10-06 | 2021-10-15 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 318.0071 | 2021-10-19 | 2021-11-02 | 2021-11-08 | 2021-11-11
3072 | 1 | 36193 | 37020 | W Lafayette Blvd | Elsmere St | Lawndale St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 381.0332
3075 | 1 | 36223 | 36919 | Longworth St | Mullane St | Springwells St | SWDET2-19805 | PROJ-0951-SWDET2.36.3.2 | Install Main - Longworth (Tie-in & Lawndale) | 08-19-21 A | 08-24-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 330.9283 | 07-15-21 A | 07-15-21 A | 2021-09-23 | 2021-09-28
3076 | 1 | 36296 | 36887 | Mandale St | Oakdale St | Cabot St | SWDET2-20485 | PROJ-0951-SWDET2.43.3.2 | Install Main - Mandale (Elsemere & Lawndale) | 03-10-21 A | 03-19-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 111.034 | 2021-09-20 | 2021-09-27 | 2021-09-23 | 2021-09-28
3078 | 1 | 36348 | 36629 | Gartner St | Lawndale St | Mullane St | SWDET2-5390 | PROJ-0951-SWDET2.48.1.2 | Install Main - Gartner 1 (Lawndale & Springwells) | 2021-11-08 | 2021-11-16 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 366.9109 | 2021-11-18 | 2021-12-03 | 2021-12-09 | 2021-12-14
3082 | 1 | 36468 | 35938 | 18th St | W Lafayette Blvd | Howard St | RR1 11181 | GRP-2021-FR.55.1.2 | Install Main - 18th (9'WEPL 18th & 3' WWPL 18th) | 2021-10-13 | 2021-10-14 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  |  | 2021 Field Recommendation | Fort | 24th | 15th | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 6/25/2020 | NAD 1983 | Detroit | Fort and St. Anne |  | 595430.7812 | 5423.835 | 158.9013 |  |  | 2021-12-10 | 2021-12-15 | Install Main - 18th (9'WEPL 18th & 3' WWPL 18th)
3084 | 1 | 36484 | 36935 | Homer St | Mullane St | Springwells St | SWDET2-18245 | PROJ-0951-SWDET2.34.3.2 | Install Main - Homer (Lawndale & Springwells) | 09-07-21 A | 2021-09-27 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 333.8475 | 2021-09-29 | 2021-10-13 | 2021-10-19 | 2021-10-22
3094 | 1 | 36592 | 36979 | Falcon St | Woodmere St | Elsmere St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 382.3699
3098 | 1 | 36793 | 36510 | Lawndale St | Pitt St | Woodmere St | SWDET2-11665 | PROJ-0951-SWDET2.74.3.2 | Install Main - Lawndale 2 (Woodmere & Tie-in) | 2021-10-26 | 2021-10-26 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 176.2268 | 2021-10-27 | 2021-10-27 | 2021-11-02 | 2021-11-05
3100 | 1 | 36832 | 36551 | Navy St | Springwells St | Central St | SWDET2-6270 | PROJ-0951-SWDET2.59.1.2 | Install Main - Navy 2 (Springwells & Central) | 2021-10-19 | 2021-10-22 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 369.5474 | 2021-10-26 | 2021-11-02 | 2021-11-08 | 2021-11-11
3103 | 1 | 36871 | 36058 | Casper St | Belle St | Dix St | SWDET2-6830 | PROJ-0951-SWDET2.66.1.2 | Install Main - Casper (Dix & Tie-In) | 02-22-21 A | 02-24-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 218.3892 | 2021-09-20 | 2021-09-23 | 2021-09-29 | 2021-10-04
3108 | 1 | 36927 | 37031 | Olivet St | Elsmere St | Lawndale St | SWDET2-3790 | PROJ-0951-SWDET2.28.1.2 | Install Main - Olivet (Woodmere & Lawndale) | 06-07-21 A | 06-18-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 381.1012 | 2021-09-20 | 2021-09-24 | 2021-10-01 | 2021-10-06
3113 | 1 | 37017 | 36888 | Oakdale St | Mandale St | W Vernor Hwy | SWDET2-7710 | PROJ-0951-SWDET2.76.1.2 | Install Main - Oakdale (NO Woodmere & Woodmere) | 02-23-21 A | 02-25-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 390.8641 | 08-16-21 A | 08-16-21 A | 09-01-21 A | 09-01-21 A
3125 | 1 | 37122 | 36913 | Mandale St | Elsmere St | Sharon St | SWDET2-20485 | PROJ-0951-SWDET2.43.3.2 | Install Main - Mandale (Elsemere & Lawndale) | 03-10-21 A | 03-19-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 145.4762 | 2021-09-20 | 2021-09-27 | 2021-09-23 | 2021-09-28
3128 | 1 | 37167 | 36498 | Ferris St | Pitt St | Woodmere St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 271.1225
3129 | 1 | 37181 | 36916 | Lane St | Lawndale St | Mullane St | SWDET2-19165 | PROJ-0951-SWDET2.41.2.2 | Install Main - Lane 1 (Lawndale & Springwells) | 05-17-21 A | 06-04-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 367.0518 | 2021-09-20 | 2021-09-30 | 2021-10-06 | 2021-10-11
3130 | 1 | 37193 | 36944 | Longworth St | Lawndale St | Mullane St | SWDET2-20125 | PROJ-0951-SWDET2.36.4.2 | Install Main - Longworth (Tie-in & Springwells) | 08-25-21 A | 08-25-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 366.5632 | 07-15-21 A | 07-15-21 A | 2021-09-23 | 2021-09-28
3131 | 1 | 37216 | 37043 | Witt St | Elsmere St | Lawndale St | SWDET2-13905 | PROJ-0951-SWDET2.30.2.2 | Install Main - Witt (Elsmere & Lawndale) | 05-18-21 A | 06-11-21 A | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 381.1731 | 2021-09-20 | 2021-09-22 | 2021-09-28 | 2021-10-01
3139 | 1 | 37346 | 36949 | Mason | Woodmere St | Elsmere St | SWDET2-5070 | PROJ-0951-SWDET2.44.1.2 | Install Main - Mason (Woodmere & Elsemere) | 05-04-21 A | 05-06-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 295.964 | 2021-09-20 | 2021-09-23 | 2021-09-29 | 2021-10-04
3146 | 1 | 37427 | 36511 | Inglis St | W Vernor Hwy | Pitt St | SWDET2-6990 | PROJ-0951-SWDET2.68.1.2 | Install Main - Inglis (ANO W Vernor & W Vernor) | 03-17-21 A | 03-18-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 321.2304 | 2021-09-20 | 2021-09-20 | 2021-09-23 | 2021-09-28
3153 | 1 | 37521 | 36534 | Gartner St | Central St | N Green St | SWDET2-17835 | PROJ-0951-SWDET2.57.3.2 | Install Main - Gartner 2 (Central & Green) | 2021-11-26 | 2021-12-01 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 385.3743 | 10-29-21* | 2021-11-03 | 2021-11-09 | 2021-11-12
3155 | 1 | 37536 | 36423 | Springwells St | Pitt St | Belle St | SWDET2-10585 | PROJ-0951-SWDET2.9.2.2 | Install Main - Springwells 1 (W Vernor & ASO Vernor) | 2021-10-29 | 2021-11-01 | Yes | 2 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 347.457 |  |  | 2021-11-05 | 2021-11-10
3156 | 1 | 37547 | 36522 | Norman St | W Vernor Hwy | Pitt St | SWDET2-21315 | PROJ-0951-SWDET2.75.3.2 | Install Main - Norman (ANO Vernor & W Vernor) | 2021-11-02 | 2021-11-04 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 322.1584 | 2021-11-05 | 2021-11-05 | 2021-11-12 | 2021-11-17
3159 | 1 | 37575 | 36069 | Stair St | Pitt St | Dix St | SWDET2-16135 | PROJ-0951-SWDET2.71.3.2 | Install Main - Stair (EOM & Dix) | 05-10-21 A | 05-11-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 261.3303 | 08-16-21 A | 08-16-21 A | 08-26-21 A | 08-26-21 A
3164 | 1 | 37658 | 36496 | Carson St | W Vernor Hwy | Pitt St | SWDET2-15485 | PROJ-0951-SWDET2.65.3.2 | Install Main - Carson (Tie-In & W Vernor) | 06-03-21 A | 06-07-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 321.2768 |  |  | 2021-09-23 | 2021-09-28
3170 | 1 | 37755 | 36388 | Rieden St | W Vernor Hwy | Pitt St | SWDET2-6350 | PROJ-0951-SWDET2.60.1.2 | Install Main - Rieden 1 (Pitt & W Vernor) | 05-24-21 A | 06-02-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 315.1471 | 07-16-21 A | 07-20-21 A | 08-18-21 A | 08-18-21 A
3180 | 1 | 37960 | 36574 | Cabot St | W Vernor Hwy | Pitt St | SWDET2-14625 | PROJ-0951-SWDET2.72.2.2 | Install Main - Cabot (ANO Vernor & W Vernor) | 04-20-21 A | 04-27-21 A | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 325.0355 | 2021-09-20 | 2021-09-20 | 2021-09-23 | 2021-09-28
3181 | 1 | 37978 | 36067 | Springwells St | Belle St | Dix St | SWDET2-10775 | PROJ-0951-SWDET2.70.3.2 | Install Main - Springwells 2 (At Dix) | 2021-10-08 | 2021-10-08 | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 260.77 |  |  | 2021-10-19 | 2021-10-22
3186 | 1 | 38060 | 36404 | N Green St | W Vernor Hwy | Pitt St | DNE IN P6 LAYOUT |  |  |  |  | Yes | 1 | Will be Installed 2021 | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SWDet2 |  |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2021-01-01 | 2021-12-31 | Dan Sand | 734-444-5737 | daniel.sand@dteenergy.com |  |  |  | 4/2/2020 | NAD 1983 | Detroit (and a bit in Dearborn) | Southwest Detroit 2 (SWDet2) | SWDet2 | 6922528.668 | 14865.9789 | 316.7681
3 | 0 | 14 | 4055 | Runyon St | Linnhurst St | Eastwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3552
4 | 0 | 16 | 1925 | Chippewa St | Prairie St | Monica St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.7969
6 | 0 | 40 | 529 | Tacoma St | Boulder St | Cordell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.9637
7 | 0 | 49 | 856 | Charleston St | Colton St | Alameda St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.9721
8 | 0 | 55 | 3112 | McCormick St | Rossiter St | Lansdowne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.7478
9 | 0 | 60 | 3837 | Prairie St | W Outer Dr | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.571
11 | 0 | 68 | 2847 | Fordham St | Rondo St | Gratiot Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 218.1938
12 | 0 | 70 | 3849 | San Juan Dr | W Outer Dr | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.6247
13 | 0 | 73 | 1456 | Mendota St | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.7975
14 | 0 | 76 | 4530 | Danbury St | W 7 Mile Rd | Penrose St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.4321
15 | 0 | 86 | 2970 | W Lantz St | Havana St | Charleston St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 324.7691
16 | 0 | 88 | 539 | Regent Dr | E State Fair St | Rossini Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.1432
17 | 0 | 94 | 3070 | Trojan St | Blackstone St | Trinity St & Griffin Drain | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.0119
18 | 0 | 101 | 1083 | Norfolk St | Gardendale St | Picadilly Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.0705
19 | 0 | 105 | 1881 | Hessel Ave | Forrer St | Winthrop St & James Couzens Fwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 175.3988
20 | 0 | 107 | 3367 | Stahelin Ave | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9293
22 | 0 | 125 | 2491 | Biltmore St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0599
23 | 0 | 128 | 4377 | Whitehill St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.2574
24 | 0 | 132 | 1436 | Norfolk St | Ilene St | Washburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.3022
25 | 0 | 133 | 810 | Greeley St | E Winchester Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.8473
28 | 0 | 149 | 1321 | Sirron St | Kempa St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 232.9989
29 | 0 | 160 | 587 | E Winchester Ave | Marx St | Dequindre St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.232
30 | 0 | 161 | 2992 | Bauman St | W Lantz St | Fernhill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.0463
31 | 0 | 172 | 373 | Savage St | Spencer St | Stotter St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.1461
32 | 0 | 175 | 1065 | Marx St | E Remington Ave | E Winchester Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.3463
33 | 0 | 205 | 2535 | Stotter St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 432.3625
34 | 0 | 212 | 2915 | Rowe St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.1802
35 | 0 | 220 | 825 | Alcoy St | E State Fair St | Fairmount Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.427
36 | 0 | 224 | 3193 | Faircrest St | Morang Dr | Rex St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 191.4162
37 | 0 | 236 | 46 | Carlisle St | Reno St | Hoyt St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.9845
38 | 0 | 253 | 1912 | Yolanda St | Kempa St | E Outer Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 423.9932
39 | 0 | 260 | 3096 | Pembroke Ave | Lesure St | Tracey St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.4088
40 | 0 | 263 | 4066 | Grandview St | Fargo St | Norfolk St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9773
41 | 0 | 266 | 4414 | Peerless St | McCormick St | Peerless Ave & Kingsville Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.2366
42 | 0 | 268 | 2933 | House St | Terrell St | Kempa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.0939
43 | 0 | 283 | 1931 | Hessel Ave | Asbury Park | Murray Hill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 127.4997
44 | 0 | 287 | 2082 | Hessel Ave | Avon Ave | Stahelin Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 97.6135
45 | 0 | 288 | 1948 | Lappin St | Schoenherr St | Mapleview St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.9934
46 | 0 | 292 | 454 | Alcoy St | Fairmount Dr | Bringard Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.82
47 | 0 | 301 | 1914 | Hessel Ave | Saint Marys St | Mansfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.109
50 | 0 | 332 | 1543 | Beland St | Sturgis St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 213.8142
52 | 0 | 352 | 1828 | Packard St | E Lantz St | E Outer Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.0632
53 | 0 | 353 | 338 | Bringard Dr | Goulburn St | Westphalia St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.5382
55 | 0 | 370 | 2497 | Marx St | E Lantz St | E State Fair St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.6512
56 | 0 | 374 | 4130 | Ward St | W Outer Dr | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.42
57 | 0 | 398 | 2539 | Archdale St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.135
58 | 0 | 444 | 2384 | Tracey St | Chippewa St | Norfolk St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.7719
59 | 0 | 457 | 3191 | Norfolk St | Cherokee St | Berg Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 499.3586
60 | 0 | 463 | 2561 | Packard St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 433.4995
61 | 0 | 475 | 4337 | Snowden St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 254.3108
63 | 0 | 478 | 182 | Westphalia St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.6405
64 | 0 | 479 | 3328 | Orleans St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.9903
65 | 0 | 499 | 64 | Collingham Dr | Regent Dr | Marbud St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.1702
66 | 0 | 503 | 1402 | Crusade St | Coram St | Novara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.8716
67 | 0 | 505 | 2415 | Vaughan St | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 249.2033
70 | 0 | 514 | 3354 | Eastwood St | Barlow St | Waltham St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.1079
71 | 0 | 523 | 3040 | Ferguson St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2124
73 | 0 | 537 | 2838 | Hamburg St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0651
74 | 0 | 539 | 2930 | Plainview Ave | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.0901
75 | 0 | 550 | 4546 | Saint Martins Ave | Sunderland Rd | Stahelin Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.8026
76 | 0 | 562 | 1517 | Ward St | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.6358
77 | 0 | 567 | 3962 | McCormick St | Balfour Rd | Beaconsfield Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 385.918
78 | 0 | 570 | 3508 | McCormick St | Beaconsfield Rd | Rossiter St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 406.9933
79 | 0 | 573 | 203 | Strasburg St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.9161
80 | 0 | 591 | 2529 | Marlowe St | Chippewa St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 185.1913
81 | 0 | 630 | 4485 | Joann St | Park Grove St | Linnhurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.4693
82 | 0 | 641 | 4651 | Prest St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 263.9884
83 | 0 | 650 | 1832 | Renfrew Rd | Bloomfield Rd | Norfolk St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 345.7906
84 | 0 | 655 | 328 | Eastburn St | Marbud St | Gratiot Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.7256
85 | 0 | 664 | 65 | Regent Dr | Collingham Dr | Carlisle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.7881
86 | 0 | 692 | 2462 | Murray Hill St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9992
87 | 0 | 709 | 1993 | Alcoy St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.0377
89 | 0 | 764 | 1525 | Barlow St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.2576
90 | 0 | 780 | 2419 | Chippewa St | Hartwell St | Snowden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.325
91 | 0 | 789 | 346 | Veach St | 8 Mile Rd | Savage St & Conner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.694
92 | 0 | 790 | 3092 | Oakfield St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8124
93 | 0 | 809 | 3532 | Stout St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.4782
94 | 0 | 810 | 3920 | Park Grove St | Salter St | Morang Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 221.7835
95 | 0 | 820 | 836 | Manning St | Boulder St | Cordell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.6069
96 | 0 | 825 | 4558 | Havana St | W 7 Mile Rd | Penrose St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 300.1914
97 | 0 | 829 | 4071 | Pinehurst St | W Outer Dr | Saint Martins Ave | [6 empty] | 1 | 2020 Carryover | [26 empty] | 274.9677
98 | 0 | 843 | 233 | Regent Dr | Bringard Dr | Edmore Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.3226
99 | 0 | 848 | 2493 | Fordham St | Hayes St | Brock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.3013
100 | 0 | 849 | 2909 | House St | Kempa St | Antwerp St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 198.0408
101 | 0 | 859 | 1487 | Norfolk St | Appoline St | Meyers Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.6162
102 | 0 | 863 | 1862 | Audrey St | Norfolk St | 8 Mile Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.606
103 | 0 | 873 | 4532 | Stahelin Ave | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.2914
105 | 0 | 883 | 30 | Carlisle St | Marbud St | Mohican St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 292.9865
106 | 0 | 888 | 2320 | Monte Vista St | Chippewa St | Norfolk St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.5818
107 | 0 | 896 | 1024 | Waltham St | Manning St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.9585
108 | 0 | 897 | 230 | Eastburn St | Redmond St | Boulder St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.5663
109 | 0 | 918 | 2622 | Fairport St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7764
110 | 0 | 923 | 3172 | Joann St | Eastwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2413
111 | 0 | 924 | 1046 | Hamburg St | Manning St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.6513
112 | 0 | 926 | 4359 | E Brentwood St | Mitchell St | Charest St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.5746
113 | 0 | 935 | 2558 | Hull St | E Lantz St | E State Fair St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.412
114 | 0 | 967 | 2033 | Derby St | W State Fair St | W Remington Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 386.3595
115 | 0 | 978 | 38 | Carlisle St | Anvil St | Regent Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8067
116 | 0 | 981 | 2897 | Huntington Rd | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.8687
117 | 0 | 988 | 4429 | Pembroke Ave | Greydale Ave | Burgess St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0317
118 | 0 | 994 | 814 | E Winchester Ave | Hull St | Greeley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.7905
120 | 0 | 1012 | 4374 | Cameron St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 382.2401
121 | 0 | 1016 | 2003 | Maddelein St | Queen St | Hayes St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 350.0452
123 | 0 | 1037 | 3521 | Norfolk St | Fenton St | Woodbine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 322.3122
124 | 0 | 1046 | 3346 | Santa Barbara Dr | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.1368
125 | 0 | 1047 | 1884 | Riopelle St | E State Fair St | E Remington Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.6518
126 | 0 | 1048 | 3320 | Faust Ave | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2034
127 | 0 | 1050 | 2062 | Waltham St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0373
128 | 0 | 1061 | 1026 | Rogge St | E Outer Dr | Milbank St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 348.4526
129 | 0 | 1062 | 2398 | Chippewa St | Littlefield St | Cheyenne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.3554
130 | 0 | 1075 | 1387 | Derby St | W Remington Ave | W Winchester Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.5081
131 | 0 | 1087 | 4590 | Grandville Ave | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.3906
133 | 0 | 1097 | 4646 | Washburn St | Cambridge Ave | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.8875
134 | 0 | 1102 | 2087 | Chippewa St | Shrewsbury Rd | Roslyn Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 126.8083
135 | 0 | 1105 | 4634 | Cambridge Ave | Kentucky St | Indiana St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.1336
136 | 0 | 1106 | 1814 | Spencer St | E Lantz St | E Outer Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.0919
137 | 0 | 1110 | 42 | Carlisle St | Hoyt St | Anvil St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.3015
138 | 0 | 1113 | 419 | Regent Dr | Fairmount Dr | Eastburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.3827
139 | 0 | 1114 | 405 | Savage St | Concord St | Helen St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.4189
140 | 0 | 1116 | 3847 | Greydale Ave | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2658
141 | 0 | 1117 | 2051 | Rex St | E 7 Mile Rd | Maddelein St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.6256
142 | 0 | 1139 | 3566 | Ward St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 280.8945
143 | 0 | 1147 | 1466 | Alcoy St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 308.1853
144 | 0 | 1160 | 4450 | Ashton Ave | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.8076
145 | 0 | 1164 | 3604 | Linnhurst St | Reno St | Gratiot Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.8741
146 | 0 | 1166 | 1531 | Teppert St | Sturgis St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 213.9317
147 | 0 | 1177 | 4408 | Omira St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 384.9294
148 | 0 | 1181 | 3181 | Spencer St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 307.1254
149 | 0 | 1182 | 4478 | Cambridge Ave | Santa Rosa Dr | Stoepel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.7063
151 | 0 | 1196 | 3843 | Danbury St | Penrose St | Exeter St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 379.5942
152 | 0 | 1205 | 3900 | Pembroke Ave | Stahelin Ave | Avon Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.8012
153 | 0 | 1214 | 1557 | Fleming St | E Outer Dr | E Remington St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 345.1485
154 | 0 | 1215 | 2455 | Saint Marys St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1648
155 | 0 | 1228 | 892 | Derby St | W Winchester Ave | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.1586
156 | 0 | 1240 | 1493 | Westphalia St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 308.0908
157 | 0 | 1245 | 488 | Strasburg St | Fairmount Dr | Bringard Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.6063
158 | 0 | 1251 | 3388 | Eastwood St | Strasburg St | Hamburg St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.1059
160 | 0 | 1263 | 3822 | Ashton Ave | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 261.7733
161 | 0 | 1264 | 200 | Edmore Dr | Hoyt St | Anvil St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2689
162 | 0 | 1265 | 3862 | Pembroke Ave | Faust Ave | Glastonbury Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 104.4127
163 | 0 | 1266 | 2028 | Rosemont Ave | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.3117
164 | 0 | 1271 | 583 | Rogge St | Milbank St | Savage St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.448
165 | 0 | 1283 | 2456 | Fordham St | Morang Dr | Rex St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 366.6385
166 | 0 | 1287 | 3075 | Lindsay St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7619
167 | 0 | 1298 | 898 | Woodstock Dr | Renfrew Rd | Briarcliff Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.8305
168 | 0 | 1305 | 4399 | Lesure St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.315
169 | 0 | 1312 | 2937 | McCormick St | Lansdowne St | Laing St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.0068
172 | 0 | 1344 | 3890 | Northrop St | Fargo St | Chippewa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 126.6786
174 | 0 | 1350 | 2869 | Dresden St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1757
175 | 0 | 1351 | 2651 | Eastwood St | Brock St | Morang Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 223.7384
176 | 0 | 1367 | 1420 | Rolyat St | Kempa St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 295.8003
177 | 0 | 1370 | 4046 | Birwood St | W Outer Dr | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.6127
178 | 0 | 1371 | 2552 | Pelkey St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.3872
179 | 0 | 1378 | 1988 | Archdale St | Hessel Ave | Circle Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 210.9712
180 | 0 | 1391 | 3183 | Rosemont Ave | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.114
181 | 0 | 1397 | 4085 | Albany St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.8744
182 | 0 | 1409 | 2085 | Trojan St | Marlowe St | Hubbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.4276
183 | 0 | 1415 | 2965 | Pinehurst St | Pembroke Ave | Chippewa St | [6 empty] | 2 | 2020 Carryover | [26 empty] | 348.236
184 | 0 | 1434 | 2987 | Kentfield St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 263.46
185 | 0 | 1437 | 999 | Fairport St | Manning St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.1395
186 | 0 | 1453 | 386 | Cordell St | Rossini Dr | Fairmount Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.8546
187 | 0 | 1460 | 4402 | Woodbine St | Leewin St | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.1708
188 | 0 | 1461 | 2005 | Chippewa St | Cherrylawn St | Northlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.3914
190 | 0 | 1494 | 2619 | Monica St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.8171
191 | 0 | 1497 | 1810 | Lauder St | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.9302
192 | 0 | 1504 | 861 | Manning St | Rex St | Redmond St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.614
194 | 0 | 1513 | 1944 | Ferguson St | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 236.7087
195 | 0 | 1515 | 4330 | E Brentwood St | Gallagher St | Klinger St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.6108
196 | 0 | 1520 | 2541 | Greeley St | E Lantz St | E State Fair St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.4608
197 | 0 | 1524 | 2483 | Bauman St | Adeline St | W State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3201
198 | 0 | 1531 | 4074 | Teppert St | Linnhurst St | Eastwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.0288
199 | 0 | 1533 | 2997 | Stout St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 262.48
200 | 0 | 1534 | 4415 | McCormick St | Peerless St | Balfour Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 386.6647
202 | 0 | 1552 | 2361 | Chippewa St | Steel St | Appoline St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.0794
203 | 0 | 1556 | 2584 | Alcoy St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 291.2342
205 | 0 | 1590 | 1934 | Chippewa St | Warrington Dr | Canterbury Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 105.3858
206 | 0 | 1608 | 223 | Mohican St | Bringard Dr | Edmore Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.8191
207 | 0 | 1613 | 1838 | Norfolk St | Basil St | Carol St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.1624
208 | 0 | 1618 | 4077 | Kentfield St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.3436
209 | 0 | 1619 | 4418 | Stansbury St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.4467
210 | 0 | 1644 | 2474 | Hessel Ave | Braile St & Griffin Drain | Patton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.5981
211 | 0 | 1654 | 4632 | Duchess St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.7158
212 | 0 | 1660 | 1928 | Crusade St | Maddelein St | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.7348
213 | 0 | 1662 | 374 | Spencer St | Savage St | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.3386
214 | 0 | 1663 | 3512 | Kentfield St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.8498
216 | 0 | 1677 | 395 | Fairmount Dr | Gratiot Ave | Queen St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 293.318
217 | 0 | 1707 | 2314 | Chippewa St | Pinehurst St | Mendota St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.8806
218 | 0 | 1709 | 3019 | Trojan St | Braile St | Patton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.0974
219 | 0 | 1718 | 1013 | Goulburn St | Manning St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.0273
220 | 0 | 1723 | 4040 | Winthrop St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.4629
221 | 0 | 1728 | 3432 | Whitcomb St | Pembroke Ave | James Couzens Fwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.8126
222 | 0 | 1751 | 2494 | Hessel Ave | Burt Rd | Pierson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.6272
223 | 0 | 1760 | 902 | Tacoma St | Pelkey St | Schoenherr St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.4594
224 | 0 | 1761 | 3189 | Monica St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.9123
225 | 0 | 1764 | 3481 | Canterbury Rd | Chesterfield Rd | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 209.6311
226 | 0 | 1765 | 57 | Mohican St | Collingham Dr | Carlisle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.4651
227 | 0 | 1767 | 50 | Carlisle St | Schoenherr St | Reno St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.5274
228 | 0 | 1768 | 1482 | Fairport St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 308.876
229 | 0 | 1769 | 3315 | Marx St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.8255
230 | 0 | 1776 | 2053 | Goulburn St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0978
231 | 0 | 1794 | 357 | Hamburg St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.4103
233 | 0 | 1796 | 3167 | Ashton Ave | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0298
234 | 0 | 1798 | 73 | Hoyt St | Collingham Dr | Carlisle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.0689
235 | 0 | 1806 | 436 | Fairmount Dr | Hoyt St | Anvil St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.5046
236 | 0 | 1808 | 3487 | Norfolk St | Salem St | Grandview St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.8183
237 | 0 | 1810 | 4430 | Greydale Ave | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 243.9926
238 | 0 | 1814 | 1324 | Monica St | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.408
239 | 0 | 1831 | 2364 | Rowe St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8552
240 | 0 | 1843 | 4635 | Kentucky St | Cambridge Ave | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.5626
241 | 0 | 1856 | 549 | Mackay St | E Winchester Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.8239
242 | 0 | 1858 | 3872 | Cooley St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.1213
243 | 0 | 1868 | 1501 | Goulburn St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.7649
244 | 0 | 1875 | 383 | Rowe St | Bringard Dr | Groesbeck Hwy & Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 284.1684
245 | 0 | 1876 | 19 | Cushing St | Collingham Dr | Carlisle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.806
246 | 0 | 1885 | 3392 | Hanna St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 356.126
247 | 0 | 1895 | 2035 | Kentucky St | Chippewa St | Norfolk St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.4342
248 | 0 | 1904 | 2032 | Fairport St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0327
249 | 0 | 1913 | 2599 | Joann St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.9102
250 | 0 | 1921 | 2996 | Trojan St | Stout St | Kentfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.4281
252 | 0 | 1930 | 3935 | Roselawn St | W Outer Dr | S Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.9497
253 | 0 | 1940 | 953 | Crusade St | Liberal St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.8559
254 | 0 | 1948 | 1509 | Lappin St | Rex St | Redmond St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.0377
255 | 0 | 1953 | 2090 | Chippewa St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.7037
256 | 0 | 1956 | 3912 | Woodingham Dr | W Outer Dr | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.2585
257 | 0 | 1968 | 4412 | Hasse St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.8285
258 | 0 | 1977 | 1462 | Pinehurst St | Norfolk St | 8 Mile Rd | [6 empty] | 2 | 2020 Carryover | [26 empty] | 356.9654
259 | 0 | 1978 | 2001 | Fenmore St | Hessel Ave | Circle Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 177.2288
262 | 0 | 2014 | 3495 | E Brentwood St | Packard St | Van Dyke St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 366.0179
263 | 0 | 2023 | 2564 | Canterbury Rd | Pembroke Ave & Warrington Dr | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.0645
264 | 0 | 2030 | 4508 | Cambridge Ave | Prairie St | Monica St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.6023
265 | 0 | 2039 | 3901 | Stahelin Ave | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 247.8914
267 | 0 | 2047 | 4019 | Saint Louis St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.5231
268 | 0 | 2052 | 1335 | Sirron St | Terrell St | Kempa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.7197
269 | 0 | 2055 | 3113 | Faircrest St | Rex St | Redmond St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3391
270 | 0 | 2061 | 2431 | Fordham St | Rex St | Redmond St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8719
272 | 0 | 2079 | 2501 | Gilchrist St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.4157
273 | 0 | 2089 | 2034 | Chippewa St | Kentucky St | Indiana St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.6806
274 | 0 | 2091 | 2027 | Hessel Ave | Ashton Ave | Rosemont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.0934
275 | 0 | 2107 | 3055 | Biltmore St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.6083
276 | 0 | 2123 | 2830 | Stahelin Ave | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.772
277 | 0 | 2129 | 2382 | Ward St | Chippewa St | Norfolk St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.6739
278 | 0 | 2139 | 333 | Westphalia St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.5275
279 | 0 | 2142 | 3646 | Lesure St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.4518
280 | 0 | 2147 | 191 | Edmore Dr | Anvil St | Regent Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.9361
282 | 0 | 2157 | 3163 | Trojan St | Greydale Ave | Burgess St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 78.9531
283 | 0 | 2198 | 1014 | E Remington St | Goddard St | Mackay St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.2887
284 | 0 | 2201 | 359 | Bramford St | Savage St | Conner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.6218
285 | 0 | 2205 | 1953 | Chippewa St | Santa Barbara Dr | San Juan Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 180.5337
286 | 0 | 2213 | 903 | Pelkey St | Tacoma St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.6065
288 | 0 | 2226 | 2064 | Chippewa St | Ilene St | Washburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.9063
289 | 0 | 2227 | 1534 | E Lantz St | Kempa St | E Outer Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.482
290 | 0 | 2232 | 4036 | Albion St | Linnhurst St | Eastwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3757
291 | 0 | 2235 | 1018 | Packard St | E Outer Dr | Milbank St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 348.6712
292 | 0 | 2238 | 2554 | Fenmore St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1305
294 | 0 | 2249 | 3332 | Pennington Ave | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.1893
295 | 0 | 2250 | 2888 | Bradford St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.3721
296 | 0 | 2270 | 353 | Fairmount Dr | Brock St | Crusade St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1785
297 | 0 | 2273 | 173 | Boulder St | Bringard Dr | Edmore Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.2132
298 | 0 | 2275 | 72 | Collingham Dr | Hoyt St | Anvil St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2273
299 | 0 | 2283 | 1011 | Spencer St | E Outer Dr | Milbank St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 349.4639
300 | 0 | 2293 | 2058 | Hessel Ave | Faust Ave | Greenview Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.9023
301 | 0 | 2296 | 1504 | Norfolk St | Sorrento St | Steel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.373
302 | 0 | 2297 | 4640 | Whitcomb St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 263.4491
304 | 0 | 2322 | 1094 | Hull St | E Remington Ave | E Winchester Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.2488
305 | 0 | 2323 | 2877 | Mendota St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 294.8431
306 | 0 | 2327 | 491 | Rossini Dr | Reno St | Hoyt St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8965
307 | 0 | 2328 | 1044 | Saint Aubin St | E Remington St | Conant St & Pointer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.8233
308 | 0 | 2331 | 849 | Manning St | Redmond St | Boulder St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.6935
309 | 0 | 2332 | 1028 | E Remington St | Lumpkin St | Fleming St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.6269
310 | 0 | 2341 | 4553 | Carman St | W 7 Mile Rd | Penrose St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 300.3989
311 | 0 | 2347 | 2566 | Hessel Ave | Chapel St | Bentler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.6706
313 | 0 | 2372 | 973 | Pelkey St | Manning St | Tacoma St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.7069
314 | 0 | 2373 | 2472 | Asbury Park | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5266
315 | 0 | 2374 | 4009 | Saint Aubin St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.219
316 | 0 | 2378 | 2313 | Strasburg St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7322
317 | 0 | 2392 | 2424 | Prevost St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0619
319 | 0 | 2403 | 4012 | Whitcomb St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.3305
320 | 0 | 2414 | 3875 | Carman St | Penrose St | Annin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 308.5259
321 | 0 | 2443 | 2436 | McCormick St | Riad St | Kelly Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 246.319
322 | 0 | 2458 | 161 | Pelkey St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.0258
323 | 0 | 2490 | 1353 | Sirron St | Van Dyke St | Terrell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 242.2696
324 | 0 | 2495 | 1461 | Norfolk St | Pinehurst St | Mendota St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.873
325 | 0 | 2498 | 4534 | Cambridge Ave | Pennington Ave | San Juan Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0965
326 | 0 | 2499 | 580 | Packard St | Milbank St | Savage St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.3302
327 | 0 | 2500 | 2401 | Winthrop St | Trojan St | James Couzens Fwy & Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 299.1783
328 | 0 | 2509 | 482 | Hamburg St | Fairmount Dr | Bringard Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.8381
329 | 0 | 2515 | 3195 | Packard St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.6043
330 | 0 | 2516 | 3663 | Payton St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 618.2258
331 | 0 | 2526 | 3131 | Trojan St | Chapel St | Bentler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.7621
332 | 0 | 2531 | 846 | Westphalia St | E State Fair St | Fairmount Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7688
333 | 0 | 2537 | 595 | Tacoma St | Hayes St | Brock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.4832
334 | 0 | 2539 | 441 | Fairmount Dr | Reno St | Hoyt St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8185
335 | 0 | 2551 | 68 | Collingham Dr | Anvil St | Regent Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8029
336 | 0 | 2555 | 1449 | Norfolk St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.2388
337 | 0 | 2575 | 2083 | Stahelin Ave | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 238.8147
339 | 0 | 2588 | 4580 | Cambridge Ave | Roselawn St | Greenlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.8357
341 | 0 | 2603 | 2044 | Redmond St | E 7 Mile Rd & Moross Rd | Maddelein St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.538
342 | 0 | 2606 | 4432 | Payton St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 300.9732
343 | 0 | 2620 | 1340 | San Juan Dr | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.1953
344 | 0 | 2633 | 367 | Dresden St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.5068
345 | 0 | 2653 | 4089 | Beland St | Linnhurst St | Eastwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.1637
347 | 0 | 2682 | 3177 | Saint Martins Ave | Santa Rosa Dr | Stoepel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.6396
348 | 0 | 2693 | 4053 | Orleans St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.2336
349 | 0 | 2697 | 345 | Waltham St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.4209
350 | 0 | 2703 | 4083 | Prevost St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5448
351 | 0 | 2708 | 2339 | Chippewa St | Meyers Rd | Manor St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.3936
352 | 0 | 2738 | 3525 | E Brentwood St | Rogge St | Packard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 192.0766
354 | 0 | 2743 | 2639 | Westphalia St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8532
355 | 0 | 2754 | 2352 | Hessel Ave | Annchester Rd | Huntington Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.801
356 | 0 | 2764 | 2381 | Chippewa St | Ward St | Sorrento St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.1348
357 | 0 | 2770 | 3180 | Saint Aubin St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.9645
358 | 0 | 2773 | 4382 | Tracey St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.7373
360 | 0 | 2793 | 1472 | Norfolk St | Manor St | Monte Vista St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.7258
361 | 0 | 2796 | 3460 | Norfolk St | Winston St | Fenton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.3944
362 | 0 | 2806 | 984 | Alcoy St | Manning St | Tacoma St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.5267
363 | 0 | 2811 | 155 | Cushing St | Bringard Dr | Edmore Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.012
364 | 0 | 2831 | 909 | Stratford Rd | Woodstock Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 146.986
365 | 0 | 2836 | 1439 | Pinewood St | Schoenherr St | Reno St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.6989
366 | 0 | 2838 | 818 | Hickory St | E State Fair St | Fairmount Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.5838
367 | 0 | 2840 | 813 | Pelkey St | E State Fair St | Fairmount Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.511
368 | 0 | 2871 | 351 | Eastburn St | Hoyt St | Anvil St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.5221
369 | 0 | 2883 | 381 | Packard St | Savage St | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.7304
370 | 0 | 2907 | 4136 | Gruebner St | Linnhurst St | Eastwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.1034
371 | 0 | 2909 | 1861 | Norfolk St | Audrey St | Oxley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.2536
373 | 0 | 2919 | 385 | Rossini Dr | Shakespeare St | Cordell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.5828
374 | 0 | 2920 | 1006 | Westphalia St | Manning St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.1574
375 | 0 | 2931 | 4356 | Conley St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.9511
376 | 0 | 2932 | 4481 | Northrop St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.7683
378 | 0 | 2938 | 2413 | Stansbury St | Chippewa St | Norfolk St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 316.4298
380 | 0 | 2943 | 1407 | Charleston St | W Remington Ave | W Winchester Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 287.9563
381 | 0 | 2946 | 2425 | Hessel Ave | Heyden St | Vaughan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.9578
384 | 0 | 2980 | 4573 | Shaftsbury Ave | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.1882
385 | 0 | 2987 | 859 | Woodstock Dr | Queenston St | E M 1 Service Drive | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 340.5801
386 | 0 | 2993 | 3469 | Runyon St | Eastwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7055
388 | 0 | 2995 | 2594 | Hessel Ave | Greydale Ave | Burgess St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 75.5626
390 | 0 | 3013 | 1559 | Dresden St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.2324
391 | 0 | 3024 | 2633 | Fordham St | Chalmers St | Celestine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.8707
392 | 0 | 3025 | 220 | Eastburn St | Cordell St | Shakespeare St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.9719
394 | 0 | 3056 | 2408 | Fordham St | Redmond St | Moross Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 230.7094
395 | 0 | 3064 | 232 | Bringard Dr | Regent Dr | Marbud St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.039
396 | 0 | 3072 | 4499 | Strathmoor St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.7639
397 | 0 | 3073 | 821 | E Winchester Ave | Russell St | Hanna St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.3221
398 | 0 | 3075 | 3081 | Tracey St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.4806
399 | 0 | 3080 | 882 | Coventry St | E Winchester Ave | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.9982
400 | 0 | 3088 | 3387 | Roselawn St | Saint Martins Ave | N Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.4737
401 | 0 | 3110 | 4045 | Fargo St | Fenton St | Woodbine St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.1851
402 | 0 | 3122 | 1567 | Tracey St | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.0861
403 | 0 | 3123 | 2081 | Barlow St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.4466
404 | 0 | 3130 | 3838 | Pembroke Ave | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 113.5924
405 | 0 | 3132 | 2919 | Saratoga St | Redmond St | Kelly Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 171.5253
408 | 0 | 3148 | 372 | Bradford St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.0826
409 | 0 | 3159 | 4075 | Riopelle St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.6847
410 | 0 | 3162 | 2097 | Goddard St | Conant St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.0486
411 | 0 | 3166 | 4613 | Vassar Ave | Sussex St | Coyle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.5042
412 | 0 | 3170 | 3168 | Stotter St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.7506
413 | 0 | 3189 | 2849 | Strasburg St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9646
414 | 0 | 3195 | 4650 | Vassar Ave | Prest St | Whitcomb St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 141.4914
415 | 0 | 3208 | 2606 | McCormick St | Laing St | Riad St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.6675
416 | 0 | 3225 | 3477 | Pinehurst St | Saint Martins Ave | Pembroke Ave | [6 empty] | 1 | 2020 Carryover | [26 empty] | 270.3741
417 | 0 | 3233 | 3894 | Havana St | Penrose St | Annin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 307.626
418 | 0 | 3240 | 2055 | Washburn St | Chippewa St | Norfolk St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.6993
419 | 0 | 3257 | 2945 | Winthrop St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.8375
420 | 0 | 3260 | 916 | Alcoy St | Tacoma St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.3253
421 | 0 | 3262 | 1806 | Lichfield Rd | Bloomfield Rd | Norfolk St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 345.7382
422 | 0 | 3277 | 1565 | Pfent St | Schoenherr St | Reno St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 261.1687
423 | 0 | 3280 | 3499 | Vaughan St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 292.015
424 | 0 | 3303 | 4078 | McIntyre St | Leewin St | Chippewa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.7191
425 | 0 | 3304 | 3473 | Grandview St | Norfolk St | Shiawassee Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.1408
426 | 0 | 3310 | 4093 | Stout St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.1004
428 | 0 | 3313 | 1851 | Lappin St | Queen St | Hayes St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.8749
429 | 0 | 3317 | 461 | Fairmount Dr | Fairport St | Joann St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.8717
430 | 0 | 3319 | 3611 | Hartwell St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.6465
431 | 0 | 3323 | 1915 | Saint Marys St | Hessel Ave | 8 Mile Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 234.572
432 | 0 | 3339 | 1486 | Lappin St | Boulder St | Kelly Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.987
433 | 0 | 3341 | 1490 | Lappin St | Redmond St | Boulder St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2078
434 | 0 | 3349 | 2835 | Griggs St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.9358
435 | 0 | 3353 | 224 | Eastburn St | Boulder St | Cordell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3333
436 | 0 | 3358 | 1809 | Norfolk St | Lauder St | Marlowe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.8267
438 | 0 | 3365 | 2511 | Orleans St | E Lantz St | E State Fair St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.5897
439 | 0 | 3369 | 318 | Hickory St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0086
440 | 0 | 3398 | 4494 | McIntyre St | Pembroke Ave | Leewin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.1092
441 | 0 | 3425 | 199 | Hamburg St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.9256
442 | 0 | 3426 | 1871 | Marx St | E State Fair St | E Remington Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.4953
443 | 0 | 3446 | 1095 | Norfolk St | Warrington Dr | Sheffield Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.2884
444 | 0 | 3461 | 1889 | Prevost St | Hessel Ave | Motor Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 223.5469
445 | 0 | 3467 | 3065 | Gilchrist St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1247
446 | 0 | 3494 | 3464 | Winthrop St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.344
447 | 0 | 3495 | 3097 | Lesure St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.3737
451 | 0 | 3508 | 875 | Woodstock Dr | Durham St | Queenston St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.8218
452 | 0 | 3510 | 2808 | Waltham St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9952
453 | 0 | 3516 | 2823 | Barlow St | E 7 Mile Rd | Lappin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0797
454 | 0 | 3518 | 3621 | Bauman St | Wildwood St | Bryson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.0998
455 | 0 | 3522 | 1004 | Stotter St | E Outer Dr | Milbank St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 351.4415
456 | 0 | 3535 | 2018 | Chippewa St | Wisconsin St | Ohio St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.0645
457 | 0 | 3540 | 2859 | Ilene St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.0052
458 | 0 | 3551 | 194 | Barlow St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 252.0459
459 | 0 | 3557 | 3841 | Woodbine St | Chippewa St | Norfolk St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 113.0445
460 | 0 | 3560 | 4096 | Greeley St | E 7 Mile Rd | Emery St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.9414
461 | 0 | 3563 | 167 | Cordell St | Bringard Dr | Edmore Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.3982
462 | 0 | 3568 | 4648 | Saint Louis St | E Hildale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.6912
463 | 0 | 3575 | 178 | Fairport St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.4127
464 | 0 | 3592 | 2451 | Goddard St | E Lantz St | Conant St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 141.3885
465 | 0 | 3597 | 2515 | Hessel Ave | Blackstone Ct & Blackstone St | Trinity St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.6474
466 | 0 | 3605 | 2611 | Eastwood St | Rex St | Redmond St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.1668
467 | 0 | 3619 | 2041 | Westphalia St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8829
468 | 0 | 3622 | 2958 | House St | Van Dyke St | Terrell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 242.1724
469 | 0 | 3625 | 1960 | Pelkey St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.5558
470 | 0 | 3630 | 2972 | Trojan St | Heyden St | Vaughan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0002
471 | 0 | 3644 | 3027 | Asbury Park | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.4279
472 | 0 | 3653 | 3845 | Joann St | Linnhurst St | Eastwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.4122
473 | 0 | 3655 | 1895 | Hessel Ave | Rutherford St | Prevost St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.8077
474 | 0 | 3657 | 2377 | Hessel Ave | Plainview Ave | Westmoreland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0494
475 | 0 | 3673 | 1892 | Greeley St | E State Fair St | E Remington Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.9425
476 | 0 | 3683 | 1952 | Biltmore St | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 236.6122
477 | 0 | 3686 | 4667 | Vaughan St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1869
478 | 0 | 3690 | 4348 | Hartwell St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 254.0802
479 | 0 | 3699 | 2336 | Bradford St | Lappin St | Pinewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0621
480 | 0 | 3714 | 4357 | Pembroke Ave | Blackstone St | Trinity St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.0645
481 | 0 | 3715 | 1865 | Wakefield St | Canterbury Rd | Warrington Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 349.3034
483 | 0 | 3718 | 4564 | Cambridge Ave | Woodingham Dr | Santa Barbara Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3734
485 | 0 | 3723 | 475 | Rossini Dr | Anvil St | Regent Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.3279
487 | 0 | 3764 | 388 | Rogge St | Savage St | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.4179
488 | 0 | 3771 | 4002 | Duchess St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.6159
489 | 0 | 3796 | 2912 | Kentucky St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.1557
490 | 0 | 3804 | 2955 | Vaughan St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.0075
491 | 0 | 3805 | 863 | Waltham St | E State Fair St | Fairmount Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8426
493 | 0 | 3808 | 1949 | Maddelein St | Brock St | Crusade St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.9916
494 | 0 | 3829 | 3120 | Canterbury Rd | Saint Martins Ave | Pembroke Ave & Warrington Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.3949
495 | 0 | 3836 | 361 | Strasburg St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.1414
496 | 0 | 3846 | 4476 | Mark Twain St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.8066
497 | 0 | 3850 | 1528 | Lappin St | Crusade St | Rex St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.9892
498 | 0 | 3852 | 216 | Eastburn St | Shakespeare St | Cushing St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2498
499 | 0 | 3860 | 873 | Manning St | Crusade St | Rex St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.9899
501 | 0 | 3864 | 1306 | Russell St | E Remington Ave | E Winchester Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.0082
502 | 0 | 3865 | 4048 | Vaughan St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 247.1279
503 | 0 | 3882 | 1923 | Murray Hill St | Hessel Ave | 8 Mile Rd & 8 Mile Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.8576
504 | 0 | 3885 | 170 | Alcoy St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.4525
505 | 0 | 3887 | 3501 | Beland St | Eastwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.086
507 | 0 | 3894 | 2514 | Lindsay St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2931
508 | 0 | 3903 | 4611 | Cambridge Ave | Wisconsin St | Ohio St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.7224
510 | 0 | 3924 | 4098 | Laing St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.6322
511 | 0 | 3939 | 1972 | Lindsay St | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 236.4682
512 | 0 | 3946 | 1030 | Lichfield Rd | Norfolk St | Woodstock Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 213.0022
513 | 0 | 3954 | 1469 | Monte Vista St | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.672
515 | 0 | 3982 | 2466 | Havana St | Adeline St | W State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.3961
516 | 0 | 3983 | 1564 | Stotter St | E Lantz St | E Outer Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 340.7359
517 | 0 | 3986 | 574 | Crusade St | Tacoma St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.7835
519 | 0 | 3997 | 4618 | McCormick St | Duprey St | Peerless St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0076
520 | 0 | 4001 | 450 | Hickory St | Fairmount Dr | Bringard Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.5172
521 | 0 | 4014 | 2308 | Mendota St | Chippewa St | Norfolk St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.4123
522 | 0 | 4018 | 467 | Westphalia St | Fairmount Dr | Bringard Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7833
523 | 0 | 4024 | 885 | Strasburg St | E State Fair St | Fairmount Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9959
524 | 0 | 4026 | 2525 | Riopelle St | E Lantz St | E State Fair St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.3347
525 | 0 | 4039 | 3130 | Annin St | Carman St | Blake St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 108.9078
526 | 0 | 4045 | 4598 | Cherrylawn St | Cambridge Ave | N Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 101.5614
527 | 0 | 4061 | 408 | Fairmount Dr | Marbud St | Gratiot Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 199.1402
528 | 0 | 4065 | 1438 | Picadilly Rd | Canterbury Rd | Norfolk St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 186.1499
529 | 0 | 4066 | 3528 | Algonac St | Eastwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.4459
530 | 0 | 4079 | 1875 | Concord St | E Lantz St | E Outer Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.1812
531 | 0 | 4080 | 4533 | Riad St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.7185
532 | 0 | 4096 | 4329 | Moenart St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.0072
533 | 0 | 4098 | 4373 | Fenelon St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.0441
534 | 0 | 4105 | 2880 | E Lantz St | Coventry St | Keating St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.92
535 | 0 | 4111 | 190 | Waltham St | Collingham Dr | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 252.2285
536 | 0 | 4118 | 568 | Milbank St | Spencer St | Stotter St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.9941
537 | 0 | 4131 | 2527 | Oakfield St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2499
538 | 0 | 4132 | 3555 | Murray Hill St | Pembroke Ave | Trojan St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 546.1577
539 | 0 | 4135 | 4125 | Saint Marys St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.8691
541 | 0 | 4141 | 3644 | Fenmore St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.883
543 | 0 | 4151 | 4436 | Ardmore St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.7593
544 | 0 | 4156 | 1448 | Pelkey St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 307.9897
546 | 0 | 4185 | 2821 | E Lantz St | Yacama Rd | Omira St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 113.5468
547 | 0 | 4190 | 3537 | Saint Marys St | Pembroke Ave | Trojan St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.5608
548 | 0 | 4196 | 4467 | Bauman St | Larchwood St | Balmoral Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 104.6529
549 | 0 | 4199 | 1980 | Oakfield St | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 236.5006
550 | 0 | 4212 | 569 | Spencer St | Milbank St | Savage St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.3335
551 | 0 | 4223 | 1808 | Bradford St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.9162
552 | 0 | 4227 | 2966 | Saratoga St | Morang Dr | Rex St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.1553
553 | 0 | 4258 | 596 | E Winchester Ave | Riopelle St | Orleans St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.4743
554 | 0 | 4279 | 2941 | Saratoga St | Rex St | Redmond St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3058
555 | 0 | 4282 | 3435 | Cameron St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.9322
556 | 0 | 4283 | 307 | Cushing St | Fairmount Dr | Eastburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.5387
557 | 0 | 4290 | 446 | Pelkey St | Fairmount Dr | Bringard Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1835
558 | 0 | 4293 | 2635 | Cameron St | E Lantz St | E State Fair St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.459
560 | 0 | 4305 | 4102 | Saint Martins Ave | Rutherford St | Prevost St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.5902
561 | 0 | 4306 | 4026 | Prest St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.4874
562 | 0 | 4307 | 440 | Rossini Dr | Brock St | Hayes St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.4221
563 | 0 | 4311 | 3063 | Pembroke Ave | Schaefer Hwy | Hartwell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.4736
564 | 0 | 4313 | 1932 | Asbury Park | Hessel Ave | 8 Mile | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.3151
565 | 0 | 4323 | 378 | Fairmount Dr | Queen St | Hayes St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 345.5342
566 | 0 | 4328 | 370 | Stotter St | Savage St | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 310.8177
567 | 0 | 4354 | 2645 | Eastwood St | Morang Dr | Rex St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.3086
569 | 0 | 4361 | 1087 | Greeley St | E Remington Ave | E Winchester Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.0306
570 | 0 | 4367 | 2846 | Washburn St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 308.1962
571 | 0 | 4371 | 3444 | Linnhurst St | Rex St | Kelly Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 291.5399
574 | 0 | 4396 | 3923 | Riad St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.7614
575 | 0 | 4397 | 3363 | Greeley St | Emery St | E Lantz St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 356.0851
576 | 0 | 4401 | 815 | Hull St | E Winchester Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.6446
577 | 0 | 4404 | 3044 | Trojan St | Burt Rd | Pierson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.259
578 | 0 | 4407 | 3468 | Eastwood St | Runyon St | Albion St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.4006
579 | 0 | 4416 | 2975 | Monte Vista St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.9382
580 | 0 | 4418 | 1342 | Beland St | Manning St | E State Fair St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.4679
581 | 0 | 4427 | 3825 | Monica St | W Outer Dr | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.5409
582 | 0 | 4429 | 2960 | Forrer St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.4669
583 | 0 | 4432 | 888 | Woodstock Dr | Lichfield Rd | Durham St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.3432
584 | 0 | 4434 | 1538 | Hamburg St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.1514
585 | 0 | 4456 | 588 | Marx St | E Winchester Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 314.3426
586 | 0 | 4461 | 2458 | Fleming St | E Lantz St | E Outer Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.3519
588 | 0 | 4464 | 3176 | Greydale Ave | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8345
589 | 0 | 4468 | 2315 | Pinehurst St | Chippewa St | Norfolk St | [6 empty] | 2 | 2020 Carryover | [26 empty] | 353.3845
590 | 0 | 4479 | 2452 | Hessel Ave | Stout St | Kentfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.0985
591 | 0 | 4480 | 3458 | Albion St | Eastwood St | E 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3502
592 | 0 | 4488 | 1430 | Washburn St | Norfolk St | 8 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.2378
593 | 0 | 4492 | 3856 | Charleston St | Penrose St | Annin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 310.9864
594 | 0 | 4497 | 4567 | Saint Martins Ave | Shaftsbury Ave | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 104.4976
595 | 0 | 4502 | 501 | Rowe St | Fairmount Dr | Bringard Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.2287
596 | 0 | 4522 | 562 | Stotter St | Milbank St | Savage St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.5584
597 | 0 | 4535 | 1964 | Gilchrist St | Hessel Ave | 8 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 236.4396
598 | 0 | 4549 | 3631 | Tracey St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.4472
599 | 0 | 4558 | 3559 | Eastwood St | Blackmoor St | Gruebner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3494
600 | 0 | 4565 | 4509 | Prairie St | Cambridge Ave | W Outer Dr | [6 empty] | 1 | 2020 Carryover | [26 empty] | 260.6656
601 | 0 | 4571 | 60 | Collingham Dr | Marbud St | Mohican St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 292.9598
602 | 0 | 4581 | 3527 | Eastwood St | Algonac St | Beland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.8737
603 | 0 | 4589 | 2936 | Lansdowne St | McCormick St | Lansdowne Ave & Kingsville Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.0426
604 | 0 | 4597 | 915 | Tacoma St | Alcoy St | Hickory St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.347
605 | 0 | 4598 | 4103 | Rutherford St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7178
606 | 0 | 4601 | 2858 | Pembroke Ave | Ilene St | Washburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.5578
607 | 0 | 4610 | 3141 | Ardmore St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 378.0878
608 | 0 | 4611 | 484 | Rossini Dr | Hoyt St | Anvil St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.4641
609 | 0 | 4625 | 3026 | Ward St | Pembroke Ave | Chippewa St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 337.0322
610 | 0 | 4629 | 1984 | Chippewa St | Roselawn St | Greenlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.248
611 | 0 | 4630 | 348 | Barlow St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.1931
612 | 0 | 4649 | 4584 | Vassar Ave | Robson St | Lauder St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.9751
613 | 0 | 4667 | 2580 | Eastwood St | Redmond St | Kelly Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 245.5729
614 | 0 | 4671 | 1927 | Maddelein St | Crusade St | Rex St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.8715
615 | 0 | 4676 | 2380 | Beland St | Lappin St | Sturgis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.1257
616 | 0 | 4681 | 34 | Carlisle St | Regent Dr | Marbud St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.2261
618 | 0 | 4688 | 4469 | Houghton St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.458
619 | 0 | 4689 | 390 | Savage St | Carrie St | Rogge St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.4449
621 | 0 | 4697 | 3122 | Fenmore St | Fargo St | Trojan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7727
622 | 0 | 4701 | 2971 | Havana St | W Lantz St | Fernhill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.3188
624 | 0 | 4705 | 2481 | Ferguson St | Trojan St | Hessel Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8125
625 | 0 | 4716 | 2467 | Fordham St | Brock St | Morang Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 173.1592
626 | 0 | 4728 | 323 | Alcoy St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1343
627 | 0 | 4740 | 314 | Pelkey St | Bringard Dr | Collingham Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8657
628 | 0 | 4746 | 4654 | Ilene St | Cambridge Ave | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2557
629 | 0 | 4760 | 1550 | Strasburg St | Pinewood St | Manning St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.4806
630 | 0 | 4782 | 7555 | Somerset Ave | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.1894
631 | 0 | 4786 | 6394 | Strathmoor St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1714
632 | 0 | 4799 | 5894 | Northlawn St | Clarita St | Wendel V Hall Blvd & W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.7823
633 | 0 | 4812 | 6324 | Duprey St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.0281
634 | 0 | 4818 | 8912 | Santa Clara St | Prairie St | Monica St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.4423
635 | 0 | 4820 | 5480 | Sorrento St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.0691
636 | 0 | 4832 | 7911 | Lansdowne St | Whittier St | Yorkshire Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.6414
637 | 0 | 4841 | 5913 | Dresden St | Gietzen St | Greiner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.9481
638 | 0 | 4843 | 5319 | Shaftsbury Ave | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.609
639 | 0 | 4844 | 8584 | Beaconsfield St | Whittier St | Yorkshire Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 320.5714
640 | 0 | 4847 | 6350 | Canyon Ave | Rockcastle St | Alstead St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 113.7933
641 | 0 | 4851 | 8090 | Avon Ave | Margareta St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 294.3473
642 | 0 | 4852 | 6444 | Margareta St | Roselawn St | Greenlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.8123
643 | 0 | 4856 | 8919 | Nashville St | Gunston St | Bradford St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 400.255
644 | 0 | 4867 | 7520 | Fielding St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.7756
645 | 0 | 4872 | 7856 | Canyon Ave | Linville St | Lannoo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 151.0031
646 | 0 | 4875 | 6091 | Lindsay St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5708
647 | 0 | 4885 | 6610 | Yorkshire Rd | Riad St | Payton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.9679
648 | 0 | 4887 | 9071 | Neff Ave | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.5678
649 | 0 | 4905 | 5368 | Whitcomb St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.0152
650 | 0 | 4906 | 6916 | Rossiter St | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.8989
651 | 0 | 4927 | 5927 | Nottingham Rd | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.2716
652 | 0 | 4956 | 7931 | San Juan Dr | London Ave | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.6297
653 | 0 | 4966 | 5820 | Prairie St | Clarita St | W 7 Mile Rd | [6 empty] | 1 | 2020 Carryover | [26 empty] | 267.6797
654 | 0 | 4970 | 7104 | Charest St | Minnesota St | E Nevada St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.6221
655 | 0 | 4978 | 8629 | Covington Dr | Manderson Rd | 3rd St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 600.2156
656 | 0 | 4985 | 8670 | Glenfield Ave | Newport St | Chalmers St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 332.8403
657 | 0 | 5027 | 8571 | Mogul St | Duchess St | Lannette St & Hayes St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.6127
658 | 0 | 5030 | 5634 | Whitehill St | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.189
659 | 0 | 5036 | 9332 | Woodhall St | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7354
660 | 0 | 5039 | 7366 | Saint Marys St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.9166
661 | 0 | 5040 | 9026 | Coyle St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7201
662 | 0 | 5046 | 6548 | Buhr St | Carrie St | Cliff St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 249.0075
663 | 0 | 5054 | 7823 | Wisconsin St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.4071
664 | 0 | 5064 | 8091 | Somerset Ave | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.1741
665 | 0 | 5083 | 5078 | Hickory St | Greiner St | Park Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.125
666 | 0 | 5090 | 7081 | Prest St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7301
667 | 0 | 5092 | 6843 | Margareta St | Littlefield St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.1686
668 | 0 | 5101 | 5357 | Annchester Rd | Vassar Ave | Pembroke Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 542.8414
669 | 0 | 5102 | 7871 | Ilene St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.1288
670 | 0 | 5108 | 8610 | Manderson Rd | Whitmore Rd | Covington Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 314.3846
671 | 0 | 5110 | 9146 | Beaconsfield St | Courville St | Whittier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.6359
672 | 0 | 5112 | 9021 | Curtis St | Huntington Rd | Grandville Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.4627
673 | 0 | 5133 | 6039 | Young St | Hayes St | Brock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.204
674 | 0 | 5136 | 5511 | Trinity St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7753
675 | 0 | 5161 | 8424 | Coyle St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.1216
676 | 0 | 5163 | 7630 | Ohio St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.8757
677 | 0 | 5179 | 5330 | Troester St | Brock St | Salter St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.9262
678 | 0 | 5195 | 6613 | Steel St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.4863
679 | 0 | 5213 | 5184 | Woodingham Dr | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.9084
680 | 0 | 5215 | 7364 | Glenhurst St | Kress/Glenhurst Cutoff & Grayfield St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.7192
681 | 0 | 5230 | 9357 | Moran St | Victoria St | E McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 195.1357
682 | 0 | 5242 | 4868 | Laing St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.9573
683 | 0 | 5249 | 7969 | Woodbine St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 350.9421
684 | 0 | 5253 | 7890 | Bradford St | Kenmoor St | Kennebec St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.0538
685 | 0 | 5256 | 7320 | Pinehurst St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.2867
686 | 0 | 5259 | 4828 | Grandview St | Pembroke Ave | Fargo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.7688
687 | 0 | 5262 | 6504 | Gable St | Iowa St | E Nevada St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 235.66
688 | 0 | 5264 | 6917 | Grayton St | Rossiter St | Wayburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.7101
689 | 0 | 5271 | 7584 | Laing St | Whittier St | Yorkshire Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.5185
690 | 0 | 5285 | 7507 | Margareta St | Fenmore St | Archdale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 112.6527
691 | 0 | 5288 | 8116 | Ardmore St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.704
692 | 0 | 5306 | 8118 | Rossiter St | Whittier St | Yorkshire Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.527
693 | 0 | 5308 | 5515 | Cedargrove St | Hayes St | Brock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.04
694 | 0 | 5313 | 6596 | Fielding St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0972
695 | 0 | 5317 | 6969 | Strathmoor St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.4535
696 | 0 | 5323 | 6607 | Saint Marys St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.2007
697 | 0 | 5336 | 8434 | Kentucky St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9394
698 | 0 | 5337 | 5628 | McKinney Ave | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 616.7591
699 | 0 | 5343 | 6993 | Strasburg St | E McNichols Rd | Sauer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 343.3121
700 | 0 | 5355 | 6082 | Balfour Rd | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.074
701 | 0 | 5356 | 8421 | Pickford St | Heyden St | Vaughan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 105.3991
702 | 0 | 5366 | 8464 | Lodewyck St | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.9417
703 | 0 | 5371 | 6443 | Lauder St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3818
704 | 0 | 5379 | 7627 | Grayton St | Balfour Rd | Somerset Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 146.1342
705 | 0 | 5391 | 8348 | Santa Barbara Dr | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8236
706 | 0 | 5397 | 8847 | Fenmore St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.253
707 | 0 | 5398 | 5388 | Winthrop St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.3904
708 | 0 | 5402 | 5167 | Beaconsfield St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.5789
709 | 0 | 5416 | 5862 | Hazelridge St | Hayes St | Brock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1792
710 | 0 | 5420 | 5323 | McCormick St | S Harper Ave | Sanilac St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.0956
711 | 0 | 5427 | 5366 | Westmoreland Rd | Vassar Ave | Pembroke Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 542.4203
712 | 0 | 5435 | 8062 | Faust Ave | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 292.5759
713 | 0 | 5436 | 8494 | Birwood St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.6649
714 | 0 | 5445 | 7844 | Kentucky St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.8522
715 | 0 | 5450 | 6867 | Lindsay St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.3285
716 | 0 | 5472 | 7547 | Margareta St | Grandville Ave | Shaftsbury Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.9283
717 | 0 | 5475 | 6947 | Beaverland St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.519
718 | 0 | 5481 | 5000 | Healy St | E Hildale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.7513
719 | 0 | 5491 | 6575 | Monte Vista St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8855
720 | 0 | 5496 | 5345 | Troester St | Hayes St | Brock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3257
721 | 0 | 5506 | 7512 | Margareta St | Sunderland Rd | Stahelin Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.0572
722 | 0 | 5511 | 9366 | Sorrento St | Santa Clara St | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.3465
723 | 0 | 5520 | 5444 | Fielding St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.8801
724 | 0 | 5532 | 8938 | Avon Ave | Pickford St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 323.2978
725 | 0 | 5534 | 5431 | Troester St | Peoria St | Chalmers St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 229.7436
726 | 0 | 5535 | 5489 | Pierson St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.0463
727 | 0 | 5551 | 7616 | Lauder St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0984
728 | 0 | 5561 | 5939 | Kentucky St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.22
729 | 0 | 5565 | 7110 | Lansdowne St | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.8931
730 | 0 | 5568 | 5164 | Pennington Ave | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.4774
731 | 0 | 5592 | 6431 | Worden St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.2049
732 | 0 | 5593 | 6539 | Ilene St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7976
733 | 0 | 5598 | 6895 | Harlow St | Clarita St | W 7 Mile Rd | [6 empty] | 1 | 2020 Carryover | [26 empty] | 274.8035
734 | 0 | 5612 | 7875 | Prest St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.1109
735 | 0 | 5621 | 4920 | Sorrento St | Cambridge Ave | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 254.8253
736 | 0 | 5635 | 5953 | Annchester Rd | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.6544
737 | 0 | 5637 | 7626 | Balfour Rd | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.9874
738 | 0 | 5654 | 7621 | Hillcrest St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 294.313
739 | 0 | 5663 | 4881 | Park Grove St | Algonac St | Beland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 128.0565
740 | 0 | 5664 | 8523 | Pinehurst St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.4281
741 | 0 | 5673 | 8621 | Ferguson St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3963
742 | 0 | 5687 | 8877 | Bishop St | W I 94 Service Drive | King Richard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.6506
743 | 0 | 5691 | 4842 | Pinehurst St | Cambridge Ave | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.7627
744 | 0 | 5698 | 9340 | Mansfield St | Thatcher St | Curtis St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 286.2665
745 | 0 | 5699 | 4846 | Prevost St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.8166
746 | 0 | 5705 | 8074 | Lesure St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.5354
747 | 0 | 5714 | 5919 | Huntington Rd | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.3651
748 | 0 | 5733 | 7417 | Margareta St | Biltmore St | Ferguson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.2603
749 | 0 | 5736 | 6071 | Trinity St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.5577
750 | 0 | 5741 | 7465 | Shiawassee Dr | Kress St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 171.3862
751 | 0 | 5767 | 6468 | Cherrylawn St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.8445
752 | 0 | 5769 | 6467 | Margareta St | Cherrylawn St | Northlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.8195
753 | 0 | 5806 | 7462 | Vaughan St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.3989
754 | 0 | 5813 | 6044 | Sorrento St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.9573
755 | 0 | 5818 | 5171 | Sunderland Rd | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.3559
756 | 0 | 5830 | 9132 | Whitehill St | Haverhill St | Mogul St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.1725
757 | 0 | 5835 | 6095 | Riverview St | Vassar Ave | Verdun St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 248.1114
758 | 0 | 5837 | 9351 | Steel St | Santa Clara St | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.8247
759 | 0 | 5841 | 5382 | Albion St | Greiner St | Park Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5593
760 | 0 | 5847 | 7532 | Curtis St | Livernois Ave | Warrington Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.974
761 | 0 | 5849 | 9487 | Quincy St | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 295.8043
762 | 0 | 5853 | 6556 | McKinney Ave | Meuse St | Morang Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.5838
763 | 0 | 5866 | 6856 | Gilchrist St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.6455
764 | 0 | 5875 | 7034 | McKinney Ave | Britain St | Merlin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.209
765 | 0 | 5878 | 7531 | Patton St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.6332
766 | 0 | 5898 | 7031 | Ohio St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.699
767 | 0 | 5901 | 6533 | Plainview Ave | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.3007
768 | 0 | 5907 | 7610 | Glenhurst St | Clarita St | Kress St & Glenhurst/Grayfield Cutoff | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 102.0577
769 | 0 | 5925 | 5358 | Kentucky St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.953
770 | 0 | 5927 | 8493 | Thatcher St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.2533
771 | 0 | 5930 | 5908 | Coyle St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.3959
772 | 0 | 5943 | 5616 | Dean St | Stockton St | E Hildale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.1681
773 | 0 | 5950 | 8921 | Faust Ave | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 321.7946
774 | 0 | 5969 | 8083 | Engleside St | Bradford St | Dresden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 248.7619
775 | 0 | 5973 | 7617 | Northlawn St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.5457
776 | 0 | 5975 | 9066 | Curtis St | Plainview Ave | Westmoreland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.0998
777 | 0 | 5976 | 5074 | Frisbee St | Lenore Ave | Woodbine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.4185
778 | 0 | 5983 | 7428 | Plainview Ave | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.2955
779 | 0 | 5990 | 8079 | Greenview Ave | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 293.9179
780 | 0 | 5991 | 8456 | Washburn St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.665
781 | 0 | 5992 | 6009 | Somerset Ave | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.5895
782 | 0 | 5998 | 7548 | Grandville Ave | Margareta St | W 7 Mile Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 474.704
783 | 0 | 6006 | 7859 | Whitcomb St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.1038
784 | 0 | 6008 | 9076 | Prest St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.6397
785 | 0 | 6016 | 6874 | Canyon Ave | Moon St | Chester St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 206.6083
786 | 0 | 6019 | 6552 | Canyon Ave | Chester St | Edgefield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 185.0818
787 | 0 | 6032 | 8609 | Asbury Park | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8653
788 | 0 | 6041 | 9428 | Nottingham Rd | Courville St | Whittier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.6764
789 | 0 | 6061 | 6114 | Tracey St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.2504
790 | 0 | 6064 | 8828 | Nottingham Rd | Whittier St | Yorkshire Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.3055
791 | 0 | 6074 | 6882 | Somerset Ave | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 379.6251
792 | 0 | 6089 | 6022 | Saint Marys St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2774
793 | 0 | 6090 | 7483 | Margareta St | Harlow St | Oakfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.9378
794 | 0 | 6099 | 5588 | Greydale Ave | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7417
795 | 0 | 6108 | 8096 | Stansbury St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.0869
796 | 0 | 6144 | 6927 | Cooley St | W 7 Mile Rd | Vassar Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.9838
797 | 0 | 6147 | 5494 | Troester St | Gratiot Ave | Grover St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 412.3652
798 | 0 | 6148 | 5335 | Strasburg St | Greiner St | Park Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.193
799 | 0 | 6149 | 8387 | Lauder St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9334
800 | 0 | 6156 | 5559 | Chapel St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7517
801 | 0 | 6157 | 8990 | Curtis St | Shaftsbury Ave | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.5926
802 | 0 | 6160 | 8032 | Pickford St | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 127.4832
804 | 0 | 6172 | 8522 | Thatcher St | Pinehurst St | Mendota St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.6494
805 | 0 | 6185 | 9433 | Lesure St | W Outer Dr | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.037
806 | 0 | 6190 | 7860 | Washburn St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.381
807 | 0 | 6194 | 8821 | University Pl | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.3765
808 | 0 | 6197 | 8634 | Littlefield St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.692
809 | 0 | 6203 | 8451 | Nashville St | Bradford St | Devon St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 233.6812
810 | 0 | 6215 | 8447 | Woodbine St | Grand River Ave | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 192.5819
811 | 0 | 6239 | 7846 | Sussex St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0648
812 | 0 | 6253 | 5856 | Sunderland Rd | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.3885
813 | 0 | 6255 | 8410 | Ohio St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3223
814 | 0 | 6262 | 8842 | Lesure St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8401
815 | 0 | 6275 | 7331 | Monte Vista St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.6805
816 | 0 | 6294 | 6932 | Stoepel St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5551
817 | 0 | 6300 | 7554 | Freeland St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.088
818 | 0 | 6303 | 9341 | University Pl | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.1183
819 | 0 | 6327 | 6360 | Stoepel St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3725
820 | 0 | 6335 | 5900 | Stockton St | Norwood St | Wexford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.8167
821 | 0 | 6357 | 6933 | Houghton St | W 7 Mile Rd | Vassar Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.7138
822 | 0 | 6360 | 6561 | Grayton St | Lansdowne St | Whitehill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.408
823 | 0 | 6362 | 5865 | Warwick St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 280.1599
824 | 0 | 6365 | 6470 | Rowe St | Clough St | Gietzen St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.9911
825 | 0 | 6366 | 8999 | Lodewyck St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.7765
826 | 0 | 6382 | 7989 | Kennebec St | Gunston St | Bradford St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 399.95
827 | 0 | 6386 | 8396 | Hereford St | Berden St | Minerva St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.9976
828 | 0 | 6394 | 4993 | Marx St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.6026
829 | 0 | 6395 | 5973 | Winthrop St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.4515
831 | 0 | 6421 | 8452 | Bradford St | Nashville St | Engleside St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.6095
832 | 0 | 6423 | 5089 | Cooley St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7263
833 | 0 | 6424 | 6558 | Birwood St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0829
834 | 0 | 6430 | 8953 | Mogul St | Whitehill St | Duchess St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.7371
835 | 0 | 6440 | 7457 | Margareta St | Faust Ave | Glastonbury Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.4945
836 | 0 | 6446 | 8974 | Warwick St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 321.8707
837 | 0 | 6469 | 8969 | Bluehill St | Berden St | Harper Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 393.6461
838 | 0 | 6476 | 8061 | Pickford St | Faust Ave | Glastonbury Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 147.2758
839 | 0 | 6480 | 8596 | Murray Hill St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.6735
841 | 0 | 6482 | 5349 | Edinborough Rd | Vassar Ave | Pembroke Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 542.6739
842 | 0 | 6506 | 5977 | Albion St | Gietzen St | Greiner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.5952
843 | 0 | 6530 | 6880 | Pickford St | Warrington Dr | Oak Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.9605
844 | 0 | 6552 | 8084 | Bradford St | Engleside St | Kenmoor St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.4149
845 | 0 | 6559 | 6577 | Buhr St | Sherwood St | Carrie St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 386.2117
846 | 0 | 6565 | 8942 | Santa Clara St | Woodingham Dr | Santa Barbara Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3729
847 | 0 | 6566 | 8120 | Pickford St | Sunderland Rd | Stahelin Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.0802
848 | 0 | 6570 | 9061 | Covington Dr | 2nd Blvd | Woodward Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 418.2986
849 | 0 | 6573 | 8564 | Engleside St | Gunston St | Bradford St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 400.0914
850 | 0 | 6580 | 6904 | Clarita St | Archdale St | Harlow St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.4096
852 | 0 | 6592 | 8918 | Farmbrook St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.9362
853 | 0 | 6595 | 6525 | Washburn St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.4863
854 | 0 | 6600 | 7376 | Riad St | Whittier St | Yorkshire Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.1854
855 | 0 | 6602 | 7975 | Sorrento St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.5443
856 | 0 | 6618 | 6483 | Margareta St | Wisconsin St | Ohio St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.2233
857 | 0 | 6641 | 7083 | Gable St | E Davison St | Iowa St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 291.9755
858 | 0 | 6643 | 8600 | Sorrento St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.6687
859 | 0 | 6646 | 7622 | Cherrylawn St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.7953
860 | 0 | 6656 | 5372 | Washburn St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.434
861 | 0 | 6667 | 4921 | Park Grove St | Blackmoor St | Gruebner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.2194
862 | 0 | 6691 | 6424 | Margareta St | Woodingham Dr | Santa Barbara Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.2109
864 | 0 | 6703 | 6388 | Greenview Ave | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.3124
865 | 0 | 6719 | 8055 | Curtis St | Tracey St | Schaefer Hwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.2284
866 | 0 | 6740 | 9087 | Pickford St | Fenton St | Lenore Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.6357
867 | 0 | 6743 | 6618 | Murray Hill St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.4815
868 | 0 | 6767 | 8448 | Pickford St | Stout St | Kentfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.455
869 | 0 | 6771 | 9510 | Cooley St | Curtis St | Karl St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.6273
870 | 0 | 6776 | 6535 | Teppert St | Clough St | Gietzen St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.7835
871 | 0 | 6806 | 8498 | Gable St | E McNichols Rd | Brimson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 382.8962
872 | 0 | 6807 | 8659 | Portlance St | Canonbury St | Algonac St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.2588
873 | 0 | 6809 | 8896 | Cooley St | Pickford St | Roxford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.4086
874 | 0 | 6812 | 7956 | Mansfield St | Pickford St | Margareta St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 277.952
875 | 0 | 6817 | 8483 | King Richard St | Bishop St | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.5973
876 | 0 | 6832 | 7452 | Britain St | King Richard St | McKinney Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 304.0561
877 | 0 | 6838 | 5328 | Vassar Ave | Grandville Ave | Shaftsbury Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.9059
878 | 0 | 6842 | 7040 | Runyon St | Sauer St | Clough St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 249.6114
879 | 0 | 6844 | 6017 | Fielding St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.0552
880 | 0 | 6848 | 5570 | Mackay St | E Grixdale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 331.057
881 | 0 | 6868 | 6942 | Alma St | Queen St | Hayes St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8439
882 | 0 | 6894 | 5946 | Whitcomb St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.6799
883 | 0 | 6898 | 7585 | McKinney Ave | Boleyn St | Harvard Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.3715
884 | 0 | 6906 | 6414 | Lanark St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 616.2274
885 | 0 | 6948 | 9044 | Curtis St | Annchester Rd | Edinborough Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.0548
886 | 0 | 6949 | 9097 | Santa Clara St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.3089
887 | 0 | 6957 | 5525 | Cedargrove St | Brock St | Kelly Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 318.5876
888 | 0 | 6959 | 8843 | Covington Dr | 3rd St | 2nd Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 381.8069
889 | 0 | 6971 | 9426 | Rosemary Ave | Newport St | Chalmers St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.5231
890 | 0 | 6975 | 5180 | Warwick St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.6509
891 | 0 | 7010 | 4941 | Cambridge Ave | W Outer Dr | Sorrento St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 166.0737
892 | 0 | 7022 | 9471 | Oak Dr | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 294.3697
893 | 0 | 7026 | 5985 | Mendota St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.2438
894 | 0 | 7027 | 4844 | Albany St | E Hildale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.6087
895 | 0 | 7028 | 8484 | Bishop St | King Richard St | McKinney Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.2872
896 | 0 | 7034 | 8853 | Canyon Ave | Southampton St | Ashley Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 151.6314
897 | 0 | 7038 | 8124 | Portlance St | Elmo St | E McNichols Rd & Hoover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.9432
898 | 0 | 7050 | 5935 | Edinborough Rd | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.2632
899 | 0 | 7053 | 6454 | Whitehill St | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.6326
900 | 0 | 7077 | 8005 | Hillcrest St | Frankfort Ave | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.1229
901 | 0 | 7084 | 6850 | Trinity St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3618
902 | 0 | 7086 | 8608 | Curtis St | Asbury Park | Murray Hill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.9001
903 | 0 | 7096 | 4970 | Fenelon St | E Hildale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.6776
904 | 0 | 7105 | 8931 | Pennington Ave | Santa Clara St | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.5971
905 | 0 | 7107 | 7355 | Mansfield St | Margareta St | Clarita St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 273.2441
906 | 0 | 7110 | 7468 | Nottingham Rd | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.3539
907 | 0 | 7115 | 7629 | Robson St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0753
908 | 0 | 7117 | 6471 | Huntington Rd | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.1961
909 | 0 | 7124 | 6975 | Fenmore St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.0127
910 | 0 | 7126 | 4831 | Cambridge Ave | Mendota St | Birwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 125.5937
911 | 0 | 7130 | 7612 | Harvard Rd | King Richard St | McKinney Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 304.7824
912 | 0 | 7135 | 4813 | Albion St | Park Grove St | Linnhurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8046
913 | 0 | 7137 | 7384 | Sorrento St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5211
914 | 0 | 7139 | 6522 | Beaconsfield St | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 379.7391
915 | 0 | 7148 | 6605 | Marne St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.106
916 | 0 | 7161 | 6040 | Marne St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 616.2281
917 | 0 | 7176 | 7499 | Stahelin Ave | Margareta St | W 7 Mile Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 477.5414
918 | 0 | 7177 | 9074 | Lenore Ave | Margareta St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.3147
919 | 0 | 7184 | 6489 | Edinborough Rd | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.0341
920 | 0 | 7185 | 6077 | Snowden St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3369
921 | 0 | 7186 | 8408 | Robson St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1572
922 | 0 | 7189 | 6974 | Clarita St | Fenmore St | Archdale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 126.5801
923 | 0 | 7196 | 9122 | Pinehurst St | Santa Clara St | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.5672
924 | 0 | 7211 | 6899 | Duprey St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.1368
925 | 0 | 7220 | 6560 | Lansdowne St | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.3392
926 | 0 | 7227 | 8095 | Curtis St | Stansbury St | Lesure St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.0517
927 | 0 | 7254 | 5929 | Bradford St | Gietzen St | Greiner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.8112
928 | 0 | 7261 | 7587 | Strathmoor St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2398
929 | 0 | 7267 | 9420 | Haverhill St | Whitehill St | Stratman St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.6899
930 | 0 | 7284 | 7898 | Mendota St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2808
931 | 0 | 7289 | 5960 | Westmoreland Rd | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.939
932 | 0 | 7308 | 6338 | Clarita St | Stansbury St | Lesure St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.0066
933 | 0 | 7349 | 8884 | Guilford St | Berden St | Minerva St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3759
934 | 0 | 7352 | 8385 | Farmbrook St | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2566
935 | 0 | 7353 | 5460 | Troester St | Grover St | Peoria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.0055
936 | 0 | 7355 | 9072 | Santa Clara St | Ilene St | Washburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.157
937 | 0 | 7360 | 8930 | Santa Clara St | Pennington Ave | San Juan Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.4446
938 | 0 | 7374 | 5339 | Huntington Rd | Vassar Ave | Pembroke Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 543.6338
939 | 0 | 7386 | 5873 | Worden St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 616.5522
940 | 0 | 7387 | 6042 | Asbury Park | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.6147
941 | 0 | 7392 | 5567 | Verdun St | Riverview St | Appleton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.3648
942 | 0 | 7395 | 6940 | Freeland St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3377
943 | 0 | 7399 | 6997 | Shiawassee Dr | W 7 Mile Rd | Verdun St | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 642.7208
944 | 0 | 7405 | 5546 | Bentler St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.5658
945 | 0 | 7408 | 7346 | Grandview St | W 7 Mile Rd | Frisbee St | [5 empty] | Yes | 5 | Will be Installed 2021 | [26 empty] | 953.886
946 | 0 | 7424 | 6418 | Sunderland Rd | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.508
947 | 0 | 7442 | 8560 | Curtis St | Rutherford St | Prevost St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.8387
948 | 0 | 7443 | 9081 | Kennebec St | Conner St | Algonac St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 308.6465
949 | 0 | 7445 | 6514 | Whitcomb St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.17
950 | 0 | 7458 | 6530 | Peerless St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.4717
951 | 0 | 7460 | 6048 | Ferguson St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.9022
952 | 0 | 7473 | 7893 | Albion St | E McNichols Rd | Sauer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.91
953 | 0 | 7494 | 7373 | Bradford St | E McNichols Rd | Sauer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 339.3694
954 | 0 | 7495 | 6905 | Archdale St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.5207
955 | 0 | 7511 | 8436 | Kentfield St | Pickford St | Clarita St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 402.2094
956 | 0 | 7521 | 5039 | Riopelle St | E Robinwood St | E 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.6443
957 | 0 | 7530 | 7070 | Grayton St | Roxbury St | Lakepointe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.5458
958 | 0 | 7532 | 7913 | Lodewyck St | Berden St | Minerva St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.869
959 | 0 | 7536 | 6918 | Cardoni St | E Nevada St | E Grixdale Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 455.2037
960 | 0 | 7548 | 8011 | Wayburn St | Whittier St | Yorkshire Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.4647
961 | 0 | 7550 | 7449 | Margareta St | Lindsay St | Gilchrist St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 127.6449
962 | 0 | 7576 | 8615 | Thatcher St | W Outer Dr | Sorrento St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.8464
963 | 0 | 7603 | 6598 | Mansfield St | Clarita St | W 7 Mile Rd | [6 empty] | 1 | 2020 Carryover | [26 empty] | 277.3206
964 | 0 | 7606 | 5337 | Cherrylawn St | W 7 Mile Rd | S Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.6024
965 | 0 | 7614 | 9463 | Kilbourne Ave | Coplin St | Newport St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 332.546
966 | 0 | 7634 | 7929 | Manor St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.5082
967 | 0 | 7642 | 9121 | Santa Clara St | Pinehurst St | Mendota St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.6563
968 | 0 | 7643 | 8394 | Hillcrest St | Hillcrest Dr & Mack Ave | Frankfort Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 297.6722
969 | 0 | 7649 | 7522 | Stansbury St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.2707
970 | 0 | 7656 | 5888 | Lansdowne St | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.6495
971 | 0 | 7670 | 8401 | Canyon Ave | Chandler Park Dr | Gateshead St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 166.4902
972 | 0 | 7687 | 6537 | Prest St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.9139
973 | 0 | 7690 | 4860 | Rutherford St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 262.6936
974 | 0 | 7714 | 8465 | Thatcher St | Ilene St | Washburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.9394
975 | 0 | 7734 | 9353 | Murray Hill St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.4693
976 | 0 | 7742 | 7886 | Birwood St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9069
977 | 0 | 7745 | 8389 | Plainview Ave | Pickford St | Clarita St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.2844
978 | 0 | 7747 | 7427 | Clarita St | Plainview Ave | Westmoreland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.2504
979 | 0 | 7751 | 6100 | Oakfield St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.7357
980 | 0 | 7757 | 8970 | McKinney Ave | Everts St | Kensington Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.8901
981 | 0 | 7767 | 7952 | Appoline St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.9823
982 | 0 | 7769 | 8619 | Lannoo St | Lannoo Dr & Mack Ave | Frankfort Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 325.7502
983 | 0 | 7780 | 6564 | Mendota St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.109
984 | 0 | 7787 | 8525 | Curtis St | Forrer St | Winthrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 153.8308
985 | 0 | 7788 | 8971 | W Parkhurst Pl | Woodward Ave | John R St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 553.0243
986 | 0 | 7794 | 8117 | Thatcher St | Stoepel St | Livernois Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.2152
988 | 0 | 7814 | 8017 | Fenmore St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.2167
989 | 0 | 7815 | 6853 | Snowden St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3551
990 | 0 | 7828 | 8585 | Curtis St | Saint Marys St | Mansfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.4932
991 | 0 | 7829 | 7891 | W Montana St | Woodward Ave | John R St | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 762.5018
992 | 0 | 7842 | 8440 | Glenhurst St | Grayfield St | Clarita St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 400.6808
993 | 0 | 7852 | 8646 | Cedarhurst Pl | Woodward Ave & Merrill Plaisance St | W Longwood Pl | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 551.1985
994 | 0 | 7855 | 6821 | Asbury Park | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.5091
995 | 0 | 7857 | 5540 | Shiawassee Dr | Verdun St | Frisbee St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 321.2639
996 | 0 | 7859 | 6451 | Chapel St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.7901
997 | 0 | 7883 | 5576 | Fenmore St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.2395
998 | 0 | 7887 | 8135 | Curtis St | Freeland St | Ardmore St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.9939
999 | 0 | 7897 | 5070 | E Hildale St | Sunset St | Shields St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.3495
1000 | 0 | 7898 | 8010 | Snowden St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.6804
1001 | 0 | 7899 | 5179 | Vassar Ave | Warwick St | Sunderland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 112.2238
1002 | 0 | 7904 | 8004 | Frankfort Ave | Hillcrest St | Moross Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 128.115
1003 | 0 | 7920 | 4982 | Whitehill St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.6121
1004 | 0 | 7938 | 9358 | King Richard St | Everts St | Kensington Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 111.0015
1005 | 0 | 7940 | 5376 | Ilene St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.8047
1006 | 0 | 7944 | 8321 | Harvard Rd | W I 94 Service Drive | King Richard St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 422.0413
1007 | 0 | 7945 | 8655 | Woodhall St | Berden St | Minerva St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.4394
1008 | 0 | 7966 | 8358 | Woodingham Dr | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.6756
1009 | 0 | 7977 | 7825 | Coyle St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.9397
1010 | 0 | 7983 | 6054 | Rossiter St | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.7475
1011 | 0 | 7985 | 5967 | Plainview Ave | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.6519
1012 | 0 | 7987 | 8893 | Santa Clara St | Santa Rosa Dr | Stoepel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.6919
1013 | 0 | 7990 | 8957 | Curtis St | Sunderland Rd | Stahelin Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.8064
1014 | 0 | 7994 | 9519 | Stoepel St | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.6663
1015 | 0 | 8003 | 6447 | Brinker St | E Nevada St | E Grixdale St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 381.0419
1016 | 0 | 8007 | 7473 | Greenview Ave | Margareta St | W 7 Mile Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 477.2683
1017 | 0 | 8009 | 9031 | Balfour Rd | Whittier St | Yorkshire Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 351.4357
1018 | 0 | 8017 | 8015 | Nottingham Rd | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 300.9557
1019 | 0 | 8021 | 7570 | Burt Rd | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.2159
1020 | 0 | 8034 | 5496 | Gallagher St | E Grixdale St | E Hildale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 181.9727
1021 | 0 | 8042 | 7352 | Beaconsfield St | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.3731
1022 | 0 | 8043 | 7437 | Hillcrest St | Linville St | Rolandale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 292.0428
1023 | 0 | 8045 | 5993 | Pinehurst St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3512
1024 | 0 | 8049 | 6600 | Appoline St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0922
1025 | 0 | 8070 | 6374 | Laing St | Grayton St | Britain St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.0752
1026 | 0 | 8077 | 8458 | Fielding St | Pickford St | Clarita St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 402.4669
1027 | 0 | 8085 | 8960 | Santa Clara St | Roselawn St | Greenlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.4819
1028 | 0 | 8086 | 7873 | Chapel St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 422.3925
1029 | 0 | 8102 | 5119 | Frisbee St | Winston St | Lenore Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 262.4661
1030 | 0 | 8106 | 8937 | Curtis St | Avon Ave | Greenview Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.6589
1031 | 0 | 8124 | 7484 | Harlow St | Margareta St | Clarita St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 271.8824
1032 | 0 | 8133 | 6498 | Albion St | Clough St | Gietzen St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.7862
1033 | 0 | 8155 | 8887 | Curtis St | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 128.4394
1034 | 0 | 8159 | 6958 | Yorkshire Rd | Laing St | Duchess St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.6445
1035 | 0 | 8164 | 4972 | Blackstone St | Pembroke Ave | St Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.0803
1036 | 0 | 8166 | 6822 | Pierson St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.9356
1037 | 0 | 8196 | 8144 | Pickford St | Shaftsbury Ave | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.2569
1038 | 0 | 8198 | 5527 | Balfour Rd | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.2715
1039 | 0 | 8199 | 5621 | Stoepel St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.2616
1040 | 0 | 8211 | 4819 | Birwood St | Cambridge Ave | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8402
1041 | 0 | 8212 | 7845 | Pickford St | Sussex St | Coyle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.6668
1042 | 0 | 8226 | 5329 | Grandville Ave | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.1894
1043 | 0 | 8227 | 5332 | Cambridge Ave | Robson St | Lauder St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0855
1044 | 0 | 8239 | 8102 | McKinney Ave | Bishop St | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.0768
1045 | 0 | 8267 | 6499 | Margareta St | Kentucky St | Indiana St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.123
1046 | 0 | 8273 | 7022 | Riverview St | Vassar Ave | 7 Mile Rd W | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 292.1306
1048 | 0 | 8279 | 7488 | Margareta St | Avon Ave | Greenview Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.0452
1049 | 0 | 8290 | 4922 | Blackmoor St | Park Grove St | Linnhurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.8225
1050 | 0 | 8297 | 6112 | Harlow St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8308
1051 | 0 | 8298 | 6322 | Clarita St | Lesure St | Tracey St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.2615
1052 | 0 | 8308 | 9431 | Harvard Rd | Berden St | Harper Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.48
1053 | 0 | 8339 | 5409 | Teppert St | Greiner St | Park Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5571
1054 | 0 | 8343 | 8359 | Annchester Rd | Pickford St | Clarita St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 397.2958
1055 | 0 | 8346 | 5054 | Greydale Ave | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.5808
1056 | 0 | 8352 | 7024 | Cherrylawn St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5046
1057 | 0 | 8367 | 8052 | Harlow St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.6881
1058 | 0 | 8370 | 8617 | Whitehill St | Craft St | Courville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.7513
1059 | 0 | 8378 | 5383 | Rossiter St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.7014
1060 | 0 | 8380 | 4882 | Algonac St | Park Grove St | Linnhurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.8458
1061 | 0 | 8389 | 7021 | Albion St | Sauer St | Clough St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 248.2316
1062 | 0 | 8408 | 6957 | Laing St | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 313.883
1063 | 0 | 8411 | 7492 | Kentfield St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.2187
1064 | 0 | 8423 | 6951 | Balfour Rd | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.6209
1065 | 0 | 8425 | 7559 | Pierson St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.1232
1066 | 0 | 8440 | 8089 | Pickford St | Avon Ave | Greenview Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.5145
1067 | 0 | 8446 | 9099 | Lafontaine St | Frankfort Ave | Canyon Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 214.6151
1068 | 0 | 8456 | 6818 | Sorrento St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2923
1069 | 0 | 8458 | 7335 | Margareta St | Prevost St | Forrer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.148
1070 | 0 | 8464 | 8067 | Archdale St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8244
1071 | 0 | 8473 | 7919 | Monte Vista St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8606
1072 | 0 | 8486 | 9034 | Kentucky St | Santa Clara St | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.816
1073 | 0 | 8492 | 6084 | Blackstone St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0112
1074 | 0 | 8498 | 5568 | Riverview St | Verdun St | Frisbee St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 289.2925
1075 | 0 | 8511 | 9068 | Greensboro St | Courville St | Whittier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.6602
1077 | 0 | 8526 | 8936 | Santa Barbara Dr | Santa Clara St | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.8629
1078 | 0 | 8539 | 7029 | Canyon Ave | Berden St | Mallina St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.7444
1079 | 0 | 8546 | 7075 | Pickford St | Washburn St | Wyoming St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.1226
1080 | 0 | 8550 | 5397 | Runyon St | Greiner St | Park Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5571
1081 | 0 | 8552 | 8414 | Vaughan St | Pickford St | Clarita St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.6249
1082 | 0 | 8566 | 9098 | Frankfort Ave | Lafontaine St | Ashley Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.3099
1083 | 0 | 8583 | 8920 | Curtis St | Faust Ave | Glastonbury Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 143.4399
1084 | 0 | 8584 | 8927 | Somerset Ave | Whittier St | Yorkshire Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.0239
1085 | 0 | 8610 | 5956 | Washburn St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.5221
1086 | 0 | 8615 | 7396 | Pickford St | W Outer Dr | Sorrento St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.863
1087 | 0 | 8616 | 4862 | Syracuse St | E Hildale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.4134
1088 | 0 | 8618 | 5020 | Chapel St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.066
1089 | 0 | 8619 | 5004 | Bentler St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1504
1090 | 0 | 8624 | 5155 | San Juan Dr | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0863
1091 | 0 | 8628 | 6342 | Margareta St | Warrington Dr | Oak Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.9078
1092 | 0 | 8634 | 8943 | Woodingham Dr | Santa Clara St | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.7115
1093 | 0 | 8638 | 7325 | Winston St | W 7 Mile Rd | Frisbee St | [5 empty] | Yes | 5 | Will be Installed 2021 | [26 empty] | 952.1901
1094 | 0 | 8639 | 6069 | Appleton St | Verdun St | Appleton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 238.1719
1095 | 0 | 8644 | 8325 | Mark Twain St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.951
1096 | 0 | 8645 | 6397 | Margareta St | Pennington Ave | San Juan Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.2333
1097 | 0 | 8657 | 5099 | Houghton St | Saint Martins Ave | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3122
1098 | 0 | 8663 | 5142 | Grandview St | Frisbee St | Pembroke Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 156.2076
1099 | 0 | 8665 | 8345 | Curtis St | Strathmoor St | Mark Twain St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.705
1100 | 0 | 8675 | 7866 | Bentler St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 425.8676
1101 | 0 | 8683 | 7076 | Washburn St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1042
1102 | 0 | 8689 | 6107 | Dale St | Vassar Ave | Verdun St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.4715
1104 | 0 | 8722 | 6382 | Mark Twain St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.4731
1105 | 0 | 8728 | 8590 | Thatcher St | Steel St | Appoline St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.0997
1106 | 0 | 8736 | 6885 | Bentler St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 167.3762
1107 | 0 | 8737 | 6111 | Bentler St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3588
1108 | 0 | 8751 | 6860 | Birchcrest Dr | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 241.9251
1109 | 0 | 8753 | 7934 | Beaconsfield St | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.7929
1110 | 0 | 8756 | 7942 | Beland St | E McNichols Rd | Sauer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.5023
1111 | 0 | 8757 | 5982 | Wayburn St | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.6721
1112 | 0 | 8758 | 8593 | Frankfort Ave | Gateshead St | Lannoo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 146.1188
1113 | 0 | 8759 | 8082 | Worcester Pl | Woodward Ave | John R St | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 699.5462
1114 | 0 | 8760 | 9001 | Gateshead St | Gateshead Dr & Mack Ave | Frankfort Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 350.6962
1115 | 0 | 8763 | 8850 | Kennebec St | Algonac St | Elmo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0531
1116 | 0 | 8771 | 4998 | McCormick St | Sanilac St | Duprey St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.1322
1117 | 0 | 8775 | 9137 | Edgevale St | John R St | Brush St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 492.5389
1118 | 0 | 8778 | 5104 | E Hildale St | Ryan Rd | Dean St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.4065
1119 | 0 | 8791 | 5542 | Healy St | Stockton St | E Hildale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.3281
1120 | 0 | 8794 | 8941 | Hereford St | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.674
1121 | 0 | 8825 | 5457 | Patton St | Vassar Ave | Saint Martins Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.173
1122 | 0 | 8828 | 6358 | McKinney Ave | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.2693
1123 | 0 | 8833 | 7421 | Wayburn St | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 314.2726
1124 | 0 | 8835 | 9485 | Canyon Ave | Frankfort Ave | Lafontaine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 242.948
1125 | 0 | 8851 | 8573 | Mansfield St | Curtis St | Pickford St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 272.5397
1126 | 0 | 8855 | 7108 | Mendota St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1448
1127 | 0 | 8860 | 8532 | Neff Ave | Berden St | Minerva St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.5026
1128 | 0 | 8884 | 7508 | Fenmore St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 215.8133
1129 | 0 | 8889 | 7401 | Clarita St | Annchester Rd | Edinborough Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.1378
1130 | 0 | 8890 | 7564 | Kennebec St | Bradford St | Dresden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.4544
1131 | 0 | 8904 | 8591 | Steel St | Thatcher St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.4874
1132 | 0 | 8932 | 4908 | Cambridge Ave | Steel St | Appoline St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.3018
1133 | 0 | 8939 | 6449 | Northlawn St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.4683
1134 | 0 | 8946 | 7967 | Neff Ave | Minerva St | Chester St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 215.4888
1135 | 0 | 8950 | 7575 | Mark Twain St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3284
1136 | 0 | 8961 | 7909 | Pinehurst St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8874
1137 | 0 | 8974 | 6403 | Stahelin Ave | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.5533
1138 | 0 | 8982 | 5530 | Laing St | Britain St | Morang Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.5376
1139 | 0 | 8999 | 5898 | Cardoni St | E Grixdale Ave | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 330.9556
1140 | 0 | 9010 | 7535 | Rossiter St | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 313.2257
1141 | 0 | 9037 | 4835 | Runyon St | Park Grove St | Linnhurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0783
1142 | 0 | 9040 | 8482 | Shiawassee Dr | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.669
1143 | 0 | 9053 | 6864 | Margareta St | Hartwell St | Snowden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.2026
1144 | 0 | 9055 | 9029 | Kilbourne Ave | Newport St | Chalmers St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.355
1146 | 0 | 9084 | 6833 | Ferguson St | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.7616
1147 | 0 | 9091 | 8428 | Portlance St | Simms St | Elmo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 183.0956
1149 | 0 | 9108 | 6604 | Patton St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.521
1150 | 0 | 9116 | 7947 | King Richard St | Boleyn St | Harvard Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.9863
1151 | 0 | 9120 | 6028 | Patton St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5752
1152 | 0 | 9121 | 8553 | Syracuse St | E McNichols Rd | E Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 389.6764
1153 | 0 | 9131 | 7848 | Hereford St | Minerva St | Chester St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 236.4628
1154 | 0 | 9138 | 5964 | Peerless St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 616.316
1155 | 0 | 9141 | 5066 | Stansbury St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.6443
1156 | 0 | 9142 | 4984 | Lamont St | E Hildale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.7451
1157 | 0 | 9153 | 8346 | Strathmoor St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7094
1158 | 0 | 9165 | 5087 | Dean St | E Hildale St | E Robinwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 232.0411
1159 | 0 | 9172 | 7362 | Huntington Rd | Clarita St & Margareta St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.2307
1160 | 0 | 9174 | 9144 | Santa Clara St | Manor St | Pinehurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.5595
1161 | 0 | 9175 | 9395 | Nashville St | Elmo St | Gunston St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 413.4318
1162 | 0 | 9176 | 5822 | W Golden Gate Ave | Woodward Ave | Charleston St | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 632.0452
1163 | 0 | 9189 | 8364 | Balfour Rd | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.1847
1164 | 0 | 9191 | 7624 | Shiawassee Dr | Clarita St | Kress St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.7623
1165 | 0 | 9219 | 7963 | Steel St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.2949
1166 | 0 | 9222 | 8472 | Kennebec St | Elmo St | Gunston St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 413.631
1167 | 0 | 9232 | 7419 | Duprey St | Cadieux Rd | Morang Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2858
1168 | 0 | 9235 | 6047 | Pierson St | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.771
1169 | 0 | 9239 | 4820 | Rossiter St | Casino St | Moross Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.4022
1170 | 0 | 9247 | 9416 | Bentler St | Curtis St | Karl St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.3328
1171 | 0 | 9252 | 7060 | Kentucky St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.058
1172 | 0 | 9266 | 7359 | Appoline St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5037
1173 | 0 | 9267 | 7424 | Snowden St | Pickford St | Margareta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2812
1174 | 0 | 9286 | 5434 | Syracuse St | Stockton St | E Hildale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.7073
1175 | 0 | 9295 | 6335 | Fenmore St | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9545
1176 | 0 | 9304 | 6844 | Littlefield St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2241
1177 | 0 | 9313 | 6430 | Riverview St | Vassar Ave | 7 Mile Rd W | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 105.7749
1178 | 0 | 9322 | 7451 | King Richard St | Britain St | Merlin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.1157
1179 | 0 | 9324 | 5999 | Barlow St | Sauer St | Greiner St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.6701
1180 | 0 | 9334 | 6954 | Mark Twain St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3689
1181 | 0 | 9342 | 6326 | W Grixdale Ave | Woodward Ave | Charleston St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 523.8297
1183 | 0 | 9353 | 7874 | Pickford St | Prest St | Whitcomb St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.1011
1184 | 0 | 9364 | 5945 | Annott St | Gietzen St | Greiner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.6612
1185 | 0 | 9365 | 6500 | Kentucky St | Margareta St | Clarita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.7561
1186 | 0 | 9368 | 7543 | Stoepel St | Curtis St | Pickford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5825
1187 | 0 | 9376 | 6938 | McIntyre St | W 7 Mile Rd | Vassar Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 493.5141
1188 | 0 | 9377 | 4905 | Gruebner St | Park Grove St | Linnhurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.1864
1189 | 0 | 9382 | 7469 | Grayton St | Nottingham Rd | Beaconsfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.657
1190 | 0 | 9399 | 6517 | Westmoreland Rd | W 7 Mile Rd | Cambridge Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.1885
1191 | 0 | 9412 | 4848 | Teppert St | Park Grove St | Linnhurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.594
1192 | 0 | 9420 | 5899 | Strasburg St | Gietzen St | Greiner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.458
1193 | 0 | 9445 | 8684 | Santa Clara St | Quincy St | Oak Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 92.2395
1194 | 0 | 9449 | 7109 | Margareta St | Winthrop St | Greenfield Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 160.0973
1195 | 0 | 9456 | 5563 | Maine St | E Grixdale St | E Robinwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.0903
1196 | 0 | 9457 | 6609 | Riad St | Yorkshire Rd | Grayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.9006
1197 | 0 | 9479 | 7053 | Teppert St | Sauer St | Clough St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.6118
1198 | 0 | 9481 | 5599 | Verdun St | Telegraph Rd | Dale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.3687
1199 | 0 | 9485 | 7008 | Ashton Ave | Clarita St | W 7 Mile Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.941
1200 | 0 | 9491 | 7073 | Merlin St | King Richard St | McKinney Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.5117
1201 | 0 | 9510 | 5841 | Beaconsfield St | Morang Dr | Casino St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.9605
1202 | 0 | 9517 | 5903 | Grandville Ave | Cambridge Ave | Vassar Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.2323
1203 | 0 | 9526 | 9491 | Hereford St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.8155
1204 | 0 | 9536 | 10376 | Syracuse St | Rupert St | Simon K St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 107.422
1205 | 0 | 9543 | 10961 | Rosemary Ave | Roseberry St | Annsbury Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.4129
1206 | 0 | 9554 | 12001 | Florence St | Cheyenne St | Ward St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.7064
1207 | 0 | 9558 | 11997 | Wormer St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.5017
1208 | 0 | 9568 | 9588 | Coyle St | W Outer Dr | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 244.6312
1209 | 0 | 9571 | 10379 | Promenade Ave | Coplin St | Newport St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.6994
1210 | 0 | 9611 | 12007 | Carpenter St | Bristow St | Caely St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 201.0188
1211 | 0 | 9662 | 11134 | Stahelin Ave | W McNichols Rd | W Outer Dr | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 533.3741
1212 | 0 | 9706 | 10094 | Santa Barbara Dr | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.7219
1213 | 0 | 9722 | 10896 | Monica St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.5448
1214 | 0 | 9750 | 10388 | Prest St | Santa Maria St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 252.0934
1215 | 0 | 9752 | 12984 | Lesure St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.6826
1216 | 0 | 9771 | 9628 | Promenade Ave | Chalmers St | Queen St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 386.6084
1217 | 0 | 9778 | 13475 | Ferguson St | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.1955
1218 | 0 | 9787 | 12465 | Prest St | Florence St | Grove St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 457.3821
1219 | 0 | 9788 | 11402 | Robson St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.1329
1220 | 0 | 9803 | 9647 | Marseilles St | Southampton St | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.3953
1222 | 0 | 9821 | 14015 | Mansfield St | Pilgrim St | Puritan St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 280.5814
1223 | 0 | 9828 | 10025 | Luce St | Dean St | Sunset St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.9336
1224 | 0 | 9837 | 14044 | Asbury Park | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.9157
1225 | 0 | 9840 | 13108 | Wilshire Dr | Conner St | Gunston Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 499.0041
1226 | 0 | 9847 | 13044 | Rosemont Ave | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.8341
1227 | 0 | 9873 | 10024 | Quincy St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.8958
1228 | 0 | 9876 | 10825 | Syracuse St | Emeline St | Rowley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.4206
1229 | 0 | 9895 | 10378 | Kentucky St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0421
1232 | 0 | 9914 | 12057 | Moran St | Carpenter St | Halleck St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.3437
1233 | 0 | 9930 | 14000 | Avon Rd | Scarsdale St | Avon Ave & Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.2566
1234 | 0 | 9933 | 12896 | Trinity St | Verne St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 246.8167
1235 | 0 | 9957 | 13927 | Bretton Dr | Shaftsbury Ave | Warwick | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 223.7007
1236 | 0 | 9965 | 11433 | Plainview Ave | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 350.3464
1238 | 0 | 9992 | 12432 | Verne St | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 153.2351
1239 | 0 | 9996 | 10002 | Hereford St | Southampton St | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.9056
1240 | 0 | 9998 | 10519 | Littlefield St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.5975
1241 | 0 | 10013 | 9908 | Asbury Park | W Outer Dr | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.6922
1242 | 0 | 10017 | 12395 | Mendota St | James Couzens Fwy | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 215.0595
1243 | 0 | 10030 | 12556 | Washburn St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.3734
1245 | 0 | 10057 | 10069 | Kilbourne Ave | Park Dr | Dickerson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.4432
1246 | 0 | 10060 | 14071 | Littlefield St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.1586
1248 | 0 | 10071 | 12885 | Wayburn St | Linville St | Hern Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 186.7679
1249 | 0 | 10079 | 14026 | Appoline St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.0225
1250 | 0 | 10083 | 9849 | Woodhall St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 252.4526
1251 | 0 | 10090 | 12429 | Florence St | Sussex St | Coyle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 126.7791
1252 | 0 | 10137 | 10003 | Luce St | Shields St | Justine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.687
1253 | 0 | 10144 | 13468 | Princeton St | Midland St | Puritan St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.8888
1254 | 0 | 10147 | 9558 | Santa Maria St | Pennington Ave | San Juan Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3449
1255 | 0 | 10149 | 13873 | Bretton Dr | Shaftsbury Ave | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 185.7312
1256 | 0 | 10171 | 10548 | Christy St | Conner St | Algonac St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 194.1829
1257 | 0 | 10189 | 13882 | Florence St | Salem St | Winston St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 170.4512
1258 | 0 | 10193 | 13987 | Pinehurst St | Pilgrim St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.137
1259 | 0 | 10197 | 11008 | Birwood St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.0187
1260 | 0 | 10199 | 10957 | 3 Mile Dr | Linville St | Harper Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 235.6105
1261 | 0 | 10215 | 9827 | Lenore Ave | Pickford St | Curtis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.2518
1263 | 0 | 10237 | 12426 | Balfour Rd | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.1058
1264 | 0 | 10252 | 10525 | Snowden St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.719
1265 | 0 | 10262 | 13422 | Bretton Dr | Huntington Rd | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.8249
1266 | 0 | 10269 | 11026 | Grove St | Pinehurst St | Mendota St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.7429
1267 | 0 | 10275 | 10352 | Shaftsbury Ave | W Outer Dr | Curtis St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 559.138
1268 | 0 | 10278 | 12407 | Florence St | Robson St | Lauder St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.7036
1269 | 0 | 10283 | 10919 | Kensington Ave | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.6631
1270 | 0 | 10291 | 10842 | Haverhill St | McKinney Ave | Evanston St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 245.9841
1271 | 0 | 10298 | 11913 | Charest St | Halleck St | Lawley St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 438.0611
1272 | 0 | 10299 | 10831 | Moran St | Lawley St | E Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.3867
1273 | 0 | 10307 | 12023 | Carpenter St | Conant St | Justine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 200.7501
1274 | 0 | 10318 | 10081 | Westmoreland Rd | Santa Clara Ave | Curtis St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 461.2143
1275 | 0 | 10321 | 12010 | Littlefield St | Florence St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 322.9069
1276 | 0 | 10327 | 13145 | Ohio St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.4923
1277 | 0 | 10345 | 10457 | Greensboro St | Berkshire St | Haverhill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.3288
1278 | 0 | 10370 | 13594 | Midland St | Petoskey Ave | Quincy St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.2103
1279 | 0 | 10371 | 12067 | Carpenter St | Radom St | Moenart St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 96.5741
1280 | 0 | 10436 | 11832 | Evanston St | Wayburn St | Lakepointe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 174.4308
1281 | 0 | 10439 | 10437 | Rosemary Ave | Park Dr | Dickerson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.948
1282 | 0 | 10444 | 10100 | Sunderland Rd | W Outer Dr | Curtis St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 531.8305
1283 | 0 | 10470 | 12344 | Florence St | Strathmoor St | Mark Twain St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.7697
1284 | 0 | 10475 | 13519 | Vaughan St | Grand River Ave | Verne St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 379.0039
1285 | 0 | 10480 | 13020 | Cruse St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.4054
1286 | 0 | 10490 | 12485 | Caely St | Conant St | Carpenter St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.2229
1288 | 0 | 10499 | 10076 | Avon Ave | Curtis St | W Outer Dr | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 531.0297
1289 | 0 | 10507 | 9922 | Nashville St | Conner St | Algonac St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.8261
1290 | 0 | 10513 | 9994 | Fairfield St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 297.9229
1291 | 0 | 10517 | 10096 | Plainview Ave | Santa Clara Ave | Curtis St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 464.4956
1292 | 0 | 10518 | 10914 | Courville St | Linville St | Harper Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.7001
1293 | 0 | 10519 | 9644 | Rosemary Ave | Coplin St | Newport St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.0882
1294 | 0 | 10526 | 11953 | Appoline St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.3159
1296 | 0 | 10542 | 11090 | Sorrento St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.4079
1297 | 0 | 10579 | 10520 | Beaconsfield St | Berkshire St | Haverhill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 280.5854
1298 | 0 | 10598 | 10427 | Birwood St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.1527
1299 | 0 | 10600 | 12109 | Mansfield St | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.916
1300 | 0 | 10610 | 11489 | Prevost St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8261
1301 | 0 | 10613 | 10570 | Promenade Ave | Dickerson St | Coplin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.5319
1302 | 0 | 10623 | 11924 | Wilshire Dr | Roseberry St | Annsbury Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.4498
1303 | 0 | 10632 | 11007 | Grove St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.2419
1304 | 0 | 10662 | 12421 | Ashton Ave | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.1846
1305 | 0 | 10664 | 10989 | Kilbourne Ave | Barrett St | Roseberry St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.1365
1306 | 0 | 10675 | 10884 | Stoepel St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.1905
1307 | 0 | 10681 | 11849 | Kentucky St | Marygrove Dr | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 252.2877
1308 | 0 | 10682 | 10879 | Whitcomb St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.1543
1309 | 0 | 10683 | 14030 | Midland St | Steel St | Appoline St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.3791
1310 | 0 | 10688 | 9632 | Kentucky St | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.3304
1311 | 0 | 10689 | 11890 | Florence St | Ilene St | Washburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.3675
1312 | 0 | 10691 | 10577 | Saint Patrick St | Gunston St | Bradford St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.4916
1313 | 0 | 10704 | 9901 | Manor St | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3408
1314 | 0 | 10710 | 9985 | Luce St | Eureka St | Hasse St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.4862
1315 | 0 | 10717 | 11869 | Washburn St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 356.233
1317 | 0 | 10731 | 12458 | Beaverland St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.9712
1319 | 0 | 10754 | 13470 | Ward St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.6356
1320 | 0 | 10774 | 12870 | Appoline St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.4598
1321 | 0 | 10784 | 13089 | Florence St | Stahelin Ave | Avon Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.7925
1322 | 0 | 10807 | 11327 | Freeland St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 327.6149
1323 | 0 | 10812 | 10986 | Ilene St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.4601
1324 | 0 | 10820 | 11429 | Whitcomb St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.5036
1325 | 0 | 10834 | 14031 | Steel St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.1619
1326 | 0 | 10835 | 10476 | Kensington Ave | Linville St | Harper Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 440.8971
1327 | 0 | 10840 | 12464 | Florence St | Prest St | Whitcomb St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.0986
1328 | 0 | 10844 | 13654 | Florence St | Wormer St | Woodbine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.1127
1329 | 0 | 10856 | 10560 | Inverness St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.3584
1330 | 0 | 10857 | 10442 | Christy St | Algonac St | Elmo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8275
1331 | 0 | 10877 | 11930 | Florence St | Pinehurst St | Mendota St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.3039
1332 | 0 | 10899 | 10030 | Fielding St | Marian Pl | Glenco St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.1683
1333 | 0 | 10907 | 11916 | Haverhill St | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.3291
1334 | 0 | 10911 | 9829 | Bonita St | Wayburn St | Whitehill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.2943
1335 | 0 | 10934 | 12369 | Florence St | Marlowe St | Hubbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.2254
1336 | 0 | 10935 | 9878 | Luce St | Syracuse St | Mound Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 186.0276
1337 | 0 | 10957 | 13135 | Fenton St | Grove St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 126.8896
1338 | 0 | 10959 | 10634 | Manistique St | Elmdale St | Promenade St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.4075
1340 | 0 | 10982 | 10382 | Santa Clara Ave | Patton St | Fielding St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.2822
1341 | 0 | 10998 | 11479 | Buckingham Ave | Linville St | Hern Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.4852
1342 | 0 | 11002 | 13940 | Wayburn St | Southampton St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.1056
1343 | 0 | 11018 | 13094 | Sunderland Rd | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.7524
1344 | 0 | 11025 | 13040 | Forrer St | Hemlock St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.343
1345 | 0 | 11036 | 12124 | Pierson St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.0338
1346 | 0 | 11039 | 13526 | Florence St | Burgess St | Chapel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.1344
1347 | 0 | 11040 | 10383 | Patton St | Santa Clara Ave | Marian Pl | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 101.6166
1348 | 0 | 11041 | 13141 | Elmdale St | Barrett St | Roseberry St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 345.9166
1349 | 0 | 11048 | 13467 | Midland St | Princeton St | Linwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 125.0462
1350 | 0 | 11057 | 9946 | Harvard Rd | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9464
1351 | 0 | 11071 | 10410 | Ilene St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.6124
1352 | 0 | 11081 | 11378 | Rosemary Ave | Barrett St | Roseberry St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.3316
1353 | 0 | 11095 | 9973 | Promenade Ave | Newport St | Chalmers St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.5941
1355 | 0 | 11102 | 13423 | Heyden St | Grand River Ave | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 317.7258
1356 | 0 | 11105 | 12463 | Greenview Ave | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.3686
1357 | 0 | 11115 | 10637 | Santa Maria St | Plainview Ave | Westmoreland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.9362
1358 | 0 | 11130 | 12417 | Rockdale St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 261.2036
1359 | 0 | 11148 | 11865 | Pinehurst St | Pinehurst St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 310.6338
1360 | 0 | 11172 | 11921 | Mendota St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 350.9802
1361 | 0 | 11177 | 10071 | Greenview Ave | W Outer Dr | Curtis St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 531.7081
1362 | 0 | 11178 | 11961 | Steel St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 344.6851
1363 | 0 | 11224 | 11073 | Appoline St | Grove St | James Couzens Fwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.1643
1364 | 0 | 11226 | 10037 | Rosemary Ave | Dickerson St | Coplin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.9628
1365 | 0 | 11228 | 11330 | Sunderland Rd | W McNichols Rd | W Outer Dr | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 529.2053
1366 | 0 | 11248 | 13149 | Westmoreland Rd | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.4798
1367 | 0 | 11250 | 11387 | Lauder St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 316.6273
1368 | 0 | 11256 | 13333 | Westmoreland Rd | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.4526
1369 | 0 | 11262 | 12423 | Coyle St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 446.6569
1370 | 0 | 11263 | 13465 | Bretton Dr | Edinborough Rd | Huntington Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3024
1371 | 0 | 11265 | 9903 | Bentler St | Thatcher Ave | Glenco St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.0709
1372 | 0 | 11266 | 10453 | Santa Maria St | Rutherford St | Prevost St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.8439
1373 | 0 | 11274 | 13061 | Mark Twain St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.6733
1374 | 0 | 11293 | 12990 | Casmere St | Fenelon St | Buffalo St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 447.6147
1375 | 0 | 11296 | 10026 | Dean St | Luce St | E Davison St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 181.8805
1376 | 0 | 11304 | 9580 | Lodewyck St | Southampton St | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.7353
1378 | 0 | 11332 | 10452 | Bentler St | Santa Clara Ave | Bennett St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.9909
1381 | 0 | 11343 | 9879 | Syracuse St | Luce St | Desner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 263.9995
1382 | 0 | 11351 | 13935 | Prest St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.0577
1383 | 0 | 11372 | 10371 | Fielding St | Santa Clara Ave | Marian Pl | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 101.997
1384 | 0 | 11375 | 12428 | Stoepel St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.3767
1385 | 0 | 11377 | 11909 | Rosemary Ave | Gratiot Ave | Gunston Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 205.5268
1386 | 0 | 11379 | 12507 | Roselawn St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 366.963
1387 | 0 | 11380 | 9652 | Promenade Ave | Queen St | Hayes St & Promenade St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 249.6424
1388 | 0 | 11381 | 13343 | Whitcomb St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.7771
1389 | 0 | 11431 | 11499 | Sobieski St | Fenelon St | Moenart St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.637
1390 | 0 | 11439 | 11531 | Stoepel St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.1935
1391 | 0 | 11448 | 13103 | Florence St | Warwick St | Sunderland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.0813
1393 | 0 | 11452 | 12449 | Whitcomb St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 454.2797
1395 | 0 | 11479 | 11910 | Florence St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.2146
1396 | 0 | 11483 | 10627 | Rosemary Ave | Annsbury Ave | Park Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.6912
1397 | 0 | 11493 | 11102 | Ward St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.6068
1398 | 0 | 11500 | 14116 | Burgess St | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 284.8102
1399 | 0 | 11515 | 11394 | Moran St | Halleck St | Lawley St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.6457
1400 | 0 | 11521 | 10904 | Balfour Rd | Berkshire St | Haverhill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.8386
1401 | 0 | 11523 | 10398 | Yorkshire Rd | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8478
1402 | 0 | 11533 | 11098 | Promenade Ave | Annsbury Ave | Park Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.9202
1403 | 0 | 11554 | 13125 | Talbot St | Conant St | Fenelon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 407.8339
1404 | 0 | 11559 | 12408 | Robson St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 439.7863
1405 | 0 | 11576 | 11437 | Kensington Ave | Southampton St | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.2304
1406 | 0 | 11585 | 12521 | Verne St | Shaftsbury Ave | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.8466
1407 | 0 | 11592 | 10999 | Griggs St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.8119
1408 | 0 | 11593 | 13894 | Coyle St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.085
1409 | 0 | 11617 | 12965 | Greydale Ave | Verne St | W McNichols Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 512.0539
1410 | 0 | 11625 | 12900 | Asbury Park | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.1076
1411 | 0 | 11633 | 13056 | Prevost St | Hemlock St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.5895
1412 | 0 | 11647 | 10933 | Prevost St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.1735
1413 | 0 | 11665 | 11408 | University Pl | Cornwall St | E Warren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 280.0958
1414 | 0 | 11689 | 13655 | Wormer St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.1879
1415 | 0 | 11695 | 13973 | Chatsworth St | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.1171
1416 | 0 | 11700 | 10843 | Marseilles St | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.7496
1417 | 0 | 11727 | 10449 | Pinehurst St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.6043
1418 | 0 | 11742 | 13837 | Florence St | Fenton St | Lenore Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.2656
1419 | 0 | 11749 | 13092 | Manistique St | Linville St | Hern Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 217.0141
1420 | 0 | 11752 | 13601 | Manistique St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.9693
1421 | 0 | 11793 | 12525 | Ohio St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.7737
1422 | 0 | 11797 | 11575 | Maiden St | Newport St | Chalmers St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.851
1423 | 0 | 11802 | 13097 | Somerset Ave | Southampton St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.7079
1424 | 0 | 11808 | 10013 | Bluehill St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.673
1425 | 0 | 11817 | 12026 | Vaughan St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.7048
1426 | 0 | 11829 | 14064 | Biltmore St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7726
1427 | 0 | 11831 | 10934 | Sparling St | Charles St & Sparling Ave | Rupert St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.6056
1429 | 0 | 11835 | 10583 | Nottingham Rd | Berkshire St | Haverhill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.9562
1430 | 0 | 11836 | 11537 | Murray Hill St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.0611
1431 | 0 | 11847 | 14083 | Lindsay St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.4807
1432 | 0 | 11859 | 13360 | Prest St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 356.3284
1433 | 0 | 11860 | 12577 | Nottingham Rd | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.4413
1434 | 0 | 11863 | 10897 | Prest St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.014
1435 | 0 | 11866 | 13835 | Bretton Dr | Westmoreland Rd | Westmoreland Rd & Lancashire St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 79.5852
1436 | 0 | 11869 | 11376 | La Salle Ave | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.333
1437 | 0 | 11884 | 11419 | Harvard Rd | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7569
1438 | 0 | 11885 | 11872 | Glastonbury Rd | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.6764
1439 | 0 | 11897 | 12053 | Carpenter St | Bloom St | Buffalo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.4664
1440 | 0 | 11910 | 11390 | Kilbourne Ave | Gratiot Ave | Barrett St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 386.4706
1441 | 0 | 11921 | 10630 | Westmoreland Rd | Santa Maria St | Santa Clara Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.2247
1442 | 0 | 11933 | 11469 | 3 Mile Dr | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.4604
1443 | 0 | 11935 | 12490 | Sunderland Rd | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.9356
1444 | 0 | 11947 | 11621 | Rosemary Ave | Gunston Ave | Barrett St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.1476
1445 | 0 | 11969 | 13938 | Fairfield St | Hughes St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 162.1668
1446 | 0 | 11979 | 11637 | Devonshire Rd | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.5057
1447 | 0 | 12024 | 9925 | Promenade St | Promenade Ave & Hayes St | Philip St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 173.2443
1448 | 0 | 12041 | 10102 | Woodingham Dr | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8915
1449 | 0 | 12049 | 14053 | Ferguson St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.4654
1450 | 0 | 12057 | 13514 | Lindsay St | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8073
1451 | 0 | 12063 | 10527 | Farmbrook St | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.4682
1452 | 0 | 12078 | 9909 | Santa Maria St | Meyers Rd | Manor St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.4716
1453 | 0 | 12083 | 11126 | Manistique St | Wade St | Elmdale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.162
1454 | 0 | 12093 | 12524 | Pierson St | Grand River Ave | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 163.6718
1455 | 0 | 12113 | 12132 | Florence St | Freeland St | Ardmore St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 111.2246
1456 | 0 | 12122 | 11504 | Rutherford St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.0657
1457 | 0 | 12125 | 11901 | Griggs St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.5487
1458 | 0 | 12141 | 12511 | Northlawn St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 366.8554
1459 | 0 | 12149 | 11972 | Grove St | Edinborough Rd | Huntington Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.1585
1460 | 0 | 12156 | 12880 | Steel St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.8417
1461 | 0 | 12174 | 13437 | Casmere St | Conant St | Fenelon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 407.7892
1463 | 0 | 12198 | 9976 | Hartwell St | Santa Maria St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.0565
1464 | 0 | 12200 | 13607 | Puritan St | Rosemont Ave | Ashton Ave & Ashton Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 152.4364
1465 | 0 | 12201 | 10881 | Patton St | Santa Maria St | Santa Clara Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.995
1467 | 0 | 12215 | 13590 | Bretton Dr | Lancashire St | Edinborough Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 194.2692
1468 | 0 | 12217 | 12089 | Baylis St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.6194
1470 | 0 | 12220 | 13626 | Somerset Ave | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8188
1471 | 0 | 12253 | 13833 | Normandy St | Hughes St | Pilgrim St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.0553
1472 | 0 | 12259 | 12377 | Promenade Ave | Gunston Ave | Barrett St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.9062
1473 | 0 | 12272 | 10836 | Vaughan St | Santa Maria St | Santa Clara Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8777
1474 | 0 | 12275 | 9638 | Prest St | W Outer Dr | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 252.8664
1476 | 0 | 12280 | 12895 | Verne St | Trinity St | Burt Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.1636
1477 | 0 | 12285 | 10597 | Wilfred St | Gratiot Ave | Roseberry St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 434.1614
1478 | 0 | 12288 | 11994 | Buckingham Ave | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.3216
1479 | 0 | 12290 | 12003 | Grove St | Plainview Ave | Westmoreland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.5414
1480 | 0 | 12295 | 11396 | Haverhill St | Linville St | Hern Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 152.1118
1481 | 0 | 12302 | 11435 | Prest St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.0605
1482 | 0 | 12305 | 14132 | Manistique St | Southampton St | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.1563
1483 | 0 | 12317 | 13897 | Berkshire St | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.2703
1484 | 0 | 12337 | 9882 | Pinehurst St | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.2299
1485 | 0 | 12347 | 10494 | Wormer St | Bennett St | Curtis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.7453
1486 | 0 | 12348 | 12583 | Braile St | Grand River Ave | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 234.5305
1487 | 0 | 12350 | 11374 | Marlowe St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 324.6192
1488 | 0 | 12379 | 9609 | Oldtown St | Linville St | Harper Ave | [6 empty] | 3 | 2020 Carryover | [26 empty] | 643.7693
1489 | 0 | 12388 | 11121 | Devonshire Rd | Linville St | Harper Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 179.0892
1491 | 0 | 12392 | 11519 | Promenade Ave | Roseberry St | Annsbury Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 345.0443
1492 | 0 | 12433 | 13931 | Washburn St | James Couzens Fwy & Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7742
1493 | 0 | 12441 | 12913 | Cheyenne St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.9604
1494 | 0 | 12444 | 9938 | Guilford St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 254.5035
1496 | 0 | 12455 | 11051 | Manor St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.9362
1497 | 0 | 12468 | 13535 | Harlow St | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.0628
1498 | 0 | 12477 | 12114 | Normandy St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.2396
1499 | 0 | 12489 | 10526 | Grayton St | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.3196
1500 | 0 | 12498 | 13136 | Coyle St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.1693
1501 | 0 | 12503 | 10431 | Haverhill St | Somerset Ave | Balfour Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 127.0418
1502 | 0 | 12520 | 12559 | Verne St | Plainview Ave | Westmoreland Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 146.2009
1503 | 0 | 12526 | 12462 | Verne St | Greenview Ave | Glastonbury Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 155.1009
1504 | 0 | 12533 | 11413 | Coyle St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.7916
1505 | 0 | 12540 | 11353 | Littlefield St | Grove St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.4167
1506 | 0 | 12543 | 13916 | Whitcomb St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.6603
1507 | 0 | 12569 | 11891 | Ilene St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.9178
1508 | 0 | 12578 | 13608 | Rosemont Ave | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.0439
1509 | 0 | 12583 | 10077 | San Juan Dr | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1508
1510 | 0 | 12585 | 10122 | Steel St | James Couzens Fwy | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 152.4417
1511 | 0 | 12587 | 10838 | Fairfield St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.8335
1513 | 0 | 12604 | 13561 | Fenmore St | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.2891
1514 | 0 | 12626 | 13489 | Midland St | Alden St | Lawton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.0443
1515 | 0 | 12628 | 11050 | Grove St | Manor St | Monte Vista St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.2129
1516 | 0 | 12634 | 10091 | Stahelin Ave | W Outer Dr | Curtis St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 531.7339
1517 | 0 | 12636 | 13597 | Ashton Ave | Puritan St & Ashton Rd | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5829
1518 | 0 | 12639 | 11855 | Grove St | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 152.4088
1519 | 0 | 12644 | 13585 | Evanston St | Park Dr | Dickerson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.0115
1520 | 0 | 12646 | 11010 | Evanston St | Balfour Rd | Berkshire St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.1262
1522 | 0 | 12690 | 11911 | Birwood St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.2585
1523 | 0 | 12701 | 12548 | Verne St | Edinborough Rd | Huntington Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0987
1524 | 0 | 12706 | 10991 | Littlefield St | Verne St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.652
1525 | 0 | 12708 | 10018 | Oak Dr | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.0339
1526 | 0 | 12729 | 12129 | Bedford St | Southampton St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.7125
1527 | 0 | 12730 | 13636 | Greenview Ave | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5577
1528 | 0 | 12736 | 12906 | Woodbine St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.245
1529 | 0 | 12739 | 10019 | Promenade St | Philip St | Manistique St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.2937
1530 | 0 | 12742 | 13389 | Wayburn St | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.064
1531 | 0 | 12743 | 10985 | Grove St | Ilene St | Washburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.1496
1532 | 0 | 12747 | 12842 | Talbot St | Fenelon St | Buffalo St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 501.913
1533 | 0 | 12762 | 13415 | Chatsworth St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0748
1534 | 0 | 12769 | 13408 | Florence St | Patton St | Fielding St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.5257
1536 | 0 | 12777 | 13527 | Burgess St | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.3257
1537 | 0 | 12783 | 9967 | Luce St | Fenelon St | Conley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.1307
1538 | 0 | 12784 | 11022 | Bedford St | Linville St | Harper Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 193.7885
1539 | 0 | 12787 | 12964 | Verne St | Greydale Ave | Burgess St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.0811
1540 | 0 | 12807 | 9929 | Luce St | Moenart St | Bloom St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 112.3476
1541 | 0 | 12822 | 11508 | Mansfield St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.1238
1542 | 0 | 12845 | 13558 | Bretton Dr | W Outer Dr | Shaftsbury Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 162.9526
1543 | 0 | 12852 | 12482 | Verne St | Stahelin Ave | Avon Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.9561
1544 | 0 | 12860 | 11840 | Ashton Ave | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.624
1545 | 0 | 12865 | 12950 | Promenade Ave | Conner St | Gunston Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 553.7331
1546 | 0 | 12872 | 11532 | Sobieski St | Justine St | Fenelon St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 317.6574
1547 | 0 | 12883 | 13624 | Midland St | Santa Rosa Dr | Stoepel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.3996
1549 | 0 | 12891 | 12329 | Asbury Park | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7941
1550 | 0 | 12893 | 10446 | Prevost St | Santa Maria St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 253.1019
1551 | 0 | 12906 | 10050 | Patton St | Marian Pl | Glenco St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.9949
1552 | 0 | 12908 | 13352 | Berkshire St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.186
1553 | 0 | 13002 | 12460 | Haverhill St | Southampton St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.4792
1554 | 0 | 13003 | 9620 | Bishop St | Berden St | Harper Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.6703
1555 | 0 | 13004 | 11568 | Sobieski St | Conant St | Justine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.4371
1556 | 0 | 13009 | 13488 | Biltmore St | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0037
1557 | 0 | 13025 | 9551 | Grayton St | Berden St | Harper Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.5539
1558 | 0 | 13038 | 10444 | Harvard Rd | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.2852
1559 | 0 | 13042 | 13028 | Haverhill St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9521
1560 | 0 | 13052 | 11082 | Tracey St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 320.5127
1561 | 0 | 13070 | 13388 | Evanston St | Dickerson St | Coplin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.3629
1562 | 0 | 13085 | 13473 | Florence St | Blackstone St | Trinity St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.9238
1563 | 0 | 13088 | 12103 | Florence St | Cruse St | Stansbury St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 125.2168
1564 | 0 | 13089 | 10538 | Bloom St | Rowley St | Rupert St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 108.0111
1565 | 0 | 13108 | 11001 | Faust Ave | Greenview Ave | W Outer Dr | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 515.1953
1566 | 0 | 13112 | 10976 | Washburn St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.5434
1567 | 0 | 13115 | 13603 | Bretton Dr | W Outer Dr | Shaftsbury Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.8754
1568 | 0 | 13120 | 10875 | Fielding St | Santa Maria St | Santa Clara Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1854
1569 | 0 | 13126 | 13562 | Midland St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.3974
1570 | 0 | 13139 | 10928 | Gallagher St | Lawley St | E Davison St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 326.3674
1571 | 0 | 13145 | 12054 | Bloom St | Carpenter St | Charles St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 506.2539
1572 | 0 | 13188 | 9959 | Santa Maria St | Littlefield St | Ward St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 150.2803
1574 | 0 | 13197 | 13464 | Bretton Dr | Huntington Rd | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.3621
1575 | 0 | 13208 | 13498 | Florence St | Bentler St | Westbrook St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.6184
1576 | 0 | 13216 | 12065 | Forrer St | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.6379
1578 | 0 | 13220 | 11084 | Steel St | Grove St | James Couzens Fwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.9408
1579 | 0 | 13225 | 13403 | Fielding St | Florence St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 160.7132
1580 | 0 | 13245 | 11977 | Sorrento St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.5116
1581 | 0 | 13247 | 12431 | Gallagher St | Carpenter St | Halleck St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.9829
1582 | 0 | 13260 | 12564 | Evanston St | Newport St | Chalmers St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 335.6999
1583 | 0 | 13268 | 13595 | Petoskey Ave | Puritan St | Midland St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.0381
1584 | 0 | 13282 | 12077 | Florence St | Lesure St | Tracey St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.0638
1585 | 0 | 13285 | 9900 | Santa Maria St | Manor St | Pinehurst St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 242.7279
1586 | 0 | 13288 | 9975 | Santa Maria St | Hartwell St | Snowden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.1008
1587 | 0 | 13293 | 13640 | Longview St | Conner St | Gunston Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 408.1789
1588 | 0 | 13295 | 13084 | Saint Marys St | Hemlock St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.5691
1589 | 0 | 13298 | 10377 | Whitcomb St | Santa Maria St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.4304
1590 | 0 | 13304 | 9546 | San Juan Dr | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.2759
1591 | 0 | 13306 | 13359 | Nottingham Rd | Southampton St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.7021
1592 | 0 | 13340 | 9568 | Woodingham Dr | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.4618
1593 | 0 | 13342 | 11460 | Evanston St | Greensboro St | Beaconsfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.8936
1594 | 0 | 13354 | 12953 | Burgess St | Verne St | W McNichols Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 511.5346
1595 | 0 | 13356 | 10927 | Lawley St | Gallagher St | Klinger St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 173.4597
1596 | 0 | 13361 | 12342 | Wilshire Dr | Barrett St | Roseberry St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.7406
1597 | 0 | 13365 | 13071 | Strathmoor St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.9815
1598 | 0 | 13381 | 12908 | Blackstone St | Verne St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.7261
1600 | 0 | 13396 | 9549 | Bluehill St | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.6789
1601 | 0 | 13397 | 12430 | Sussex St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 451.0106
1602 | 0 | 13402 | 9598 | Neff Ave | Chandler Park Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.874
1603 | 0 | 13413 | 10939 | Mansfield St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.478
1604 | 0 | 13416 | 10917 | Harvard Rd | Southampton St | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.5111
1605 | 0 | 13418 | 10086 | Pennington Ave | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3751
1606 | 0 | 13424 | 10385 | Sparling St | Rupert St | Luce St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 214.9597
1607 | 0 | 13430 | 10845 | Somerset Ave | Berkshire St | Haverhill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.4466
1608 | 0 | 13433 | 13450 | Steel St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8195
1609 | 0 | 13487 | 9996 | Belden St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 297.6069
1610 | 0 | 13492 | 12944 | Verne St | Chapel St | Bentler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.3342
1611 | 0 | 13496 | 9559 | Pennington Ave | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.2267
1612 | 0 | 13497 | 10035 | Grayton St | Linville St | Berden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9094
1613 | 0 | 13501 | 10092 | Oldtown St | Chandler Park Dr | Linville St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 255.4777
1614 | 0 | 13509 | 11585 | Bentler St | W McNichols Rd | Orchard St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 488.0343
1615 | 0 | 13521 | 13579 | Quincy St | Midland St | Puritan St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.3256
1616 | 0 | 13529 | 10010 | Birchcrest Dr | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 287.0588
1617 | 0 | 13530 | 10396 | Washburn St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7419
1618 | 0 | 13540 | 13363 | Wade St | Annsbury Ave | Park Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.2911
1619 | 0 | 13542 | 11027 | Pinehurst St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.3616
1620 | 0 | 13545 | 11360 | Florence St | Inverness St | Baylis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.1547
1621 | 0 | 13546 | 9937 | Haverhill St | Roxbury St | Greensboro St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.1672
1622 | 0 | 13552 | 11993 | Westmoreland Rd | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.144
1623 | 0 | 13561 | 13834 | Bretton Dr | Westmoreland Rd | Lancashire St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 80.0073
1624 | 0 | 13565 | 13031 | Ashton Ave | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.4076
1626 | 0 | 13604 | 12547 | Kentucky St | Florence St | Puritan St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.9637
1627 | 0 | 13622 | 12567 | Vaughan St | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.1956
1628 | 0 | 13628 | 12916 | Verne St | Westbrook St | Blackstone St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.3971
1629 | 0 | 13642 | 13128 | University Pl | Mack Ave | Munich St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 602.7858
1630 | 0 | 13655 | 11463 | Florence St | Muirland St | Fairfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0573
1631 | 0 | 13656 | 11422 | Sussex St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 293.3867
1632 | 0 | 13665 | 12370 | Marlowe St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 425.0052
1633 | 0 | 13670 | 11856 | Rosemont Ave | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.6491
1634 | 0 | 13671 | 10574 | La Salle Ave | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.7485
1635 | 0 | 13672 | 10565 | Baylis St | Grove St | W McNichols Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.5105
1636 | 0 | 13676 | 12051 | Kentfield St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 249.3329
1637 | 0 | 13679 | 11867 | Beaverland St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.0108
1638 | 0 | 13680 | 13051 | Freeland St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.8027
1639 | 0 | 13686 | 10611 | Santa Maria St | Edinborough Rd | Huntington Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.8004
1640 | 0 | 13715 | 9596 | Balfour Rd | Courville St | Whittier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.8578
1641 | 0 | 13729 | 11522 | Saint Marys St | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.0325
1642 | 0 | 13731 | 11893 | Grove St | Greenview Ave | Glastonbury Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 159.2696
1643 | 0 | 13737 | 10935 | Rutherford St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.3159
1644 | 0 | 13741 | 9651 | Washburn St | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8242
1645 | 0 | 13744 | 10638 | Plainview Ave | Santa Maria St | Santa Clara Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.2031
1646 | 0 | 13753 | 12029 | Manistique St | Evanston St | Wade St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.1789
1647 | 0 | 13754 | 13015 | Normandy St | Pilgrim St | Puritan St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.9161
1648 | 0 | 13758 | 13007 | Stansbury St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.4782
1649 | 0 | 13773 | 13000 | Fenmore St | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.5535
1650 | 0 | 13777 | 12993 | Rockdale St | Verne St | Grove St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.5945
1651 | 0 | 13785 | 9851 | Birwood St | Santa Maria St | Santa Clara St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8629
1652 | 0 | 13787 | 13046 | Beaverland St | Verne St | S Riverdale Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 228.5794
1653 | 0 | 13788 | 11894 | Greenview Ave | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.6256
1654 | 0 | 13795 | 13066 | Greenview Ave | Florence St | Verne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5899
1655 | 0 | 13802 | 13434 | Bretton Dr | Edinborough Rd | Huntington Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3919
1656 | 0 | 13808 | 9858 | Prevost St | W Outer Dr | Thatcher St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 231.1618
1657 | 0 | 13815 | 9880 | Canyon Ave | Opal St | Frankfort Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 195.8747
1658 | 0 | 13817 | 9832 | Whitehill St | E Outer Dr | Bonita St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.8291
1660 | 0 | 13823 | 10556 | Moenart St | Rowley St & Lasky Park Entrance | Luce St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.0147
1661 | 0 | 13831 | 12904 | Ward St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.6377
1662 | 0 | 13836 | 13354 | Washburn St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.6191
1664 | 0 | 13847 | 10038 | Huntington Rd | Santa Clara Ave | Curtis St | [6 empty] | 2 | 2020 Carryover | [26 empty] | 455.0132
1665 | 0 | 13873 | 13122 | Florence St | W Outer Dr | Shaftsbury Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.2095
1666 | 0 | 13881 | 11441 | Vaughan St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.5568
1667 | 0 | 13883 | 11938 | Promenade Ave | Barrett St | Roseberry St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.6308
1668 | 0 | 13888 | 12995 | Eldridge Ave | Conant St | Fenelon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 407.7207
1669 | 0 | 13894 | 10911 | University Pl | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 288.2712
1670 | 0 | 13897 | 10079 | Lodewyck St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5659
1671 | 0 | 13909 | 10029 | Moran St | E Davison St | Victoria St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 385.164
1672 | 0 | 13933 | 10420 | Elmo St | Findlay St | Christy St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.5197
1673 | 0 | 13985 | 14048 | Ward St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.3264
1674 | 0 | 13987 | 10920 | Promenade Ave | Park Dr | Dickerson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.0201
1675 | 0 | 14003 | 12475 | Courville St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.08
1677 | 0 | 14028 | 12971 | Tracey St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.8135
1678 | 0 | 14036 | 11385 | Courville St | E Outer Dr | Linville St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.3601
1679 | 0 | 14039 | 10588 | Lodewyck St | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.5767
1680 | 0 | 14046 | 12532 | Buckingham Ave | Southampton St | E Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.611
1681 | 0 | 14050 | 13680 | Sunderland Rd | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.533
1682 | 0 | 14065 | 12037 | Carpenter St | Fenelon St | Commor St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.3496
1683 | 0 | 14073 | 12106 | Longview St | Annsbury Ave | Park Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.4374
1684 | 0 | 14080 | 9883 | Mansfield St | W Outer Dr | Thatcher St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 241.2671
1685 | 0 | 14081 | 9970 | Snowden St | Santa Maria St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.2997
1686 | 0 | 14086 | 12461 | San Juan Dr | Puritan St | W McNichols Rd | [6 empty] | 6 | 2020 Carryover | [26 empty] | 1097.95
1687 | 0 | 14094 | 10059 | Faust Ave | W Outer Dr | Curtis St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 531.8498
1688 | 0 | 14102 | 10090 | Haverhill St | Beaconsfield St | Nottingham Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.2209
1689 | 0 | 14110 | 12891 | Sorrento St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.4107
1690 | 0 | 14124 | 13838 | Fenton St | Grove St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 244.697
1691 | 0 | 14132 | 13642 | Buckingham Ave | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.1569
1692 | 0 | 14135 | 11934 | Evanston St | E Outer Dr | Wayburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 164.0808
1693 | 0 | 14137 | 10432 | Santa Maria St | Forrer St | Winthrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.3264
1694 | 0 | 14152 | 13440 | Appoline St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.3753
1695 | 0 | 14155 | 13528 | Oakfield St | Puritan St | Florence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.7736
1696 | 0 | 14191 | 12397 | Lauder St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 432.64
1697 | 0 | 14210 | 11923 | Sunderland Rd | Grove St | W McNichols Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.4112
1698 | 0 | 14226 | 11967 | Kensington Ave | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1964
1699 | 0 | 14231 | 13947 | Evanston St | Annsbury Ave | Park Dr | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.5213
1700 | 0 | 14233 | 13567 | Bretton Dr | Westmoreland Rd & Lancashire St | Edinborough Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 217.2838
1701 | 0 | 14239 | 10463 | Santa Maria St | Saint Marys St | Mansfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.7325
1702 | 0 | 14241 | 10912 | Wilshire Dr | Dickerson St | Coplin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 346.4412
1703 | 0 | 14247 | 10433 | Forrer St | Santa Maria St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 252.9971
1704 | 0 | 14255 | 10057 | Stoepel St | W McNichols Rd | Santa Maria St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.4562
1705 | 0 | 14264 | 13442 | Florence St | Pierson St | Braile St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.0224
1706 | 0 | 14267 | 11094 | Flanders St | Elmo St | Gunston St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 410.8189
1707 | 0 | 14275 | 13053 | W Parkway St | Verne St | S Riverdale Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 192.3448
1708 | 0 | 14279 | 11446 | Florence St | Parkside St | Wildemere St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0375
1709 | 0 | 14282 | 12059 | Tracey St | Florence St | Grove St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 404.3103
1711 | 0 | 14302 | 19040 | Kendall St | Piedmont St | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.1636
1712 | 0 | 14304 | 18944 | Kendall St | Grandmont Ave | Woodmont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.914
1713 | 0 | 14309 | 18045 | Wildemere St | Waverly | W Davison St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 106.1428
1714 | 0 | 14317 | 17981 | Belvidere St | Cairney St | Gratiot Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 288.1655
1715 | 0 | 14319 | 14334 | Ashton Rd | Pilgrim St | Puritan St & Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3447
1716 | 0 | 14322 | 15836 | Monte Vista St | Fenkell St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.8833
1717 | 0 | 14334 | 15392 | Desoto St | Greenlawn St | Tuller St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 349.0854
1718 | 0 | 14342 | 15531 | Norcross St | Olga St | Hern St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 261.9067
1719 | 0 | 14349 | 16087 | Chalfonte St | Sussex St | Coyle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.4538
1720 | 0 | 14350 | 18136 | Acacia St | Prevost St | Forrer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.8022
1721 | 0 | 14362 | 18987 | Kendall St | Rosemont Ave | Ashton Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.1166
1722 | 0 | 14365 | 17596 | Mettetal St | Lyndon St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 320.2158
1723 | 0 | 14367 | 18492 | Highland St | La Salle Blvd | 14th St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 397.8801
1724 | 0 | 14368 | 17570 | Montville Pl | Glendale St | W Buena Vista St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.6356
1725 | 0 | 14369 | 18378 | Strathmoor St | Intervale St | Lyndon St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 535.5083
1726 | 0 | 14376 | 14468 | Ilene St | Keeler Ave | James Couzens Fwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 262.0079
1727 | 0 | 14417 | 14345 | Avon Rd | Bretton Dr | Scarsdale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 113.9099
1730 | 0 | 14459 | 17050 | Oliver St | City/Twp Line | Mount Elliott St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 553.0066
1731 | 0 | 14471 | 17909 | Stahelin Rd | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.5165
1732 | 0 | 14472 | 16522 | Faust Ave | Chalfonte St | Fenkell St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 371.9064
1734 | 0 | 14532 | 15396 | Lamphere St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.1802
1735 | 0 | 14541 | 15625 | Mansfield St | Fenkell St | Keeler St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 270.123
1737 | 0 | 14557 | 17383 | Rutland St | Monnier Rd | Grand River Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 416.1675
1738 | 0 | 14559 | 14522 | Fielding St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.1485
1739 | 0 | 14571 | 15578 | Winthrop St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.3879
1740 | 0 | 14595 | 15356 | Ashton Rd | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.0679
1741 | 0 | 14600 | 17349 | Faust Ave | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.3496
1742 | 0 | 14601 | 17648 | Rutland St | Lyndon St | Monnier Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 254.2528
1743 | 0 | 14622 | 17575 | La Salle Blvd | W Buena Vista St | Tyler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 126.567
1744 | 0 | 14673 | 15984 | Chalfonte St | Cruse St | Stansbury St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.31
1745 | 0 | 14679 | 18407 | Burlingame St | Hamilton Ave | 3rd St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.6746
1747 | 0 | 14689 | 17024 | Mettetal St | Grand River Ave | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 407.9556
1748 | 0 | 14691 | 15453 | Bretton Dr | Kentford St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.7423
1749 | 0 | 14718 | 14860 | Ashton Rd | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.554
1750 | 0 | 14724 | 18347 | Acacia St | Mettetal St | Saint Marys St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.8615
1751 | 0 | 14729 | 16909 | Whitcomb St | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 394.9807
1754 | 0 | 14770 | 17965 | E Boston Blvd | Brush St | Oakland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.2844
1755 | 0 | 14771 | 16423 | Birwood St | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 340.6488
1756 | 0 | 14791 | 15150 | Ward St | Fenkell St | Keeler Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.965
1757 | 0 | 14812 | 16004 | Chalfonte St | Freeland St | Ardmore St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 111.2124
1758 | 0 | 14814 | 17443 | Strathmoor St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 369.0156
1759 | 0 | 14835 | 18059 | Pennsylvania St | Chapin St | Shoemaker St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 411.4781
1760 | 0 | 14838 | 18468 | Collingwood St | 3rd St | 2nd Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.0239
1761 | 0 | 14841 | 15604 | Fielding St | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.7064
1762 | 0 | 14879 | 16155 | Roselawn St | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.2168
1763 | 0 | 14908 | 14544 | Mansfield St | Midland St | Pilgrim St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 273.1928
1764 | 0 | 14914 | 17081 | Saint Marys St | Grand River | Chalfonte St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 486.9012
1765 | 0 | 14917 | 14568 | Keeler Ave | Steel St | Appoline St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.9825
1767 | 0 | 14939 | 16025 | Chalfonte St | Strathmoor St | Mark Twain St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.8738
1768 | 0 | 14958 | 17921 | Farr St | Klein St | Mount Elliott St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 147.4964
1769 | 0 | 14967 | 18418 | Archdale St | Acacia St | Lyndon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.3874
1770 | 0 | 14976 | 17451 | Vaughan St | Eaton St | W Outer Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 315.8187
1771 | 0 | 14981 | 19057 | Burlingame St | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.6726
1772 | 0 | 14985 | 17080 | Clements St | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.4852
1773 | 0 | 14988 | 14875 | Woodlawn Ave | McClellan St | Raymond Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 504.5649
1775 | 0 | 15025 | 14866 | Gainsborough Rd | Avon Rd | Glastonbury Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 288.95
1776 | 0 | 15062 | 18585 | Sturtevant St | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 421.7111
1777 | 0 | 15080 | 17858 | Ashton Rd | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 348.3346
1779 | 0 | 15094 | 17647 | Lyndon St | Rutland St | Abington Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.3561
1780 | 0 | 15132 | 16894 | Eaton St | Sussex St | Coyle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.4346
1781 | 0 | 15136 | 16022 | Mettetal St | Ellsworth St | Fenkell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 167.6652
1782 | 0 | 15139 | 14980 | Knodell St | Raymond Ave | Armour St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.8045
1784 | 0 | 15159 | 19062 | Cortland St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.7188
1785 | 0 | 15173 | 16082 | Stout St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0052
1786 | 0 | 15203 | 16386 | Chalfonte St | Saint Marys St | Prevost St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 409.8737
1787 | 0 | 15208 | 17841 | Archdale St | Lyndon St | Monnier Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.2098
1788 | 0 | 15261 | 15027 | Midland St | Plainview Ave | Auburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.4069
1789 | 0 | 15265 | 18514 | Clements St | Petoskey Ave | Holmur St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.777
1790 | 0 | 15284 | 17417 | Grandville Ave | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.1751
1791 | 0 | 15291 | 18901 | Mansfield St | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 351.2465
1792 | 0 | 15297 | 18990 | Kenilworth St | John R St | Brush St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.3392
1793 | 0 | 15298 | 14868 | Keeler Ave | Cruse St | Stansbury St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 125.3494
1794 | 0 | 15301 | 16153 | Winthrop St | Chalfonte St | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 332.9214
1795 | 0 | 15302 | 17545 | Prevost St | Grand River Ave | Eaton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 330.4222
1796 | 0 | 15312 | 15180 | Snowden St | Fenkell St | Keeler Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.9528
1797 | 0 | 15313 | 14501 | Heyden St | Pilgrim St | Puritan St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 271.5033
1798 | 0 | 15316 | 18988 | Rosemont Ave | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.5452
1799 | 0 | 15319 | 15612 | Rutherford St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.301
1800 | 0 | 15322 | 15565 | Chalfonte St | Roselawn St | Greenlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 114.292
1801 | 0 | 15324 | 16496 | Clements St | 14th St | Rosa Parks Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.7246
1802 | 0 | 15326 | 18363 | Lyndon St | Bramell St | Chatham St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.773
1804 | 0 | 15354 | 18516 | Acacia St | Piedmont St | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.5508
1805 | 0 | 15361 | 18600 | Sherwood St | Strong St | Miller St | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 727.2148
1806 | 0 | 15385 | 18476 | Pennsylvania St | Barker Ave | Chapin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 231.2063
1807 | 0 | 15420 | 18120 | Montrose St | Acacia St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.9264
1808 | 0 | 15432 | 15588 | Kentfield St | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.7977
1809 | 0 | 15457 | 18454 | Waverly | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 427.4124
1810 | 0 | 15463 | 19001 | Kendall St | Faust Ave | Penrod St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.0743
1811 | 0 | 15478 | 18448 | Klein St | Conant St | Farr St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.0266
1812 | 0 | 15489 | 16876 | Kentfield St | W Outer Dr | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 388.9236
1813 | 0 | 15491 | 15519 | Chalfonte St | Monica St | Santa Rosa Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.5034
1814 | 0 | 15495 | 14514 | Stout St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.6326
1815 | 0 | 15502 | 14346 | Bretton Dr | Warwick St | Avon Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 389.4561
1816 | 0 | 15514 | 19046 | Mark Twain St | Grand River Ave | Intervale St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 507.5274
1817 | 0 | 15528 | 16158 | Holcomb Ave | Georgia St | Marcus Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 326.8705
1818 | 0 | 15537 | 14510 | Traverse St | McClellan St | Raymond Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 504.972
1819 | 0 | 15539 | 15156 | Ellsworth St | Wyoming St | Cherrylawn St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 541.0663
1820 | 0 | 15554 | 15122 | Appoline St | Fenkell St | Keeler Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.6579
1821 | 0 | 15569 | 16638 | Archdale St | Tournier St | Grand River Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 343.7157
1822 | 0 | 15573 | 18622 | Pierson St | Acacia St | Lyndon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.028
1823 | 0 | 15584 | 14973 | Bretton Dr | Glastonbury Ave | Rosemont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 182.1634
1824 | 0 | 15639 | 18518 | Robson St | Grand River Ave | Lyndon St | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 626.6165
1825 | 0 | 15649 | 14584 | Wade St | Conner St | Gunston Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.7981
1826 | 0 | 15677 | 18443 | Rosemont Ave | Acacia St | Lyndon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.2332
1827 | 0 | 15698 | 18634 | Ohio St | Schoolcraft St | Intervale St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 476.5319
1828 | 0 | 15702 | 18897 | Wildemere St | Leslie St | Glendale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.5184
1830 | 0 | 15737 | 15949 | Tracey St | Chalfonte St | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 332.299
1831 | 0 | 15743 | 17432 | Mark Twain St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.5034
1832 | 0 | 15764 | 14499 | Gainsborough Rd | Warwick St | Avon Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.3213
1833 | 0 | 15772 | 15057 | Heyden St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.741
1834 | 0 | 15781 | 18971 | Archdale St | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.3517
1835 | 0 | 15787 | 18379 | Clements St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.0599
1836 | 0 | 15788 | 18958 | Kendall St | Rutland St | Abington Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.4633
1837 | 0 | 15802 | 14610 | Littlefield St | Keeler Ave | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.7348
1838 | 0 | 15822 | 15060 | Winthrop St | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 313.2474
1839 | 0 | 15860 | 16399 | Georgia St | Crane St | Rohns St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.5485
1840 | 0 | 15871 | 14569 | Steel St | Keeler Ave | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.8229
1841 | 0 | 15873 | 16161 | Steel St | Hillview St | Chalfonte St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 225.1233
1842 | 0 | 15882 | 16896 | Clements St | La Salle Blvd | 14th St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 384.6175
1843 | 0 | 15896 | 14967 | Wayburn St | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.0725
1844 | 0 | 15909 | 18654 | Whitcomb St | Kendall St | Grand River Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.9969
1846 | 0 | 15913 | 16874 | Eaton St | Robson St | Terry St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.7789
1847 | 0 | 15915 | 18883 | Montrose St | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.4865
1848 | 0 | 15925 | 18978 | Glendale St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.5241
1849 | 0 | 15931 | 18463 | Coyle St | Grand River Ave | Lyndon St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 567.6906
1850 | 0 | 15948 | 15081 | Pinehurst St | Keeler Ave | Fenkell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.422
1851 | 0 | 15955 | 16860 | Vaughan St | W Outer Dr | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 388.7888
1852 | 0 | 15961 | 16157 | Georgia St | Holcomb Ave | McClellan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.9014
1853 | 0 | 15999 | 19009 | Greenview Rd | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.5263
1854 | 0 | 16003 | 15428 | Desoto St | Cherrylawn St | Greenlawn St | [6 empty] | 3 | 2020 Carryover | [26 empty] | 548.7137
1855 | 0 | 16021 | 16625 | Longacre St | Tournier St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 246.8137
1856 | 0 | 16041 | 15021 | Whitcomb St | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7413
1857 | 0 | 16042 | 14630 | Manistique St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.8191
1858 | 0 | 16044 | 17958 | Pasadena St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.1577
1859 | 0 | 16073 | 15129 | Manistique St | E Warren Ave | Frankfort St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.7907
1861 | 0 | 16075 | 15031 | Prest St | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.875
1862 | 0 | 16110 | 14447 | Whitcomb St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3654
1863 | 0 | 16134 | 18999 | Fullerton St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.4447
1864 | 0 | 16194 | 14609 | Keeler Ave | Littlefield St | Cheyenne St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.4854
1867 | 0 | 16267 | 19063 | Lawton St | Cortland St | Sturtevant St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.0719
1868 | 0 | 16273 | 18364 | Bramell St | Lyndon St | Wanamaker Pl | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 242.974
1869 | 0 | 16275 | 18912 | Saint Marys St | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.1965
1871 | 0 | 16279 | 14437 | Winthrop St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 232.6876
1872 | 0 | 16298 | 18458 | Acacia St | Faust Ave | Penrod St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.2314
1873 | 0 | 16308 | 18967 | Sturtevant St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.6922
1874 | 0 | 16328 | 17404 | Archdale St | Monnier Rd | Tournier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 330.1745
1875 | 0 | 16340 | 14899 | Evanston St | Gunston Ave | Barrett St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.7509
1876 | 0 | 16342 | 15532 | Chalfonte St | San Juan Dr | Prairie St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.7191
1878 | 0 | 16379 | 18461 | Wildemere St | W Buena Vista St | Tyler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.5144
1880 | 0 | 16388 | 15063 | Kentfield St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.2804
1881 | 0 | 16393 | 17881 | Winthrop St | Grand River Ave | Eaton St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 513.8638
1882 | 0 | 16405 | 17631 | Beaverland St | Eaton St | Chalfonte St & Grayfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.5515
1883 | 0 | 16423 | 18561 | Plainview Ave | Acacia St | Lyndon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 365.1987
1884 | 0 | 16432 | 19049 | Hurlbut St | Moffat St | E Warren Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 395.3015
1885 | 0 | 16434 | 19025 | Kendall St | Artesian St | Stahelin Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.4132
1886 | 0 | 16467 | 14592 | Ward St | Keeler Ave | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 278.8214
1888 | 0 | 16487 | 16452 | La Belle St | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.383
1889 | 0 | 16495 | 17501 | Robson St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.6576
1890 | 0 | 16542 | 17972 | Lawrence St | 2nd Blvd | Rosedale Ct & Woodward Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.3266
1892 | 0 | 16561 | 18088 | Whitcomb St | Grand River Ave | Lyndon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 388.4887
1893 | 0 | 16568 | 18921 | Kendall St | Mettetal St | Saint Marys St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.7857
1894 | 0 | 16578 | 16394 | Chalfonte St | Mettetal St | Saint Marys St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.1448
1895 | 0 | 16624 | 18535 | Lawrence St | Hamilton Ave | 3rd St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.4818
1896 | 0 | 16655 | 16968 | Gray St | E Forest Ave | E Warren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.0872
1897 | 0 | 16666 | 16618 | Chalfonte St | Westwood St | Grandville Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.8572
1898 | 0 | 16679 | 16918 | Eaton St | Prest St | Whitcomb St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.0511
1899 | 0 | 16682 | 17346 | Woodland St | Woodward | John R St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.3276
1900 | 0 | 16683 | 17988 | Lakewood St | Mack Ave | Lozier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 297.4036
1901 | 0 | 16690 | 15678 | Bretton Dr | Lancashire St | Bretton Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.0784
1902 | 0 | 16695 | 14432 | Wayburn St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.6215
1903 | 0 | 16702 | 17902 | Glastonbury Ave | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 343.6788
1904 | 0 | 16707 | 15334 | Hartwell St | Fenkell St | Keeler Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.1976
1905 | 0 | 16711 | 16053 | Chalfonte St | Lauder St | Marlowe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.9053
1906 | 0 | 16714 | 16124 | Chalfonte St | Prest St | Whitcomb St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.1419
1907 | 0 | 16721 | 17011 | Kentucky St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 412.2279
1909 | 0 | 16724 | 15364 | Desoto St | Tuller St | Monica St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 355.0619
1910 | 0 | 16746 | 14382 | Evanston St | Norcross St | Annsbury Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 423.4781
1911 | 0 | 16753 | 18070 | Fullerton St | La Salle Blvd | 14th St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 395.9271
1912 | 0 | 16760 | 16014 | Grandville Ave | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5735
1913 | 0 | 16761 | 17920 | Farr St | Mount Elliott St | Consolidated Rail Corporation | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.9621
1914 | 0 | 16762 | 14633 | Hartwell St | Keeler Ave | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.877
1915 | 0 | 16774 | 15504 | Chalfonte St | Stoepel St | Livernois Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.6282
1916 | 0 | 16779 | 16072 | Kentfield St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.0935
1917 | 0 | 16786 | 18417 | Acacia St | Archdale St | Longacre St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 168.0634
1918 | 0 | 16790 | 18644 | Wisconsin St | Schoolcraft St | Intervale St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 476.2894
1919 | 0 | 16810 | 18345 | Acacia St | Mansfield St | Rutherford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.0914
1920 | 0 | 16815 | 17839 | Dwyer St | Farr St | Selkirk St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 92.7044
1921 | 0 | 16825 | 16091 | Fielding St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.0807
1922 | 0 | 16835 | 14546 | Bretton Dr | Avon Rd | Glastonbury Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.0856
1923 | 0 | 16841 | 15389 | Bretton Dr | Kentford St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 104.3886
1924 | 0 | 16872 | 18152 | Lawrence St | 3rd St | 2nd Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.2687
1925 | 0 | 16894 | 18636 | Kenilworth St | Brush St | Oakland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 369.5047
1926 | 0 | 16903 | 15846 | Drexel St | Frankfort St | Southampton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.2184
1927 | 0 | 16904 | 18882 | Kendall St | Montrose St | Winthrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.2375
1928 | 0 | 16911 | 17594 | Kendall St | Livernois Ave | Holmur St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 396.4323
1929 | 0 | 16920 | 17994 | Sturtevant St | 14th St | Rosa Parks Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 290.1677
1930 | 0 | 16934 | 15514 | Grandville Ave | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.8109
1931 | 0 | 16956 | 17540 | Prest St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.8813
1932 | 0 | 16960 | 17087 | Ashton Rd | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.2962
1933 | 0 | 16976 | 15131 | Bretton Dr | Rosemont Ave | Kentford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 179.0542
1934 | 0 | 16977 | 16854 | Eaton St | Lauder St | Marlowe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.6306
1935 | 0 | 16998 | 16980 | Rutherford St | Eaton St | Hackett St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 238.1839
1936 | 0 | 17010 | 17531 | Whitcomb St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 366.1098
1937 | 0 | 17023 | 14478 | Fenton St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.8422
1938 | 0 | 17032 | 14615 | Frankfort St | Manistique St | Alter Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 111.2111
1939 | 0 | 17035 | 17366 | Glastonbury Ave | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.0421
1940 | 0 | 17040 | 15548 | Chalfonte St | Cloverdale St | Turner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.2253
1942 | 0 | 17053 | 18062 | W Grand St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.1146
1944 | 0 | 17081 | 18033 | Clements St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.4447
1945 | 0 | 17113 | 19051 | Burns St | Chapin St | Gratiot Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 200.1697
1946 | 0 | 17143 | 18410 | Lauder St | Intervale St | Lyndon St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 535.5939
1947 | 0 | 17176 | 15049 | Ellsworth St | Monica St | Livernois Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.5795
1948 | 0 | 17177 | 15545 | Prest St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.0377
1949 | 0 | 17185 | 17441 | Montville Pl | W Buena Vista St | Indiandale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.1239
1950 | 0 | 17205 | 15343 | Desoto St | Monica St | Livernois Ave | [6 empty] | 2 | 2020 Carryover | [26 empty] | 357.3666
1951 | 0 | 17222 | 17589 | Lyndon St | Saint Marys St | Mansfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.0012
1952 | 0 | 17227 | 15630 | Washburn St | Chalfonte St | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 343.4016
1953 | 0 | 17254 | 14872 | Lamphere St | Pilgrim St | Puritan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 263.6659
1954 | 0 | 17261 | 18374 | Acacia St | Grandmont Ave | Woodmont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.8348
1955 | 0 | 17275 | 15597 | Stout St | Keeler St | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.5124
1956 | 0 | 17276 | 17051 | Birwood St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 410.6456
1957 | 0 | 17277 | 16063 | Heyden St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.424
1958 | 0 | 17312 | 18934 | Clements St | Livernois Ave | Petoskey Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 442.8215
1959 | 0 | 17326 | 14394 | Bluehill St | Windsor St | Bremen St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8442
1960 | 0 | 17360 | 18471 | Greenview Rd | Acacia St | Lyndon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.9644
1961 | 0 | 17364 | 16498 | Ashton Rd | Chalfonte St | Bretton Dr & Grand River Ave & Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.1277
1962 | 0 | 17368 | 17885 | Faust Ave | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 345.0926
1964 | 0 | 17413 | 16008 | Saint Marys St | Ellsworth St | Fenkell | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 167.0847
1965 | 0 | 17420 | 14448 | Wormer St | Puritan St | Florence St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.6829
1966 | 0 | 17424 | 14378 | Bretton Dr | Warwick St | Avon Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.5033
1967 | 0 | 17428 | 14639 | Bluehill St | Denver St | Gravier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 108.9972
1968 | 0 | 17433 | 16560 | Hartwell St | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 397.1573
1969 | 0 | 17446 | 15061 | Norcross St | Hern St | E I 94 Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 216.6319
1971 | 0 | 17453 | 14952 | Bretton Dr | Glastonbury/Bretton Cutoff | Rosemont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.837
1972 | 0 | 17481 | 18352 | Ashton Rd | Dead End or Start | Lyndon St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 289.603
1973 | 0 | 17534 | 18121 | Dwyer St | Conant St | Farr St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 289.9212
1974 | 0 | 17553 | 16597 | Chalfonte St | Piedmont St | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.9882
1975 | 0 | 17566 | 18421 | Glendale St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 337.1992
1976 | 0 | 17580 | 18460 | W Buena Vista St | Wildemere St | Lawton St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 311.8613
1977 | 0 | 17610 | 16583 | Ferguson St | Grand River Ave | Chalfonte St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 291.2592
1978 | 0 | 17611 | 14558 | Appoline St | Keeler Ave | Midland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.9634
1979 | 0 | 17640 | 18847 | Fullerton St | Lawton St | Linwood | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.6874
1981 | 0 | 17648 | 18083 | Pasadena St | Petoskey Ave | Holmur St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.6197
1982 | 0 | 17651 | 19016 | Kendall St | Glastonbury Ave | Greenview Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.5941
1983 | 0 | 17668 | 15959 | Chalfonte St | Lesure St | Tracey St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.0659
1984 | 0 | 17687 | 14591 | Keeler Ave | Ward St | Sorrento St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.2381
1985 | 0 | 17699 | 16575 | Chalfonte St | Artesian St | Stahelin Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.5741
1986 | 0 | 17704 | 18442 | Acacia St | Rosemont Ave | Southfield Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 211.8678
1988 | 0 | 17717 | 18655 | Collingwood St | Hamilton Ave | 3rd St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.4778
1989 | 0 | 17727 | 18874 | Winthrop St | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.7392
1990 | 0 | 17734 | 17840 | Lyndon St | Archdale St | Longacre St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 167.7879
1992 | 0 | 17760 | 15125 | Ellsworth St | Cherrylawn St | Greenlawn St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 549.2683
1993 | 0 | 17766 | 18381 | Sturtevant St | La Salle Blvd | 14th St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 397.1727
1994 | 0 | 17775 | 17608 | Lyndon St | Asbury Park | Mettetal St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.1183
1997 | 0 | 17937 | 14332 | Gainsborough Rd | W Outer Dr | Warwick St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 385.86
1998 | 0 | 17944 | 15074 | Stout St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.5769
1999 | 0 | 17952 | 15679 | Gilchrist St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5902
2000 | 0 | 17977 | 15022 | Washburn St | Fenkell St | Keeler Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.4538
2001 | 0 | 18016 | 18870 | Bramell St | Ray St | Malta St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 212.7143
2002 | 0 | 18048 | 16505 | Chalfonte St | Rosemont Ave | Ashton Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.7213
2003 | 0 | 18073 | 14466 | Prest St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.2851
2004 | 0 | 18078 | 17354 | W Grand St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.5006
2005 | 0 | 18083 | 16609 | Grandville Ave | Chalfonte St | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.5268
2006 | 0 | 18147 | 16125 | Prest St | Chalfonte St | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.9476
2007 | 0 | 18155 | 16838 | Plainview Ave | W Outer Dr | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 387.3335
2008 | 0 | 18160 | 17644 | Clements St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.3751
2010 | 0 | 18186 | 16336 | Chalfonte St | Forrer St | Winthrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 153.8642
2012 | 0 | 18192 | 15459 | Desoto St | Wyoming St | Cherrylawn St | [6 empty] | 3 | 2020 Carryover | [26 empty] | 541.2049
2013 | 0 | 18195 | 15051 | Frankfort St | Chalmers St | Marlborough St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.1892
2014 | 0 | 18209 | 15535 | Whitcomb St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.3115
2015 | 0 | 18221 | 15677 | Bretton Dr | Keeler St | Bretton Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 198.0465
2016 | 0 | 18245 | 18848 | Lawton St | Fullerton St | Leslie St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.8692
2017 | 0 | 18249 | 17359 | W Buena Vista St | Ellen St | Rosa Parks Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.474
2018 | 0 | 18253 | 15682 | Pinehurst St | Fenkell St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.5789
2019 | 0 | 18265 | 18579 | Glendale St | Wildemere St | Lawton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 313.5079
2020 | 0 | 18272 | 16555 | Chalfonte St | Glastonbury Ave | Greenview Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.5156
2021 | 0 | 18275 | 16919 | Prest St | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 395.1477
2022 | 0 | 18279 | 15066 | Lakeview St | Southampton St | Chandler Park Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.4046
2023 | 0 | 18280 | 16062 | Chalfonte St | Robson St | Terry St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.42
2024 | 0 | 18287 | 15160 | Bretton Dr | Rosemont Ave | Kentford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 184.8822
2025 | 0 | 18295 | 15431 | Holmur St | Chalfonte St | Fenkell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 319.5958
2026 | 0 | 18317 | 15110 | Mansfield St | Keeler St | Midland St | [6 empty] | 1 | 2020 Carryover | [26 empty] | 272.9619
2028 | 0 | 18381 | 18027 | Burlingame St | 3rd St | 2nd Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.5327
2029 | 0 | 18396 | 15092 | Ellsworth St | Greenlawn St | Tuller St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 348.6515
2032 | 0 | 18440 | 15897 | Cheyenne St | Chalfonte St | Fenkell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.753
2033 | 0 | 18497 | 18393 | Acacia St | Rutland St | Abington Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.3174
2034 | 0 | 18498 | 16106 | Whitcomb St | Chalfonte St | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.892
2036 | 0 | 18515 | 17657 | Burlingame St | 2nd Blvd | Woodward Ave & Englewood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.4164
2037 | 0 | 18526 | 15636 | Saint Marys St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.0065
2038 | 0 | 18536 | 18119 | Acacia St | Montrose St | Winthrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.3606
2039 | 0 | 18537 | 18483 | Fullerton St | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 421.7747
2041 | 0 | 18554 | 18110 | E Boston Blvd | John R St | Brush St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.9874
2042 | 0 | 18555 | 14412 | Lauder St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.0075
2043 | 0 | 18556 | 14632 | Keeler Ave | Hartwell St | Snowden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.6032
2044 | 0 | 18559 | 15667 | Chalfonte St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.8458
2045 | 0 | 18568 | 18899 | Kendall St | Prevost St | Forrer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.0773
2047 | 0 | 18582 | 16651 | Auburn St | W Outer Dr | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 386.0569
2048 | 0 | 18586 | 16986 | Mansfield St | Eaton St | Hackett St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 232.3417
2049 | 0 | 18595 | 16950 | Winthrop St | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 394.6808
2050 | 0 | 18601 | 14983 | Grandville Ave | Midland St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.4732
2051 | 0 | 18610 | 18481 | Acacia St | Glastonbury Ave | Greenview Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.5373
2052 | 0 | 18617 | 17393 | Longacre St | Monnier Rd | Tournier St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.3709
2053 | 0 | 18626 | 15924 | Hartwell St | Chalfonte St | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.0639
2054 | 0 | 18631 | 17472 | Clements St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.6105
2055 | 0 | 18633 | 18399 | Marlowe St | Intervale St | Lyndon St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 535.8691
2057 | 0 | 18671 | 18970 | Kendall St | Archdale St | Longacre St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 167.9385
2058 | 0 | 18697 | 18386 | Sussex St | Grand River Ave | Lyndon St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 488.8102
2059 | 0 | 18754 | 18145 | E Boston Blvd | John R St | Brush St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.1073
2060 | 0 | 18755 | 18919 | Kendall St | Mansfield St | Rutherford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.7185
2063 | 0 | 18831 | 17628 | Lyndon St | Grandmont Ave | Woodmont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.4638
2064 | 0 | 18840 | 16484 | Peter Hunt St | May St | Robert St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.67
2065 | 0 | 18841 | 16521 | Chalfonte St | Faust Ave | Penrod St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.706
2066 | 0 | 18847 | 14518 | Pinehurst St | Midland St | Keeler Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.7194
2067 | 0 | 18857 | 15673 | Biltmore St | Fenkell St | Keeler St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5367
2069 | 0 | 18902 | 16574 | Tracey St | Eaton St | Chalfonte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 396.867
2070 | 0 | 18907 | 17936 | E Boston Blvd | Brush St | Oakland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.0357
2071 | 0 | 18910 | 18498 | Acacia St | Artesian St | Stahelin Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.5832
2072 | 0 | 18932 | 14574 | Bretton Dr | Avon Rd | Glastonbury Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 327.1683
2073 | 0 | 18942 | 16870 | Heyden St | W Outer Dr | Fenkell St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 388.7858
2074 | 0 | 18946 | 14458 | Auburn St | Pilgrim St | Grand River Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 208.106
2075 | 0 | 18966 | 18596 | Roselawn St | Schoolcraft St | Intervale St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 477.8431
2076 | 0 | 19036 | 16972 | Roselawn St | Lyndon St | Eaton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 410.8817
2077 | 0 | 19044 | 14390 | Strathmoor St | Midland St | Pilgrim St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.0619
2078 | 0 | 19050 | 15069 | Ellsworth St | Tuller St | Monica St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.7729
2079 | 0 | 19071 | 19852 | Artesian St | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.3425
2080 | 0 | 19078 | 20545 | Elmhurst St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.7977
2081 | 0 | 19103 | 21916 | Woodrow Wilson St | Taylor St | Clairmount St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.7617
2083 | 0 | 19139 | 22408 | Hartwell St | Capitol St | Foley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 299.8657
2084 | 0 | 19150 | 22426 | E Bethune St | Beaubien St | Saint Antoine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 208.1585
2086 | 0 | 19198 | 22367 | Smith St | Brush St | Beaubien St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.7209
2087 | 0 | 19199 | 19998 | W Davison St | Montrose St | Winthrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.1905
2089 | 0 | 19212 | 22363 | Maxwell St | Norvell Ct | Manila St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.9869
2090 | 0 | 19239 | 21019 | Edison St | Woodrow Wilson St | Byron St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.0335
2091 | 0 | 19241 | 23644 | Cedarlawn St | Mendota St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 290.7116
2092 | 0 | 19256 | 23599 | Farnsworth St | Elmwood St | Moran St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 298.5628
2093 | 0 | 19344 | 23609 | Stahelin Ave | Wadsworth St | Dead End or Start | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 218.3822
2095 | 0 | 19403 | 23402 | Delaware St | Bethune Ct | 3rd St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 263.4144
2096 | 0 | 19420 | 19105 | Wildemere St | Sturtevant St | Fullerton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.9951
2097 | 0 | 19421 | 22855 | Capitol St | Rutherford St | Forrer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.3325
2098 | 0 | 19437 | 21929 | Glendale St | W Parkway St | Beaverland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 124.7403
2099 | 0 | 19439 | 23129 | Wadsworth St | Hubbell St | Strathmoor St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.0803
2101 | 0 | 19468 | 19457 | Prevost St | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 348.7809
2102 | 0 | 19471 | 21006 | Melbourne St | Beaubien St | Kingsley Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 208.1427
2103 | 0 | 19479 | 22548 | Lenox St | E Jefferson Ave | Kercheval St | [6 empty] | 5 | 2020 Carryover | [26 empty] | 892.4644
2104 | 0 | 19494 | 23563 | Theodore St | Ellery St | Moran St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 198.926
2105 | 0 | 19508 | 20958 | Baldwin St | Frederick St | E Kirby St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.1709
2106 | 0 | 19534 | 19351 | Fielding St | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.2615
2107 | 0 | 19557 | 20993 | Glendale St | Abington Ave | Grandmont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.5593
2108 | 0 | 19562 | 22952 | E Bethune St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.7279
2109 | 0 | 19568 | 21853 | Abington Ave | Fullerton St | Glendale St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.6213
2110 | 0 | 19576 | 20480 | Petoskey Ave | Cortland St | Sturtevant St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.1924
2111 | 0 | 19578 | 19382 | Kenilworth St | Woodward Ave | John R St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.016
2112 | 0 | 19582 | 20360 | Collingwood St | La Salle Blvd | 14th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 160.6967
2113 | 0 | 19583 | 20865 | Woodrow Wilson St | Longfellow St | Chicago Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 143.3478
2114 | 0 | 19647 | 19565 | Sturtevant St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 427.8646
2115 | 0 | 19655 | 20434 | Prest St | Tyler St | Schoolcraft St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 497.5122
2116 | 0 | 19659 | 19469 | Cortland St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.5092
2117 | 0 | 19660 | 23414 | Hurlbut St | Charlevoix St | Goethe Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 433.9559
2118 | 0 | 19690 | 20563 | Fullerton St | Old Mill Pl | Broadstreet Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.0535
2119 | 0 | 19692 | 21069 | Webb St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 427.0778
2120 | 0 | 19749 | 20457 | Longfellow St | Byron St | S M 10 Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 188.1321
2122 | 0 | 19771 | 19408 | Indiana St | W Davison St | Schoolcraft St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.5426
2123 | 0 | 19813 | 22516 | E Bethune St | Brush St | Beaubien St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.7494
2124 | 0 | 19845 | 20076 | Wildemere St | Elmhurst St | Monterey St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 141.2205
2125 | 0 | 19849 | 22531 | Hurlbut St | Goethe Ave | Mack Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.1926
2127 | 0 | 19885 | 19966 | Alger St | Beaubien St | Oakland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 390.1139
2128 | 0 | 19897 | 22378 | Chandler St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.8239
2129 | 0 | 19938 | 23406 | Wadsworth St | Prest St | Whitcomb St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.0861
2130 | 0 | 19941 | 20965 | Atkinson St | Byron St | Hamilton | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.4825
2132 | 0 | 19957 | 19560 | Archdale St | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.4195
2134 | 0 | 19992 | 21375 | Glynn Ct | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.3711
2135 | 0 | 20012 | 21866 | Memorial St | Fullerton St | Glendale St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.2393
2136 | 0 | 20020 | 23430 | Montrose St | Wadsworth St | Capitol St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.4909
2137 | 0 | 20034 | 19427 | Pennsylvania St | E Warren Ave | Moffat St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 393.457
2138 | 0 | 20041 | 23045 | Wadsworth St | Shirley Ave | Schaefer Hwy | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 483.967
2139 | 0 | 20085 | 21587 | Lawrence St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 427.1171
2140 | 0 | 20098 | 22456 | Helen St | E Warren Ave | Theodore St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.7304
2142 | 0 | 20111 | 20012 | Rohns St | E Warren Ave | Moffat St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 417.4208
2143 | 0 | 20143 | 22911 | Castleton St | Shirley Ave | Schaefer Hwy | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 484.3563
2144 | 0 | 20211 | 21992 | W Philadelphia St | 3rd St | 2nd Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.691
2145 | 0 | 20220 | 19595 | Greenview Rd | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.8519
2146 | 0 | 20250 | 20408 | Archdale St | W Davison St | Schoolcraft St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 349.0909
2147 | 0 | 20266 | 23452 | Field St | E Canfield St | E Forest Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.0989
2148 | 0 | 20278 | 21950 | W Euclid St | Second Ave | Woodward Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.9102
2149 | 0 | 20297 | 23109 | Maxwell St | Sylvester St | Ruedisale Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.5329
2150 | 0 | 20323 | 21014 | Rutland St | Glendale St | W Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.1387
2151 | 0 | 20341 | 21510 | Maxwell St | Willard St | E Warren Ave & Maxwell Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.1597
2152 | 0 | 20372 | 23555 | Bethune Ct | W Bethune St | Pallister St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.2171
2153 | 0 | 20397 | 20357 | Grandmont Ave | W Davison St | Schoolcraft St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 337.2976
2154 | 0 | 20407 | 20975 | Seminole St | E Warren Ave | Moffat St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 417.2869
2155 | 0 | 20452 | 19419 | Richton St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 340.1342
2156 | 0 | 20472 | 20046 | W Davison St | Saint Marys St | Mansfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.2138
2157 | 0 | 20476 | 22538 | Chandler St | Woodward Ave & Delaware St | John R St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.3428
2158 | 0 | 20488 | 23024 | Lakewood St | Freud St | E Jefferson Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 499.1037
2159 | 0 | 20492 | 23368 | Petoskey Ave | W Boston Blvd | Collingwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.0251
2160 | 0 | 20493 | 23471 | Helen St | Garfield St | E Forest Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 186.3813
2162 | 0 | 20596 | 23422 | Winthrop St | Wadsworth St | Capitol St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.78
2163 | 0 | 20601 | 21036 | Archdale St | Glendale St | W Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.0617
2164 | 0 | 20610 | 20429 | Webb St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 349.6202
2166 | 0 | 20692 | 20961 | Glendale St | Mettetal St | Saint Marys St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.1338
2167 | 0 | 20724 | 22051 | Seyburn St | E Forest Ave | E Warren Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.6573
2168 | 0 | 20737 | 23046 | Shirley Ave | Wadsworth St | Castleton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.0973
2169 | 0 | 20741 | 21485 | Marston St | Beaubien St | Oakland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 389.5047
2170 | 0 | 20757 | 20900 | Iroquois St | E Warren Ave | Moffat St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 417.2834
2172 | 0 | 20777 | 20353 | Atkinson St | 3rd St | 2nd Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.8556
2173 | 0 | 20778 | 20049 | Leslie St | Broadstreet Ave | Petoskey Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 463.3367
2174 | 0 | 20789 | 20466 | Fullerton St | Broadstreet Ave | Petoskey Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 462.9099
2175 | 0 | 20815 | 19891 | Elmhurst St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 344.9259
2176 | 0 | 20876 | 19442 | Montrose St | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.3504
2177 | 0 | 20887 | 21090 | Lawrence St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.4269
2178 | 0 | 20890 | 19388 | Monterey St | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 419.998
2179 | 0 | 20893 | 19086 | Plainview Ave | Kendall St | Acacia St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.5084
2180 | 0 | 20911 | 20495 | W Boston Blvd | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.9857
2181 | 0 | 20930 | 20994 | Abington Ave | Glendale St | W Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.2487
2182 | 0 | 20937 | 20906 | Fullerton St | Livernois | Old Mill Pl | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 160.7822
2183 | 0 | 20941 | 22416 | Seward St | Virginia Park Ct | Woodward Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 108.8976
2184 | 0 | 21008 | 19588 | Richton St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.4842
2186 | 0 | 21045 | 19947 | Lawrence St | La Salle Blvd | 14th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 225.0752
2187 | 0 | 21062 | 23065 | Collingwood St | Broadstreet Ave | N Martindale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 139.1274
2189 | 0 | 21077 | 19975 | Longfellow St | Hamilton Ave | 3rd St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.7372
2191 | 0 | 21119 | 21585 | Marston St | Brush St | Beaubien St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.8415
2192 | 0 | 21138 | 21365 | Gladstone St | 3rd St | 2nd Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.9709
2193 | 0 | 21142 | 20944 | Glynn Ct | La Salle Blvd | 14th St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 337.2926
2194 | 0 | 21149 | 23365 | W Philadelphia St | Woodrow Wilson St | Byron St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.1867
2195 | 0 | 21154 | 21357 | Mount Vernon St | Beaubien St | Kingsley Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 208.29
2196 | 0 | 21170 | 20976 | Crane St | E Forest Ave | E Warren Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.1701
2197 | 0 | 21179 | 19426 | Fullerton St | Dexter | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.5881
2198 | 0 | 21231 | 22899 | Seneca St | Sylvester St | E Canfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.2555
2199 | 0 | 21245 | 21505 | Northlawn St | Cortland St | Fullerton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.4462
2200 | 0 | 21254 | 19901 | Cortland St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 427.7256
2201 | 0 | 21272 | 21095 | Burns St | Mack | E Warren Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.2348
2202 | 0 | 21304 | 21848 | Grandmont Ave | Fullerton St | Glendale St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 351.8376
2203 | 0 | 21307 | 23485 | W Euclid St | Woodrow Wilson St | Byron St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.0843
2204 | 0 | 21311 | 22421 | W Philadelphia St | N M 10 Service Drive | 3rd St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.7208
2205 | 0 | 21315 | 23403 | Bethune Ct | Pallister St | Delaware St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.2575
2206 | 0 | 21322 | 23432 | Pingree St | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 323.6965
2207 | 0 | 21338 | 19589 | Wildemere St | Richton St | Cortland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.8827
2208 | 0 | 21365 | 23407 | Prest St | Wadsworth St | Castleton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 228.9225
2209 | 0 | 21371 | 21545 | Kentucky St | Cortland St | Fullerton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.7441
2210 | 0 | 21397 | 20368 | Abington Ave | W Davison St | Schoolcraft St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.2023
2211 | 0 | 21406 | 21941 | Dale St | Glendale St | W Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 369.1367
2212 | 0 | 21424 | 20066 | Bramell St | Schoolcraft St | Kendall St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.9956
2213 | 0 | 21434 | 21606 | Atkinson St | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.0733
2214 | 0 | 21442 | 22369 | Washburn St | Grand River Ave | Fullerton St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 540.8852
2215 | 0 | 21522 | 21851 | Maxwell St | E Forest Ave | Willard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.1435
2216 | 0 | 21562 | 23121 | Strathmoor St | Wadsworth St | Capitol St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 327.7074
2218 | 0 | 21634 | 23571 | Seward St | Merrill St | Hamilton | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 261.8453
2219 | 0 | 21662 | 20992 | Indiana St | Fullerton St | W Buena Vista St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 438.7128
2220 | 0 | 21695 | 20035 | W Boston Blvd | Woodrow Wilson St | S M 10 Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.5589
2221 | 0 | 21812 | 21385 | Woodrow Wilson St | Atkinson St | Edison St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.9721
2222 | 0 | 21817 | 23032 | Seward St | 3rd St | 2nd Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.7507
2223 | 0 | 21846 | 20540 | Lawton St | Burlingame St | Webb St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.5284
2224 | 0 | 21886 | 21477 | Melbourne St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.0407
2225 | 0 | 21902 | 23404 | Fischer Ave | Mack Ave | Sylvester St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 453.5697
2226 | 0 | 21917 | 20986 | Grandmont Ave | Glendale St | W Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.4125
2227 | 0 | 21933 | 20000 | W Boston Blvd | Woodrow Wilson St | S M 10 Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.8787
2228 | 0 | 21938 | 21856 | Chandler St | Beaubien St | Oakland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 389.59
2229 | 0 | 21956 | 23453 | Wadsworth St | Rutherford St | Forrer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.4414
2230 | 0 | 21964 | 19847 | Stahelin Rd | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.998
2231 | 0 | 21983 | 20978 | Glendale St | Woodmont Ave | Asbury Park | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.7434
2232 | 0 | 22095 | 20384 | Hague St | Beaubien St | Oakland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 390.1046
2233 | 0 | 22166 | 20930 | W Boston Blvd | 14th St | Rosa Parks Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 409.9808
2234 | 0 | 22178 | 21536 | W Boston Blvd | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.6133
2235 | 0 | 22182 | 21017 | Mount Vernon St | Kingsley Ct | Oakland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 180.9049
2236 | 0 | 22195 | 20983 | E Philadelphia St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.9894
2237 | 0 | 22204 | 23633 | Helen St | E Canfield St | Garfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 166.6838
2238 | 0 | 22257 | 23351 | Wadsworth St | Lauder St | Marlowe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.3946
2239 | 0 | 22282 | 21958 | Chandler St | Brush St | Beaubien St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.8722
2240 | 0 | 22291 | 20015 | Tuxedo St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.2027
2241 | 0 | 22296 | 20886 | Melbourne St | Kingsley Ct | Oakland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 182.0262
2242 | 0 | 22311 | 21001 | Memorial St | Glendale St | W Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.2912
2243 | 0 | 22340 | 19585 | Longfellow St | 3rd St | 2nd Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.5714
2245 | 0 | 22354 | 22495 | Fischer Ave | Sylvester St | E Canfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.8959
2246 | 0 | 22374 | 19943 | Fullerton St | Petoskey Ave | Holmur St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 234.26
2247 | 0 | 22379 | 23083 | W Euclid St | Byron St | S M 10 Service Drive | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.6956
2249 | 0 | 22397 | 23387 | Sussex | Wadsworth St | Castleton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 229.2084
2250 | 0 | 22398 | 20520 | Burns St | E Warren Ave | Moffat St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 416.9888
2251 | 0 | 22422 | 20948 | W Boston Blvd | 14th St | Rosa Parks Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 410.4822
2252 | 0 | 22423 | 22883 | Maxwell St | Sprague Ave | E Canfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.4774
2253 | 0 | 22455 | 21013 | Glendale St | Rutland St | Memorial St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.1733
2254 | 0 | 22484 | 23020 | Hartwell St | Wadsworth St | Capitol St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 289.322
2255 | 0 | 22535 | 21051 | Dale St | W Davison St | Schoolcraft St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 222.1603
2256 | 0 | 22553 | 19907 | Plainview Ave | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.792
2257 | 0 | 22589 | 21999 | Smith St | Beaubien St | Saint Antoine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 208.0356
2258 | 0 | 22597 | 19989 | Iroquois St | Moffat St | Gratiot Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 427.9975
2259 | 0 | 22606 | 21065 | Lawton St | Collingwood St | Lawrence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.3525
2260 | 0 | 22613 | 19944 | Petoskey Ave | Fullerton St | Leslie St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.318
2261 | 0 | 22614 | 20941 | Tuxedo St | Dexter | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.8303
2262 | 0 | 22626 | 22573 | Seward St | 2nd Ave | Virginia Park Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.046
2263 | 0 | 22641 | 19409 | Whitcomb St | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.4148
2264 | 0 | 22642 | 20387 | Baldwin St | E Ferry St | E Palmer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.9636
2265 | 0 | 22658 | 20388 | W Davison St | Rutland St | Memorial St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.7181
2266 | 0 | 22722 | 21087 | W Boston Blvd | La Salle Blvd | 14th St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 335.9078
2267 | 0 | 22765 | 19405 | Bramell St | S Kane St | Ray St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.8045
2269 | 0 | 22799 | 19434 | Winthrop St | Schoolcraft St | Kendall St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 347.4875
2270 | 0 | 22804 | 20407 | W Davison St | Archdale St | Longacre St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.6902
2271 | 0 | 22808 | 19429 | Rohns St | Moffat St | Chapin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 405.3191
2273 | 0 | 22830 | 20570 | Edison St | Byron St | S M 10 Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 293.247
2274 | 0 | 22869 | 20072 | W Buena Vista St | Birwood St | Griggs St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.6478
2275 | 0 | 22892 | 23536 | W Boston Blvd | N Martindale St | Otsego St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 160.3323
2277 | 0 | 22936 | 23634 | Virginia Park St | Woodrow Wilson St | Byron St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.3814
2278 | 0 | 22968 | 23382 | Sheridan St | E Canfield St | E Forest Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 350.6807
2279 | 0 | 22974 | 21957 | Melrose St | Custer St | Clay St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 288.5521
2280 | 0 | 22979 | 21468 | Byron St | Taylor St | Clairmount St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.8798
2281 | 0 | 22983 | 21974 | Marston St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.8258
2282 | 0 | 22984 | 22542 | Smith St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.8005
2284 | 0 | 23047 | 21035 | Glendale St | Archdale St | Longacre St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.431
2285 | 0 | 23078 | 23429 | Wadsworth St | Montrose St | Winthrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.9926
2286 | 0 | 23083 | 23385 | Virginia Park St | Merrill St | Virginia Park St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 198.4976
2287 | 0 | 23084 | 20864 | Longfellow St | Woodrow Wilson St | Byron St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.889
2288 | 0 | 23085 | 20343 | W Davison St | Woodmont Ave | Asbury Park | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.1027
2289 | 0 | 23150 | 21621 | Fischer Ave | E Canfield St | E Forest Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 339.8091
2290 | 0 | 23188 | 20472 | W Boston Blvd | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.88
2291 | 0 | 23222 | 23361 | Wadsworth St | Robson St | Terry St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.3216
2292 | 0 | 23231 | 20578 | Webb St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.4774
2293 | 0 | 23237 | 20018 | W Davison St | Rutherford St | Forrer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.6151
2294 | 0 | 23241 | 20075 | Elmhurst St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.6313
2295 | 0 | 23259 | 21384 | Atkinson St | Woodrow Wilson St | Byron St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.289
2296 | 0 | 23263 | 19104 | Sturtevant St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.5815
2297 | 0 | 23286 | 21058 | Hurlbut St | E Canfield St | Sylvester St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 406.9041
2299 | 0 | 23302 | 21960 | Glendale St | Bramell St | Chatham St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 165.1556
2300 | 0 | 23361 | 19982 | Collingwood St | 14th St | Rosa Parks Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 403.7634
2301 | 0 | 23399 | 23610 | Hartwell St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.8896
2302 | 0 | 23450 | 20367 | W Davison St | Abington Ave | Grandmont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.6542
2303 | 0 | 23497 | 19985 | Winthrop St | Schoolcraft St | W Davison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.4079
2304 | 0 | 23500 | 22493 | Hazelwood St | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 322.7668
2306 | 0 | 23504 | 21360 | W Boston Blvd | La Salle Blvd | 14th St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 335.8359
2307 | 0 | 23533 | 19848 | Lawrence St | 14th St | Rosa Parks Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 339.4907
2308 | 0 | 23556 | 23456 | Theodore St | Mount Elliott St | Ellery St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 316.0561
2309 | 0 | 23569 | 19871 | Burns St | Moffat St | Chapin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 405.8426
2310 | 0 | 23593 | 21539 | Indiana St | Cortland St | Fullerton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.4674
2311 | 0 | 23594 | 19398 | Longfellow St | 2nd Blvd | Woodward Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.8437
2312 | 0 | 23671 | 23386 | Wadsworth St | Sussex | Coyle St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.8395
2313 | 0 | 23685 | 20011 | Richton St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.5016
2315 | 0 | 23706 | 21577 | W Boston Blvd | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.6341
2316 | 0 | 23739 | 20453 | Leslie St | Old Mill Pl | Broadstreet Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.3858
2317 | 0 | 23768 | 23001 | Collingwood St | N Martindale St | Petoskey Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 332.6816
2318 | 0 | 23807 | 20523 | Glynn Ct | 14th St | Rosa Parks Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 403.2251
2319 | 0 | 23816 | 23363 | Seward St | N M 10 Service Drive | 3rd St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 254.9686
2320 | 0 | 23831 | 24415 | Steel St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.5064
2321 | 0 | 23846 | 27002 | Columbus St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 408.7991
2322 | 0 | 23877 | 24082 | Algonquin | Freud St | E Jefferson Ave | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 756.3188
2323 | 0 | 23897 | 27030 | Montgomery St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.6009
2324 | 0 | 23907 | 25635 | Woodrow Wilson St | W Grand Blvd | W Bethune St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 403.8724
2325 | 0 | 23912 | 26624 | Piedmont St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.3061
2326 | 0 | 23930 | 25574 | Algonquin | Avondale St | Essex Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.2924
2327 | 0 | 23932 | 25645 | Abington Ave | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.6255
2328 | 0 | 23936 | 28594 | Seyburn St | Van Dyke Pl | E Lafayette St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.2324
2329 | 0 | 23957 | 27439 | Hogarth St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 405.4
2330 | 0 | 23971 | 27979 | Pacific St | Firwood St | Turner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 210.9423
2331 | 0 | 23973 | 27887 | Iroquois St | E Lafayette St | Agnes St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 289.2786
2332 | 0 | 23986 | 23915 | Seward St | Poe St | Merrill St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.0227
2333 | 0 | 23995 | 27080 | Ashton Ave | Westfield St | Fitzpatrick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.249
2334 | 0 | 24004 | 26439 | Riverside Dr | Scripps St | Korte St & Drexel St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 417.8915
2335 | 0 | 24005 | 23956 | Sussex | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.3833
2336 | 0 | 24044 | 26506 | Seyburn St | E Vernor Hwy | Charlevoix St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.615
2338 | 0 | 24058 | 27904 | Vaughan St | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.2398
2339 | 0 | 24067 | 26921 | Vaughan St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.8004
2340 | 0 | 24070 | 24497 | Auburn St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.6552
2341 | 0 | 24082 | 28037 | Hartwell St | Joy Rd | Ellis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 340.9557
2342 | 0 | 24092 | 26465 | Mettetal St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 369.8263
2343 | 0 | 24100 | 26100 | Pierson St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.9637
2345 | 0 | 24105 | 25860 | Holmur St | Blaine St | Carter St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.9631
2346 | 0 | 24133 | 24574 | Avondale St | Newport St | Lakewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.8308
2347 | 0 | 24134 | 27877 | Cloverlawn St | Joy Rd | Stawell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.9156
2348 | 0 | 24147 | 26617 | Warwick St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.5383
2349 | 0 | 24176 | 28384 | Beechwood St | Pacific St | Oregon St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.6582
2350 | 0 | 24194 | 27399 | Plainview Ave | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.545
2351 | 0 | 24196 | 27868 | Roselawn St | Joy Rd | Stawell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.2242
2352 | 0 | 24216 | 26903 | Wildemere St | Whitney St | Columbus St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.6387
2353 | 0 | 24217 | 27614 | Stahelin Ave | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 256.7333
2354 | 0 | 24218 | 25136 | Westwood | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.8553
2355 | 0 | 24224 | 27421 | Townsend St | Kercheval St | E Vernor Hwy | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.775
2356 | 0 | 24239 | 25555 | Goethe Ave | Field St | Sheridan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.2754
2357 | 0 | 24262 | 26009 | La Salle Blvd | Lamothe St | S La Salle Gdns | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 198.2875
2359 | 0 | 24270 | 27475 | 15th St | Marquette St | Ferry Park St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 282.063
2360 | 0 | 24277 | 26959 | Iroquois St | Saint Paul St | Kercheval St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.746
2361 | 0 | 24278 | 27616 | Wildemere St | W Grand Blvd | Lothrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 169.6119
2362 | 0 | 24295 | 25946 | Beechwood St | Greenway St | Ridgewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.1561
2363 | 0 | 24299 | 26039 | Decatur St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 378.6262
2364 | 0 | 24306 | 27673 | Grandville Ave | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 258.9136
2365 | 0 | 24319 | 24986 | Iroquois St | Charlevoix St | Goethe Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.7695
2366 | 0 | 24323 | 26049 | Vaughan St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 368.0137
2367 | 0 | 24331 | 27361 | Grandville Ave | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.3856
2368 | 0 | 24360 | 28076 | Baldwin St | Agnes St | Saint Paul St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.522
2369 | 0 | 24373 | 26443 | Beals St | E Vernor Hwy | Charlevoix St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.011
2370 | 0 | 24422 | 23990 | Winthrop St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.6979
2371 | 0 | 24469 | 25976 | Cheyenne St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.8832
2372 | 0 | 24476 | 25384 | Vaughan St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 352.9778
2373 | 0 | 24477 | 26411 | Wildemere St | Montgomery St | Vicksburg St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.0701
2374 | 0 | 24513 | 25010 | Archdale St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.9785
2375 | 0 | 24514 | 24948 | Piper Blvd | Avondale St | Averhill Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 161.0443
2376 | 0 | 24583 | 26908 | Joseph Campau St | Leland St | E Alexandrine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 127.1258
2377 | 0 | 24621 | 25372 | Field St | Preston St | Mack Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 184.9958
2378 | 0 | 24632 | 26917 | Robson St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 288.377
2381 | 0 | 24643 | 26859 | Grandville Ave | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.1986
2382 | 0 | 24650 | 28491 | Vancouver St | Northfield St | Ironwood St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 464.8801
2383 | 0 | 24655 | 27940 | Patton St | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.9673
2384 | 0 | 24663 | 27124 | Columbus St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.3939
2386 | 0 | 24696 | 27507 | Trinity St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 280.2077
2387 | 0 | 24722 | 27924 | Burns St | E Jefferson Ave | Agnes St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 436.1414
2388 | 0 | 24730 | 26877 | Whitfield St | Northfield St | Beechwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 326.9902
2389 | 0 | 24733 | 27535 | Dawes St | Wyoming St | Stawell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.6489
2390 | 0 | 24735 | 26014 | E Palmer St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 299.2182
2391 | 0 | 24739 | 27627 | Artesian St | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.2512
2393 | 0 | 24760 | 25131 | Grandville Ave | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.0677
2394 | 0 | 24783 | 24860 | Averhill Ct | Drexel St | New Town St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 76.8442
2395 | 0 | 24785 | 28069 | Dover St | Greenview Ave | Faust Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.6756
2396 | 0 | 24788 | 27427 | Heyden St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.7185
2398 | 0 | 24820 | 24569 | Lauder St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.5168
2399 | 0 | 24951 | 27016 | Hogarth St | Wildemere St | Lawton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.7228
2400 | 0 | 24953 | 25527 | E Palmer St | Beaubien St | Saint Antoine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 207.6765
2402 | 0 | 24964 | 24125 | W Euclid St | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 323.7618
2404 | 0 | 24976 | 27113 | Stahelin Ave | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.5471
2405 | 0 | 24980 | 27551 | Field St | Kercheval St | E Vernor Hwy | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.092
2406 | 0 | 25009 | 26870 | Westwood | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.1068
2408 | 0 | 25070 | 27907 | Agnes St | Parker St | Van Dyke St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 166.1602
2409 | 0 | 25073 | 25107 | Korte St | Newport St | Lakewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 137.0193
2410 | 0 | 25085 | 26514 | Rutland St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 369.936
2411 | 0 | 25103 | 27549 | Northwestern St | Dexter Ave | Wildemere St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 404.978
2412 | 0 | 25109 | 24883 | W Bethune St | Kipling St | Poe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.8777
2413 | 0 | 25110 | 23958 | Maxwell St | Mack Ave | Sylvester St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 457.5122
2416 | 0 | 25119 | 24459 | Littlefield St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.7244
2417 | 0 | 25147 | 25098 | Warwick St | Elmira St | Fitzpatrick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.5952
2418 | 0 | 25195 | 26613 | Hartwell St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.1125
2420 | 0 | 25214 | 25990 | Littlefield St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.4264
2421 | 0 | 25245 | 25359 | Decatur St | Orangelawn St | Keal St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 258.9848
2422 | 0 | 25261 | 25396 | Goethe Ave | Townsend St | Baldwin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.7466
2423 | 0 | 25284 | 25867 | Rutland St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.7202
2424 | 0 | 25289 | 27518 | Hartwell St | Ellis St | Westfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 422.7141
2425 | 0 | 25304 | 28442 | Trinity St | Dover St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.576
2426 | 0 | 25313 | 26006 | Hartwell St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.9426
2427 | 0 | 25325 | 28079 | Stahelin Ave | Dover St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 284.5434
2428 | 0 | 25343 | 28376 | American St | Mackenzie St | Joy Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.7727
2429 | 0 | 25357 | 28363 | Plainview Ave | Dover St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.8831
2430 | 0 | 25407 | 25029 | Avondale St | Drexel St | Piper Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 156.6263
2431 | 0 | 25414 | 25042 | Algonquin | Essex Ave | Freud St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 469.5161
2432 | 0 | 25422 | 24893 | Concord St | Sylvester St | Stuart St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 227.1451
2433 | 0 | 25433 | 27955 | Maplewood St | Northfield St | Ironwood St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 462.2731
2434 | 0 | 25437 | 24994 | Rutland St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.7274
2436 | 0 | 25446 | 26116 | N Martindale St | Grand River Ave | Joy Rd | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 617.7119
2437 | 0 | 25506 | 27867 | Rutherford St | Ellis St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 191.0557
2439 | 0 | 25544 | 24872 | Burns St | Charlevoix St | Goethe Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.6611
2440 | 0 | 25585 | 25551 | Morley | Griggs St | Wyoming St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 377.2622
2441 | 0 | 25590 | 28070 | Greenview Ave | Dover St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.0135
2442 | 0 | 25592 | 28364 | Robson St | Joy Rd | Ellis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.8635
2443 | 0 | 25597 | 25127 | Hartwell St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.7836
2444 | 0 | 25617 | 27374 | Westwood | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.2952
2445 | 0 | 25633 | 25939 | Appoline | W Chicago St | Elmira St | [5 empty] | Yes | 4 | Will be Installed 2021 | [26 empty] | 728.2953
2446 | 0 | 25679 | 28372 | Vaughan St | Dover St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.9355
2447 | 0 | 25680 | 28466 | Asbury Park | Joy Rd | Ellis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.3924
2448 | 0 | 25684 | 28481 | Field St | Agnes St | Saint Paul St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 284.9627
2449 | 0 | 25691 | 27103 | Westfield St | Faust Ave | Penrod St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.2853
2450 | 0 | 25753 | 27894 | Northwestern St | Grand River Ave & Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 296.1774
2451 | 0 | 25789 | 25896 | Beechwood St | Ridgewood St | Woodside | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 210.6298
2453 | 0 | 25822 | 26136 | Columbus St | Lawton St | Linwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.8407
2454 | 0 | 25825 | 27096 | W Parkway St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.7534
2457 | 0 | 25877 | 24933 | Virginia Park St | La Salle Blvd | 14th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.59
2458 | 0 | 25886 | 25463 | Lauder St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.8852
2460 | 0 | 25898 | 28473 | Linsdale St | Burnette St | Livernois Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 309.9729
2461 | 0 | 25922 | 25033 | Elmira St | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.6716
2462 | 0 | 25935 | 26109 | Helen St | Benson St | Mack Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 477.3272
2463 | 0 | 25958 | 27575 | Ashton Ave | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.6619
2464 | 0 | 25971 | 27922 | Esper St | Joy Rd | Otto St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 172.877
2465 | 0 | 25974 | 24515 | Helen St | Sylvester St | Stuart St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 220.2294
2466 | 0 | 26001 | 26509 | Meadowbrook St | Freud St | Lisette St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.8649
2467 | 0 | 26010 | 27977 | Trinity St | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.5854
2468 | 0 | 26023 | 25397 | Townsend St | Goethe Ave | Mack Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.1979
2470 | 0 | 26036 | 25073 | Sorrento St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.9883
2471 | 0 | 26055 | 27612 | Sussex | Ellis St | Westfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 388.3487
2472 | 0 | 26061 | 27860 | Westwood | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.296
2473 | 0 | 26065 | 25487 | Piper Blvd | Korte St | Avondale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.855
2474 | 0 | 26087 | 26358 | Field St | Charlevoix St | Goethe Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 376.7875
2475 | 0 | 26094 | 27519 | Maplewood St | Ironwood St | Beechwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 243.049
2476 | 0 | 26109 | 24028 | Theodore St | Elmwood St | McDougall St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 204.3241
2477 | 0 | 26114 | 25438 | Braile St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.8662
2478 | 0 | 26174 | 26398 | Burnette St | Westfield St | W Chicago St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 391.8407
2479 | 0 | 26185 | 27087 | Westfield St | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.9074
2480 | 0 | 26193 | 25521 | Burns St | E Vernor Hwy | Charlevoix St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.2864
2481 | 0 | 26221 | 24471 | Hartwell St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.7163
2483 | 0 | 26261 | 25630 | E Palmer St | Brush St | Beaubien St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.9025
2484 | 0 | 26319 | 26088 | Braile St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.615
2485 | 0 | 26329 | 25023 | Elmira St | Ashton Ave | Southfield Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 113.131
2486 | 0 | 26338 | 26969 | Winthrop St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.9251
2487 | 0 | 26385 | 27031 | Holmur St | Montgomery St | Vicksburg St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.0763
2488 | 0 | 26401 | 26861 | Carlin St | Westfield St | W Chicago St & Carlin Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 334.2405
2490 | 0 | 26443 | 26956 | Patton St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.601
2491 | 0 | 26447 | 24361 | Iroquois St | Goethe Ave | Mack Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 337.2664
2492 | 0 | 26451 | 26528 | Longacre St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.5498
2493 | 0 | 26454 | 25393 | Garfield St | Elmwood St | McDougall St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 203.9185
2494 | 0 | 26477 | 28032 | Littlefield St | Joy Rd | Ellis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.0354
2495 | 0 | 26488 | 25459 | Lillibridge St | Lisette St | Edlie St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 296.7696
2496 | 0 | 26510 | 25377 | Helen St | Mack Ave | Sylvester St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.1238
2498 | 0 | 26569 | 26942 | Preston St | Ellery St | Mount Elliott St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 318.9998
2499 | 0 | 26576 | 24432 | Seyburn St | Mack Ave | Sylvester St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 378.1362
2500 | 0 | 26621 | 26999 | W Euclid St | Grand River | Radford St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.2697
2501 | 0 | 26628 | 25917 | Lakewood St | Scripps St | Korte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 417.3733
2502 | 0 | 26647 | 25982 | Lothrop St | Hanover St | Dunedin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.1205
2503 | 0 | 26652 | 26024 | Mackinaw St | Arcadia St | Kimberly Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 208.6552
2504 | 0 | 26679 | 24877 | Winthrop St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.434
2505 | 0 | 26689 | 26008 | Lamothe St | La Salle Blvd | 14th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.4165
2506 | 0 | 26704 | 28082 | Artesian St | Dover St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.644
2507 | 0 | 26718 | 26081 | Patton St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.263
2508 | 0 | 26722 | 24425 | Sorrento St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.6962
2509 | 0 | 26726 | 23885 | Strathmoor St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 327.3945
2510 | 0 | 26727 | 27366 | Montgomery St | Radford St | Holmur St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.7049
2511 | 0 | 26737 | 25378 | Elmira St | Plainview Ave | Auburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.4195
2512 | 0 | 26738 | 25035 | W Bethune St | Churchill St | Woodrow Wilson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.044
2513 | 0 | 26771 | 28423 | Elmwood St | Hendricks St | Hunt St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.1984
2514 | 0 | 26780 | 25531 | Concord St | Mack Ave | Pulford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 195.5303
2515 | 0 | 26792 | 28368 | Coyle St | Joy Rd | Ellis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.5082
2516 | 0 | 26793 | 26948 | Prest St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.0443
2517 | 0 | 26794 | 25390 | Meadowbrook St | Edlie St | E Jefferson Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.3538
2518 | 0 | 26797 | 25034 | Rosemont Ave | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.9129
2519 | 0 | 26799 | 24527 | Averhill Ct | Piper Blvd | Eastlawn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 96.4785
2520 | 0 | 26844 | 25537 | Winthrop St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.9431
2521 | 0 | 26866 | 28564 | Artesian St | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.5724
2523 | 0 | 26905 | 27921 | Helen St | Kercheval St | E Vernor Hwy | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.8628
2524 | 0 | 26923 | 27407 | Northlawn St | Stawell St | Westfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 427.0991
2525 | 0 | 26945 | 27516 | Beechwood St | Spokane St | Maplewood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.885
2526 | 0 | 26959 | 28426 | Helen St | Saint Paul St | Kercheval St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.1472
2527 | 0 | 26967 | 24562 | Marlowe St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.4921
2528 | 0 | 26981 | 24532 | Fielding St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 326.0037
2529 | 0 | 26983 | 26519 | Archdale St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.2189
2530 | 0 | 26997 | 26093 | Holmur St | W Philadelphia St | Pingree St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 118.2481
2532 | 0 | 27065 | 26408 | Iroquois St | Kercheval St | E Vernor Hwy | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.2917
2533 | 0 | 27075 | 26919 | Vicksburg St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.8486
2534 | 0 | 27077 | 27883 | Plainview Ave | Cathedral St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.3875
2535 | 0 | 27121 | 25032 | Holmur St | Hazelwood St | Taylor St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.5397
2536 | 0 | 27146 | 27431 | Iroquois St | Agnes St | Saint Paul St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.2009
2537 | 0 | 27147 | 28549 | Greenview Ave | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.7279
2538 | 0 | 27204 | 27414 | Vaughan St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.4468
2540 | 0 | 27231 | 24935 | W Parkway St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 364.3082
2541 | 0 | 27237 | 26895 | Ohio St | Dawes St | Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.9263
2542 | 0 | 27249 | 25142 | Carlin Ave | Orangelawn St | Keal St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 257.7312
2543 | 0 | 27272 | 27613 | Cathedral St | Stahelin Ave | Brace St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.6839
2544 | 0 | 27279 | 24015 | Burns St | Goethe Ave | Mack Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.4912
2545 | 0 | 27296 | 25030 | Drexel St | Avondale St | Averhill Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 161.1395
2546 | 0 | 27304 | 26547 | Parker St | Durand St | Vernor Hwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.2607
2547 | 0 | 27305 | 25994 | Westwood | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.7817
2548 | 0 | 27319 | 27404 | Robson St | Cathedral St | Unknown & Westfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 213.0719
2549 | 0 | 27339 | 27129 | Warwick St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 275.1292
2550 | 0 | 27381 | 27587 | W Parkway St | Hazelton Ave | Meadow Park | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 143.718
2551 | 0 | 27384 | 26866 | La Salle Blvd | Grand Service Drive | Lothrop St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 195.5041
2552 | 0 | 27393 | 26491 | Beaubien St | Frederick Douglass Ave | E Kirby St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 152.9524
2554 | 0 | 27418 | 26419 | Lamothe St | Linwood St | La Salle Blvd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.865
2555 | 0 | 27442 | 25028 | Lakewood St | Korte St | Avondale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 287.3269
2556 | 0 | 27445 | 26026 | Carlin Ave | W Chicago St & Carlin St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.686
2557 | 0 | 27463 | 27007 | Field St | E Vernor Hwy | Charlevoix St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.1226
2558 | 0 | 27477 | 27593 | Robson St | Ellis St | Cathedral St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.1326
2559 | 0 | 27479 | 28024 | Cheyenne St | Joy Rd | Ellis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 341.2974
2560 | 0 | 27485 | 26572 | Sorrento St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.1438
2562 | 0 | 27487 | 25089 | Concord St | Pulford St | Sylvester St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 186.793
2563 | 0 | 27510 | 24371 | New Town St | Victoria Park Dr N | Victoria Park Dr S | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 407.7357
2564 | 0 | 27513 | 23879 | Lakewood St | Essex Ave | Freud St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 469.7157
2566 | 0 | 27574 | 25579 | Korte St | Riverside Dr & Drexel St | Piper Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 156.6314
2567 | 0 | 27592 | 27951 | Vancouver St | Beechwood St | Firwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 420.1841
2568 | 0 | 27593 | 26566 | Holmur St | Virginia Park St | W Euclid St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 122.5952
2569 | 0 | 27600 | 24061 | Helen St | Stuart St | E Canfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 227.8913
2570 | 0 | 27613 | 27362 | Preston St | Elmwood St | Ellery St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 399.3404
2571 | 0 | 27631 | 25887 | Archdale St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.512
2572 | 0 | 27643 | 27624 | Agnes St | Seminole St | Parker St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 180.6514
2574 | 0 | 27664 | 28383 | Pacific St | Beechwood St | Firwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 420.2776
2575 | 0 | 27674 | 27524 | Concord St | E Vernor Hwy | Charlevoix St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.2047
2576 | 0 | 27680 | 27663 | Winthrop St | Ellis St | Westfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 445.9944
2577 | 0 | 27689 | 26119 | Lauder St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.7148
2578 | 0 | 27691 | 26142 | Coyle St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 375.4973
2579 | 0 | 27693 | 27637 | Prest St | Ellis St | Westfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 444.6694
2580 | 0 | 27697 | 23949 | Coyle St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 328.4886
2581 | 0 | 27706 | 25104 | Littlefield St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.716
2582 | 0 | 27717 | 25913 | Lothrop St | Dunedin St | Rosa Parks Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 231.0148
2583 | 0 | 27719 | 26064 | Scripps St | Eastlawn St | Newport St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.1247
2584 | 0 | 27724 | 26907 | Leland St | Joseph Campau St | Mitchell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.0491
2585 | 0 | 27751 | 26478 | Asbury Park | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 369.8864
2586 | 0 | 27772 | 26893 | Parker St | Kercheval St | Durand St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.1325
2587 | 0 | 27780 | 26395 | Winthrop St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 373.3742
2588 | 0 | 27797 | 27952 | Beechwood St | Vancouver St | Ivanhoe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.7939
2589 | 0 | 27801 | 24449 | Cheyenne St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.6155
2590 | 0 | 27822 | 27665 | Baldwin St | Saint Paul St | Kercheval St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 301.7589
2591 | 0 | 27829 | 26569 | Helen St | Charlevoix St | Benson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 232.5426
2592 | 0 | 27835 | 27375 | Maplewood St | Beechwood St | Turner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 192.4811
2593 | 0 | 27848 | 28468 | W Parkway St | Dover Ave | Meadow Park St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 428.5994
2594 | 0 | 27874 | 25094 | Cheyenne St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.7939
2596 | 0 | 27888 | 25456 | Marlowe St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.5118
2598 | 0 | 27911 | 25118 | Piedmont St | Elmira St | Plymouth Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 361.1298
2600 | 0 | 27949 | 26583 | Underwood St | Northfield St | Beechwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 326.9148
2601 | 0 | 27971 | 27111 | Burns St | Agnes St | Saint Paul St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.3313
2602 | 0 | 27975 | 25043 | Goethe Ave | Seyburn St | Beals St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 102.3121
2603 | 0 | 27977 | 27536 | S Martindale St | Colfax St | Northfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.9062
2604 | 0 | 27981 | 28058 | Dover St | Penrod St | Rosemont Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.6
2605 | 0 | 27984 | 27586 | Esper St | Otto St | Stawell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.7432
2606 | 0 | 28050 | 26110 | Marlowe St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.2997
2607 | 0 | 28062 | 27395 | Cloverlawn St | Stawell St | Westfield St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 426.9546
2608 | 0 | 28077 | 25925 | Beaubien St | E Ferry St | E Palmer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 174.8903
2609 | 0 | 28084 | 25509 | Gladstone St | Dumbarton Ave & Quincy St | Holmur St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 207.5292
2610 | 0 | 28093 | 24906 | Chatham St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.9946
2611 | 0 | 28103 | 26542 | Manor | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.5032
2612 | 0 | 28105 | 25985 | Grandville Ave | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.5268
2613 | 0 | 28109 | 25647 | Iroquois St | E Vernor Hwy | Charlevoix St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.4082
2614 | 0 | 28111 | 28408 | Alpine St | Mackenzie St | Joy Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 342.6094
2615 | 0 | 28119 | 26522 | Greenway St | Northfield St | Beechwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 327.063
2616 | 0 | 28123 | 26373 | Prest St | W Chicago St | Orangelawn St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 374.1419
2617 | 0 | 28132 | 26082 | Parker St | E Vernor Hwy | Charlevoix St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 401.2889
2618 | 0 | 28137 | 23984 | Prest St | Plymouth Rd | Wadsworth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 329.9566
2619 | 0 | 28138 | 28488 | Prairie St | Linsdale St | Mackenzie St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 114.3104
2620 | 0 | 28140 | 26619 | Burns St | Saint Paul St | Kercheval St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.4486
2621 | 0 | 28146 | 26905 | Lauder St | Westfield St | W Chicago St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 287.881
2622 | 0 | 28156 | 24593 | Ohio St | Orangelawn St | Beechdale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 157.8392
2623 | 0 | 28159 | 28487 | Linsdale St | Prairie St | Burnette St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 230.3676
2624 | 0 | 28179 | 26133 | Piper Blvd | Scripps St | Korte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 417.3176
2626 | 0 | 28190 | 26437 | La Salle Blvd | Lothrop St | Lamothe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 202.0123
2628 | 0 | 28314 | 25580 | Drexel St | Korte St & Riverside Dr | Avondale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.7619
2629 | 0 | 28331 | 26589 | W Euclid St | Radford St | Holmur St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.7122
2630 | 0 | 28332 | 27370 | Prairie St | Dover St | Westfield St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 470.4763
2631 | 0 | 28346 | 25973 | Piedmont St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.5896
2632 | 0 | 28364 | 23999 | Virginia Park St | Rosa Parks Blvd | Woodrow Wilson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 324.7885
2633 | 0 | 28379 | 24502 | Lakewood St | Avondale St | Essex Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.2138
2634 | 0 | 28383 | 25907 | Churchill St | W Grand Blvd | W Bethune St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 404.338
2635 | 0 | 28397 | 26091 | Burns St | Kercheval St | E Vernor Hwy | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.6711
2636 | 0 | 28432 | 25528 | Beaubien St | E Palmer St | Hendrie St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 174.9238
2637 | 0 | 28449 | 27582 | Hogarth St | Holmur St | Dexter Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.9151
2639 | 0 | 28460 | 26090 | Beechwood St | Whitfield St | Underwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.9359
2640 | 0 | 28462 | 28567 | Warwick St | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.5712
2641 | 0 | 28467 | 24868 | Field St | Pulford St | Sylvester St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.4353
2642 | 0 | 28469 | 28054 | Maplewood St | Colfax St | Northfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.0203
2643 | 0 | 28511 | 28377 | Sussex | Joy Rd | Ellis St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 363.5836
2644 | 0 | 28535 | 24115 | Field St | Sylvester St | E Canfield St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 459.79
2645 | 0 | 28546 | 27115 | Wildemere St | Northwestern St | Hogarth St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.1902
2646 | 0 | 28558 | 25507 | Whitcomb St | Orangelawn St | Elmira St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.6331
2647 | 0 | 28563 | 27452 | Saint Paul St | Van Dyke St | Parker St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 166.016
2649 | 0 | 28598 | 31581 | Parkland St | Sawyer St | Rockdale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.6865
2650 | 0 | 28638 | 32047 | Grandmont Ave | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.916
2651 | 0 | 28647 | 31506 | Heyden St | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 530.4459
2652 | 0 | 28649 | 33047 | Greenview Ave | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.4568
2653 | 0 | 28651 | 32454 | Heyden St | W Warren Rd & W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 555.6727
2654 | 0 | 28659 | 33041 | Faust Ave | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 546.8387
2655 | 0 | 28667 | 29625 | Grandville Ave | Constance Ave | Van Buren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 267.6348
2656 | 0 | 28673 | 31452 | Piedmont St | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 532.8465
2657 | 0 | 28680 | 30374 | Coyle St | Payne Ave & Tireman Ave | Belton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 380.7348
2658 | 0 | 28683 | 32939 | Montrose St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.8719
2659 | 0 | 28716 | 32963 | Saint Marys St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.3797
2660 | 0 | 28749 | 33029 | Ashton Ave | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.8279
2661 | 0 | 28750 | 32471 | Patton St | W Warren Rd | Braile St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.8355
2662 | 0 | 28788 | 30884 | Parkland St | Dacosta | Lamphere St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 227.3397
2663 | 0 | 28789 | 31433 | Wykes St | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.9887
2664 | 0 | 28792 | 32974 | Whitlock St | Asbury Park | Mettetal St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.2436
2665 | 0 | 28854 | 29501 | Concord St | E Lafayette St | Saint Paul St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 563.0188
2666 | 0 | 28887 | 29571 | Commonwealth St | W Hancock St | W Warren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.5878
2667 | 0 | 28928 | 30978 | Forrer St | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.2007
2668 | 0 | 28946 | 31409 | Penrod St | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 536.7135
2669 | 0 | 28978 | 30384 | Wetherby St | Diversey | Eagle | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 127.4279
2670 | 0 | 28983 | 31430 | Stahelin Ave | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 533.4569
2671 | 0 | 28995 | 30064 | Commonwealth St | Lysander St | W Forest Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.6445
2672 | 0 | 29022 | 31423 | Sawyer St | Brace St | Greenview Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.0517
2673 | 0 | 29049 | 32046 | Woodmont Ave | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.8681
2674 | 0 | 29065 | 31934 | Wheeler St | Proctor St | Sarena St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 248.5713
2675 | 0 | 29103 | 30392 | Burnette St | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.85
2677 | 0 | 29154 | 29886 | Belfast St | Rangoon St | Livernois Ave & Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.9104
2678 | 0 | 29190 | 32410 | Artesian St | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 551.8948
2679 | 0 | 29196 | 31405 | Rosemont Ave | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 537.2076
2680 | 0 | 29228 | 30614 | Plainview Ave | Tireman St | Belton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.6258
2681 | 0 | 29237 | 31525 | Woodmont Ave | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.8058
2682 | 0 | 29289 | 33078 | Warwick St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 548.1766
2683 | 0 | 29337 | 32043 | Tarnow St | Burwell St | Sarena St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 117.8282
2685 | 0 | 29395 | 30612 | Clifton St | Rangoon St | Livernois Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 383.4113
2686 | 0 | 29405 | 29382 | Vaughan St | Van Buren Ave | Joy Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.3534
2688 | 0 | 29422 | 29108 | Beechwood St | Tireman St | Larchmont St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 143.1095
2689 | 0 | 29440 | 28905 | Patton St | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.4808
2690 | 0 | 29457 | 32399 | Brace St | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 551.6366
2692 | 0 | 29473 | 29988 | Rangoon St | Eagle | Belfast St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.9388
2693 | 0 | 29510 | 32052 | Abington Ave | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.9459
2694 | 0 | 29528 | 31512 | Stout St | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 530.8032
2695 | 0 | 29567 | 29912 | Commonwealth St | W Forest Ave | W Hancock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.6053
2696 | 0 | 29583 | 32975 | Asbury Park | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.396
2698 | 0 | 29608 | 29632 | Avery St | W Hancock St | W Warren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.7839
2699 | 0 | 29725 | 33032 | Rosemont Ave | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 546.0627
2700 | 0 | 29745 | 28860 | Vancouver St | Colfax St | Northfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 251.1361
2701 | 0 | 29761 | 31009 | Woodmont Ave | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.9385
2702 | 0 | 29765 | 29928 | Saint Marys St | Belton St | Constance St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 270.1535
2703 | 0 | 29771 | 32446 | Auburn St | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 552.2014
2704 | 0 | 29780 | 30903 | Braile St | Tireman St | Belton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.0461
2705 | 0 | 29796 | 30937 | Burnette St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.2173
2706 | 0 | 29808 | 32957 | Chopin St | Wagner St | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 380.6343
2707 | 0 | 29812 | 30373 | Vaughan St | Belton Ave | Constance Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8431
2708 | 0 | 29814 | 32415 | Warwick St | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 552.0179
2709 | 0 | 29838 | 30073 | Grandville Ave | Belton Ave | Constance Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.3832
2710 | 0 | 29850 | 30380 | Avery St | Lysander St | W Forest Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 177.3706
2711 | 0 | 29858 | 32955 | Mansfield St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.3056
2712 | 0 | 29875 | 32426 | Grandville Ave | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 551.7886
2713 | 0 | 29879 | 29587 | Whitcomb St | Belton St | Mackenzie St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.5054
2714 | 0 | 29885 | 30421 | American St | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.995
2715 | 0 | 29909 | 31531 | Grandmont Ave | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.7671
2716 | 0 | 29914 | 30061 | Warwick St | Belton St | Constance St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.1259
2717 | 0 | 29940 | 32420 | Piedmont St | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 551.871
2718 | 0 | 29960 | 32560 | Larkins St | Wagner St | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 380.7354
2719 | 0 | 29977 | 31047 | Lamphere St | Tireman St | Parkland St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 419.6014
2720 | 0 | 30018 | 30452 | Saint Marys St | Tireman St | Belton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8827
2721 | 0 | 30030 | 30394 | Whitcomb St | Tireman Ave & Coleman Ave | Belton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 379.571
2722 | 0 | 30032 | 29002 | Commonwealth St | Putnam St | Merrick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 175.8639
2723 | 0 | 30049 | 29152 | Plainview Ave | Van Buren Ave | Joy Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.1458
2724 | 0 | 30061 | 33021 | Archdale St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.6572
2725 | 0 | 30113 | 30400 | Wykes St | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.8698
2726 | 0 | 30160 | 31444 | Prairie St | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.2464
2727 | 0 | 30181 | 31390 | Avery St | Grand River Ave | W Alexandrine St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 197.2089
2728 | 0 | 30203 | 28868 | Plainview Ave | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.1675
2730 | 0 | 30266 | 31894 | Lamphere St | Sawyer St | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 413.5104
2731 | 0 | 30290 | 28995 | Prest St | Mackenzie St | Joy Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 356.9924
2732 | 0 | 30294 | 33061 | 24th St | Magnolia St | Selden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 246.7703
2733 | 0 | 30295 | 30897 | Wetherby St | Majestic St | Barton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.3759
2734 | 0 | 30308 | 32025 | Mansfield St | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 359.1079
2735 | 0 | 30403 | 32930 | Lovett St | Buchanan St | Kinsman St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 113.8811
2737 | 0 | 30439 | 31092 | Floyd St | Wetherby St | Rangoon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 430.8927
2738 | 0 | 30444 | 31542 | Memorial St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.4869
2739 | 0 | 30448 | 32371 | Ashton Ave | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 553.608
2740 | 0 | 30464 | 32942 | Forrer St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.9697
2741 | 0 | 30477 | 30422 | Barton St | Rangoon St | Livernois Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 387.6893
2742 | 0 | 30506 | 30390 | Stout St | Belton Ave | Constance Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.7932
2743 | 0 | 30507 | 31909 | Beaverland St | Sawyer St | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 397.1839
2744 | 0 | 30555 | 31093 | Wetherby St | Floyd St | Clifton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.7252
2745 | 0 | 30586 | 29001 | Putnam St | Commonwealth St | Trumbull St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.7051
2747 | 0 | 30605 | 31904 | Sawyer St | Bramell St | Chatham St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.8621
2748 | 0 | 30607 | 30369 | Aretha Ave | Four Tops Dr | W Canfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.3674
2749 | 0 | 30631 | 32558 | Lovett St | Kinsman St | Rich St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 116.3116
2750 | 0 | 30660 | 31028 | Avery St | W Alexandrine St | W Willis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 157.1189
2751 | 0 | 30671 | 29895 | Wetherby St | Belfast St | Tireman St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.1425
2752 | 0 | 30677 | 29868 | Vaughan St | Constance Ave | Van Buren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.318
2753 | 0 | 30690 | 32367 | Patton St | Braile St | Sawyer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 407.7228
2754 | 0 | 30715 | 33000 | Memorial St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.4894
2755 | 0 | 30723 | 31488 | Sawyer St | Plainview Ave | Auburn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.3454
2756 | 0 | 30769 | 30094 | Vinewood St | McGraw St | Milford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 145.8734
2757 | 0 | 30773 | 29976 | Beaverland St | Constance Ave | Parkland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 222.0018
2758 | 0 | 30774 | 30927 | 16th St | W Forest Ave | W Hancock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 288.7546
2761 | 0 | 30875 | 31022 | Abington Ave | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.4932
2762 | 0 | 30884 | 30546 | Commonwealth St | Calumet St | W Canfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.9389
2763 | 0 | 30899 | 32428 | Beaverland St | Majestic Ave | Sawyer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.9669
2764 | 0 | 30902 | 31039 | Rutland St | Diversey | Rutland Ave & Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 379.7586
2765 | 0 | 30944 | 29449 | Trinity St | Van Buren Ave | Joy Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.9829
2766 | 0 | 30963 | 32536 | Rich St | 28th St | Lovett St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 207.4756
2767 | 0 | 30966 | 29100 | Piedmont St | Van Buren Ave & Van Buren St | Joy Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.1865
2768 | 0 | 30967 | 29142 | Auburn St | Van Buren Ave | Joy Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.9822
2769 | 0 | 31005 | 31030 | Memorial St | Diversey | Tireman St & Memorial Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 372.9898
2770 | 0 | 31032 | 30446 | Trinity St | Belton Ave | Constance Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8942
2771 | 0 | 31044 | 28867 | Beechwood St | Seebaldt St | Allendale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.582
2772 | 0 | 31050 | 29092 | Warwick St | Van Buren St | Joy Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.1971
2773 | 0 | 31086 | 31875 | Dolphin St | Sawyer St | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 424.8497
2774 | 0 | 31088 | 31520 | Sawyer St | Fielding St | Stout St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.1033
2775 | 0 | 31092 | 32395 | Greenview Ave | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 551.6804
2776 | 0 | 31098 | 32898 | Rockdale St | Rockdale Ave & W Warren Rd | Majestic Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 360.0932
2777 | 0 | 31099 | 31373 | Parkland St | Rockdale St | Tireman St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 190.5479
2778 | 0 | 31138 | 29441 | Burt Rd | Van Buren Ave | Joy Rd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 276.4021
2779 | 0 | 31140 | 29397 | Commonwealth St | W Warren Ave | Putnam St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 178.0453
2780 | 0 | 31144 | 30371 | Robson St | Tireman Ave & Mead Ave | Belton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 381.0101
2781 | 0 | 31163 | 29544 | Beechwood St | Moore Pl | Tireman St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 197.0682
2782 | 0 | 31167 | 31090 | Tireman St | City/Twp Line | Beaverland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 129.5779
2783 | 0 | 31234 | 31417 | Faust Ave | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 535.83
2784 | 0 | 31235 | 29918 | Trinity St | Constance Ave | Van Buren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.5464
2785 | 0 | 31244 | 29456 | Avery St | W Warren Ave | Putnam St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 178.1184
2786 | 0 | 31272 | 32502 | Rich St | Lovett St | Scotten St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 155.9099
2787 | 0 | 31318 | 30102 | Plainview Ave | Belton Ave | Constance Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.5418
2788 | 0 | 31330 | 29038 | W Parkway St | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 277.9878
2789 | 0 | 31331 | 32914 | Smart St | McDonald St | Central St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 310.3186
2790 | 0 | 31332 | 31491 | Rutherford St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.5064
2791 | 0 | 31356 | 31019 | Parkland St | Tireman St | Dacosta | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.6991
2792 | 0 | 31382 | 32984 | Grandmont Ave | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.4075
2793 | 0 | 31399 | 32503 | Lovett St | Rich St | Horatio St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.2958
2794 | 0 | 31430 | 31540 | Pierson St | Sawyer St | Dead End or Start | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 312.083
2795 | 0 | 31431 | 30423 | Rangoon St | Barton St | Diversey | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.6565
2796 | 0 | 31433 | 33055 | Brace St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.659
2798 | 0 | 31484 | 32387 | Faust Ave | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 552.115
2799 | 0 | 31485 | 31538 | Abington Ave | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.6553
2800 | 0 | 31539 | 32380 | Penrod St | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 552.5669
2801 | 0 | 31578 | 28946 | Trinity St | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.5752
2802 | 0 | 31595 | 32935 | Winthrop St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.6447
2803 | 0 | 31602 | 30486 | Parkland St | Lamphere St | Belton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 228.1841
2804 | 0 | 31663 | 31901 | Lovett St | Herbert St | E I 94 Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 323.659
2805 | 0 | 31688 | 30393 | Eliot St | John R St | Brush St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.4102
2806 | 0 | 31703 | 31046 | Tireman St | Lamphere St | Dacosta | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.8988
2807 | 0 | 31722 | 28882 | Vaughan St | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 266.0725
2808 | 0 | 31726 | 30467 | Asbury Park | Tireman St | Belton Ave & Belton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.8138
2809 | 0 | 31782 | 30953 | American St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.2716
2811 | 0 | 31798 | 29455 | Wabash St | Bryant St | Merrick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 107.865
2812 | 0 | 31813 | 31484 | Auburn St | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 534.0364
2813 | 0 | 31828 | 28866 | Seebaldt St | Beechwood St | Firwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 420.221
2814 | 0 | 31840 | 30000 | Ashton Ave | Belton St | Constance St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 287.6721
2815 | 0 | 31870 | 31457 | Grandville Ave | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 533.0703
2816 | 0 | 31890 | 32049 | Barlum St | Martin St | Cicotte St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 395.9578
2817 | 0 | 31915 | 31568 | Holmes St | Proctor St | Sarena St & Wetherby St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 461.4519
2818 | 0 | 31917 | 28988 | Whitcomb St | Mackenzie St | Joy Rd | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 356.8357
2819 | 0 | 31923 | 31534 | Sawyer St | Braile St | Patton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 119.5936
2821 | 0 | 31933 | 31062 | Chatham St | Tireman St | Belton Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 543.5993
2823 | 0 | 31972 | 31014 | Grandmont Ave | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 371.5651
2824 | 0 | 32011 | 30508 | Majestic St | Rangoon St | Livernois Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 387.2774
2825 | 0 | 32012 | 32477 | Pierson St | W Warren Rd | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 569.0384
2826 | 0 | 32015 | 31434 | Sawyer St | Artesian St | Stahelin Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.0133
2827 | 0 | 32031 | 32886 | Parkland St | W Warren Rd | Majestic Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.2027
2828 | 0 | 32046 | 31428 | Burnette St | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.5155
2829 | 0 | 32074 | 31460 | Sawyer St | Westwood | Grandville Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.4677
2830 | 0 | 32093 | 30896 | Majestic St | Wetherby St | Rangoon St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.4203
2831 | 0 | 32163 | 32056 | Memorial St | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.9985
2832 | 0 | 32197 | 32407 | Stahelin Ave | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 551.904
2833 | 0 | 32215 | 32933 | Cicotte St | Devereaux St | Gladys St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.1446
2834 | 0 | 32239 | 29054 | Avery St | Putnam St | Merrick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 175.5051
2835 | 0 | 32275 | 31386 | Sparta St | Wetherby St | Rangoon St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 476.2077
2836 | 0 | 32285 | 31034 | Beechwood St | Begole St | Cobb Pl | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.8596
2837 | 0 | 32314 | 29384 | Putnam St | Rosa Parks Blvd | Avery St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 218.7765
2838 | 0 | 32316 | 31508 | Mettetal St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.0709
2839 | 0 | 32321 | 31582 | Holmes St | Central St | Proctor St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 244.996
2840 | 0 | 32338 | 32521 | Elm St | Rosa Parks Blvd | Harrison St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 152.5765
2841 | 0 | 32351 | 32456 | Stout St | W Warren Rd | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 556.1462
2842 | 0 | 32368 | 32553 | Gladys St | Cicotte St | Gilbert St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 143.4347
2843 | 0 | 32414 | 30598 | Avery St | Calumet St | W Canfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.9723
2844 | 0 | 32428 | 28608 | Auburn St | Joy Rd | Dover St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.2849
2845 | 0 | 32448 | 30914 | Trinity St | Tireman St | Belton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 271.8498
2846 | 0 | 32453 | 29960 | Avery St | W Forest Ave | W Hancock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 176.046
2847 | 0 | 32454 | 30481 | Abington Ave | Tireman St | Belton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 274.1296
2848 | 0 | 32457 | 29088 | Pacific St | Colfax St | Northfield St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.8998
2849 | 0 | 32480 | 31441 | Warwick St | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 532.1733
2850 | 0 | 32486 | 31489 | Plainview Ave | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 533.9175
2853 | 0 | 32587 | 30405 | Prest St | Tireman Ave & Yinger Ave | Belton St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 378.7288
2854 | 0 | 32590 | 32917 | Cecil St | Wagner St | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 380.3748
2855 | 0 | 32600 | 32368 | Braile St | Patton St | Sawyer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 431.4144
2856 | 0 | 32618 | 31472 | Commonwealth St | Grand River Ave | Selden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 173.7257
2857 | 0 | 32626 | 32467 | 30th St | Horatio St | Herbert St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 289.0194
2858 | 0 | 32647 | 30999 | Mettetal St | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.0083
2859 | 0 | 32661 | 30988 | Mansfield St | Diversey | Tireman St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 370.3729
2860 | 0 | 32672 | 30940 | Wykes St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.0005
2861 | 0 | 32689 | 31498 | Vaughan St | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 529.9728
2862 | 0 | 32713 | 31075 | W Alexandrine St | Grand River Ave | Avery St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 156.5565
2863 | 0 | 32777 | 33016 | Longacre St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.6946
2864 | 0 | 32807 | 29388 | Carbondale St | Vancouver St | Linsdale St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.8713
2865 | 0 | 32811 | 30608 | Aretha Ave | Contours Ln | Temptations Ln | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 158.252
2866 | 0 | 32897 | 33005 | Tarnow St | Wagner St | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 380.7676
2867 | 0 | 32901 | 32461 | Radcliffe St | Mather St | Central St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 157.3863
2868 | 0 | 32911 | 30928 | Floyd St | Rangoon St | Livernois Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 383.7517
2869 | 0 | 32915 | 31420 | Greenview Ave | Sawyer St | Tireman St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 534.9132
2870 | 0 | 32918 | 33063 | Stahelin Ave | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.7488
2871 | 0 | 32935 | 31451 | Sawyer St | Piedmont St | Warwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.1961
2872 | 0 | 32952 | 32484 | Tarnow St | Kirkwood St | Burwell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 292.3599
2873 | 0 | 32976 | 29655 | Plainview Ave | Constance Ave | Van Buren Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 268.7491
2874 | 0 | 32988 | 30973 | W Alexandrine St | Commonwealth St | Trumbull St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 148.0875
2876 | 0 | 33016 | 31505 | Sawyer St | Heyden St | Vaughan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 136.3374
2877 | 0 | 33021 | 30883 | Stout St | Tireman St | Belton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3258
2878 | 0 | 33044 | 31868 | Rockdale St | Sawyer St | Parkland St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 300.2687
2879 | 0 | 33070 | 29606 | Prairie St | Tireman St | Garden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 233.3632
2880 | 0 | 33075 | 29594 | Prest St | Belton St | Mackenzie St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.5965
2881 | 0 | 33101 | 33076 | Smart St | Lonyo St | McDonald St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 406.6249
2882 | 0 | 33128 | 31496 | Mansfield St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.6537
2883 | 0 | 33197 | 31069 | Tireman St | Bramell St | Chatham St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.8729
2885 | 0 | 33237 | 31560 | Rutland St | Majestic St | Diversey | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 351.3712
2886 | 0 | 33257 | 32954 | Whitlock St | Mansfield St | Rutherford St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.4481
2887 | 0 | 33264 | 32450 | Vaughan St | W Warren Ave | Sawyer St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 556.2884
2888 | 0 | 33286 | 31453 | American St | W Warren Ave | Majestic St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.4591
2889 | 0 | 33318 | 28968 | Field St | E Lafayette St | Agnes St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 283.4824
2890 | 0 | 33384 | 36072 | Christiancy St | Campbell St | Junction St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.1217
2891 | 0 | 33400 | 34920 | Kirkwood St | Rosemont Ave | Ashton Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 133.0161
2892 | 0 | 33432 | 37960 | S Dartmouth | Outer Dr | Gleason St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.7207
2893 | 0 | 33466 | 35399 | Waldo St | Parkinson St | Martin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 412.3972
2894 | 0 | 33510 | 34925 | Piedmont St | Kirkwood St | Dayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.2165
2895 | 0 | 33532 | 35578 | 25th St | W Vernor Hwy | Toledo St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 522.1316
2896 | 0 | 33546 | 35549 | 18th St | Porter St | Bagley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.7338
2897 | 0 | 33557 | 36547 | Beard St | Chatfield St | Bostwick St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 108.2008
2898 | 0 | 33561 | 33564 | Tillman St | Ash St | Martin Luther King Jr Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 248.9159
2900 | 0 | 33576 | 34372 | Vaughan St | Ann Arbor Trl | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 554.8436
2901 | 0 | 33578 | 33961 | Rutland St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 542.4049
2903 | 0 | 33586 | 37988 | S Edsel St | Le Blanc St | Gleason St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 367.725
2904 | 0 | 33608 | 37586 | S Annabelle St | Schaefer Hwy | Toronto St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 104.33
2905 | 0 | 33637 | 35442 | Edward | Parkinson St | Martin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 408.2224
2907 | 0 | 33691 | 36051 | Lansing St | Porter St | Christiancy St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 231.8202
2908 | 0 | 33698 | 35917 | Western St | Saint Stephens St | Michigan Ave | [5 empty] | Yes | 5 | Will be Installed 2021 | [26 empty] | 977.9427
2909 | 0 | 33719 | 36627 | Beard St | Lexington St | Army St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.6521
2910 | 0 | 33721 | 37889 | S Beatrice St | Downing St | Miami St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 336.4718
2912 | 0 | 33762 | 35559 | Saint Lawrence St | Saint John St | Baubee St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 338.6465
2913 | 0 | 33789 | 35400 | Parkinson St | Waldo St | Parkwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 95.9689
2914 | 0 | 33806 | 35483 | Cabot St | Arnold St | Michigan Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 488.8858
2916 | 0 | 33814 | 33931 | Asbury Park | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 541.6844
2917 | 0 | 33815 | 35422 | Springwells St | Cypress St | Saint Stephens St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 330.6229
2918 | 0 | 33825 | 33401 | Plainview Ave | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 548.163
2919 | 0 | 33840 | 33383 | Cecil St | McGraw St | Wagner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.5668
2920 | 0 | 33854 | 36488 | Cavalry St | Amherst St | Howard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.0134
2921 | 0 | 33863 | 37591 | S Liddesdale St | Schaefer | Toronto St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 299.3401
2922 | 0 | 33872 | 36543 | Casgrain St | Army St | Regular St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 299.3384
2923 | 0 | 33891 | 35910 | Cabot St | Saint John St | Arnold St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 618.7445
2925 | 0 | 33949 | 36071 | Lansing St | Howard St | Porter St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 164.4434
2926 | 0 | 33975 | 34475 | Piedmont St | Dayton St | Paul Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.9998
2927 | 0 | 33976 | 33915 | Mansfield St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 544.4836
2929 | 0 | 34008 | 34530 | Lawndale St | McGraw St | Dennison St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 530.2982
2931 | 0 | 34057 | 34450 | Faust Ave | Dayton St | Paul Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.9364
2932 | 0 | 34074 | 36508 | N Rademacher St | Regular St | Cadet St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 279.5858
2933 | 0 | 34095 | 36025 | Lansing St | Christiancy St | W Vernor Hwy | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 413.2641
2934 | 0 | 34119 | 37949 | S Ethel St | Visger St | Omaha St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 355.5826
2935 | 0 | 34120 | 34006 | Faust Ave | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 546.6258
2936 | 0 | 34128 | 36439 | Porter St | Cavalry St | Campbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 234.3541
2938 | 0 | 34193 | 33489 | 24th St | Martin Luther King Jr Blvd | Magnolia St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 226.7325
2939 | 0 | 34202 | 35471 | Konkel St | Junction St | Wesson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 418.8608
2940 | 0 | 34228 | 36456 | Amherst St | Campbell St | Junction St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.0655
2942 | 0 | 34232 | 35412 | Parkwood St | Freer St | Parkinson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 220.803
2943 | 0 | 34241 | 34381 | Pelouze St | Martin St | Burton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 273.7108
2944 | 0 | 34244 | 35970 | McKinstry St | W Vernor Hwy | Uthes St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 183.3059
2945 | 0 | 34260 | 37970 | S Greyfriars St | Outer Dr | Gleason St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.2036
2949 | 0 | 34321 | 34943 | Stahelin Ave | Kirkwood St | Dayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 307.1533
2951 | 0 | 34342 | 35926 | Palms St | W Vernor Hwy | Wolff St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.2958
2952 | 0 | 34377 | 33382 | Westwood | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 548.2564
2953 | 0 | 34410 | 35508 | Otis St | Gilbert St | Livernois Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 171.7775
2954 | 0 | 34423 | 34398 | Stahelin Ave | Paul St | Dayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 121.5404
2955 | 0 | 34433 | 35041 | Parkinson St | Saint John St | Cecil St & Michigan Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 406.4843
2957 | 0 | 34447 | 33883 | Saint Lawrence St | Wagner St | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 388.4561
2958 | 0 | 34454 | 33554 | Elmer St | Wagner St | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 387.449
2959 | 0 | 34461 | 33884 | Wesson St | Vigo St | Rich St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 167.1274
2960 | 0 | 34465 | 36013 | Porter St | Scotten St | Hubbard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 258.7045
2963 | 0 | 34497 | 35901 | 17th St | Howard St | Porter St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 298.4855
2964 | 0 | 34516 | 37938 | S Edsel St | Francis St | Visger St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.0677
2965 | 0 | 34518 | 34020 | Elmer St | McGraw St | Wagner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.4643
2966 | 0 | 34522 | 33895 | Pelouze St | Gilbert St | Livernois Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 171.6746
2967 | 0 | 34534 | 33568 | Roosevelt St | Martin Luther King Jr Blvd | Magnolia St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 260.3139
2968 | 0 | 34551 | 34942 | Kirkwood St | Stahelin Ave | Brace St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.4573
2969 | 0 | 34571 | 38030 | S Ethel St | Salliotte St | Peters St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 297.0057
2970 | 0 | 34594 | 33388 | Minock St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 548.2607
2971 | 0 | 34645 | 33436 | Winthrop St | Radcliffe St | Whitlock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.4084
2972 | 0 | 34661 | 35475 | Otis St | Livernois Ave | Military St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 150.2519
2973 | 0 | 34684 | 33531 | Florida St | McGraw St | Wagner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 264.1661
2974 | 0 | 34740 | 34514 | Wesson St | Michigan Ave | Buchanan St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 484.5592
2976 | 0 | 34752 | 36054 | Eldred St | Campbell St | Junction St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.3626
2977 | 0 | 34763 | 33892 | Tarnow St | Panama St | Gladys Ct | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 138.6686
2978 | 0 | 34782 | 34061 | Plainview Ave | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 546.7031
2979 | 0 | 34789 | 33395 | Auburn St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 548.4087
2980 | 0 | 34800 | 34518 | Joe St | Michigan Ave | Dead End or Start | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 387.203
2981 | 0 | 34816 | 34472 | Warwick St | Dayton St | Paul Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.246
2982 | 0 | 34841 | 34009 | Horatio St | Martin St | Daniels St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.9791
2983 | 0 | 34855 | 37907 | S Bassett St | Downing St | Miami St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 357.3866
2984 | 0 | 34868 | 36540 | Regular St | Lewerenz St | Waterman St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 152.0763
2985 | 0 | 34879 | 33370 | Piedmont St | Whitlock St | W Warren Ave | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 548.267
2987 | 0 | 34886 | 37955 | S Bassett St | Visger St | Omaha St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.4906
2988 | 0 | 34907 | 35561 | Clippert St | Otis St | Dennis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.2159
2989 | 0 | 34914 | 37920 | S Dartmouth | Francis St | Visger St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.5018
2991 | 0 | 34926 | 37878 | S Ethel St | Miami St | Melvin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 358.554
2993 | 0 | 34977 | 36007 | Morrell St | W Vernor Hwy | McMillan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 260.5398
2994 | 0 | 34978 | 34418 | Williams St | Michigan Ave | Butternut St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 255.5847
2995 | 0 | 35039 | 35387 | Lumley St | Cypress St | Jennie St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 165.6354
2996 | 0 | 35051 | 38028 | S Annabelle St | Outer Dr | Salliotte St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 192.1665
2997 | 0 | 35067 | 35899 | Plumer St | Junction St | McKinstry St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 555.2285
2998 | 0 | 35068 | 37901 | S Ethel St | Downing St | Miami St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 356.3913
2999 | 0 | 35072 | 37976 | S Ethel St | Francis St | Visger St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.1489
3000 | 0 | 35112 | 35963 | Military St | Federal St | Plumer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 185.3346
3001 | 0 | 35120 | 33894 | Winthrop St | Paul Dr | Radcliffe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 262.2555
3004 | 0 | 35183 | 34430 | N Campbell St | Jackson St | Buchanan St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 419.1721
3005 | 0 | 35196 | 36618 | Lisbon St | N Green St | Beard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.4523
3006 | 0 | 35217 | 34059 | Saint Lawrence St | McGraw St | Henderson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 140.1119
3007 | 0 | 35233 | 33917 | Jackson St | 30th St | 29th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 115.3452
3008 | 0 | 35265 | 36415 | Rogers St | Cavalry St | Campbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 234.8109
3009 | 0 | 35281 | 35498 | Bulwer St | Martin St | Parkinson St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 398.1696
3010 | 0 | 35285 | 34515 | Labrosse St | Brooklyn St | 6th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 164.9436
3011 | 0 | 35288 | 36587 | Beard St | Lisbon St | Rowan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.9312
3012 | 0 | 35303 | 38024 | S Liddesdale St | Outer Dr | Salliotte St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 170.0427
3014 | 0 | 35392 | 35962 | Vinewood St | Shady Ln | Bagley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 226.6151
3017 | 0 | 35458 | 34002 | Penrod St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 546.2374
3018 | 0 | 35472 | 33948 | Abington Ave | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 540.4191
3019 | 0 | 35478 | 35083 | Otis St | Wesson St | Greusel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 242.8907
3020 | 0 | 35501 | 35988 | Campbell St | Romeyn St | Toledo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.7832
3021 | 0 | 35512 | 37091 | Melville St | S Yale | S Westend St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 439.9799
3022 | 0 | 35529 | 34048 | Westwood | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.2187
3023 | 0 | 35543 | 35462 | Saint James St | Michigan Ave | Dead End or Start | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 383.6424
3024 | 0 | 35545 | 37924 | S Ethel St | Omaha St | Downing St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 351.2612
3025 | 0 | 35559 | 33973 | Florida St | Panama St | McGraw St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 258.0801
3026 | 0 | 35566 | 34038 | Piedmont St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.5944
3027 | 0 | 35571 | 36049 | Military St | W Vernor Hwy | McMillan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 259.1591
3029 | 0 | 35586 | 36074 | Eldred St | Cavalry St | Campbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 235.7331
3030 | 0 | 35590 | 34435 | Roosevelt St | Michigan Ave | Ash St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 245.9613
3031 | 0 | 35597 | 34532 | Church St | Rosa Parks Blvd | Eleventh St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 153.2174
3032 | 0 | 35609 | 34543 | Larkins St | Michigan Ave | Horatio St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 289.6366
3033 | 0 | 35614 | 37974 | S Liddesdale St | Gleason St | Francis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.1649
3034 | 0 | 35638 | 34032 | Henderson St | Lonyo St | Saint Lawrence St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 155.8406
3035 | 0 | 35662 | 35425 | Ternes | Baubee St | Cypress St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 199.3838
3036 | 0 | 35704 | 35560 | Otis St | Clippert St | Cicotte St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 155.1559
3037 | 0 | 35711 | 37952 | S Liddesdale St | Francis St | Visger St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.0136
3038 | 0 | 35713 | 36578 | Chatfield St | N Green St | Beard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.5708
3039 | 0 | 35721 | 37940 | S Dartmouth | Gleason St | Francis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.2553
3040 | 0 | 35732 | 34407 | Larkins St | Horatio St | E I 94 Service Drive | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 192.2705
3042 | 0 | 35738 | 38039 | S Ethel St | Outer Dr | Salliotte St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 325.8666
3043 | 0 | 35761 | 33951 | Pelouze St | Cicotte St | Gilbert St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.5952
3044 | 0 | 35778 | 37578 | S Liddesdale St | Toronto St | Gilroy St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 286.0786
3045 | 0 | 35812 | 35881 | Bagley St | 25th St | 24th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 172.6894
3046 | 0 | 35821 | 34929 | Edward | Gilbert St | Livernois Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 168.9149
3048 | 0 | 35864 | 35032 | Kopernick St | Wesson St | Greusel St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 242.6901
3049 | 0 | 35883 | 33465 | Tarnow St | McGraw St | Wagner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.6375
3051 | 0 | 35922 | 33537 | Horatio St | Gilbert St | Livernois Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 175.2699
3052 | 0 | 35932 | 35075 | Parkwood St | Parkinson St | Martin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 415.5121
3053 | 0 | 35942 | 35919 | Bagley St | Vinewood St | W Grand Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.0328
3054 | 0 | 35954 | 33996 | Rosemont Ave | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.7752
3055 | 0 | 35981 | 36012 | Campbell St | Newberry St | McMillan St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.8496
3056 | 0 | 36025 | 33962 | Longacre St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 536.3243
3057 | 0 | 36045 | 37931 | S Bassett St | Omaha St | Downing St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 353.229
3058 | 0 | 36046 | 34921 | Rosemont Ave | Kirkwood St | Dayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 303.9896
3059 | 0 | 36056 | 37958 | S Edsel St | Gleason St | Francis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.5384
3061 | 0 | 36073 | 36022 | McMillan St | Military St | Cavalry St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 156.2598
3062 | 0 | 36083 | 34431 | 25th St | Michigan Ave | Ash St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 293.055
3063 | 0 | 36084 | 34466 | Ogden St | McGraw St | Henderson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 143.7946
3064 | 0 | 36091 | 34437 | Rosemont Ave | Dayton St | Paul Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.8876
3066 | 0 | 36108 | 35932 | Military St | Federal St | Ranspach St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.3333
3067 | 0 | 36137 | 35534 | Clayton St | Parkinson St | Martin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 388.0308
3068 | 0 | 36153 | 37604 | S Ethel St | Melvin St | Schaefer & S Deacon St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 406.7665
3069 | 0 | 36158 | 37909 | Visger St | S Greyfriars St | S Waring St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 120.7295
3070 | 0 | 36165 | 34411 | Florida St | W I 94 Service Drive | Panama St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 244.6876
3071 | 0 | 36187 | 35973 | Morrell St | McMillan St | Toledo St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 269.8237
3073 | 0 | 36213 | 33942 | Grandmont Ave | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 540.1014
3074 | 0 | 36219 | 33380 | Florida St | Wagner St | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 381.7173
3077 | 0 | 36344 | 33510 | Rich St | Wesson St | N Campbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.2932
3079 | 0 | 36386 | 36440 | Cavalry St | Porter St | Rogers St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.9241
3080 | 0 | 36417 | 34397 | Ogden St | Henderson St | Kirkwood St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 513.8697
3081 | 0 | 36467 | 35539 | 17th St | Porter St | Bagley St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.2501
3083 | 0 | 36472 | 34422 | Trenton St | Henderson St | Dennison St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 383.3818
3085 | 0 | 36491 | 36475 | Military St | Army St | Regular St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 302.5082
3086 | 0 | 36494 | 37433 | Lyon St | S Leigh St | Dearborn St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 532.5879
3087 | 0 | 36496 | 33405 | Cicotte St | W I 94 Service Drive | Hanson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.1389
3088 | 0 | 36507 | 34932 | Faust Ave | Kirkwood St | Dayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 305.3775
3089 | 0 | 36511 | 34987 | Lumley St | Michigan Ave | Sumner | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 218.3373
3090 | 0 | 36521 | 34895 | Addison St | McGraw St | Dennison St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 532.9813
3091 | 0 | 36532 | 35450 | Saint Lawrence St | Baubee St | Sumner Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 333.0435
3092 | 0 | 36566 | 35390 | Otis St | Hammond St | Wesson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 131.0246
3093 | 0 | 36590 | 34064 | Tarnow St | W I 94 Service Drive | Panama St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 261.613
3095 | 0 | 36650 | 33975 | Archdale St | City/Twp Line | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 543.5281
3096 | 0 | 36664 | 34953 | Warwick St | Kirkwood St | Dayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 306.3081
3097 | 0 | 36776 | 34026 | Stahelin Ave | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.6334
3099 | 0 | 36821 | 34879 | Labrosse St | 8th St | Brooklyn St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 165.0549
3101 | 0 | 36853 | 35920 | Vinewood St | Bagley St | W Vernor Hwy | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 151.7591
3102 | 0 | 36854 | 34444 | Penrod St | Dayton St | Paul Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 239.9685
3104 | 0 | 36882 | 34911 | Labrosse St | Trumbull St | 8th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 153.9308
3105 | 0 | 36889 | 35022 | Springwells St | Michigan Ave | Cypress St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 311.2162
3106 | 0 | 36893 | 35953 | Campbell St | Brandon St | Plumer St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 132.929
3107 | 0 | 36918 | 34933 | Kirkwood St | Greenview Ave | Faust Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 135.5354
3109 | 0 | 36949 | 35911 | Hubbard St | W Vernor Hwy | Toledo St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 516.6182
3110 | 0 | 36962 | 33990 | Ashton Ave | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.3229
3111 | 0 | 36983 | 33958 | Horatio St | Daniels St | Cicotte St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 245.2255
3112 | 0 | 37014 | 33970 | 25th St | Ash St | Martin Luther King Jr Blvd | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 224.8587
3114 | 0 | 37019 | 33897 | Trenton St | Dennison St | Kirkwood St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 130.0091
3115 | 0 | 37024 | 34427 | Renville St | McGraw St | Henderson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 142.402
3116 | 0 | 37028 | 37615 | S Beatrice St | Miami St | Melvin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 386.3067
3117 | 0 | 37056 | 34406 | Horatio St | Larkins St | Braden St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 144.9448
3118 | 0 | 37062 | 35432 | Military St | Otis St | Dennis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 231.9987
3119 | 0 | 37074 | 35040 | Saint John St | Parkinson St | Larkins St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 110.1274
3120 | 0 | 37079 | 35417 | Faust Ave | Unknown | Kirkwood St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 431.6349
3121 | 0 | 37086 | 38000 | S Ethel St | Gleason St | Francis St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 304.9969
3122 | 0 | 37092 | 36411 | Lansing St | W Lafayette Blvd | Howard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 263.9759
3123 | 0 | 37100 | 35469 | Stahelin Ave | Ford Rd | Kirkwood St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 517.0531
3124 | 0 | 37111 | 34886 | Leverette St | Eleventh St | 10th St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 186.1806
3126 | 0 | 37124 | 37623 | Corbin St | N I 75 Service Drive | S Fort St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 383.804
3127 | 0 | 37166 | 35518 | 24th St | Randall St | Ruskin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 181.288
3132 | 0 | 37227 | 35992 | Vinewood St | Porter St | Shady Ln | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 225.9932
3133 | 0 | 37249 | 35922 | Brandon St | Junction St | McKinstry St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 555.4122
3134 | 0 | 37257 | 35023 | Ternes | Sumner Ave | Elmer St & Michigan Ave | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 245.6941
3135 | 0 | 37287 | 38015 | S Ethel St | Peters St | Gleason St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 307.1739
3136 | 0 | 37308 | 34912 | Leverette St | Rosa Parks Blvd | Eleventh St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 153.1444
3137 | 0 | 37317 | 35986 | Cabot St | John Kronk St | Saint John St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 485.5699
3138 | 0 | 37329 | 33488 | Wagner St | Springwells St | Casper St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 123.8795
3140 | 0 | 37347 | 36390 | Rogers St | Campbell St | Junction St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.1285
3141 | 0 | 37369 | 37893 | Conway St | N I 75 Service Drive | S Fort St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 387.0574
3142 | 0 | 37378 | 35913 | 18th St | Howard St | Porter St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 300.3743
3143 | 0 | 37388 | 37580 | S Annabelle St | Toronto St | Gilroy St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 285.9145
3144 | 0 | 37391 | 37565 | S Liddesdale St | Gilroy St | Leonard St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 313.6661
3145 | 0 | 37419 | 33920 | Saint Marys St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 545.5555
3147 | 0 | 37432 | 34019 | Brace St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.0767
3148 | 0 | 37469 | 38002 | S Edsel St | Outer Dr | Le Blanc St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 192.495
3149 | 0 | 37474 | 36002 | Romeyn St | Cavalry St | Campbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.3527
3150 | 0 | 37492 | 36014 | McMillan St | Cavalry St | Campbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 238.7861
3151 | 0 | 37500 | 36029 | Vinewood St | W Lafayette Blvd | Porter St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 417.1163
3152 | 0 | 37513 | 36420 | Military St | Regular St | Cadet St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 272.8251
3154 | 0 | 37522 | 33899 | Montrose St | Paul Dr | Radcliffe St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 262.623
3157 | 0 | 37554 | 33985 | Dennison St | Cabot St | Lawndale St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 98.4085
3158 | 0 | 37563 | 36392 | Christiancy St | Cavalry St | Campbell St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 235.328
3160 | 0 | 37586 | 34525 | Leverette St | 10th St | Trumbull St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 175.7894
3161 | 0 | 37590 | 33439 | Montrose St | Radcliffe St | Whitlock St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 281.4057
3162 | 0 | 37595 | 35448 | Saint John St | Central St | Freer St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 362.2365
3163 | 0 | 37608 | 38014 | S Liddesdale St | Salliotte St | Peters St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 296.8893
3165 | 0 | 37660 | 36000 | McMillan St | Campbell St | Junction St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.1157
3166 | 0 | 37687 | 37595 | S Beatrice St | Melvin St | Schaefer | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 154.6982
3167 | 0 | 37718 | 33427 | Rich St | 35th St | Junction St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 109.6168
3168 | 0 | 37740 | 35562 | Brandon St | Clark St | Scotten St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 237.184
3169 | 0 | 37741 | 34968 | Auburn St | Kirkwood St | Dayton St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 299.6253
3171 | 0 | 37769 | 36011 | Newberry St | Campbell St | Junction St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 250.1697
3172 | 0 | 37787 | 36403 | Cadet St | Livernois Ave | Dragoon St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 157.9234
3173 | 0 | 37797 | 36433 | Cadet St | Casgrain St | Infantry St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 160.6371
3174 | 0 | 37808 | 35010 | Larkins St | Saint John St | Michigan Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 331.647
3175 | 0 | 37831 | 34035 | Warwick St | Paul Dr | Whitlock St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 547.9732
3176 | 0 | 37892 | 34042 | 33rd St | Jackson St | Buchanan St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 418.2619
3177 | 0 | 37920 | 34952 | Kirkwood St | Warwick St | Artesian St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 134.7716
3178 | 0 | 37933 | 37882 | S Bassett St | Miami St | Melvin St | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.1657
3179 | 0 | 37934 | 34983 | Saint John St | Apple St | Martin St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 185.056
3182 | 0 | 37989 | 33517 | Whitehead St | Cicotte St | Gilbert St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 141.5324
3183 | 0 | 38008 | 34066 | Renville St | Henderson St | Kirkwood St | [5 empty] | Yes | 3 | Will be Installed 2021 | [26 empty] | 513.9253
3184 | 0 | 38032 | 37608 | S Bassett St | Melvin St | Bromley Ave | [5 empty] | Yes | 2 | Will be Installed 2021 | [26 empty] | 354.1047
3185 | 0 | 38038 | 33424 | Chopin St | McGraw St | Wagner St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 265.7851
3187 | 0 | 38067 | 34493 | Auburn St | Dayton St | Paul Dr | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 240.037
3188 | 0 | 38083 | 34512 | N Campbell St | Michigan Ave | Jackson St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 143.9191
3189 | 0 | 38085 | 34447 | Horatio St | Cecil St | Larkins St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 149.9725
3190 | 0 | 38112 | 35447 | Lumley St | Jennie St | Saint Stephens St | [5 empty] | Yes | 1 | Will be Installed 2021 | [26 empty] | 165.1538
Formulas:
Restoration Start = IFERROR(VLOOKUP([WBS],Rest!$B:$G,5,FALSE),"")
Restoration Finish = IFERROR(VLOOKUP([WBS],Rest!$B:$G,6,FALSE),"")
Service Start = IFERROR(VLOOKUP([WBS],Service!$B:$G,5,FALSE),"")
Service Finish = IFERROR(VLOOKUP([WBS],Service!$B:$G,6,FALSE),"")

## Main (hidden)
Activity ID | WBS | Project Name | Activity Name | Budgeted Units | Start | Finish
SCDet-4775 | GRP-2021-SCDet1.36.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Roselawn (Joy & Tireman) | 0 | 11-17-20 A | 12-09-20 A
SCDet-4615 | GRP-2021-SCDet1.34.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Northlawn (Joy & Tireman) | 0 | 11-24-20 A | 12-07-20 A
SCDet-4695 | GRP-2021-SCDet1.35.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Cloverlawn (Joy & Tireman) | 0 | 12-07-20 A | 12-16-20 A
SCDet-4455 | GRP-2021-SCDet1.32.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Wisconsin (Joy & Tireman) | 0 | 12-08-20 A | 12-17-20 A
SCDet-4855 | GRP-2021-SCDet1.37.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Greenlawn (Joy & Tireman) | 0 | 12-14-20 A | 12-21-20 A
CDET-1960 | PROJ-0951-CDET1-2.46.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main - Tuxedo Stub (AWO Linwood & Linwood) - Completed 2020 | 0 | 12-21-20 A | 12-22-20 A
CDET-2270 | PROJ-0951-CDET1-2.52.53.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main - Wildemere (2) (Webb & Tuxedo) - Completed 2020 | 120 | 12-21-20 A | 12-21-20 A
CDET-1560 | PROJ-0951-CDET1-2.41.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main - Davison (4) (Dexter & Livernois) - Descoped | 2400 | 12-28-20 A | 12-28-20 A
CDET-1605 | PROJ-0951-CDET1-2.23.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main - Lawton (2) (Glendale & Leslie) - Completed 2020 | 170 | 12-28-20 A | 12-28-20 A
CDET-1740 | PROJ-0951-CDET1-2.18.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main - Dexter (2) (Waverly & Davison) - Descoped | 200 | 12-28-20 A | 12-28-20 A
CDET-2185 | PROJ-0951-CDET1-2.51.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main - Wildemere (1) (Davison & ANO Davison) - Completed 2020 | 120 | 12-29-20 A | 12-29-20 A
GP 41150 | PROJ-0951-GP 5 -3.77.76.2 | 2020 GRP - Carry Over - GP 5 | Elevate Main - Kercheval Pl (ASO Kercheval & Kerchval) GP4 | 540 | 12-29-20 A | 12-29-20 A
GP 41220 | PROJ-0951-GP 5 -3.77.76.2 | 2020 GRP - Carry Over - GP 5 | Elevate Main - Kercheval South (ASO Kercheval & Kerchval) GP4 | 540 | 12-29-20 A | 12-29-20 A
WDET-5385 | PROJ-0951-WDET9-4.72.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Elevate Main - Stahelin 3 (W Warren & Whitlock) not available.... | 513 | 12-29-20 A | 01-12-21 A
WDET-15220 | PROJ-0951-WDET9-4.106.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Elevate Main - Warwick 1 (Tireman & W Warren) | 2525 | 12-29-20 A | 12-30-20 A
ND2-18610 | PROJ-0951-NDET2-2.40.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Elevate Main - ENO E Outer (Milbank & Milbank Greenway) Included the main loop around the BLDs | 2179 | 12-29-20 A | 12-30-20 A
CDET2-4975 | GRP-2021-CDet2.47.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Lawton 2 (Clairmount & Clairmount) | 0 | 12-30-20 A | 12-30-20 A
CDET-12195 | PROJ-0951-CDET1-2.61.53.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main - Wildemere (4) (Tyler & Waverly) - Completed 2020 | 150 | 12-30-20 A | 12-31-20 A
NCDET - 5490 | NEWPROJ-6.8.2.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - Manor (ANO Fenkell & Fenkell) | 93 | 01-04-21 A | 01-07-21 A
NWDET-13520 | PROJ-0951-NWDET1CO.13.3.2 | 2021 GRP - North West Detroit 1b | Install Main - Westwood (1) (ASO Schoolcraft & Davison) | 677 | 01-04-21 A | 01-06-21 A
NWDET-13610 | PROJ-0951-NWDET1CO.13.2.2 | 2021 GRP - North West Detroit 1b | Install Main - Westwood (1) (Davison & Glendale) | 839 | 01-04-21 A | 01-08-21 A
NWDET-20130 | PROJ-0951-NWDET1CO.53.2.2 | 2021 GRP - North West Detroit 1b | Install Main - Penrod (2) (Davison & EOM) | 442 | 01-04-21 A | 01-05-21 A
GP-6370 | PROJ-0951-GP 5 -3.132.1.2 | 2020 GRP - Carry Over - GP 5 | Install Main - Mack North 1 (Balfour & Cadieux) GP4 | 3317 | 01-04-21 A | 01-12-21 A
SCDet-2055 | GRP-2021-SCDet1.1.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd W 3 (Joy & Birwood) | 968 | 01-04-21 A | 01-08-21 A
SCDet-2615 | GRP-2021-SCDet1.9.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Littlefield 1 (Joy & Sorrento) | 1968 | 01-04-21 A | 01-19-21 A
SCDet-2855 | GRP-2021-SCDet1.12.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Carlin (Joy & Tireman) | 2420 | 01-04-21 A | 01-28-21 A
SCDet-4295 | GRP-2021-SCDet1.30.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Kentucky (Joy & Tireman) | 2547 | 01-04-21 A | 01-27-21 A
SCDet-4375 | GRP-2021-SCDet1.31.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Indiana (Joy & Tireman) | 2549 | 01-04-21 A | 01-25-21 A
SCDet-5735 | GRP-2021-SCDet1.48.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Tireman 2 (Manor & Wisconsin) | 3305 | 01-04-21 A | 03-01-21 A
CDET2-2495 | GRP-2021-CDet2.15.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Edison 2 (Linwood & Rosa Parks) | 2651 | 01-04-21 A | 01-12-21 A
CDET2-4815 | GRP-2021-CDet2.45.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Genessee (Chicago & Joy) | 1150 | 01-04-21 A | 01-06-21 A
SWDET2-2750 | PROJ-0951-SWDET2.14.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Central 2 (NO Dix & Dix) | 1509 | 01-04-21 A | 01-19-21 A
SWDET2-12475 | PROJ-0951-SWDET2.18.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 1 (Dix & Pearl) | 706 | 01-04-21 A | 01-11-21 A
SCDet-6480 | GRP-2021-SCDet1.8.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Esper (Manor & Mendota) | 772 | 01-04-21 A | 01-08-21 A
SCDet-5335 | GRP-2021-SCDet1.43.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Joy 3 (Wyoming & Ohio) | 1303 | 01-04-21 A | 01-14-21 A
SCDet-5175 | GRP-2021-SCDet1.41.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Joy 1 (Schaefer & Manor) | 2972 | 01-04-21 A | 02-22-21 A
AA4 21768 | GRP-2021-AA4.36.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Eberwhite Blvd West (W Liberty & Lutz) | 930 | 01-04-21 A | 01-08-21 A
AA4 21848 | GRP-2021-AA4.36.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - Eberwhite Blvd West (Lutz & W Madison) | 380 | 01-04-21 A | 01-09-21 A
EDET1 50648 | GRP-2021-ED1.28.1.2 | 2021 GRP - East Detroit 1 | Install Main - Harvard Rd (2) (Waveney St & Mack Ave) | 2600 | 01-04-21 A | 01-20-21 A
AA4 23958 | GRP-2021-AA4.40.4.2 | 2021 GRP - Ann Arbor 4 | Install Main - Lutz Ave (Eberwhite Blvd & S 7th St) | 840 | 01-04-21 A | 01-06-21 A
AA4 28458 | GRP-2021-AA4.6.6.2 | 2021 GRP - Ann Arbor 4 | Install Main - S 7th St (Jefferson & Jefferson Ct) | 120 | 01-04-21 A | 01-07-21 A
NWDET-22700 | PROJ-0951-NWDET1CO.61.7.2 | 2021 GRP - North West Detroit 1b | Install Main - Schoolcraft (3) (Glastonbury & Ashton) | 1260 | 01-04-21 A | 01-19-21 A
EDET1 50657 | GRP-2021-ED1.37.1.2 | 2021 GRP - East Detroit 1 | Install Main - Yorkshire Rd (2) (Waveney St & Mack Ave) | 2610 | 01-04-21 A | 01-12-21 A
WDET-5045 | PROJ-0951-WDET9-4.39.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Elevate Main - Greenview 3 (Paul & Ford) | 95 | 01-04-21 A | 01-07-21 A
WDET-5295 | PROJ-0951-WDET9-4.66.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Elevate Main - Crossroad Center (Ford & EOM) | 575 | 01-04-21 A | 01-04-21 A
NDET1-4441 | PROJ-0951-NDET1-1.16.1 | 2019 GRP - Carry Over - North Detroit 1 | Elevate Main - Outer Dr E (Rayalt & 7 Mile) | 2223 | 01-04-21 A | 04-13-21 A
EDET1 50892 | GRP-2021-ED1.27.1.2 | 2021 GRP - East Detroit 1 | Install Main - Grayton St (2) (Waveney St & Mack Ave) | 1550 | 01-04-21 A | 01-07-21 A
EDET1 50643 | GRP-2021-ED1.22.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bishop St (2) (Waveney St & Mack Ave) | 1400 | 01-04-21 A | 01-07-21 A
SCDet-5255 | GRP-2021-SCDet1.42.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Joy 2 (Manor & Wyoming) | 2438 | 01-05-21 A | 01-29-21 A
NCDET - 24955 | NEWPROJ-6.19.4.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - Fenkell (1) (Manor & Pinehurst) | 528 | 01-06-21 A | 01-08-21 A
SCDet-5655 | GRP-2021-SCDet1.47.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Tireman 1 (Decatur & Appoline) | 3135 | 01-06-21 A | 02-23-21 A
NWDET-9200 | PROJ-0951-NWDET1CO.56.2.2 | 2021 GRP - North West Detroit 1b | Install Main - Glastonbury (4) (Davison & EOM) | 447 | 01-06-21 A | 01-07-21 A
AA4 23058 | GRP-2021-AA4.39.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Jefferson Ct (19' WWPL S 7th & 10' WEPL S 7th St) | 60 | 01-07-21 A | 01-07-21 A
NWDET-15200 | PROJ-0951-NWDET1CO.32.2.2 | 2021 GRP - North West Detroit 1b | Install Main - Stahelin (2) (Davison & EOM) | 465 | 01-07-21 A | 01-08-21 A
GP-6375 | PROJ-0951-GP 5 -3.131.1.2 | 2020 GRP - Carry Over - GP 5 | Install Main - Mack North 2 (Balfour & Cadieux) GP4 | 130 | 01-07-21 A | 01-07-21 A
CDET2-2015 | GRP-2021-CDet2.9.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Chicago Blvd 2 (Wildemere & Genessee) | 3245 | 01-07-21 A | 01-08-21 A
CDET2-7510 | GRP-2021-CDet2.39.38.2 | 2021 GRP - Central Detroit 2 | Install Main - Wildemere 2 (W Chicago & Joy) | 1314 | 01-07-21 A | 01-12-21 A
EDET1 50651 | GRP-2021-ED1.31.1.2 | 2021 GRP - East Detroit 1 | Install Main - Kensington Ave (2) (Waveney St & Mack Ave)- Grosse pointe CL | 2637 | 01-07-21 A | 01-13-21 A
NCDET - 5675 | NEWPROJ-6.12.2.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - Pinehurst (ANO Fenkell & Fenkell) | 110 | 01-07-21 A | 01-08-21 A
SCDet-2135 | GRP-2021-SCDet1.2.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd N 2 (Steel & Birwood) | 1926 | 01-08-21 A | 01-20-21 A
AA4 23788 | GRP-2021-AA4.40.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - Lutz Ave (11' EWPL Crest Ave & Eberwhite Blvd) | 450 | 01-08-21 A | 01-08-21 A
AA4 26268 | GRP-2021-AA4.6.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - S 7th St (Jefferson Ct & W Madison St) | 550 | 01-08-21 A | 01-13-21 A
AA4 23618 | GRP-2021-AA4.40.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Lutz Ave (14' WEPL Soule Blvd & 11' EWPL Crest Ave) | 185 | 01-09-21 A | 01-09-21 A
NWDET-15530 | PROJ-0951-NWDET1CO.25.2.2 | 2021 GRP - North West Detroit 1b | Install Main - ASO Schoolcraft (1) (Artesian & Stahelin) | 328 | 01-11-21 A | 01-12-21 A
NCDET - 5165 | NEWPROJ-6.42.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - ANO Fenkell 2 (Pinehurst & Mendota) | 286 | 01-11-21 A | 01-14-21 A
CDET2-2735 | GRP-2021-CDet2.18.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Atkinson 2 (Linwood & Rosa Parks) | 2654 | 01-11-21 A | 01-22-21 A
CDET2-4095 | GRP-2021-CDet2.36.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Euclid 1 (Dexter & Linwood) | 2590 | 01-11-21 A | 01-20-21 A
EDET1 50641 | GRP-2021-ED1.20.1.2 | 2021 GRP - East Detroit 1 | Install Main - Audubon Rd (1) (Waveney St & Mack Ave) | 2700 | 01-11-21 A | 01-22-21 A
SCDet-6640 | GRP-2021-SCDet1.8.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Esper (Mendota & Joy) | 2390 | 01-11-21 A | 01-21-21 A
AA4 23138 | GRP-2021-AA4.39.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - Jefferson Ct (272' WWPL S 7th St & 16' WWPL S 7th St) | 290 | 01-11-21 A | 01-11-21 A
NWDET-13700 | PROJ-0951-NWDET1CO.13.4.2 | 2021 GRP - North West Detroit 1b | Install Main - Westwood (1) (Glendale & EOM) | 700 | 01-11-21 A | 01-13-21 A
NWDET-2445 | PROJ-0951-NWDET1CO.25.4.2 | 2021 GRP - North West Detroit 1b | Install Main - ASO Schoolcraft (1) (EOM & Auburn) | 195 | 01-12-21 A | 01-13-21 A
AA4 22248 | GRP-2021-AA4.37.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - Elder Blvd (4' WEPL Eberwhite Blvd & 4' EWPL Eberwhite Blvd) | 75 | 01-12-21 A | 01-12-21 A
AA4 20780 | GRP-2021-AA4.37.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Elder Blvd (11' WWPL Crest Ave & Eberwhite Blvd) | 275 | 01-12-21 A | 01-12-21 A
AA4 20779 | GRP-2021-AA4.36.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Eberwhite Blvd East (Woodbridge & Elder) | 285 | 01-12-21 A | 01-29-21 A
SWDET2-3070 | PROJ-0951-SWDET2.18.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 1 (At Dix) | 20 | 01-12-21 A | 01-12-21 A
SWDET2-12635 | PROJ-0951-SWDET2.18.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 1 (Wendall & Pearl) | 497 | 01-12-21 A | 01-15-21 A
NCDET - 5535 | NEWPROJ-6.9.2.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - Mendota (ANO Fenekell & Fenkell) - "Only to be installed if services cannot be moved to the alley" | 111 | 01-13-21 A | 01-14-21 A
NWDET-7340 | PROJ-0951-NWDET1CO.24.2.2 | 2021 GRP - North West Detroit 1b | Install Main - Auburn (1) (Davison & EOM) | 367 | 01-13-21 A | 01-15-21 A
CDET2-4735 | GRP-2021-CDet2.44.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Savery (Chicago & Joy) | 1315 | 01-13-21 A | 01-19-21 A
AA4 20798 | GRP-2021-AA4.55.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Woodbridge Blvd (Eberwhite Blvd & EOM) | 295 | 01-13-21 A | 01-29-21 A
SCDet-6270 | GRP-2021-SCDet1.43.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Joy 3 (Ohio & Greenlawn) | 1056 | 01-14-21 A | 01-22-21 A
NCDET - 5160 | NEWPROJ-6.41.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - ANO Fenkell 1 (Birwood & Washburn) | 931 | 01-14-21 A | 01-27-21 A
EDET1 50645 | GRP-2021-ED1.25.1.2 | 2021 GRP - East Detroit 1 | Install Main - Courville St (2) (Waveney St & Mack Ave) | 2530 | 01-14-21 A | 01-22-21 A
NWDET-2530 | PROJ-0951-NWDET1CO.18.1.2 | 2021 GRP - North West Detroit 1b | Install Main - Glendale (1) (Auburn & Artesian) | 1894 | 01-15-21 A | 02-26-21 A
SWDET2-12315 | PROJ-0951-SWDET2.18.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 1 (Wendall & WO Cabot) | 1911 | 01-15-21 A | 02-03-21 A
SCDet-5495 | GRP-2021-SCDet1.45.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Belton 1 (Decatur & Carlin) | 362 | 01-19-21 A | 01-28-21 A
EDET1 501846 | GRP-2021-ED1.34.3.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (N) (3) (Harvard & Harvard) | 50 | 01-19-21 A | 01-19-21 A
EDET1 507636 | GRP-2021-ED1.6.1.2 | 2021 GRP - East Detroit 1 | Install Main - Harvard Rd (1) (Waveney & ANO Warren) | 2090 | 01-19-21 A | 01-25-21 A
SCDet-3095 | GRP-2021-SCDet1.15.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Hartwell (Joy & Tireman) | 2569 | 01-19-21 A | 01-28-21 A
EDET1 501055 | GRP-2021-ED1.63.1.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (3) (E Outer Dr & Harvard Rd) | 1595 | 01-19-21 A | 01-25-21 A
CDET2-2255 | GRP-2021-CDet2.12.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Longfellow 1 (Dexter & Lawton) | 515 | 01-19-21 A | 01-20-21 A
SCDet-5815 | GRP-2021-SCDet1.49.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Mackenzie 1 (Hartwell & Littlefield) | 448 | 01-19-21 A | 01-20-21 A
AA4 20787 | GRP-2021-AA4.44.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Mt Vernon Ave (W Madison St & Mt Vernon Ave) | 135 | 01-20-21 A | 01-20-21 A
NWDET-20750 | PROJ-0951-NWDET1CO.60.4.2 | 2021 GRP - North West Detroit 1b | Install Main - Schoolcraft (2) (EOM & Warwick) | 251 | 01-20-21 A | 01-21-21 A
NWDET-20420 | PROJ-0951-NWDET1CO.60.3.2 | 2021 GRP - North West Detroit 1b | Install Main - Schoolcraft (2) (At Westwood) | 208 | 01-20-21 A | 01-20-21 A
SWDET2-8645 | PROJ-0951-SWDET2.16.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 4 (Casper & Central) | 464 | 01-20-21 A | 01-21-21 A
RR1 7801 | GRP-2021-RR.32.1.2 | 2021 GRP - Risk Rank | Install Main - Lamphere (Fenkell & Eaton) | 1729 | 01-20-21 A | 02-02-21 A
SCDet-9830 | GRP-2021-SCDet1.49.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Mackenzie 1 (Littlefield & Oakman Blvd) | 872 | 01-20-21 A | 01-21-21 A
SWDET2-2830 | PROJ-0951-SWDET2.15.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 3 (Woodmere & Casper) | 848 | 01-21-21 A | 02-03-21 A
AA4 24458 | GRP-2021-AA4.44.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Mt Vernon Ave (Mt Pleasant Ave & Manhattan Ave) | 765 | 01-21-21 A | 01-21-21 A
AA4 22168 | GRP-2021-AA4.37.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Elder Blvd (Eberwhite Blvd & EOM 280' EEPL Eberwhite Blvd) | 360 | 01-21-21 A | 01-21-21 A
CDET2-2415 | GRP-2021-CDet2.14.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Edison 1 (Dexter & Savery) | 523 | 01-22-21 A | 01-22-21 A
SCDet-10770 | GRP-2021-SCDet1.14.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Schaefer Hwy W 1 (PL Tireman & 15' NSPL Tireman) | 69 | 01-22-21 A | 01-22-21 A
NWDET-20560 | PROJ-0951-NWDET1CO.60.4.2 | 2021 GRP - North West Detroit 1b | Install Main - Schoolcraft (2) (Warwick & EOM) | 159 | 01-22-21 A | 01-22-21 A
CDET2-10300 | GRP-2021-CDet2.36.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Euclid 1 (Linwood & Linwood) | 79 | 01-22-21 A | 01-22-21 A
CDET2-5135 | GRP-2021-CDet2.49.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Linwood 2 (Carter & Euclid) | 1152 | 01-22-21 A | 02-19-21 A
SCDet-7640 | GRP-2021-SCDet1.27.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Morrow (Esper & Mackenzie) | 170 | 01-22-21 A | 02-23-21 A
SCDet-9670 | GRP-2021-SCDet1.55.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Mackenzie 2 (Oakman Blvd & Morrow Circle) | 244 | 01-22-21 A | 02-23-21 A
CDET2-2575 | GRP-2021-CDet2.16.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Wagner (Dexter & Savery) | 522 | 01-22-21 A | 01-25-21 A
EDET1 507796 | GRP-2021-ED1.6.3.2 | 2021 GRP - East Detroit 1 | Install Main - Harvard Rd (1) (ASO Warren & Waveney) | 1765 | 01-25-21 A | 02-03-21 A
NWDET-20700 | PROJ-0951-NWDET1CO.60.6.2 | 2021 GRP - North West Detroit 1b | Install Main - Schoolcraft (2) (At Artesian) | 190 | 01-25-21 A | 01-25-21 A
CDET2-2975 | GRP-2021-CDet2.21.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Clairmount 2 (Linwood & La Salle) | 818 | 01-25-21 A | 02-02-21 A
SCDet-5415 | GRP-2021-SCDet1.44.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Van Buren (Meadowdale & Schaefer) | 261 | 01-25-21 A | 01-28-21 A
CDET2-4175 | GRP-2021-CDet2.37.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Euclid 2 (Linwood & 14th) | 1780 | 01-25-21 A | 02-01-21 A
CDET2-6150 | GRP-2021-CDet2.21.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Clairmount 2 (La Salle & Rosa Parks) | 1844 | 01-25-21 A | 02-01-21 A
EDET1 501114 | GRP-2021-ED1.68.1.2 | 2021 GRP - East Detroit 1 | Install Main - 3 Mile Rd (2) (Waveney St & ANO Mack Ave) | 2525 | 01-25-21 A | 02-01-21 A
EDET1 50646 | GRP-2021-ED1.26.1.2 | 2021 GRP - East Detroit 1 | Install Main - Grayton St (1) (ASO E Warrern Ave & Waveney St) 2" | 1780 | 01-25-21 A | 02-01-21 A
SWDET2-7550 | PROJ-0951-SWDET2.74.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 2 (NO Woodmere & Woodmere) | 147 | 01-25-21 A | 02-03-21 A
CDET2-2655 | GRP-2021-CDet2.17.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Atkinson 1 (Dexter & Savery) | 520 | 01-27-21 A | 01-28-21 A
SCDet-7480 | GRP-2021-SCDet1.26.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Middlepointe (Esper & Tireman) | 1302 | 01-27-21 A | 02-23-21 A
SWDET2-24035 | PROJ-0951-SWDET2.82.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 1W (ASO Vernor & Chamberlain) | 2975 | 01-27-21 A | 03-19-21 A
SCDet-2375 | GRP-2021-SCDet1.6.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd S 2 (Steel & Birwood) | 1998 | 01-27-21 A | 02-23-21 A
SWDET2-7390 | PROJ-0951-SWDET2.72.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Cabot (NO Woodmere & Woodmere) | 353 | 01-27-21 A | 02-03-21 A
AA4 28418 | GRP-2021-AA4.7.6.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - ESO Jefferson Ct (Jefferson Ct & EOS) | 190 | 01-27-21 A | 01-27-21 A
AA4 20782 | GRP-2021-AA4.39.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Jefferson Ct (3' EWPL ESO Jefferson Ct & 272' WWPL S 7th St) | 65 | 01-27-21 A | 01-27-21 A
AA4 26748 | GRP-2021-AA4.49.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Soule Blvd (102' SSPL Wakefield Ave & 373' SSPL Lutz Ave) | 575 | 01-27-21 A | 01-27-21 A
EDET1 506916 | GRP-2021-ED1.65.3.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (2) (Courville & E Outer Dr) | 630 | 01-28-21 A | 01-29-21 A
CDET2-1855 | GRP-2021-CDet2.7.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Chicago Blvd 1 (Dexter & Wildemere) | 590 | 01-28-21 A | 02-01-21 A
AA4 20794 | GRP-2021-AA4.51.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Virginia St (Bemidji St & W Liberty St) | 257 | 01-28-21 A | 01-28-21 A
EDET1 50654 | GRP-2021-ED1.34.1.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (N) (3) (E Outer Dr & Harvard Rd) | 1595 | 01-29-21 A | 01-30-21 A
SCDet-8520 | GRP-2021-SCDet1.29.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Wyoming Ave East (26' SSPL Joy Rd & Tireman) | 29 | 01-29-21 A | 01-29-21 A
CDET2-4575 | GRP-2021-CDet2.42.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Wildemere 1 (Glynn & W Chicago) | 841 | 01-29-21 A | 02-01-21 A
AA4 27548 | GRP-2021-AA4.52.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Madison St (6' WEPL Eberwhite Blvd & Madison Pl) | 460 | 01-29-21 A | 01-29-21 A
NCDET - 25135 | NEWPROJ-6.19.6.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - Fenkell (1) (Mendota & Birwood) - "Only to be installed if services cannot be moved to the alley" | 306 | 02-01-21 A | 02-02-21 A
SCDet-3175 | GRP-2021-SCDet1.16.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Bingham (Littlefield & Tireman) | 1732 | 02-01-21 A | 03-04-21 A
SCDet-7800 | GRP-2021-SCDet1.28.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Normile (Esper & Belton) | 1279 | 02-01-21 A | 02-25-21 A
SCDet-10650 | GRP-2021-SCDet1.5.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd E 3 (13' NSPL Mackenzie & 16' NSPL Mackenzie) | 5 | 02-01-21 A | 02-01-21 A
SCDet-11060 | GRP-2021-SCDet1.18.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Ward (Mackenzie & Littlefield) | 431 | 02-01-21 A | 02-02-21 A
CDET2-10180 | GRP-2021-CDet2.8.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Euclid 2 (Rosa Parks & Rosa Parks) | 55 | 02-01-21 A | 04-05-21 A
SWDET2-23955 | PROJ-0951-SWDET2.82.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 1W (W Vernor & ASO Vernor) | 123 | 02-01-21 A | 02-02-21 A
EDET1 507956 | GRP-2021-ED1.6.2.2 | 2021 GRP - East Detroit 1 | Install Main - Harvard Rd (1) (ASO Warren & Warren) | 125 | 02-01-21 A | 02-01-21 A
NWDET-20490 | PROJ-0951-NWDET1CO.60.2.2 | 2021 GRP - North West Detroit 1b | Install Main - Schoolcraft (2) (At Piedmont) | 162 | 02-01-21 A | 02-01-21 A
SCDet-3655 | GRP-2021-SCDet1.22.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Manor (Esper & Tireman) | 295 | 02-01-21 A | 03-02-21 A
EDET1 50640 | GRP-2021-ED1.19.1.2 | 2021 GRP - East Detroit 1 | Install Main - Audubon Rd (2) (E Warrern Ave & Waveney St) | 1765 | 02-01-21 A | 03-09-21 A
NCDET - 5220 | NEWPROJ-6.3.2.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Main - Birwood (ANO Fenkell & Fenkell) - "Only to be installed if services cannot be moved to the alley" | 104 | 02-02-21 A | 02-02-21 A
RR1 6661 | GRP-2021-RR.16.1.2 | 2021 GRP - Risk Rank | Install Main - Patton (Tireman & Sawyer) | 1220 | 02-02-21 A | 02-04-21 A
SCDet-4055 | GRP-2021-SCDet1.4.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Freda (Esper & Tireman) | 1972 | 02-02-21 A | 02-23-21 A
CDET2-1535 | GRP-2021-CDet2.2.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Glynn 1 (Dexter & Linwood) | 2624 | 02-02-21 A | 02-23-21 A
EDET1 501526 | GRP-2021-ED1.21.3.2 | 2021 GRP - East Detroit 1 | Install Main - Bishop St (1) (ASO E Warrern Ave & Waveney St) | 1775 | 02-02-21 A | 02-22-21 A
EDET1 501057 | GRP-2021-ED1.65.1.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (2) (Balfour Rd & Courville St) | 2335 | 02-03-21 A | 02-26-21 A
CDET2-8170 | GRP-2021-CDet2.49.2.2 | 2021 GRP - Central Detroit 2 | Install Main - Linwood 2 (Joy & Euclid) | 2579 | 02-03-21 A | 03-09-21 A
SWDET2-1870 | PROJ-0951-SWDET2.2.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 2 (Lonyo & Woodmere) | 667 | 02-03-21 A | 02-26-21 A
CDET2-10830 | GRP-2021-CDet2.24.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Taylor 2 (La Salle & Rosa Parks) | 1856 | 02-03-21 A | 02-19-21 A
EDET1 501116 | GRP-2021-ED1.70.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bedford St (2) West (Waveney St & Mack Ave) West | 2545 | 02-03-21 A | 03-03-21 A
SCDet-5575 | GRP-2021-SCDet1.46.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Belton 2 (Mendota & Middlepointe) | 493 | 02-03-21 A | 02-24-21 A
SCDet-5895 | GRP-2021-SCDet1.50.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Civic (Appoline & Manor) | 644 | 02-03-21 A | 03-02-21 A
CDET2-8590 | GRP-2021-CDet2.5.2.2 | 2021 GRP - Central Detroit 2 | Install Main - W Boston Blvd 1 (Wildemere & EOM) | 187 | 02-04-21 A | 02-04-21 A
CDET2-5830 | GRP-2021-CDet2.5.3.2 | 2021 GRP - Central Detroit 2 | Install Main - W Boston Blvd 1 (Wildemere & Wildemere) | 543 | 02-04-21 A | 02-23-21 A
AA4 20532 | GRP-2021-AA4.19.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Madison Pl (W Madison St & EOM) | 715 | 02-04-21 A | 02-24-21 A
AA4 20784 | GRP-2021-AA4.41.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Manhattan Dr (Mt Vernon Ave& Mt Pleasant Dr) | 210 | 02-04-21 A | 02-04-21 A
SWDET2-3870 | PROJ-0951-SWDET2.29.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Richard (EOM & Woodmere) | 406 | 02-04-21 A | 02-23-21 A
SCDet-8450 | GRP-2021-SCDet1.29.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Wyoming Ave West (Joy & Tireman) | 2517 | 02-04-21 A | 03-04-21 A
CDET2-8010 | GRP-2021-CDet2.49.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Linwood 2 (Gladstone & Carter) | 278 | 02-19-21 A | 02-22-21 A
SCDet-4935 | GRP-2021-SCDet1.38.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Steel (Tireman & Oakman) | 781 | 02-22-21 A | 02-25-21 A
SWDET2-6830 | PROJ-0951-SWDET2.66.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Casper (Dix & Tie-In) | 437 | 02-22-21 A | 02-24-21 A
SWDET2-12955 | PROJ-0951-SWDET2.31.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 3 (W Vernor & ASO Vernor) | 153 | 02-22-21 A | 03-11-21 A
CDET2-6310 | GRP-2021-CDet2.24.57.2 | 2021 GRP - Central Detroit 2 | Install Main - Taylor 2 (Linwood & La Salle) | 818 | 02-22-21 A | 02-23-21 A
SCDet-9330 | GRP-2021-SCDet1.11.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Decatur (309' NNPL Tireman & Tireman) | 309 | 02-22-21 A | 02-25-21 A
RR1 7961 | GRP-2021-RR.34.1.2 | 2021 GRP - Risk Rank | Install Main - Appoline (Santa Clara & Mcnichols) | 1255 | 02-22-21 A | 03-02-21 A
SCDet-5095 | GRP-2021-SCDet1.40.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Griggs (Joy & Oakman) | 383 | 02-22-21 A | 02-23-21 A
CDET2-8330 | GRP-2021-CDet2.49.4.2 | 2021 GRP - Central Detroit 2 | Install Main - Linwood 2 (Atkinson & Gladstone) | 1325 | 02-22-21 A | 02-25-21 A
SCDet-11300 | GRP-2021-SCDet1.20.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Appoline (Civic & Tireman) | 302 | 02-22-21 A | 03-02-21 A
EDET1 50656 | GRP-2021-ED1.36.1.2 | 2021 GRP - East Detroit 1 | Install Main - Yorkshire Rd (1) (E Warrern Ave & Waveney St) | 1775 | 02-22-21 A | 02-26-21 A
SCDet-6340 | GRP-2021-SCDet1.47.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Tireman 1 East (3' SNPL Tireman & 4' NSPL Tireman) | 80 | 02-23-21 A | 02-23-21 A
EDET1 506266 | GRP-2021-ED1.70.3.2 | 2021 GRP - East Detroit 1 | Install Main - Bedford St East (2) (Waveney St & Mack Ave) East | 2545 | 02-23-21 A | 03-01-21 A
SCDet-6330 | GRP-2021-SCDet1.47.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Tireman 1 West (3' SNPL Tireman & 4' NSPL Tireman) | 80 | 02-23-21 A | 02-23-21 A
EDET1 503586 | GRP-2021-ED1.11.6.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (3) (Neff Ave & Hereford St) | 400 | 02-23-21 A | 02-24-21 A
SCDet-10150 | GRP-2021-SCDet1.3.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd W 1 (10' SNPL Mackenzie & 13' NSPL Mackenzie) | 68 | 02-23-21 A | 02-25-21 A
SWDET2-7710 | PROJ-0951-SWDET2.76.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Oakdale (NO Woodmere & Woodmere) | 421 | 02-23-21 A | 02-25-21 A
SCDet-3895 | GRP-2021-SCDet1.26.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Middlepointe (Mendota & Esper) | 455 | 02-24-21 A | 03-02-21 A
SWDET2-10265 | PROJ-0951-SWDET2.8.3.2 | 2021 GRP - South West Detroit 2 | Install Main - ASO W Vernor 1 (Lawndale & Central) | 2065 | 02-24-21 A | 03-23-21 A
SCDet-2455 | GRP-2021-SCDet1.7.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd E 1 (Mackenzie & Tireman) | 1555 | 02-24-21 A | 03-01-21 A
CDET2-6470 | GRP-2021-CDet2.26.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Hazelwood 2 (La Salle & Rosa Parks) | 1857 | 02-24-21 A | 03-01-21 A
AA4 24298 | GRP-2021-AA4.43.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Mt Pleasant Ave (Manhattan Dr & Sunnyside Blvd) | 872 | 02-24-21 A | 02-24-21 A
SCDet-3975 | GRP-2021-SCDet1.27.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Morrow (Esper & Tireman) | 1658 | 02-25-21 A | 03-05-21 A
SWDET2-3150 | PROJ-0951-SWDET2.19.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 2 (Richard & EO Oakdale) | 632 | 02-25-21 A | 02-25-21 A
SWDET2-7870 | PROJ-0951-SWDET2.78.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Sharon (NO Woodmere & Woodmere) | 365 | 02-25-21 A | 02-25-21 A
AA4 20793 | GRP-2021-AA4.50.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Sunnyside Blvd (EOM & S 7th St) | 985 | 02-25-21 A | 02-26-21 A
SCDet-5015 | GRP-2021-SCDet1.39.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Birwood (Joy & Oakman) | 716 | 02-25-21 A | 03-01-21 A
CDET2-7850 | GRP-2021-CDet2.48.2.2 | 2021 GRP - Central Detroit 2 | Install Main - Linwood 1 (Longfellow & Atkinson) | 650 | 02-25-21 A | 02-26-21 A
EDET1 505036 | GRP-2021-ED1.18.9.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) S (Woodhall St & Neff Ave) | 350 | 02-25-21 A | 02-25-21 A
SWDET2-4030 | PROJ-0951-SWDET2.31.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 3 (Richard & ANO W Vernor) | 697 | 02-26-21 A | 03-03-21 A
CDET2-1040 | GRP-2021-CDet2.4.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Calvert 1 (Dexter & Linwood) | 2669 | 02-26-21 A | 03-05-21 A
EDET1 504876 | GRP-2021-ED1.18.7.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (E Warren Ave & ASO E Warren Ave @ Woodhall St (West Side) | 110 | 02-26-21 A | 02-26-21 A
AA4 24128 | GRP-2021-AA4.40.5.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Lutz Ave (EOM 215' WWPL Soule Blvd & 3' WWPL Soule Blvd) | 5 | 02-26-21 A | 02-26-21 A
Ypsi 3-10900 | PROJ-0951-YSP3.37.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Nash 1 (Old Ecorse & Desoto) | 1375 | 03-01-21 A | 03-08-21 A
Ypsi 3-2760 | PROJ-0951-YSP3.36.3.2 | 2021 GRP - Ypsilanti 3 | Install Main - Old Ecorse (Nash & Onandaga) | 340 | 03-01-21 A | 03-03-21 A
Ypsi 3-2860 | PROJ-0951-YSP3.41.3.2 | 2021 GRP - Ypsilanti 3 | Install Main - Desoto (Old Ecorse & Dodge) | 1260 | 03-01-21 A | 03-05-21 A
SCDet-3415 | GRP-2021-SCDet1.19.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Sorrento (Joy & Mackenzie) | 834 | 03-01-21 A | 03-04-21 A
AA4 20378 | GRP-2021-AA4.3.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Potter Ave (Hutchins & Presscott Ave) | 275 | 03-01-21 A | 03-01-21 A
AA4 20797 | GRP-2021-AA4.53.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Stadium Blvd (Hutchins Ave & Prescott Ave) | 282 | 03-01-21 A | 03-02-21 A
SWDET2-8485 | PROJ-0951-SWDET2.2.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 2 (EOM & Lonyo) | 268 | 03-01-21 A | 03-02-21 A
SCDet-6360 | GRP-2021-SCDet1.47.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Tireman 1 East (3' SNPL Tireman & 15' NSPL Tireman) | 70 | 03-01-21 A | 03-02-21 A
SCDet-7230 | GRP-2021-SCDet1.25.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Mendota (Joy & Oakman) | 716 | 03-01-21 A | 03-05-21 A
SCDet-8510 | GRP-2021-SCDet1.29.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Wyoming Ave West (3' SNPL TIREMAN AVENUE & 5' NSPL TIREMAN AVENUE) | 80 | 03-01-21 A | 03-01-21 A
RR1 7561 | GRP-2021-RR.29.1.2 | 2021 GRP - Risk Rank | Install Main - Fielding (McNichols & Grand River) | 1465 | 03-01-21 A | 03-10-21 A
EDET1 503426 | GRP-2021-ED1.11.4.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (3) (Harvard Rd & Cadieux Rd) | 365 | 03-01-21 A | 03-08-21 A
EDET1 508626 | GRP-2021-ED1.11.8.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (3) (E Warren & ASO Warren) | 145 | 03-01-21 A | 03-01-21 A
EDET1 503506 | GRP-2021-ED1.11.5.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (3) (E Warren Ave & Woodhall St) | 1135 | 03-01-21 A | 03-05-21 A
EDET1 507256 | GRP-2021-ED1.5.1.2 | 2021 GRP - East Detroit 1 | Install Main - Kensington Ave (ASO E Warren & Waveney) | 1770 | 03-01-21 A | 03-04-21 A
CDET2-3295 | GRP-2021-CDet2.26.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Hazelwood 2 (Linwood & La Salle) | 813 | 03-01-21 A | 03-03-21 A
CDET2-7690 | GRP-2021-CDet2.48.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Linwood 1 (ANO Chicago & Llongfellow) | 658 | 03-01-21 A | 03-02-21 A
SWDET2-6190 | PROJ-0951-SWDET2.58.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Lonyo 1 (EOM & Dix) | 965 | 03-01-21 A | 03-05-21 A
EDET1 501056 | GRP-2021-ED1.64.1.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (1) (Wayburn Ave & Balfour Rd) | 2090 | 03-01-21 A | 03-09-21 A
SCDet-5975 | GRP-2021-SCDet1.51.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Blowers (Mendota & Middlepointe) | 535 | 03-02-21 A | 03-03-21 A
SCDet-9500 | GRP-2021-SCDet1.10.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Littlefield 2 (Oakman & Appoline) | 432 | 03-02-21 A | 03-03-21 A
SWDET2-2430 | PROJ-0951-SWDET2.10.1.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor 2 (Dearborn City Limit & Woodmere) | 2013 | 03-02-21 A | 03-11-21 A
AA4 24938 | GRP-2021-AA4.3.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Potter Ave (4' EWPL Hutchins Ave & 4' WEPL Hutchins Ave) | 60 | 03-03-21 A | 03-03-21 A
SCDet-2775 | GRP-2021-SCDet1.11.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Decatur (Belton & EOM) | 297 | 03-03-21 A | 03-05-21 A
SCDet-9170 | GRP-2021-SCDet1.11.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Decatur (Belton & 309' NNPL Tireman) | 617 | 03-03-21 A | 03-03-21 A
CDET2-5215 | GRP-2021-CDet2.50.1.2 | 2021 GRP - Central Detroit 2 | Install Main - LaSalle 1 (Clairmount & Gladstone) | 1105 | 03-03-21 A | 03-05-21 A
SCDet-6135 | GRP-2021-SCDet1.53.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Westover (Mendota & Middlepointe) | 497 | 03-03-21 A | 03-04-21 A
SWDET2-12795 | PROJ-0951-SWDET2.31.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 3 (ANO W Vernor & W Vernor) | 127 | 03-03-21 A | 03-03-21 A
SCDet-7310 | GRP-2021-SCDet1.25.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Mendota (Oakman & Esper) | 755 | 03-03-21 A | 03-04-21 A
Ypsi 3-10670 | PROJ-0951-YSP3.36.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Old Ecorse (Nash & Hudson) | 605 | 03-03-21 A | 03-03-21 A
Ypsi 3-2520 | PROJ-0951-YSP3.36.2.2 | 2021 GRP - Ypsilanti 3 | Install Main - Old Ecorse (73' NSPL Ecorse Rd & 3' NSPL Ecorse Rd) | 70 | 03-03-21 A | 03-03-21 A
RR1 8041 | GRP-2021-RR.35.1.2 | 2021 GRP - Risk Rank | Install Main - Stoepel (8 Mile & Pembroke) | 2563 | 03-04-21 A | 03-12-21 A
SCDet-3015 | GRP-2021-SCDet1.14.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Schaefer Hwy W 1 (Joy & Tireman) | 2578 | 03-04-21 A | 03-15-21 A
SWDET2-13115 | PROJ-0951-SWDET2.31.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 3 (ASO Vernor & Elsmere) | 732 | 03-04-21 A | 03-11-21 A
AA4 22818 | GRP-2021-AA4.1.4.2 | 2021 GRP - Ann Arbor 4 | Install Main - Hutchins Ave (Pauline Bvd & Potter Ave) | 670 | 03-04-21 A | 03-18-21 A
AA4 22898 | GRP-2021-AA4.1.5.2 | 2021 GRP - Ann Arbor 4 | Install Main - Hutchins Ave (Potter Ave & W Stadium Blvd) | 930 | 03-04-21 A | 03-05-21 A
EDET1 506556 | GRP-2021-ED1.76.3.2 | 2021 GRP - East Detroit 1 | Install Main - Devonshire Rd (2) (Brunswick St & Mack Ave) | 565 | 03-04-21 A | 03-08-21 A
SCDet-10900 | GRP-2021-SCDet1.19.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Sorrento (Mackenzie & Tireman) | 1722 | 03-04-21 A | 03-10-21 A
EDET1 504716 | GRP-2021-ED1.18.5.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (Cadieux Dr & ASO E Warren Ave) | 110 | 03-05-21 A | 03-05-21 A
EDET1 503666 | GRP-2021-ED1.11.7.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (3) (E Warren Ave & ASO E Warren Ave) | 110 | 03-05-21 A | 03-05-21 A
EDET1 50837 | GRP-2021-ED1.39.1.2 | 2021 GRP - East Detroit 1 | Install Main - Barham St (2) (Waveney St & Mack Ave) | 700 | 03-05-21 A | 04-20-21 A
CDET2-8510 | GRP-2021-CDet2.50.3.2 | 2021 GRP - Central Detroit 2 | Install Main - LaSalle 1 (Gladstone & W Euclid) | 1366 | 03-05-21 A | 03-10-21 A
RR1 6741 | GRP-2021-RR.18.1.2 | 2021 GRP - Risk Rank | Install Main - St Marys (Chicago & Plymouth) | 2535 | 03-05-21 A | 03-15-21 A
SCDet-3735 | GRP-2021-SCDet1.24.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Pinehurst (Joy & Oakman) | 725 | 03-08-21 A | 03-17-21 A
RR1 51437 | GRP-2021-RR1.86.1.2 | 2021 GRP - River Rouge | Install Main - Lafferty Ave (Salliotte & EOM) - Removed from Scope | 0 | 03-08-21 A | 03-08-21 A
AA4 20783 | GRP-2021-AA4.40.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Lutz Ave (4' EWPL Soule Blvd & 11' WEPL Soule Blvd) | 80 | 03-08-21 A | 03-08-21 A
EDET1 50642 | GRP-2021-ED1.21.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bishop St (1) (E Warrern Ave & Waveney St) | 110 | 03-08-21 A | 03-08-21 A
SWDET2-2910 | PROJ-0951-SWDET2.16.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 4 (Central & W Vernor) | 2953 | 03-08-21 A | 03-23-21 A
SCDet-8280 | GRP-2021-SCDet1.24.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Pinehurst (Esper & Tireman) | 600 | 03-08-21 A | 03-24-21 A
SCDet-9010 | GRP-2021-SCDet1.17.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Cheyenne (Littlefield & Tireman) | 1581 | 03-08-21 A | 03-19-21 A
SCDet-11220 | GRP-2021-SCDet1.18.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Ward (Littlefield & Tireman) | 1305 | 03-08-21 A | 03-11-21 A
RR1 57950 | GRP-2021-RR1.85.3.2 | 2021 GRP - River Rouge | Install Main - Labadie St (190' WWPL Webster St & 55' WWPL Webster St) - Removed from Scope | 0 | 03-08-21 A | 03-08-21 A
RR1 8761 | GRP-2021-RR.44.1.2 | 2021 GRP - Risk Rank | Install Main - Kenmoor (Conner & Gunston) | 2291 | 03-08-21 A | 03-17-21 A
EDET1 505196 | GRP-2021-ED1.18.11.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) S (Bishop St & Grayton St) | 315 | 03-08-21 A | 03-09-21 A
EDET1 501124 | GRP-2021-ED1.78.1.2 | 2021 GRP - East Detroit 1 | Install Main - Haverhill St (2) (Waveney St& ANO Mack Ave) | 2535 | 03-08-21 A | 03-11-21 A
SCDet-6880 | GRP-2021-SCDet1.22.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Manor East (Oakman & Belton) | 915 | 03-08-21 A | 03-15-21 A
SWDET2-2190 | PROJ-0951-SWDET2.7.1.2 | 2021 GRP - South West Detroit 2 | Install Main - ANO W Vernor (Woodmere & Norman) | 2123 | 03-08-21 A | 03-18-21 A
Ypsi 3-10550 | PROJ-0951-YSP3.35.2.2 | 2021 GRP - Ypsilanti 3 | Install Main - Hudson (Ecorse & Olds) | 760 | 03-09-21 A | 03-10-21 A
SCDet-4215 | GRP-2021-SCDet1.29.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Wyoming Ave East (Joy & Tireman) | 2521 | 03-09-21 A | 03-17-21 A
SWDET2-3470 | PROJ-0951-SWDET2.24.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Elsmere 1 (Woodmere & Avis) | 994 | 03-09-21 A | 03-12-21 A
Ypsi 3 - 10551 | PROJ-0951-YSP3.41.5.2 | 2021 GRP - Ypsilanti 3 | Install Main - Desoto (Desoto & Dodge) | 60 | 03-09-21 A | 03-09-21 A
EDET1 501122 | GRP-2021-ED1.76.1.2 | 2021 GRP - East Detroit 1 | Install Main - Devonshire Rd (2) (Waveney Ave & Bremen St) | 730 | 03-09-21 A | 03-09-21 A
Ypsi 3-10050 | PROJ-0951-YSP3.33.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Dodge (Desoto & Nash) | 415 | 03-09-21 A | 03-10-21 A
Ypsi 3-2980 | PROJ-0951-YSP3.37.2.2 | 2021 GRP - Ypsilanti 3 | Install Main - Nash 1 (Desoto & Tyler) | 1555 | 03-09-21 A | 03-16-21 A
SWDET2-2670 | PROJ-0951-SWDET2.13.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Central 1 W (ASO Vernor & Logan) | 1500 | 03-10-21 A | 04-02-21 A
EDET1 503346 | GRP-2021-ED1.11.3.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (3) (Grayton St & Harvard Rd) | 310 | 03-10-21 A | 03-10-21 A
EDET1 505276 | GRP-2021-ED1.26.3.2 | 2021 GRP - East Detroit 1 | Install Main - Grayton St (1) (E Warrern Ave & ASO E Waveney St) 6'' | 110 | 03-10-21 A | 03-10-21 A
EDET1 506166 | GRP-2021-ED1.49.2.2 | 2021 GRP - East Detroit 1 | Install Main - Balfour Rd (Waveney Crossing) (East Side)) | 45 | 03-10-21 A | 03-10-21 A
EDET1 506226 | GRP-2021-ED1.49.2.2 | 2021 GRP - East Detroit 1 | Install Main - Balfour Rd (Waveney Crossing (West Side) | 45 | 03-10-21 A | 03-10-21 A
SWDET2-20485 | PROJ-0951-SWDET2.43.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Mandale (Elsemere & Lawndale) | 1082 | 03-10-21 A | 03-19-21 A
AA4 20375 | GRP-2021-AA4.4.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Franklin Blvd (S 7th St & Hutchins Ave) | 460 | 03-10-21 A | 03-10-21 A
Ypsi 3-10300 | PROJ-0951-YSP3.34.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Olds (Hudson & Desoto) | 485 | 03-10-21 A | 03-10-21 A
EDET1 50644 | GRP-2021-ED1.24.1.2 | 2021 GRP - East Detroit 1 | Install Main - Courville St (1) (E Warrern Ave & Waveney St) | 1765 | 03-11-21 A | 03-12-21 A
EDET1 501120 | GRP-2021-ED1.74.1.2 | 2021 GRP - East Detroit 1 | Install Main - Buckingham Ave (2) (Waveney St & Mack Ave) | 2600 | 03-11-21 A | 03-17-21 A
Ypsi 3-2430 | PROJ-0951-YSP3.41.2.2 | 2021 GRP - Ypsilanti 3 | Install Main - Desoto (Tyler & Nash) | 1505 | 03-11-21 A | 03-17-21 A
CDET2-4015 | GRP-2021-CDet2.35.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Philadelphia 2 (Linwood & La Salle) | 859 | 03-11-21 A | 03-15-21 A
SCDet-2695 | GRP-2021-SCDet1.10.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Littlefield 2 (Belton & Oakman) | 251 | 03-12-21 A | 03-17-21 A
SCDet-8850 | GRP-2021-SCDet1.54.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Belton 3 (Sorrento & Littlefield) | 141 | 03-12-21 A | 03-17-21 A
EDET1 501118 | GRP-2021-ED1.72.1.2 | 2021 GRP - East Detroit 1 | Install Main - Berkshire St (2) (Bremen St & Mack Ave) | 1885 | 03-12-21 A | 03-16-21 A
CDET2-7150 | GRP-2021-CDet2.35.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Philadelphia 2 (La Salle & 14th) | 756 | 03-12-21 A | 03-12-21 A
CDET2-5055 | GRP-2021-CDet2.48.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Linwood 1 (Collingwood & Longfellow) | 1916 | 03-12-21 A | 03-17-21 A
RR1 7221 | GRP-2021-RR.25.1.2 | 2021 GRP - Risk Rank | Install Main - Irvington (State Fair & 7 Mile) | 2615 | 03-12-21 A | 03-29-21 A
SCDet-2935 | GRP-2021-SCDet1.13.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Schaefer Hwy E 1 (Joy & Tireman) | 2584 | 03-15-21 A | 03-23-21 A
SCDet-3335 | GRP-2021-SCDet1.18.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Ward (Joy & Mackenzie) | 844 | 03-15-21 A | 03-17-21 A
SWDET2-2270 | PROJ-0951-SWDET2.8.1.2 | 2021 GRP - South West Detroit 2 | Install Main - ASO W Vernor 1 (Woodmere & Lawndale) | 1120 | 03-15-21 A | 03-24-21 A
SCDet-8120 | GRP-2021-SCDet1.24.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Pinehurst (Oakman & Esper) | 1108 | 03-15-21 A | 03-23-21 A
SWDET2-13595 | PROJ-0951-SWDET2.80.1.2 | 2021 GRP - South West Detroit 2 | Install Main - ASO W Vernor 2 (Central & Beard) | 1714 | 03-15-21 A | 03-23-21 A
EDET1 507456 | GRP-2021-ED1.65.83.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (Warren & Waveney) | 85 | 03-15-21 A | 03-15-21 A
EDET1 502226 | GRP-2021-ED1.67.2.2 | 2021 GRP - East Detroit 1 | Install Main - 3 Mile Rd (1) (E Warrern Ave & Waveney St) | 1820 | 03-15-21 A | 03-17-21 A
EDET1 50462 | GRP-2021-ED1.11.1.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (3) (E Outer Dr & Bishop St) | 980 | 03-15-21 A | 03-17-21 A
SCDet-6800 | GRP-2021-SCDet1.22.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Manor West (Oakman & Civic) | 1407 | 03-15-21 A | 03-17-21 A
SWDET2-21635 | PROJ-0951-SWDET2.75.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Norman (ANO Vernor & ANO Vernor) | 132 | 03-15-21 A | 03-18-21 A
SCDet-10310 | GRP-2021-SCDet1.3.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd W 1 (Belton & Tireman) | 908 | 03-16-21 A | 03-17-21 A
CDET2-7310 | GRP-2021-CDet2.35.2.2 | 2021 GRP - Central Detroit 2 | Install Main - Philadelphia 2 (14th & EOM) | 157 | 03-16-21 A | 03-16-21 A
RR1 7881 | GRP-2021-RR.33.1.2 | 2021 GRP - Risk Rank | Install Main - Florence (Hamilton & Woodward) | 2665 | 03-16-21 A | 06-01-21 A
SWDET2-10105 | PROJ-0951-SWDET2.7.3.2 | 2021 GRP - South West Detroit 2 | Install Main - ANO W Vernor (Norman & Inglis) | 270 | 03-16-21 A | 03-18-21 A
SWDET2-4590 | PROJ-0951-SWDET2.38.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Avis (Woodmere & Elsmere) | 718 | 03-16-21 A | 03-19-21 A
CDET2-5375 | GRP-2021-CDet2.52.1.2 | 2021 GRP - Central Detroit 2 | Install Main - 14th 1 (Pingree & W Euclid) | 626 | 03-17-21 A | 03-17-21 A
AA4 28638 | GRP-2021-AA4.2.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Pauline Blvd (S 7th St & Hutchinst) | 338 | 03-17-21 A | 03-17-21 A
SWDET2-6990 | PROJ-0951-SWDET2.68.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Inglis (ANO W Vernor & W Vernor) | 251 | 03-17-21 A | 03-18-21 A
Ypsi 3-4090 | PROJ-0951-YSP3.9.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Onandaga (Eugene & Old Ecorse) | 2140 | 03-17-21 A | 03-24-21 A
EDET1 50461 | GRP-2021-ED1.10.1.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (2) (Chatsworth St & E Outer Dr) | 2670 | 03-17-21 A | 03-30-21 A
EDET1 50846 | GRP-2021-ED1.48.1.2 | 2021 GRP - East Detroit 1 | Install Main - Wayburn Ave (2) (Waveney St & Mack Ave) | 1975 | 03-17-21 A | 03-22-21 A
SWDET2-15885 | PROJ-0951-SWDET2.13.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Central 1 E (ASO Vernor & Logan) | 1501 | 03-18-21 A | 04-06-21 A
CDET2-1935 | GRP-2021-CDet2.7.2.2 | 2021 GRP - Central Detroit 2 | Install Main - Chicago Blvd 1 (Lawton & Linwood) | 970 | 03-18-21 A | 03-18-21 A
CDET2-10330 | GRP-2021-CDet2.6.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Collingwood (AWO Linwood & Linwood) | 127 | 03-18-21 A | 03-18-21 A
CDET2-6990 | GRP-2021-CDet2.33.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Pingree 2 (La Salle & 14th) | 792 | 03-18-21 A | 03-18-21 A
EDET1 503756 | GRP-2021-ED1.69.3.2 | 2021 GRP - East Detroit 1 | Install Main - Bedford St (1) (E Warren Ave & Waveney St) East | 1820 | 03-18-21 A | 03-23-21 A
Ypsi 3-3590 | PROJ-0951-YSP3.7.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Cayuga (Eugene & Onandaga) | 695 | 03-19-21 A | 03-19-21 A
CDET2-3855 | GRP-2021-CDet2.33.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Pingree 2 (Linwood & La Salle) | 856 | 03-19-21 A | 03-19-21 A
CDET2-7570 | GRP-2021-CDet2.47.3 | 2021 GRP - Central Detroit 2 | Install Main - Lawton 1 (W Boston & W Chicago) | 559 | 03-19-21 A | 03-19-21 A
EDET1 501048 | GRP-2021-ED1.56.1.2 | 2021 GRP - East Detroit 1 | Install Main - Chatsworth St (2) (Bremen St & Mack Ave) | 1805 | 03-19-21 A | 03-24-21 A
CDET2-1695 | GRP-2021-CDet2.5.1.2 | 2021 GRP - Central Detroit 2 | Install Main - W Boston Blvd 1 (Linwood & Lawton) | 786 | 03-19-21 A | 03-19-21 A
CDET2-5990 | GRP-2021-CDet2.11.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Rochester (Wildemere & lawton) | 869 | 03-19-21 A | 03-22-21 A
SCDet-3575 | GRP-2021-SCDet1.21.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Meyers (Joy & Oakman) | 714 | 03-22-21 A | 03-23-21 A
Ypsi 3-3840 | PROJ-0951-YSP3.8.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Oswego (Onandaga & Eugene) | 1305 | 03-22-21 A | 03-24-21 A
SCDet-3255 | GRP-2021-SCDet1.17.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Cheyenne (Joy & Littlefield) | 1022 | 03-22-21 A | 03-23-21 A
SWDET2-4990 | PROJ-0951-SWDET2.43.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Mandale (Woodmere & Elsemere) | 652 | 03-22-21 A | 03-24-21 A
RR1 7141 | GRP-2021-RR.24.1.2 | 2021 GRP - Risk Rank | Install Main - Spokane (Beechwood & Colfax) | 2255 | 03-22-21 A | 04-01-21 A
RR1 8521 | GRP-2021-RR.41.1.2 | 2021 GRP - Risk Rank | Install Main - 8th (Southfield & W Outer) | 2458 | 03-22-21 A | 04-13-21 A
RR1 10151 | GRP-2021-RR.27.2.2 | 2021 GRP - Risk Rank | Install Main - Burt (Westfield & Joy) West | 1873 | 03-22-21 A | 03-31-21 A
EDET1 507396 | GRP-2021-ED1.69.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bedford St (1) (E Warren Ave & Waveney St) West | 1820 | 03-22-21 A | 03-30-21 A
SCDet-4535 | GRP-2021-SCDet1.33.1.2 | 2021 GRP - South Central Detroit 1 | Elevate Main - Ohio (Joy & Tireman) | 2539 | 03-22-21 A | 03-31-21 A
SCDet-4135 | GRP-2021-SCDet1.28.1.2 | 2021 GRP - South Central Detroit 1 | Elevate Main - Normile (Belton & Tireman) | 880 | 03-22-21 A | 03-30-21 A
SWDET2-13275 | PROJ-0951-SWDET2.32.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 4 (Avis & Fort) | 2770 | 03-22-21 A | 04-09-21 A
CDET2-2175 | GRP-2021-CDet2.11.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Rochester (Dexter & Wildemere) | 965 | 03-22-21 A | 03-23-21 A
CDET2-3535 | GRP-2021-CDet2.29.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Carter (Dexter & Linwood) | 2589 | 03-22-21 A | 03-29-21 A
CDET2-3695 | GRP-2021-CDet2.31.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Blaine 2 (Linwood & La Salle) | 853 | 03-22-21 A | 03-23-21 A
SCDet-7040 | GRP-2021-SCDet1.22.5.2 | 2021 GRP - South Central Detroit 1 | Install Main - Manor East (Joy & Oakman) | 717 | 03-23-21 A | 03-25-21 A
CDET2-6670 | GRP-2021-CDet2.31.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Blaine 2 (La Salle & Rosa Parks) | 1331 | 03-23-21 A | 03-25-21 A
RR1 7061 | GRP-2021-RR.22.1.2 | 2021 GRP - Risk Rank | Install Main - Bloom (7 Mile & Nevada) East | 2675 | 03-23-21 A | 04-26-21 A
SCDet-6960 | GRP-2021-SCDet1.22.4.2 | 2021 GRP - South Central Detroit 1 | Install Main - Manor West (Joy & Oakman) | 726 | 03-23-21 A | 03-25-21 A
RR1 55 | GRP-2021-RR1.1.1.2 | 2021 GRP - River Rouge | Install Main - Southfield Rd (207' WWPL Webster & High) | 505 | 03-23-21 A | 04-09-21 A
SWDET2-14705 | PROJ-0951-SWDET2.72.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Cabot (ASO Vernor & Mandale) | 796 | 03-23-21 A | 03-30-21 A
EDET1 506716 | GRP-2021-ED1.76.2.2 | 2021 GRP - East Detroit 1 | Elevate Main - Devonshire Rd (2) (Bremen St & Brunswick St) | 1247 | 03-23-21 A | 03-23-21 A
EDET1 50688 | GRP-2021-ED1.4.1.2 | 2021 GRP - East Detroit 1 | Install Main - ANO Mack Ave (1) (Alter Rd & Nottingham Rd) | 1735 | 03-23-21 A | 04-01-21 A
Ypsi 3-2320 | PROJ-0951-YSP3.39.2.2 | 2021 GRP - Ypsilanti 3 | Install Main - Tyler (EOM & Desoto) | 2565 | 03-24-21 A | 03-26-21 A
RR1 6981 | GRP-2021-RR.21.1.2 | 2021 GRP - Risk Rank | Install Main - Dwyer (Charles & Casemere) | 1190 | 03-24-21 A | 04-02-21 A
SCDet-3495 | GRP-2021-SCDet1.20.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Appoline (Joy & Oakman) | 714 | 03-24-21 A | 03-25-21 A
SWDET2-2990 | PROJ-0951-SWDET2.17.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 1E (ASO Vernor & Chamberlain) | 2973 | 03-25-21 A | 05-10-21 A
AA4 20380 | GRP-2021-AA4.6.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - S 7th St (12' SNPL W Madison St & 6' NNPL Pauline Blvd) | 2011 | 03-25-21 A | 04-19-21 A
EDET1 501045 | GRP-2021-ED1.53.1.2 | 2021 GRP - East Detroit 1 | Install Main - Bremen St (2) (Balfour Rd & Buckingham Ave) | 885 | 03-25-21 A | 03-26-21 A
RR1 57450 | GRP-2021-RR1.83.3.2 | 2021 GRP - River Rouge | Install Main - High St 2 (40' SSPL Labadie St & Southfield Rd) | 340 | 03-25-21 A | 03-29-21 A
AA4 20538 | GRP-2021-AA4.26.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Davis Ave (S 7th St & Hutchins) | 336 | 03-25-21 A | 04-09-21 A
Ypsi 3-5570 | PROJ-0951-YSP3.15.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Eugene (Tyler & 94 Service Drive) | 1680 | 03-25-21 A | 03-31-21 A
EDET1 507146 | GRP-2021-ED1.60.3.2 | 2021 GRP - East Detroit 1 | Install Main - Nottingham Rd (2) (Mack Ave & ANO Mack Ave) | 80 | 03-25-21 A | 03-25-21 A
CDET2-9300 | GRP-2021-CDet2.1.2.2 | 2021 GRP - Central Detroit 2 | Install Main - ASO Chicago (Linwood & 14th) | 1597 | 03-25-21 A | 03-30-21 A
EDET1 501119 | GRP-2021-ED1.73.1.2 | 2021 GRP - East Detroit 1 | Elevate Main - Buckingham Ave (1) (E Warrern Ave & Waveney St) | 1910 | 03-26-21 A | 03-30-21 A
CDET2-6830 | GRP-2021-CDet2.30.3.2 | 2021 GRP - Central Detroit 2 | Install Main - Blaine 1 (Wildemere & Linwood) | 1606 | 03-26-21 A | 03-30-21 A
RR1 59010 | GRP-2021-RR1.92.2.2 | 2021 GRP - River Rouge | Install Main - Salliotte St (141' WWPL High St & 1' WWPL High St) | 140 | 03-26-21 A | 03-29-21 A
SWDET2-2350 | PROJ-0951-SWDET2.9.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Springwells 1 (ASO Vernor & Rathbone) | 2784 | 03-26-21 A | 05-12-21 A
CDET2-3775 | GRP-2021-CDet2.32.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Pingree 1 (Dexter & Linwood) | 2587 | 03-29-21 A | 04-07-21 A
SWDET2-11095 | PROJ-0951-SWDET2.13.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Central 1 W (Logan & Pershing) | 267 | 03-29-21 A | 04-06-21 A
SCDet-9990 | GRP-2021-SCDet1.21.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Meyers (Oakman & Civic) | 1457 | 03-29-21 A | 04-08-21 A
RR1 59090 | GRP-2021-RR1.92.4.2 | 2021 GRP - River Rouge | Install Main - Salliotte St (5' EEPL High St & W Jefferson Ave) | 795 | 03-29-21 A | 05-03-21 A
SCDet-8570 | GRP-2021-SCDet1.33.4.2 | 2021 GRP - South Central Detroit 1 | Install Main - Ohio (Joy & 12' SSPL Joy) | 17 | 03-29-21 A | 03-31-21 A
CDET2-8980 | GRP-2021-CDet2.3.57.2 | 2021 GRP - Central Detroit 2 | Install Main - ANO Chicago (La Salle & Rosa Parks) | 1757 | 03-29-21 A | 04-07-21 A
RR1 58930 | GRP-2021-RR1.92.3.2 | 2021 GRP - River Rouge | Install Main - Salliotte St (96' WWPL Drennan St & High St) | 390 | 03-29-21 A | 05-03-21 A
RR1 51436 | GRP-2021-RR1.85.1.2 | 2021 GRP - River Rouge | Install Main - Labadie St (55' WWPL Webster St & High St) | 350 | 03-29-21 A | 04-09-21 A
SCDet-8690 | GRP-2021-SCDet1.20.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Appoline (Oakman & Civic) | 1404 | 03-29-21 A | 04-08-21 A
SCDet-7960 | GRP-2021-SCDet1.28.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Normile (6' NNPL Tireman & Tireman) | 11 | 03-29-21 A | 03-30-21 A
SWDET2-4190 | PROJ-0951-SWDET2.33.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Chamberlain (Woodmere & Lawndale) | 1809 | 03-30-21 A | 04-13-21 A
EDET1 508466 | GRP-2021-ED1.8.3.2 | 2021 GRP - East Detroit 1 | Install Main - ANO Mack Ave (3) (Yorkshire & Yorkshire) | 130 | 03-30-21 A | 03-30-21 A
Ypsi 3-5340 | PROJ-0951-YSP3.14.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - 94 Service Drive (Eugene & Gates) | 1940 | 03-30-21 A | 04-05-21 A
RR1 7381 | GRP-2021-RR.27.1.2 | 2021 GRP - Risk Rank | Install Main - Burt (Westfield & Joy) East | 1776 | 03-30-21 A | 04-20-21 A
EDET1 501054 | GRP-2021-ED1.62.1.2 | 2021 GRP - East Detroit 1 | Install Main - Somerset Ave (2) (Waveney St & Mack Ave) | 2335 | 03-30-21 A | 04-07-21 A
EDET1 50460 | GRP-2021-ED1.9.1.2 | 2021 GRP - East Detroit 1 | Install Main - ASO E Warren Ave (1) (Alter Rd & Chatsworth St) | 2630 | 03-30-21 A | 04-12-21 A
CDET2-5535 | GRP-2021-CDet2.38.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Rosa Parks Blvd 1 (ANO W. Chicago & Longfellow) | 650 | 03-30-21 A | 03-31-21 A
RR1 51451 | GRP-2021-RR1.101.1.2 | 2021 GRP - River Rouge | Install Main - Webster St (Labadie St & EOM @ 158' SSPL Labadie St) | 205 | 03-30-21 A | 04-06-21 A
SCDet-8550 | GRP-2021-SCDet1.33.2.2 | 2021 GRP - South Central Detroit 1 | Install Main - Ohio (14' NNPL Tireman & Tireman) | 79 | 03-30-21 A | 03-30-21 A
AA4 22738 | GRP-2021-AA4.1.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - Hutchins Ave (W Davis St & Pauline Blvd) | 655 | 03-31-21 A | 03-31-21 A
AA4 20795 | GRP-2021-AA4.52.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Madison St (Soule Blvd & Eberwhite Blvd) | 762 | 04-01-21 A | 04-01-21 A
EDET1 503906 | GRP-2021-ED1.75.3.2 | 2021 GRP - East Detroit 1 | Install Main - Devonshire Rd (1) (ASO E Warren Ave & Waveney Ave) | 1820 | 04-01-21 A | 04-07-21 A
RR1 51442 | GRP-2021-RR1.92.1.2 | 2021 GRP - River Rouge | Install Main - Salliotte St (351' WWPL Drennan St & 96' WWPL Drennan St) | 255 | 04-02-21 A | 05-03-21 A
EDET1 50649 | GRP-2021-ED1.29.1.2 | 2021 GRP - East Detroit 1 | Install Main - Haverhill St (1) (E Warrern Ave & Waveney St) | 1820 | 04-05-21 A | 04-13-21 A
SWDET2-21955 | PROJ-0951-SWDET2.76.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Oakdale (ASO W Vernor & Mandale) | 790 | 04-05-21 A | 04-08-21 A
RR1 7721 | GRP-2021-RR.31.1.2 | 2021 GRP - Risk Rank | Install Main - Whitney (Grand River & Dexter) | 1040 | 04-05-21 A | 04-12-21 A
RR1 10781 | GRP-2021-RR.22.1.2 | 2021 GRP - Risk Rank | Install Main - Bloom (7 Mile & Nevada) West | 2640 | 04-05-21 A | 05-06-21 A
RR1 6261 | GRP-2021-RR.13.1.2 | 2021 GRP - Risk Rank | Install Main - Lafayette (Rademacher & Campbell) | 3105 | 04-05-21 A | 08-20-21 A
CDET2-3935 | GRP-2021-CDet2.34.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Philadelphia 1 (Dexter & Linwood) | 2587 | 04-05-21 A | 04-14-21 A
Ypsi 3-1710 | PROJ-0951-YSP3.39.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Tyler (Desoto & McCartney) | 920 | 04-06-21 A | 06-01-21 A
Ypsi 3-4340 | PROJ-0951-YSP3.10.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Calder (Tyler & 94 Service Drive) | 1720 | 04-06-21 A | 06-01-21 A
EDET1 505746 | GRP-2021-ED1.3.3.2 | 2021 GRP - East Detroit 1 | Install Main - Mack Ave (Alter Rd & Alter Rd) | 65 | 04-06-21 A | 04-06-21 A
EDET1 505846 | GRP-2021-ED1.3.2.2 | 2021 GRP - East Detroit 1 | Install Main - Mack Ave (Nottingham Rd & Somerset Ave) | 250 | 04-06-21 A | 04-06-21 A
NDET3-4480 | GRP-2021-ND3.4.2.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (North) - 6 (Mt Elliot St & Conrail) | 680 | 04-06-21 A | 04-07-21 A
RR1 51446 | GRP-2021-RR1.96.1.2 | 2021 GRP - River Rouge | Install Main - W Charlotte (14' EEPL High St & 5' WWPL W Jefferson Ave) | 820 | 04-06-21 A | 04-08-21 A
CDET2-10940 | GRP-2021-CDet2.37.3 | 2021 GRP - Central Detroit 2 | Elevate Main - Euclid (14th & Rosa Parks) | 980 | 04-06-21 A | 04-06-21 A
SCDet-2295 | GRP-2021-SCDet1.5.1.2 | 2021 GRP - South Central Detroit 1 | Elevate Main - Oakman Blvd E 3 (Joy & Birwood) | 1108 | 04-06-21 A | 04-12-21 A
Ypsi 3-12690 | PROJ-0951-YSP3.15.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Eugene (Tyler & 94 Service Drive) | 285 | 04-06-21 A | 2021-10-20
CDET-21010 | PROJ-0951-CDET1-2.32.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Elevate Main - Ewald N (1) (Petoskey & Petoskey) | 314 | 04-07-21 A | 04-08-21 A
SWDET2-16965 | PROJ-0951-SWDET2.78.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Sharon (Woodmere & ANO W Vernor) | 696 | 04-07-21 A | 04-12-21 A
RR1 7641 | GRP-2021-RR.30.1.2 | 2021 GRP - Risk Rank | Install Main - Grand River (61' NNPL Whitney & Whitney) | 157 | 04-07-21 A | 04-14-21 A
SWDET2-11175 | PROJ-0951-SWDET2.13.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Central 1 E (W Vernor & ASO Vernor) | 127 | 04-07-21 A | 05-18-21 A
SWDET2-5790 | PROJ-0951-SWDET2.53.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Pershing (Springwells & Central) | 907 | 04-07-21 A | 04-15-21 A
EDET1 505796 | GRP-2021-ED1.3.1.2 | 2021 GRP - East Detroit 1 | Install Main - Mack Ave (ASO Mack Ave & ANO Mack Ave) | 300 | 04-07-21 A | 04-07-21 A
NDET3-4645 | GRP-2021-ND3.4.1.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (North) - (Anglin St & Mt Elliot St) | 9590 | 04-07-21 A | 05-07-21 A
CDET2-11130 | GRP-2021-CDet2.51.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Wildemere 3 (Pingree & Pingree) | 139 | 04-07-21 A | 04-07-21 A
Ypsi 3-4590 | PROJ-0951-YSP3.11.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Fox (94 Service Drive & Tyler) | 1325 | 04-08-21 A | 04-08-21 A
SWDET2-2030 | PROJ-0951-SWDET2.5.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Fort (Woodmere & Distel) | 161 | 04-08-21 A | 04-12-21 A
EDET1 501052 | GRP-2021-ED1.60.1.2 | 2021 GRP - East Detroit 1 | Install Main - Nottingham Rd (2) (Waveney St & ANO Mack Ave) | 2260 | 04-08-21 A | 04-14-21 A
NDET3-5135 | GRP-2021-ND3.56.1.2 | 2021 GRP - North Detroit 3 | Install Main - Fenelon Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 2350 | 04-08-21 A | 04-15-21 A
SCDet-2215 | GRP-2021-SCDet1.3.1.2 | 2021 GRP - South Central Detroit 1 | Elevate Main - Oakman Blvd W 1 (Mackenzie & Belton) | 801 | 04-08-21 A | 04-08-21 A
SWDET2-22995 | PROJ-0951-SWDET2.69.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Pitt (Honorah & EOM) | 108 | 04-09-21 A | 04-09-21 A
AA4 20376 | GRP-2021-AA4.1.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Hutchins Ave (23' NNPL W Davis Ave & 8' SSPL W Davis Ave) | 81 | 04-09-21 A | 04-09-21 A
SCDet-8530 | GRP-2021-SCDet1.33.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Ohio (12' SSPL Joy & 25' SSPL Joy) | 20 | 04-09-21 A | 04-09-21 A
CDET2-10610 | GRP-2021-CDet2.41.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Lawton 2 (Clairmount & Clairmount ) | 76 | 04-12-21 A | 04-12-21 A
RR1 51434 | GRP-2021-RR1.83.1.2 | 2021 GRP - River Rouge | Install Main - High St 2 (7' NSPL W Woodward Ave & 373' SSPL W Outer Dr) | 990 | 04-12-21 A | 05-03-21 A
EDET1 50469 | GRP-2021-ED1.18.1.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) N (Bishop St & Grayton St) | 0 | 04-12-21 A | 04-28-21 A
SWDET2-17285 | PROJ-0951-SWDET2.78.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Sharon (ASO W Vernor & Mandale) | 788 | 04-12-21 A | 04-13-21 A
SWDET2-21795 | PROJ-0951-SWDET2.76.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Oakdale (Woodmere & ANO W Vernor) | 697 | 04-12-21 A | 04-16-21 A
EDET1 503856 | GRP-2021-ED1.25.1.2 | 2021 GRP - East Detroit 1 | Install Main - Courville St (2) (Waveney St & Waveney Ave) | 65 | 04-12-21 A | 04-12-21 A
CDET2-10970 | GRP-2021-CDet2.37.2 | 2021 GRP - Central Detroit 2 | Install Main - Euclid 2 (Rosa Parks & Rosa Parks) | 55 | 04-12-21 A | 04-14-21 A
SWDET2-6910 | PROJ-0951-SWDET2.67.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Honorah (Dix & W Vernor) | 1509 | 04-12-21 A | 04-19-21 A
RR1 51699 | GRP-2021-RR1.110.1.2 | 2021 GRP - River Rouge | Install Main - W Alexis Ave (8' EEPL High St & 9' WWPL W Jefferson Ave) | 800 | 04-13-21 A | 04-16-21 A
EDET1 50836 | GRP-2021-ED1.38.1.2 | 2021 GRP - East Detroit 1 | Install Main - Barham St (1) (E Warrern Ave & Waveney St) | 1790 | 04-13-21 A | 05-12-21 A
SCDet-10570 | GRP-2021-SCDet1.5.3.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd E 3 (5' SSPL Joy & Joy) | 11 | 04-13-21 A | 04-13-21 A
SCDet-10380 | GRP-2021-SCDet1.7.1.2 | 2021 GRP - South Central Detroit 1 | Install Main - Oakman Blvd E 1 (3' SNPL Tireman & 4' NSPL Tireman) | 89 | 04-13-21 A | 04-13-21 A
EDET1 50839 | GRP-2021-ED1.41.1.2 | 2021 GRP - East Detroit 1 | Install Main - Lakepointe St (1) (ASO E Warrern Ave & Waveney St) | 1810 | 04-13-21 A | 05-17-21 A
RR1 51428 | GRP-2021-RR1.77.1.2 | 2021 GRP - River Rouge | Install Main - Broadway Ave (270' WWPL W Jefferson Ave & 6' WWPL W Jeferson Ave) | 270 | 04-13-21 A | 04-13-21 A
SWDET2-11495 | PROJ-0951-SWDET2.17.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 1E (Chamberlain & Witt) | 962 | 04-13-21 A | 05-12-21 A
RR1 5781 | GRP-2021-RR.5.1.2 | 2021 GRP - Risk Rank | Install Main - Bringard (Reno & Regent) | 1925 | 04-14-21 A | 04-29-21 A
EDET1 504336 | GRP-2021-ED1.2.4.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (W) (Crossing At ASO E Warren Ave) | 150 | 04-14-21 A | 04-14-21 A
EDET1 504306 | GRP-2021-ED1.2.3.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (W) (Crossing At Waveney Ave) | 150 | 04-14-21 A | 04-14-21 A
EDET1 507316 | GRP-2021-ED1.2.3.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (W) (Crossing At Waveney Ave) | 150 | 04-14-21 A | 04-14-21 A
EDET1 501117 | GRP-2021-ED1.71.1.2 | 2021 GRP - East Detroit 1 | Install Main - Berkshire St (1) (ASO E Warrern Ave & Waveney St) | 1820 | 04-14-21 A | 04-16-21 A
EDET1 501044 | GRP-2021-ED1.52.1.2 | 2021 GRP - East Detroit 1 | Install Main - Beaconsfield St (2) (Waveney St & Mack Ave) | 2190 | 04-14-21 A | 04-19-21 A
EDET1 501041 | GRP-2021-ED1.49.1.4 | 2021 GRP - East Detroit 1 | Install Main - Balfour Rd (ASO E Warren Ave & Waveney Ave) | 1820 | 04-14-21 A | 04-20-21 A
RR1 8601 | GRP-2021-RR.42.1.2 | 2021 GRP - Risk Rank | Install Main - Coram (Gratiot & Hayes) | 2611 | 04-14-21 A | 05-06-21 A
SWDET2-14545 | PROJ-0951-SWDET2.72.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Cabot (Woodmere & ANO W Vernor) | 787 | 04-14-21 A | 04-21-21 A
SWDET2-4110 | PROJ-0951-SWDET2.32.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Woodmere 4 (Mandale & Avis) | 5 | 04-15-21 A | 04-19-21 A
AA4 22658 | GRP-2021-AA4.1.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Hutchins Ave (Princeton Ave & 23' NNPL W Davis Ave) | 860 | 04-15-21 A | 04-19-21 A
NDET3-5530 | GRP-2021-ND3.13.1.2 | 2021 GRP - North Detroit 3 | Install Main - Dwyer St (1) (8 Mile Rd (M102) & Hamlet St) 4" | 485 | 04-15-21 A | 04-15-21 A
NDET3-6830 | GRP-2021-ND3.52.1.2 | 2021 GRP - North Detroit 3 | Install Main - Conley Ave (1) (8 Mile Rd (M102) & Hamlet St) | 345 | 04-15-21 A | 04-15-21 A
SWDET2-18675 | PROJ-0951-SWDET2.37.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Rathbone (Lawndale & Springwells) | 1649 | 04-15-21 A | 05-13-21 A
SWDET2-16055 | PROJ-0951-SWDET2.33.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Chamberlain (Lawndale & Springwells) | 1701 | 04-16-21 A | 05-12-21 A
RR1 51427 | GRP-2021-RR1.76.1.2 | 2021 GRP - River Rouge | Install Main - Bell St (High & Visgar) | 130 | 04-16-21 A | 04-20-21 A
NDET3-6925 | GRP-2021-ND3.52.3.2 | 2021 GRP - North Detroit 3 | Install Main - Conley Ave (1) (Hamlet St & E Outer Dr) | 1935 | 04-16-21 A | 04-16-21 A
CDET2-3615 | GRP-2021-CDet2.30.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Blaine 1 (Dexter & Dexter) | 34 | 04-19-21 A | 04-19-21 A
AA4 20535 | GRP-2021-AA4.22.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Princeton Ave (9' EWPL S 77th St & 2' WEPL S 77th St) | 55 | 04-19-21 A | 04-19-21 A
CDET2-6550 | GRP-2021-CDet2.29.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Carter (Linwood & Linwood) | 79 | 04-19-21 A | 04-19-21 A
RR1 8201 | GRP-2021-RR.37.1.2 | 2021 GRP - Risk Rank | Install Main - Varjo (Sherwood & Cliff) | 1453 | 04-19-21 A | 05-17-21 A
EDET1 504466 | GRP-2021-ED1.16.4.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (1) (Balfour Rd & Balfour Rd) | 220 | 04-19-21 A | 04-19-21 A
EDET1 506346 | GRP-2021-ED1.70.4.2 | 2021 GRP - East Detroit 1 | Install Main - Bedford St (2) (Bedford & Bedford) crossing | 55 | 04-19-21 A | 04-21-21 A
EDET1 501047 | GRP-2021-ED1.55.1.2 | 2021 GRP - East Detroit 1 | Install Main - Chatsworth St (1) (E Warrern Ave & Waveney St) | 1820 | 04-19-21 A | 04-21-21 A
CDET2-10000 | GRP-2021-CDet2.28.3.2 | 2021 GRP - Central Detroit 2 | Elevate Main - Gladstone 2 (Linwood & Rosa Parks) | 2650 | 04-19-21 A | 04-22-21 A
EDET1 502396 | GRP-2021-ED1.35.1.2 | 2021 GRP - East Detroit 1 | Install Main - ANO E Warren Ave (1) (Devonshire Rd & E Outer Dr) | 1515 | 04-19-21 A | 04-22-21 A
AA3-5700 | GRP-2021-RR1.9.1.2 | 2021 GRP - River Rouge | Install Main - Florence St 2 (Joseph st & E Charlotte Ave) | 280 | 04-19-21 A | 04-27-21 A
SWDET2-14625 | PROJ-0951-SWDET2.72.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Cabot (ANO Vernor & W Vernor) | 116 | 04-20-21 A | 04-27-21 A
EDET1 502866 | GRP-2021-ED1.4.3.2 | 2021 GRP - East Detroit 1 | Install Main - ANO Mack Ave (1) (Somerset Ave & Balfour Rd) | 230 | 04-20-21 A | 04-20-21 A
NDET3-5295 | GRP-2021-ND3.58.1.2 | 2021 GRP - North Detroit 3 | Install Main - Hamlet St (2) (Fenelon Ave & Mound Rd) | 2745 | 04-20-21 A | 04-26-21 A
RR1 51450 | GRP-2021-RR1.100.1.2 | 2021 GRP - River Rouge | Install Main - W Westfield St (EOM & High St) | 460 | 04-20-21 A | 05-06-21 A
NDET3-325 | GRP-2021-ND3.59.3.2 | 2021 GRP - North Detroit 3 | Install Main - Keystone St (1) (Hamlet St & E Outer Dr) | 1935 | 04-20-21 A | 04-23-21 A
RR1 51696 | GRP-2021-RR1.107.1.2 | 2021 GRP - River Rouge | Install Main - Joseph St (W Jefferson Ave & Eliza St) | 690 | 04-20-21 A | 04-27-21 A
EDET1 505116 | GRP-2021-ED1.18.10.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) N (ANO E Warren Ave & ASO E Warren Ave @ Neff Ave) | 315 | 04-21-21 A | 05-18-21 A
SWDET2-18085 | PROJ-0951-SWDET2.49.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Green (W Vernor & EOM) | 1696 | 04-21-21 A | 04-30-21 A
RR1 51449 | GRP-2021-RR1.99.1.2 | 2021 GRP - River Rouge | Install Main - W Woodward Ave (EOM & High St) | 405 | 04-22-21 A | 05-06-21 A
EDET1 502546 | GRP-2021-ED1.80.1.2 | 2021 GRP - East Detroit 1 | Install Main - ANO E Warren Ave (2) (E Outer Dr & Cadiuex Rd) | 2000 | 04-22-21 A | 05-12-21 A
EDET1 501053 | GRP-2021-ED1.61.1.2 | 2021 GRP - East Detroit 1 | Install Main - Somerset Ave (1) (ASO E Warrern Ave & Waveney St) | 1820 | 04-22-21 A | 04-26-21 A
EDET1 50838 | GRP-2021-ED1.40.1.2 | 2021 GRP - East Detroit 1 | Install Main - Lakepointe Sr (2) (Waveney St & Mack Ave) | 2120 | 04-22-21 A | 04-27-21 A
EDET1 50845 | GRP-2021-ED1.47.1.2 | 2021 GRP - East Detroit 1 | Install Main - Wayburn Ave (1) (E Warrern Ave & Waveney St) | 1790 | 04-22-21 A | 04-28-21 A
EDET1 506796 | GRP-2021-ED1.62.1.2 | 2021 GRP - East Detroit 1 | Install Main - Somerset Ave (2) (ANO Mack & Mack) | 160 | 04-22-21 A | 04-22-21 A
RR1 8841 | GRP-2021-RR.45.1.2 | 2021 GRP - Risk Rank | Install Main - Engleside (Conner & Gunston) | 2249 | 04-23-21 A | 04-30-21 A
RR1 51690 | GRP-2021-RR1.90.1.2 | 2021 GRP - River Rouge | Install Main - E Auburn Ave (W Jefferson Ave & Ironton Ave) | 1045 | 04-23-21 A | 04-27-21 A
SWDET2-7470 | PROJ-0951-SWDET2.73.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Ferris (Woodmere & ANO W Vernor) | 1250 | 04-23-21 A | 05-06-21 A
AA4 20786 | GRP-2021-AA4.43.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Mt Pleasant Ave (Mt Vernon Ave & Manhattan Dr) | 678 | 04-23-21 A | 04-28-21 A
EDET1 508746 | GRP-2021-ED1.13.1 | 2021 GRP - East Detroit 1 | Install Main - Bremen (1) (Barham st & Beaconsfield st) | 160 | 04-26-21 A | 04-26-21 A
EDET1 508786 | GRP-2021-ED1.18.1 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (Grayton & Kensington) | 1060 | 04-26-21 A | 05-03-21 A
AA4 29208 | GRP-2021-AA4.15.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Easement (EOM & S 7th) | 305 | 04-26-21 A | 04-27-21 A
NDET3-6780 | GRP-2021-ND3.59.1.2 | 2021 GRP - North Detroit 3 | Install Main - Keystone St (1) (8 Mile Rd (M102) & Hamlet St) | 415 | 04-26-21 A | 04-26-21 A
NDET3-5485 | GRP-2021-ND3.58.3.2 | 2021 GRP - North Detroit 3 | Install Main - Hamlet St (2) (Mound Rd & Dwyer St) | 470 | 04-26-21 A | 04-27-21 A
NDET3-6605 | GRP-2021-ND3.60.1.2 | 2021 GRP - North Detroit 3 | Install Main - Moenart St (1) (8 Mile Rd (M102) & Hamlet St) | 455 | 04-26-21 A | 04-26-21 A
NDET3-6665 | GRP-2021-ND3.60.3.2 | 2021 GRP - North Detroit 3 | Install Main - Moenart St (1) (Hamlet St & E Outer Dr) | 1935 | 04-26-21 A | 05-04-21 A
RR1 10691 | GRP-2021-RR.37.2.2 | 2021 GRP - Risk Rank | Install Main - Varjo (Cliff & Van Dyke) | 1103 | 04-27-21 A | 05-17-21 A
EDET1 50842 | GRP-2021-ED1.44.1.2 | 2021 GRP - East Detroit 1 | Install Main - Maryland St (2) (Waveney St & ANO Mack Ave) | 2055 | 04-27-21 A | 05-06-21 A
NDET3-6140 | GRP-2021-ND3.5.3.2 | 2021 GRP - North Detroit 3 | Install Main - Mound Rd (east) - (Hamlet Crossing) | 175 | 04-27-21 A | 07-12-21 A
SWDET2-16295 | PROJ-0951-SWDET2.25.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Elsmere 2 (Lafayette & Olivet) | 278 | 04-27-21 A | 04-29-21 A
SWDET2-16455 | PROJ-0951-SWDET2.25.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Elsmere 2 (Olivet & Witt) | 265 | 04-27-21 A | 04-29-21 A
SWDET2-7150 | PROJ-0951-SWDET2.71.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Stair (Dix & W Vernor) | 1336 | 04-27-21 A | 05-06-21 A
EDET1 501051 | GRP-2021-ED1.59.1.2 | 2021 GRP - East Detroit 1 | Install Main - Nottingham Rd (1) (ASO E Warren Ave & Waveney Ave) | 1825 | 04-27-21 A | 05-04-21 A
NDET3-6160 | GRP-2021-ND3.6.1.2 | 2021 GRP - North Detroit 3 | Install Main - Mound Rd (west) - (8 Mile Rd & Hamlet St)west side | 370 | 04-28-21 A | 04-28-21 A
CDET2-8750 | GRP-2021-CDet2.1.1.2 | 2021 GRP - Central Detroit 2 | Elevate Main - ASO Chicago (14th & Rosa Parks) | 1047 | 04-28-21 A | 04-28-21 A
CDET2-11290 | GRP-2021-CDet2.53.1.2 | 2021 GRP - Central Detroit 2 | Install Main - AEO Linwood (Clairmount & Clairmount) | 144 | 04-30-21 A | 04-30-21 A
NDET3-6050 | GRP-2021-ND3.5.1.2 | 2021 GRP - North Detroit 3 | Install Main - Mound Rd (east) - (8 Mile Rd & Hamlet St) | 485 | 04-30-21 A | 04-30-21 A
SWDET2-10425 | PROJ-0951-SWDET2.9.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Springwells 1 (Rathbone & Chamberlain) | 121 | 04-30-21 A | 05-12-21 A
RR1 533 | GRP-2021-RR1.10.1.2 | 2021 GRP - River Rouge | Install Main - Outer Dr (162' WWPL High St & High St) | 170 | 04-30-21 A | 05-04-21 A
AA4 27468 | GRP-2021-AA4.52.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Madison St (4' EWPL Soule Blvd & Tie In 35' EEPL Soule Blvd) | 140 | 04-30-21 A | 04-30-21 A
EDET1 502676 | GRP-2021-ED1.80.3.2 | 2021 GRP - East Detroit 1 | Install Main - ANO E Warren Ave (2) (E Warren Ave & Woodhall St) | 0 | 05-03-21 A | 05-04-21 A
EDET1 504796 | GRP-2021-ED1.18.6.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Woodhall St) | 0 | 05-03-21 A | 05-03-21 A
EDET1 506776 | GRP-2021-ED1.59.1.2 | 2021 GRP - East Detroit 1 | Install Main - Nottingham Rd (1) (E Warren Ave & ASOE Warren Ave) Optional | 0 | 05-03-21 A | 05-04-21 A
Ypsi 3-4840 | PROJ-0951-YSP3.12.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Dorset (Tyler & 94 Service Drive) | 965 | 05-03-21 A | 05-03-21 A
CDET2-3455 | GRP-2021-CDet2.28.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Gladstone 2 (Linwood & Linwood) | 11 | 05-03-21 A | 05-03-21 A
CDET2-4895 | GRP-2021-CDet2.46.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Lawton 3 (Gladstone & Carter) | 0 | 05-03-21 A | 05-03-21 A
CDET2-9140 | GRP-2021-CDet2.1.3.2 | 2021 GRP - Central Detroit 2 | Install Main - ASO Chicago (Rosa Parks & Rosa Parks) | 16 | 05-03-21 A | 05-03-21 A
NDET3-4490 | GRP-2021-ND3.4.4.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (North) (Conrail Crossing) | 70 | 05-03-21 A | 05-06-21 A
EDET1 508826 | GRP-2021-ED1.18.12.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Kensigton | 120 | 05-03-21 A | 05-03-21 A
CDET2-6530 | GRP-2021-CDet2.28.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Gladstone 2 (Rosa Parks & Rosa Parks) | 28 | 05-03-21 A | 05-03-21 A
EDET1 50844 | GRP-2021-ED1.46.1.2 | 2021 GRP - East Detroit 1 | Install Main - Waveney Ave (N) (1) (Wayburn & Balfour) duplicate do not update it. | 0 | 05-04-21 A | 05-07-21 A
EDET1 502946 | GRP-2021-ED1.4.4.2 | 2021 GRP - East Detroit 1 | Install Main - ANO Mack Ave (1) (Crossing At Balfour Rd) | 0 | 05-04-21 A | 05-06-21 A
EDET1 508146 | GRP-2021-ED1.7.1.2 | 2021 GRP - East Detroit 1 | Install Main - ANO Mack Ave 2 (Courville & Courville) | 0 | 05-04-21 A | 05-06-21 A
SWDET2-5070 | PROJ-0951-SWDET2.44.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Mason (Woodmere & Elsemere) | 717 | 05-04-21 A | 05-06-21 A
AA3-5770 | GRP-2021-RR1.8.3.2 | 2021 GRP - River Rouge | Install Main - Eliza St (Joseph St & E Charlotte Ave) | 280 | 05-04-21 A | 05-11-21 A
RR1 51663 | GRP-2021-RR1.11.1.2 | 2021 GRP - River Rouge | Install Main - Cherrygrove St (W Jefferson Ave & EOM) | 575 | 05-04-21 A | 05-06-21 A
AA3-5840 | GRP-2021-RR1.8.2.2 | 2021 GRP - River Rouge | Install Main - Eliza St (E Charlotte Ave & EOM @ 108' SSPL E Alexis Ave) | 295 | 05-04-21 A | 05-11-21 A
EDET1 506086 | GRP-2021-ED1.49.3.1 | 2021 GRP - East Detroit 1 | Install Main - Balfour (ASO Warren & ANO Warren) | 310 | 05-04-21 A | 05-04-21 A
AA3-5630 | GRP-2021-RR1.8.1.2 | 2021 GRP - River Rouge | Install Main - Eliza St (35' NNPL E Charlotte Ave & 4' NSPL E Charlotte Ave) | 90 | 05-05-21 A | 05-11-21 A
RR1 61600 | GRP-2021-RR1.10.3.2 | 2021 GRP - River Rouge | Install Main - Outer Dr (High St & 252' EEPL High St) | 17 | 05-05-21 A | 05-05-21 A
CDET2-10240 | GRP-2021-CDet2.30.2.2 | 2021 GRP - Central Detroit 2 | Elevate Main - Blaine 1 (Dexter & Wildemere) | 965 | 05-05-21 A | 05-06-21 A
SWDET2-4830 | PROJ-0951-SWDET2.41.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Lane 1 (Woodmere & Elsmere) | 737 | 05-05-21 A | 05-11-21 A
EDET1 501043 | GRP-2021-ED1.51.1.2 | 2021 GRP - East Detroit 1 | Install Main - Beaconsfield St (1) (E Warrern Ave & Waveney St) | 1815 | 05-05-21 A | 05-10-21 A
RR1 8441 | GRP-2021-RR.40.1.2 | 2021 GRP - Risk Rank | Install Main - Glenwood (Gratiot & Chalmers) | 1383 | 05-05-21 A | 05-19-21 A
NDET3-5760 | GRP-2021-ND3.11.3.2 | 2021 GRP - North Detroit 3 | Install Main - ANO 7 Mile Rd (3) (Mound Rd & Mt Elliott) | 1135 | 05-05-21 A | 05-10-21 A
EDET1 504256 | GRP-2021-ED1.2.4.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (W) (Crossing At ANO E Warren Ave) | 0 | 05-06-21 A | 05-06-21 A
RR1 51697 | GRP-2021-RR1.108.1.2 | 2021 GRP - River Rouge | Install Main - Ironton Ave 2 (River Rouge City Limits & Rockwood Ave) | 650 | 05-06-21 A | 05-21-21 A
SWDET2-16805 | PROJ-0951-SWDET2.73.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Ferris (ANO Vernor & EOM) | 45 | 05-06-21 A | 05-10-21 A
SWDET2-4350 | PROJ-0951-SWDET2.35.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Lafayette (Woodmere & Lawndale) | 1796 | 05-06-21 A | 05-31-21 A
SCDet-3815 | GRP-2021-SCDet1.25.1.2 | 2021 GRP - South Central Detroit 1 | Elevate Main - Mendota (Esper & Tireman) | 957 | 05-06-21 A | 05-11-21 A
SCDet-2535 | GRP-2021-SCDet1.8.1.2 | 2021 GRP - South Central Detroit 1 | Elevate Main - Esper (Belton & Mendota) | 67 | 05-06-21 A | 05-06-21 A
SCDet-8340 | GRP-2021-SCDet1.53.1.2 | 2021 GRP - South Central Detroit 1 | Elevate Main - Westover (11' EWPL Mendota & 6" WEPL Mendota) | 46 | 05-06-21 A | 05-06-21 A
RR1 51691 | GRP-2021-RR1.102.1.2 | 2021 GRP - River Rouge | Install Main - E Charlotte Ave (W Jefferson Ave & Eliza St) | 670 | 05-06-21 A | 05-11-21 A
Muni9430 | PROJ-0951-MUN-2.19.2.2 | 2021 GRP - Municipality | Install Main - Vinewood (Michigan & ASO Michigan) | 70 | 05-06-21 A | 06-08-21 A
Muni8710 | PROJ-0951-MUN-2.19.1.2 | 2021 GRP - Municipality | Install Main - Vinewood (Magnolia & Michigan) | 1562 | 05-06-21 A | 05-24-21 A
NDET3-5995 | GRP-2021-ND3.45.1.2 | 2021 GRP - North Detroit 3 | Install Main - 8 Mile Rd (2) (Mound Rd & Dwyer St) | 470 | 05-06-21 A | 05-06-21 A
RR1 57780 | GRP-2021-RR1.108.3.2 | 2021 GRP - River Rouge | Install Main - Ironton Ave 2 (Rockwood Ave & E Glenwood Ave) | 245 | 05-06-21 A | 05-10-21 A
NDET3-6365 | GRP-2021-ND3.49.3.2 | 2021 GRP - North Detroit 3 | Install Main - Bloom St (1) (Hamlet St & E Outer Dr) | 1925 | 05-06-21 A | 05-11-21 A
Ypsi 3-5090 | PROJ-0951-YSP3.13.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Gates (94 Service Drive & Tyler) | 670 | 05-06-21 A | 05-20-21 A
RR1 8921 | GRP-2021-RR.46.1.2 | 2021 GRP - Risk Rank | Install Main - College (Conner & Gunston) | 2155 | 05-06-21 A | 05-25-21 A
EDET1 50841 | GRP-2021-ED1.43.1.2 | 2021 GRP - East Detroit 1 | Install Main - Maryland St (1) (E Warrern Ave & Waveney St) | 1785 | 05-07-21 A | 05-12-21 A
NDET3-5665 | GRP-2021-ND3.45.3.2 | 2021 GRP - North Detroit 3 | Install Main - 8 Mile Rd (Dwyer St & Elliot St) | 620 | 05-07-21 A | 05-07-21 A
AA4 20776 | GRP-2021-AA4.11.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Crest Ave (W Liberty St & Luts Ave) | 891 | 05-07-21 A | 05-14-21 A
EDET1 501121 | GRP-2021-ED1.75.1.2 | 2021 GRP - East Detroit 1 | Install Main - Devonshire Rd (1) (ANO E Warren Ave & ASO E Warren Ave) | 315 | 05-10-21 A | 05-10-21 A
SWDET2-7950 | PROJ-0951-SWDET2.79.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Wendell (Woodmere & ANO W Vernor) | 1461 | 05-10-21 A | 05-18-21 A
CDET2-8910 | GRP-2021-CDet2.3.1.2 | 2021 GRP - Central Detroit 2 | Install Main - ANO Chicago (Linwood & Linwood) | 10 | 05-10-21 A | 05-10-21 A
SWDET2-16135 | PROJ-0951-SWDET2.71.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Stair (EOM & Dix) | 380 | 05-10-21 A | 05-11-21 A
SWDET2-20325 | PROJ-0951-SWDET2.44.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Mason (Elsemere & Lawndale) | 1086 | 05-10-21 A | 05-14-21 A
Muni8070 | PROJ-0951-MUN-2.12.1.2 | 2021 GRP - Municipality | Install Main - Pinehurst (Chicago & Joy) | 2722 | 05-10-21 A | 06-30-21 A
RR1 8281 | GRP-2021-RR.38.1.2 | 2021 GRP - Risk Rank | Install Main - Cliff (Varjo & EOM 181' SSPL Varjo) | 276 | 05-10-21 A | 05-17-21 A
NDET3-6270 | GRP-2021-ND3.46.1.2 | 2021 GRP - North Detroit 3 | Install Main - Albany Ave (1) (Hamlet & Amrad St) | 655 | 05-10-21 A | 05-11-21 A
NDET3-4650 | GRP-2021-ND3.3.1.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Anglin St & Mt Elliott St) | 10355 | 05-10-21 A | 06-24-21 A
SWDET2-19005 | PROJ-0951-SWDET2.41.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Lane 1 (Elsmere & Lawndale) | 1086 | 05-10-21 A | 05-13-21 A
RR1 51692 | GRP-2021-RR1.103.1.2 | 2021 GRP - River Rouge | Install Main - E Glenwood Ave (W Jefferson Ave & Ironton Ave) | 1025 | 05-11-21 A | 05-14-21 A
NDET3-5615 | GRP-2021-ND3.11.1.2 | 2021 GRP - North Detroit 3 | Install Main - ANO 7 Mile Rd (3) (Bloom & Mound Rd)) | 1400 | 05-11-21 A | 06-08-21 A
NDET3-5385 | GRP-2021-ND3.31.2.2 | 2021 GRP - North Detroit 3 | Install Main - Mound Rd (Mound & Mound) Crossing at ANO 7 Mile Rd | 210 | 05-11-21 A | 05-11-21 A
NDET3-6225 | GRP-2021-ND3.46.3.2 | 2021 GRP - North Detroit 3 | Install Main - Albany Ave (1) (Hamlet St & EOM) | 405 | 05-11-21 A | 05-11-21 A
NDET3-6540 | GRP-2021-ND3.49.1.2 | 2021 GRP - North Detroit 3 | Install Main - Bloom St (1) (8 Mile Rd (M102) & Hamlet St) | 455 | 05-11-21 A | 05-12-21 A
CDET2-3135 | GRP-2021-CDet2.3.6.2 | 2021 GRP - Central Detroit 2 | Elevate Main - ANO Chicago (Linwood & La Salle) | 886 | 05-11-21 A | 05-11-21 A
EDET1 504956 | GRP-2021-ED1.18.8.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) N (Caduiex St & Neff Ave) | 1845 | 05-12-21 A | 05-20-21 A
NDET3-6825 | GRP-2021-ND3.50.1.2 | 2021 GRP - North Detroit 3 | Install Main - Buffalo St (1) (8 Mile Rd (M102) & Hamlet St) | 430 | 05-12-21 A | 05-14-21 A
NDET3-6390 | GRP-2021-ND3.62.3.2 | 2021 GRP - North Detroit 3 | Install Main - Syracuse Ave (1) (Hamlet St & Amrad St) | 655 | 05-12-21 A | 05-13-21 A
AA4 25098 | GRP-2021-AA4.22.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Princeton Ave (S 7th St & 5th St) | 670 | 05-12-21 A | 05-13-21 A
AA3-6120 | GRP-2021-RR1.7.5.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (2) (5' NSPL Salliotte Rd & 12' SNPL Salliotte Rd) | 105 | 05-13-21 A | 05-14-21 A
SWDET2-18835 | PROJ-0951-SWDET2.35.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Lafayette (Lawndale & EOM) | 937 | 05-13-21 A | 05-20-21 A
SWDET2-5470 | PROJ-0951-SWDET2.49.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Green (Dix & W Vernor) | 1044 | 05-13-21 A | 05-20-21 A
AA3-6190 | GRP-2021-RR1.7.6.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (2) (11' WEPL W Jefferson Ave & 6' EWPL W Jefferson Ave) | 20 | 05-13-21 A | 05-13-21 A
EDET1 504556 | GRP-2021-ED1.18.3.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Cadieux Rd) | 105 | 05-13-21 A | 05-13-21 A
EDET1 504636 | GRP-2021-ED1.18.4.2 | 2021 GRP - East Detroit 1 | Install Main - E Warren Ave (3) (Cadieux Rd & ANO E Warren Ave) | 100 | 05-13-21 A | 05-13-21 A
RR1 6421 | GRP-2021-RR.15.1.2 | 2021 GRP - Risk Rank | Install Main - Crawford (56' NNPL Lafayette & 124' SSPL Lafayette) | 250 | 05-13-21 A | 06-24-21 A
EDET1 504066 | GRP-2021-ED1.1.3.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (E) (Waveney Ave & Mack Ave) | 2660 | 05-13-21 A | 05-20-21 A
NDET3-6385 | GRP-2021-ND3.62.1.2 | 2021 GRP - North Detroit 3 | Install Main - Syracuse Ave (1) (8 Mile Rd (M102) & Hamlet St) | 380 | 05-13-21 A | 05-13-21 A
RR1 51430 | GRP-2021-RR1.79.1.2 | 2021 GRP - River Rouge | Install Main - E Alexis Ave (W Jefferson & Eliza) | 635 | 05-14-21 A | 05-21-21 A
SWDET2-13745 | PROJ-0951-SWDET2.30.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Witt (Lawndale & EOM) | 229 | 05-14-21 A | 06-11-21 A
NDET3-6660 | GRP-2021-ND3.51.3.2 | 2021 GRP - North Detroit 3 | Install Main - Caldwell St (1) (Hamlet St & Amrad St) | 655 | 05-14-21 A | 05-14-21 A
NDET3-6920 | GRP-2021-ND3.50.4.2 | 2021 GRP - North Detroit 3 | Install Main - Buffalo St (1) (Hamlet St & Amrad St) | 655 | 05-14-21 A | 05-14-21 A
RR1 6501 | GRP-2021-RR.49.1.2 | 2021 GRP - Risk Rank | Install Main - Livernois (EOM & W Lafayette) | 105 | 05-14-21 A | 05-25-21 A
RR1 51443 | GRP-2021-RR1.93.1.2 | 2021 GRP - River Rouge | Install Main - Sunnyside St (Salliotte Rd & 157' SSPL Salliotte Rd) | 355 | 05-17-21 A | 05-17-21 A
SWDET2-2510 | PROJ-0951-SWDET2.11.1.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor 3 (Inglis & Central) North | 1265 | 05-17-21 A | 06-03-21 A
AA3-6050 | GRP-2021-RR1.7.4.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (2) (32' SSPL Knox & 8' SSPL W Alexis) | 1005 | 05-17-21 A | 05-24-21 A
SWDET2-19165 | PROJ-0951-SWDET2.41.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Lane 1 (Lawndale & Springwells) | 1622 | 05-17-21 A | 06-04-21 A
RR1 5861 | GRP-2021-RR.6.1.2 | 2021 GRP - Risk Rank | Install Main - Iowa (Sherwood & School) | 2165 | 05-17-21 A | 06-14-21 A
RR1 6581 | GRP-2021-RR.50.1.2 | 2021 GRP - Risk Rank | Install Main - Rademacher (Lafayette & 157' SSPL Lafayette) | 240 | 05-17-21 A | 06-24-21 A
RR1 7441 | GRP-2021-RR.49.1.2 | 2021 GRP - Risk Rank | Install Main - Livernois (W Lafayette & EOM) | 65 | 05-17-21 A | 05-21-21 A
NDET3-6425 | GRP-2021-ND3.51.1.2 | 2021 GRP - North Detroit 3 | Install Main - Caldwell St (1) (8 Mile Rd (M102) & Hamlet St) | 450 | 05-17-21 A | 05-17-21 A
AA4 28718 | GRP-2021-AA4.2.15.2 | 2021 GRP - Ann Arbor 4 | Install Main - Pauline Blvd (Hutchins & S Main Stt) | 1891 | 05-17-21 A | 08-30-21 A
Muni8150 | PROJ-0951-MUN-2.7.1.2 | 2021 GRP - Municipality | Install Main - Ash (Vinewood & Roosevelt) | 715 | 05-17-21 A | 05-24-21 A
NCDET - 20445 | NEWPROJ-6.2.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Ardmore (Puritan & Fenkell) | 2586 | 05-17-21 A | 05-27-21 A
SWDET2-13905 | PROJ-0951-SWDET2.30.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Witt (Elsmere & Lawndale) | 917 | 05-18-21 A | 06-11-21 A
EDET1 50689 | GRP-2021-ED1.1.1.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (E) (E Warren Ave & Waveney Ave) | 1770 | 05-18-21 A | 06-02-21 A
NDET3-4860 | GRP-2021-ND3.14.1.2 | 2021 GRP - North Detroit 3 | Install Main - Dwyer St (2) (E Outer Dr & ANO 7 Mile Rd) | 2400 | 05-18-21 A | 05-20-21 A
NDET3-4825 | GRP-2021-ND3.22.1.2 | 2021 GRP - North Detroit 3 | Install Main - St Louis Ave (E Outer Dr & ANO 7 Mile Rd) | 2420 | 05-18-21 A | 05-20-21 A
NDET3-220 | GRP-2021-ND3.3.5.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Norwood St) | 145 | 05-18-21 A | 05-18-21 A
NDET3-7960 | GRP-2021-ND3.9.1.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (3) (Sherwood & Conrail RR) | 450 | 05-18-21 A | 05-19-21 A
Ypsi 3-7070 | PROJ-0951-YSP3.21.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Eileen (Tyler & Chevrolet) | 1230 | 05-18-21 A | 09-17-21 A
EDET1 504146 | GRP-2021-ED1.2.3.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (W) (ASO E Warren Ave & Waveney Ave) | 1770 | 05-19-21 A | 05-20-21 A
NDET3-265 | GRP-2021-ND3.3.8.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Bloom St) | 145 | 05-19-21 A | 05-19-21 A
RR1 51693 | GRP-2021-RR1.104.1.2 | 2021 GRP - River Rouge | Install Main - E Rockwood Ave (W Jefferson Ave & Ironton Ave) | 115 | 05-20-21 A | 05-21-21 A
NDET3-235 | GRP-2021-ND3.3.6.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Sunset St) | 145 | 05-20-21 A | 05-20-21 A
NDET3-8110 | GRP-2021-ND3.9.3.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (3) (Filer & Conrail RR) | 320 | 05-20-21 A | 05-24-21 A
Ypsi 3 - 7071 | PROJ-0951-YSP3.39.4.2 | 2021 GRP - Ypsilanti 3 | Install Main - Desoto (Tyler & Tyler) | 120 | 05-20-21 A | 05-20-21 A
RR1 9081 | GRP-2021-RR.48.1.2 | 2021 GRP - Risk Rank | Install Main - Gunston (EOM 8' SSPL Nashville & College) | 247 | 05-21-21 A | 05-25-21 A
RR1 57620 | GRP-2021-RR1.71.3.2 | 2021 GRP - River Rouge | Install Main - Ironton Ave 1 (Catherine St & Orchard St) | 1435 | 05-21-21 A | 06-09-21 A
EDET1 504226 | GRP-2021-ED1.2.4.2 | 2021 GRP - East Detroit 1 | Install Main - E Outer Dr (W) (Waveney St & Mack Ave) | 2665 | 05-21-21 A | 06-02-21 A
NDET3-250 | GRP-2021-ND3.3.7.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Fenelon Ave) | 145 | 05-21-21 A | 05-21-21 A
SWDET2-6350 | PROJ-0951-SWDET2.60.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Rieden 1 (Pitt & W Vernor) | 789 | 05-24-21 A | 06-02-21 A
SWDET2-9465 | PROJ-0951-SWDET2.12.3.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor 4 (At Central) | 132 | 05-24-21 A | 05-24-21 A
SWDET2-19645 | PROJ-0951-SWDET2.51.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Logan 2 (EOM & Central) | 36 | 05-24-21 A | 05-24-21 A
Muni8310 | PROJ-0951-MUN-2.14.1.2 | 2021 GRP - Municipality | Install Main - Michigan (Hubbard & Vinewood) | 427 | 05-24-21 A | 06-08-21 A
SWDET2-22515 | PROJ-0951-SWDET2.77.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Pearl (Tie-In & ANO Vernor) | 1683 | 05-24-21 A | 06-10-21 A
NDET3-5010 | GRP-2021-ND3.19.1.2 | 2021 GRP - North Detroit 3 | Install Main - Gable Ave (E Outer Dr & ANO 7 Mile Rd) | 2405 | 05-24-21 A | 06-02-21 A
EDET1 502806 | GRP-2021-ED1.80.2.2 | 2021 GRP - East Detroit 1 | Install Main - ANO E Warren Ave (2) (Neff Ave & Hereford St) | 400 | 05-24-21 A | 05-27-21 A
RR1 51312 | GRP-2021-RR1.72.1.2 | 2021 GRP - River Rouge | Install Main - Orcahard St (W Jefferson & Ecorse City Limit) | 730 | 05-25-21 A | 06-10-21 A
RR1 10381 | GRP-2021-RR.48.1.2 | 2021 GRP - Risk Rank | Install Main - Gunston (Collage & Gunston) | 80 | 05-25-21 A | 05-25-21 A
RR1 10231 | GRP-2021-RR.46.2.2 | 2021 GRP - Risk Rank | Install Main - College (Gunston & Devon) | 1482 | 05-25-21 A | 05-25-21 A
CDET2-2815 | GRP-2021-CDet2.19.1.2 | 2021 GRP - Central Detroit 2 | Elevate Main - ANO Joy (Savery & Savery) | 104 | 05-26-21 A | 05-26-21 A
AA4 21608 | GRP-2021-AA4.13.2.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - 5th St (W Davis Ave & Pauline Blvd) | 716 | 05-26-21 A | 05-26-21 A
NDET3-7015 | GRP-2021-ND3.1.1.2 | 2021 GRP - North Detroit 3 | Install Main - 8 Mile Rd (M102) (1) (Harned St & Sunset St) | 3625 | 05-27-21 A | 06-16-21 A
NDET3-6085 | GRP-2021-ND3.18.3.2 | 2021 GRP - North Detroit 3 | Install Main - Filer Ave (2) (ANO 7 Mile Rd & 7 Mile Rd) | 105 | 05-27-21 A | 06-02-21 A
SWDET2-16615 | PROJ-0951-SWDET2.25.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Elsmere 2 (Witt & Fort) | 490 | 05-27-21 A | 06-11-21 A
NCDET - 22755 | NEWPROJ-6.6.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Hartwell (Puritan & Fenkell) | 2704 | 05-31-21 A | 06-16-21 A
AA3-5980 | GRP-2021-RR1.7.2.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (2) (82' NNPL Ridge & 265' NNPL W Charlotte) | 775 | 05-31-21 A | 06-10-21 A
SWDET2-24125 | PROJ-0951-SWDET2.82.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 1W (At Witt) | 58 | 05-31-21 A | 06-07-21 A
Muni8790 | PROJ-0951-MUN-2.20.1.2 | 2021 GRP - Municipality | Install Main - Lahser (Santa Clara & Mcnichols) | 725 | 05-31-21 A | 06-17-21 A
NDET3-5600 | GRP-2021-ND3.44.1.2 | 2021 GRP - North Detroit 3 | Install Main - Syracuse Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 2415 | 05-31-21 A | 06-08-21 A
NDET3-8180 | GRP-2021-ND3.13.1.2 | 2021 GRP - North Detroit 3 | Install Main - Dwyer St (1) (8 Mile & 8 Mile) | 40 | 06-01-21 A | 06-01-21 A
Muni9030 | PROJ-0951-MUN-2.14.2.2 | 2021 GRP - Municipality | Install Main - Michigan (At Vinewood) | 223 | 06-01-21 A | 06-08-21 A
NDET3-5895 | GRP-2021-ND3.11.2.2 | 2021 GRP - North Detroit 3 | Install Main - ANO 7 Mile Rd (3) (Mt Elliott & Filer Ave) | 370 | 06-02-21 A | 06-08-21 A
NDET3-6790 | GRP-2021-ND3.61.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Sunset St (1) (8 Mile Rd (M102) & E Outer Dr) | 2356 | 06-03-21 A | 06-04-21 A
SWDET2-14065 | PROJ-0951-SWDET2.30.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Witt (At Lawndale) | 58 | 06-03-21 A | 06-11-21 A
SWDET2-15485 | PROJ-0951-SWDET2.65.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Carson (Tie-In & W Vernor) | 56 | 06-03-21 A | 06-07-21 A
NDET3-6505 | GRP-2021-ND3.18.1.2 | 2021 GRP - North Detroit 3 | Install Main - Filer Ave (2) (Emery St & ANO 7 Mile Rd) | 1110 | 06-03-21 A | 06-03-21 A
NDET3-5415 | GRP-2021-ND3.24.1.2 | 2021 GRP - North Detroit 3 | Install Main - Albany Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 2415 | 06-03-21 A | 06-10-21 A
AA4 28878 | GRP-2021-AA4.26.3.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Davis Ave (Hutchins & 5th) | 337 | 06-03-21 A | 06-03-21 A
RR1 51698 | GRP-2021-RR1.109.1.2 | 2021 GRP - River Rouge | Install Main - Orchard St (River Rouge City Limits & Ironton Ave) | 425 | 06-04-21 A | 06-10-21 A
RR1 51311 | GRP-2021-RR1.71.1.2 | 2021 GRP - River Rouge | Install Main - Ironton Ave 1 (E Great Lakes St & Catherine St) | 290 | 06-04-21 A | 06-09-21 A
Ypsi 3-12730 | PROJ-0951-YSP3.39.3.2 | 2021 GRP - Ypsilanti 3 | Install Main - Tyler (Nevada & Desoto) | 1965 | 06-07-21 A | 06-07-21 A
SWDET2-3790 | PROJ-0951-SWDET2.28.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Olivet (Woodmere & Lawndale) | 1797 | 06-07-21 A | 06-18-21 A
SWDET2-13825 | PROJ-0951-SWDET2.38.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Avis (Elsmere & Lawndale) | 1087 | 06-07-21 A | 06-11-21 A
NDET3-7510 | GRP-2021-ND3.55.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Dean Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 2339 | 06-07-21 A | 06-11-21 A
NDET3-5610 | GRP-2021-ND3.13.1.2 | 2021 GRP - North Detroit 3 | Install Main - Dwyer St (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 06-07-21 A | 06-07-21 A
AA4 22328 | GRP-2021-AA4.37.4.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Elder Blvd (Crest Ave & 11' WEPL Crest Ave) | 66 | 06-07-21 A | 06-07-21 A
AA4 22008 | GRP-2021-AA4.17.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Edgewood Pl (W Davis Ave & EOM) | 345 | 06-07-21 A | 06-07-21 A
SWDET2-8955 | PROJ-0951-SWDET2.5.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Fort (EO Distal & Elsmere) | 604 | 06-07-21 A | 06-11-21 A
NDET3-8160 | GRP-2021-ND3.3.8.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Bloom St) | 145 | 06-08-21 A | 06-21-21 A
NDET3-190 | GRP-2021-ND3.3.2.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Harned St) | 145 | 06-08-21 A | 06-08-21 A
NDET3-205 | GRP-2021-ND3.3.4.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Mitchell St) | 145 | 06-08-21 A | 06-08-21 A
Muni8470 | PROJ-0951-MUN-2.16.1.2 | 2021 GRP - Municipality | Install Main - ASO Michigan (At Vinewood) | 5 | 06-08-21 A | 06-08-21 A
RR1 53450 | GRP-2021-RR1.67.3.2 | 2021 GRP - River Rouge | Install Main - Cattherine St (38' WWPL Ironton St & Ironton St) | 10 | 06-08-21 A | 06-09-21 A
RR1 5174 | GRP-2021-RR1.59.1.2 | 2021 GRP - River Rouge | Install Main - E Great Lakes St (57' WWPL Ironton Ave & Ironton Ave) | 65 | 06-08-21 A | 06-09-21 A
NDET3-5225 | GRP-2021-ND3.31.1.2 | 2021 GRP - North Detroit 3 | Install Main - Mound Rd (E Outer Dr & ANO 7 Mile Rd) | 2490 | 06-09-21 A | 06-14-21 A
NDET3-6115 | GRP-2021-ND3.26.1.2 | 2021 GRP - North Detroit 3 | Install Main - Buffalo St (2) (E Outer Dr & ANO 7 Mile Rd) | 2415 | 06-09-21 A | 06-15-21 A
NDET3-280 | GRP-2021-ND3.3.9.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Crossing At Mt Elliot St) | 180 | 06-09-21 A | 06-09-21 A
SWDET2-15645 | PROJ-0951-SWDET2.66.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Casper (Tie-In & W Vernor) | 699 | 06-09-21 A | 06-10-21 A
NDET3-5230 | GRP-2021-ND3.10.1.2 | 2021 GRP - North Detroit 3 | Install Main - ANO 7 Mile Rd (2) (Ryan Rd & Bloom St) | 3835 | 06-09-21 A | 06-29-21 A
SWDET2-7790 | PROJ-0951-SWDET2.77.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Pearl (Woodmere & Tie-In) | 45 | 06-10-21 A | 06-10-21 A
Muni8550 | PROJ-0951-MUN-2.17.1.2 | 2021 GRP - Municipality | Install Main - Hubbard (West Grand Blvd & Michigan) | 701 | 06-10-21 A | 06-16-21 A
SWDET2-3390 | PROJ-0951-SWDET2.22.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Distel (Olivet & Fort) | 733 | 06-10-21 A | 06-30-21 A
AA3-5910 | GRP-2021-RR1.7.3.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (2) (133' SSPL Rockwood & W Glenwood) | 120 | 06-14-21 A | 06-15-21 A
RR1 569 | GRP-2021-RR1.24.1.2 | 2021 GRP - River Rouge | Install Main - Furgason (W Pleasant St & Myrtle St) | 270 | 06-14-21 A | 06-15-21 A
RR1 51447 | GRP-2021-RR1.97.1.2 | 2021 GRP - River Rouge | Install Main - W Glenwood Ave (420' WWPL W Jefferson Ave & 12' WWPL W Jefferson Ave) | 85 | 06-14-21 A | 06-15-21 A
SWDET2-4750 | PROJ-0951-SWDET2.40.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Falcon (Woodmere & Lawndale) | 1801 | 06-14-21 A | 06-23-21 A
SWDET2-15395 | PROJ-0951-SWDET2.79.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Wendell (ANO W Vernor & EOM) | 64 | 06-14-21 A | 06-14-21 A
RR1 6021 | GRP-2021-RR.8.1.2 | 2021 GRP - Risk Rank | Install Main - Westphalia (7 Mile & Greiner) | 2575 | 06-14-21 A | 07-07-21 A
NDET3-7270 | GRP-2021-ND3.40.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Ryan Rd (1) (8 Mile Rd (M102) & E Outer Dr) | 2280 | 06-14-21 A | 06-17-21 A
NDET3-6330 | GRP-2021-ND3.27.3.2 | 2021 GRP - North Detroit 3 | Install Main - Caldwell St (2) (Emery St & ANO 7 Mile Rd) | 340 | 06-14-21 A | 06-14-21 A
Muni7590 | PROJ-0951-MUN-2.6.1.2 | 2021 GRP - Municipality | Install Main - W Chicago 1 (Pinehurst & Griggs) | 1160 | 06-14-21 A | 06-30-21 A
NDET3-5765 | GRP-2021-ND3.27.1.2 | 2021 GRP - North Detroit 3 | Install Main - Caldwell St (2) (E Outer Dr & Emery St) | 1710 | 06-14-21 A | 06-17-21 A
RR1 6341 | GRP-2021-RR.14.1.2 | 2021 GRP - Risk Rank | Install Main - Casgrain (40' NNPL Lafayette & 131' NNPL Lafayette) | 250 | 06-14-21 A | 06-23-21 A
AA4 20530 | GRP-2021-AA4.17.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Edgewood Pl (W Hoover Ave & W Davis Ave) | 418 | 06-14-21 A | 06-14-21 A
AA4 20539 | GRP-2021-AA4.27.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Hoover Ave (5th St & S Main St) | 1267 | 06-14-21 A | 07-16-21 A
SWDET2-24595 | PROJ-0951-SWDET2.20.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - AEO Distel (Olivet & EOM) | 522 | 06-15-21 A | 06-15-21 A
Muni9110 | PROJ-0951-MUN-2.15.2.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (West Grand Blvd & Vinewood) | 336 | 06-15-21 A | 06-16-21 A
Muni8390 | PROJ-0951-MUN-2.15.1.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (West Grand Blvd & EOM) | 109 | 06-15-21 A | 06-16-21 A
RR1 51310 | GRP-2021-RR1.70.1.2 | 2021 GRP - River Rouge | Install Main - Hill St (Genessee St & 27' WWPL Alexander St) | 495 | 06-16-21 A | 06-17-21 A
NDET3-5930 | GRP-2021-ND3.102.1.2 | 2021 GRP - North Detroit 3 | Install Main - Emery St (Buffalo St & Caldwell St) | 285 | 06-16-21 A | 06-16-21 A
NDET3-6745 | GRP-2021-ND3.25.3.2 | 2021 GRP - North Detroit 3 | Install Main - Bloom St (2) (E Lantz Ave & ANO 7Mile Rd) | 1665 | 06-16-21 A | 06-22-21 A
RR1 56730 | GRP-2021-RR1.68.3.2 | 2021 GRP - River Rouge | Install Main - Forest St (Genessee St & Ironton Ave) | 1160 | 06-16-21 A | 06-29-21 A
AA3-3480 | GRP-2021-RR1.7.1.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (2) (River Rouge City Limits & E Glenwood) | 815 | 06-16-21 A | 06-22-21 A
NCDET - 23055 | NEWPROJ-6.13.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Snowden (Puritan & Fenkell) | 2714 | 06-17-21 A | 06-30-21 A
SWDET2-22355 | PROJ-0951-SWDET2.77.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Pearl (ANO W Vernor & EOM) | 78 | 06-17-21 A | 06-17-21 A
AA4 28938 | GRP-2021-AA4.26.2.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Davis Ave (5th & Main) | 1580 | 06-17-21 A | 07-08-21 A
SWDET2-9035 | PROJ-0951-SWDET2.5.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Fort (Elsmere & EOM) | 384 | 06-17-21 A | 06-18-21 A
Muni8870 | PROJ-0951-MUN-2.21.1.2 | 2021 GRP - Municipality | Install Main - Orchard (At Lahser) | 24 | 06-17-21 A | 06-17-21 A
Muni9270 | PROJ-0951-MUN-2.22.4.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (2) (Mckinley & Ash) | 589 | 06-17-21 A | 06-22-21 A
RR1 60860 | GRP-2021-RR1.2.13.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (E Great Lakes St & 5' NSPL W Great Lakes St) | 120 | 06-21-21 A | 07-15-21 A
RR1 61340 | GRP-2021-RR1.2.19.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (Forest St & River Rouge City Limits) | 550 | 06-21-21 A | 06-28-21 A
NDET3-6685 | GRP-2021-ND3.25.1.2 | 2021 GRP - North Detroit 3 | Install Main - Bloom St (2) (E Outer Dr & E Lantz Ave) | 760 | 06-21-21 A | 06-21-21 A
NDET3-7515 | GRP-2021-ND3.63.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 2301 | 06-21-21 A | 06-29-21 A
Ypsi 3-1260 | PROJ-0951-YSP3.1.1.2 | 2021 GRP - Ypsilanti 3 | Elevate Main - Carol Ann (Eileen & Mary Catherine) | 709 | 06-21-21 A | 06-22-21 A
AA4 20796 | GRP-2021-AA4.54.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Wakefield Ave (Hutchins & Prescott) | 337 | 06-21-21 A | 06-21-21 A
NDET3-4550 | GRP-2021-ND3.21.1.2 | 2021 GRP - North Detroit 3 | Install Main - Mt Elliote St (2) (E Outer Dr & ANO 7 Mile Rd) | 2405 | 06-21-21 A | 06-29-21 A
AA4 20792 | GRP-2021-AA4.49.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Soule Blvd (4' SSPL W Liberty St & 19' NNPL Lutz Ave) | 830 | 06-21-21 A | 07-09-21 A
SWDET2-22195 | PROJ-0951-SWDET2.28.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Olivet (Lawndale & EOM) | 528 | 06-22-21 A | 06-23-21 A
NDET3-7070 | GRP-2021-ND3.97.3.2 | 2021 GRP - North Detroit 3 | Install Main - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) - Bloom Crossing | 45 | 06-22-21 A | 06-22-21 A
NDET3-7245 | GRP-2021-ND3.39.3.2 | 2021 GRP - North Detroit 3 | Install Main - Moenart St (2) (E Outer Dr & ANO 7 Mile Rd) | 1665 | 06-22-21 A | 06-28-21 A
RR1 11371 | GRP-2021-FR.65.1.2 | 2021 GRP - Field Recommendation | Install Main - Rohns (Mack & Goethe) | 891 | 06-22-21 A | 06-24-21 A
Muni9350 | PROJ-0951-MUN-2.18.2.2 | 2021 GRP - Municipality | Install Main - Mckinley (Magnolia & West Grand Blvd) | 606 | 06-22-21 A | 06-24-21 A
RR1 51308 | GRP-2021-RR1.68.1.2 | 2021 GRP - River Rouge | Install Main - Forest St (W Jefferson Ave & Genessee St) | 155 | 06-23-21 A | 06-29-21 A
RR1 60940 | GRP-2021-RR1.2.14.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (5' EWPL W Jefferson Ave & 4' WEPL W Jefferson Ave) | 125 | 06-23-21 A | 07-15-21 A
RR1 7301 | GRP-2021-RR.26.1.2 | 2021 GRP - Risk Rank | Install Main - Alger (Woodward & Beaubien) | 1701 | 06-23-21 A | 07-19-21 A
AA4 20543 | GRP-2021-AA4.31.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Wilder Pl (W Davis Ave & W Hoover Ave) | 262 | 06-23-21 A | 07-06-21 A
Muni9190 | PROJ-0951-MUN-2.15.3.2 | 2021 GRP - Municipality | Install Main - West Grand Blvd (1) (EOM & Mckinley) | 82 | 06-23-21 A | 06-24-21 A
Muni8630 | PROJ-0951-MUN-2.18.1.2 | 2021 GRP - Municipality | Install Main - Mckinley (NO Magnolia & Magnolia) | 234 | 06-23-21 A | 06-28-21 A
RR1 59250 | GRP-2021-RR1.74.3.2 | 2021 GRP - River Rouge | Install Main - Stone St (Genessee St & Ironton Ave) | 1160 | 06-24-21 A | 07-07-21 A
RR1 60700 | GRP-2021-RR1.2.11.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (Maple St & E Great Lakes St) | 1255 | 06-24-21 A | 07-15-21 A
Muni7430 | PROJ-0951-MUN-2.4.1.2 | 2021 GRP - Municipality | Install Main - ANO Chicago (Griggs & Wyoming) | 968 | 06-24-21 A | 06-30-21 A
Muni7510 | PROJ-0951-MUN-2.5.1.2 | 2021 GRP - Municipality | Install Main - Griggs (ANO Chicago & Chicago) | 95 | 06-24-21 A | 06-30-21 A
Ypsi 3-7320 | PROJ-0951-YSP3.22.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Mary Catherine (Woodglen & Eileen) | 3010 | 06-24-21 A | 07-20-21 A
RR1 11511 | GRP-2021-FR.67.1.2 | 2021 GRP - Field Recommendation | Install Main - Belvidere (Mack & Charlevoix) | 1820 | 06-24-21 A | 07-02-21 A
Muni8950 | PROJ-0951-MUN-2.13.2.2 | 2021 GRP - Municipality | Install Main - Magnolia (Mckinley & Roosevelt) | 328 | 06-25-21 A | 06-30-21 A
Ypsi 3-6570 | PROJ-0951-YSP3.19.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Lori (Mary Catherine & Tyler) | 1270 | 06-25-21 A | 07-15-21 A
SWDET2-4430 | PROJ-0951-SWDET2.36.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Longworth (Woodmere & Lawndale) | 1800 | 06-28-21 A | 07-13-21 A
NDET3-4790 | GRP-2021-ND3.28.1.2 | 2021 GRP - North Detroit 3 | Install Main - Conley Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 2430 | 06-28-21 A | 07-06-21 A
NDET3-4950 | GRP-2021-ND3.91.1.2 | 2021 GRP - North Detroit 3 | Install Main - ANO 7 Mile Rd (1) (Mitchell St & Ryan St) | 2485 | 06-28-21 A | 07-15-21 A
NDET3-7025 | GRP-2021-ND3.97.1.2 | 2021 GRP - North Detroit 3 | Install Main - E Lantz Ave (1) (Keystone & Bloom) | 590 | 06-28-21 A | 06-28-21 A
NDET3-295 | GRP-2021-ND3.3.10.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Mt Elliot St & Filer Ave) | 415 | 06-28-21 A | 06-28-21 A
CDET2-2985 | GRP-2021-CDet2.21.1.2 | 2021 GRP - Central Detroit 2 | Install Main - Clairmount 2 (Linwood & Rosa Parks) | 2392 | 06-28-21 A | 07-06-21 A
RR1 61180 | GRP-2021-RR1.2.17.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (Stoner St & Forest St) | 410 | 06-28-21 A | 06-28-21 A
RR1 51297 | GRP-2021-RR1.74.1.2 | 2021 GRP - River Rouge | Install Main - Stone St (W Jefferson Ave & Genessee St) | 325 | 06-29-21 A | 06-30-21 A
RR1 61260 | GRP-2021-RR1.2.18.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (0' WEPL W Jefferson Ave & 22' WEPL W Jefferson Ave) | 25 | 06-29-21 A | 06-29-21 A
NDET3-7285 | GRP-2021-ND3.39.1.2 | 2021 GRP - North Detroit 3 | Install Main - Moenart St (2) (EOM & E Lantz Ave) | 180 | 06-29-21 A | 06-29-21 A
NDET3-310 | GRP-2021-ND3.3.11.2 | 2021 GRP - North Detroit 3 | Install Main - E Outer Dr (South) - (Filer Ave & EOM) | 210 | 06-29-21 A | 06-29-21 A
Ypsi 3-6820 | PROJ-0951-YSP3.20.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Chevrolet (Tyler & Desoto) | 2385 | 06-29-21 A | 07-30-21 A
Muni8230 | PROJ-0951-MUN-2.13.1.2 | 2021 GRP - Municipality | Install Main - Magnolia (Vinewood & Mckinley) | 424 | 06-29-21 A | 06-30-21 A
NDET3-7125 | GRP-2021-ND3.37.1.2 | 2021 GRP - North Detroit 3 | Install Main - Keystone St (2) (E Lantz St & ANO 7 Mile Rd) | 1800 | 06-30-21 A | 07-07-21 A
NDET3-7195 | GRP-2021-ND3.84.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Wexford (1) (8 Mile Rd & E Outer Dr) | 2292 | 06-30-21 A | 07-06-21 A
RR1 5168 | GRP-2021-RR1.57.1.2 | 2021 GRP - River Rouge | Install Main - Chestnut St (W Jefferson & 489' WWPL Genessee St) | 295 | 06-30-21 A | 07-15-21 A
NCDET - 23445 | NEWPROJ-6.7.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Littlefield (Puritan & Fenkell) | 2664 | 06-30-21 A | 07-14-21 A
NDET3-6675 | GRP-2021-ND3.17.1.2 | 2021 GRP - North Detroit 3 | Install Main - Filer Ave (1) (E Outer Dr & EOM) | 345 | 07-01-21 A | 07-01-21 A
NDET3-5730 | GRP-2021-ND3.20.1.2 | 2021 GRP - North Detroit 3 | Install Main - Mt Elliote St (1) (8 Mile Rd (M102) & 8 Mile Rd (M102)) | 815 | 07-01-21 A | 07-02-21 A
NDET3-5840 | GRP-2021-ND3.20.3.2 | 2021 GRP - North Detroit 3 | Install Main - Mt Elliote St (1) (Mt Elliott Crossing) | 70 | 07-01-21 A | 07-02-21 A
NDET3-5850 | GRP-2021-ND3.20.2.2 | 2021 GRP - North Detroit 3 | Install Main - Mt Elliote St (1) (8 Mile Rd (M102) & 8 Mile Rd (M102) 2) | 25 | 07-01-21 A | 07-02-21 A
NDET3-4525 | GRP-2021-ND3.20.4.2 | 2021 GRP - North Detroit 3 | Install Main - Mt Elliote St (1) (E Outer Dr & E Outer Dr) | 1250 | 07-01-21 A | 07-02-21 A
NDET3-4840 | GRP-2021-ND3.33.1.2 | 2021 GRP - North Detroit 3 | Install Main - Fenelon Ave (2) (E Outer Dr & 7 Mile Rd) | 2445 | 07-01-21 A | 07-14-21 A
Ypsi 3-6320 | PROJ-0951-YSP3.18.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Zephyr (Tyler & Chevrolet) | 1065 | 07-01-21 A | 07-06-21 A
AA4 20785 | GRP-2021-AA4.42.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Maxwell Ave (EOM & Soule Blvd) | 368 | 07-01-21 A | 07-01-21 A
Ypsi 3-1030 | PROJ-0951-YSP3.5.4.1 | 2021 GRP - Ypsilanti 3 | Install Main - McCartney 1 (Tyler & EOM) | 385 | 07-01-21 A | 07-01-21 A
RR1 11581 | GRP-2021-FR.68.1.2 | 2021 GRP - Field Recommendation | Install Main - Charlevoix (Belvidere & McClellan) | 313 | 07-02-21 A | 07-02-21 A
Muni7350 | PROJ-0951-MUN-2.3.1.2 | 2021 GRP - Municipality | Install Main - Wyoming (ANO Chicago & Chicago) | 167 | 07-02-21 A | 07-13-21 A
SWDET2-3950 | PROJ-0951-SWDET2.30.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Witt (EOM & Elsmere) | 305 | 07-05-21 A | 07-08-21 A
RR1 61100 | GRP-2021-RR1.2.16.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (Neiman St & 118' NNPL Cora St) | 715 | 07-06-21 A | 07-14-21 A
RR1 11301 | GRP-2021-FR.64.1.2 | 2021 GRP - Field Recommendation | Install Main - Rolfs (571' NNPL Mack & Mack) | 639 | 07-07-21 A | 07-28-21 A
WCDET1-1865 | GRP-2021-WCDet1.8.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Dexter W (Davison & Buena Vista) | 745 | 07-07-21 A | 07-09-21 A
NDET3-85 | GRP-2021-ND3.86.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Yonka (1) (8 Mile Rd (M102) & E Remington Ave) | 1582 | 07-07-21 A | 07-08-21 A
NDET3-5200 | GRP-2021-ND3.35.1.2 | 2021 GRP - North Detroit 3 | Install Main - Healy St (E Outer Dr & ANO 7 Mile Rd) | 2445 | 07-08-21 A | 07-20-21 A
NDET3-5030 | GRP-2021-ND3.38.1.2 | 2021 GRP - North Detroit 3 | Install Main - Lamont Ave (E Outer Dr & 7 Mile Rd) | 2445 | 07-08-21 A | 07-13-21 A
RR1 9801 | GRP-2021-FR.57.1.2 | 2021 GRP - Field Recommendation | Install Main - Jefferson (24Th & 95' EEPL 23Rd) | 483 | 07-08-21 A | 07-22-21 A
RR1 51309 | GRP-2021-RR1.69.1.2 | 2021 GRP - River Rouge | Install Main - Genessee St 2 (12' NSPL E Great Lakes St & 5' SNPL Forest St) | 1515 | 07-08-21 A | 07-30-21 A
RR1 57050 | GRP-2021-RR1.69.3.2 | 2021 GRP - River Rouge | Install Main - Genessee St 2 (5' SNPL Forest St & 4' NSPL Forest St) | 45 | 07-08-21 A | 07-27-21 A
RR1 7481 | GRP-2021-RR.28.1.2 | 2021 GRP - Risk Rank | Install Main - Calvert (Hamilton & Woodward) | 2675 | 07-08-21 A | 08-03-21 A
SWDET2-3630 | PROJ-0951-SWDET2.26.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Fulton (EOM & Elsmere) | 305 | 07-09-21 A | 07-14-21 A
WCDET1-14560 | GRP-2021-WCDet1.8.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Dexter West (Buena Vista & Leslie) | 744 | 07-09-21 A | 08-10-21 A
Muni7270 | PROJ-0951-MUN-2.2.1.2 | 2021 GRP - Municipality | Install Main - Chicago 2 (Wyoming & EOM) | 210 | 07-09-21 A | 07-13-21 A
RR1 10841 | GRP-2021-FR.59.1.2 | 2021 GRP - Field Recommendation | Install Main - Mack (Crane & McClellan) | 1257 | 07-09-21 A | 07-28-21 A
SWDET2-4270 | PROJ-0951-SWDET2.34.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Homer (Woodmere & Lawndale) | 1799 | 07-12-21 A | 08-02-21 A
AA4 24618 | GRP-2021-AA4.57.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Myron Ct (W Hoover & EOM) | 138 | 07-12-21 A | 07-14-21 A
RR1 56010 | GRP-2021-RR1.62.3.2 | 2021 GRP - River Rouge | Install Main - E Oak St (4' EWPL Burke St & 2' WEPL Burke St) | 40 | 07-12-21 A | 08-16-21 A
RR1 8361 | GRP-2021-RR.39.1.2 | 2021 GRP - Risk Rank | Install Main - Fairport (E McNichols & Gratiot) | 1565 | 07-12-21 A | 07-22-21 A
Muni7910 | PROJ-0951-MUN-2.10.1.2 | 2021 GRP - Municipality | Install Main - Birwood (Chicago & ASO Chicago) | 118 | 07-12-21 A | 07-12-21 A
Muni7990 | PROJ-0951-MUN-2.11.1.2 | 2021 GRP - Municipality | Install Main - ASO Chicago (Pinehurst & Birwood) | 665 | 07-12-21 A | 07-19-21 A
RR1 10101 | GRP-2021-FR.56.1.2 | 2021 GRP - Field Recommendation | Install Main - 24th (30' SSPL Fort & Jefferson) | 504 | 07-12-21 A | 07-22-21 A
SWDET2-13435 | PROJ-0951-SWDET2.26.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Fulton (Elsmere & EOM) | 565 | 07-12-21 A | 07-15-21 A
RR1 60780 | GRP-2021-RR1.2.12.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (4' NSPL Burke St & W Great Lakes St) | 1080 | 07-13-21 A | 07-21-21 A
RR1 53130 | GRP-2021-RR1.50.5.2 | 2021 GRP - River Rouge | Install Main - Burke 1 (2' NSPL Coolidge Hwy & 2' NSPL W Oak St) | 270 | 07-13-21 A | 07-15-21 A
Muni7750 | PROJ-0951-MUN-2.6.2.2 | 2021 GRP - Municipality | Install Main - W Chicago 1 (Pinehurst & Birwood) | 664 | 07-13-21 A | 07-13-21 A
Muni7830 | PROJ-0951-MUN-2.9.1.2 | 2021 GRP - Municipality | Install Main - Mendota (Chicago & ASO Chicago) | 118 | 07-13-21 A | 07-13-21 A
RR1 53290 | GRP-2021-RR1.50.6.2 | 2021 GRP - River Rouge | Install Main - Burke 1 (2' NSPL W Oak St & 3' NSPL Maple St) | 535 | 07-13-21 A | 08-12-21 A
RR1 60620 | GRP-2021-RR1.2.10.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (2' WEPL Burke St & 3' NSPL Maple St) | 65 | 07-13-21 A | 07-15-21 A
RR1 51870 | GRP-2021-RR1.65.3.2 | 2021 GRP - River Rouge | Install Main - Abbott (Genessee St & Ironton Ave) | 1165 | 07-13-21 A | 07-30-21 A
RR1 61020 | GRP-2021-RR1.2.15.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (W Great Lakes St & Neiman St) | 285 | 07-13-21 A | 07-15-21 A
RR1 11441 | GRP-2021-FR.66.1.2 | 2021 GRP - Field Recommendation | Install Main - Holcomb (Mack & 74' SSPL Mack) | 77 | 07-14-21 A | 07-28-21 A
WCDET1-4345 | GRP-2021-WCDet1.40.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Buena Vista 2 (Livernois & Dexter) | 3040 | 07-14-21 A | 08-02-21 A
NDET3-7405 | GRP-2021-ND3.80.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Norwood St (1) (8 Mile Rd (M102) & E Outer Dr) | 2506 | 07-14-21 A | 07-20-21 A
NDET3-5550 | GRP-2021-ND3.32.1.2 | 2021 GRP - North Detroit 3 | Install Main - Eureka St (E Outer Dr & ANO 7 Mile Rd) | 2445 | 07-15-21 A | 07-21-21 A
AA4 27068 | GRP-2021-AA4.8.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Liberty St (Soule Blvd & Crest Ave) | 370 | 07-19-21 A | 07-21-21 A
NDET3-5740 | GRP-2021-ND3.36.1.2 | 2021 GRP - North Detroit 3 | Install Main - Justine Ave (E Outer Dr & 7 Mile Rd) | 2450 | 07-19-21 A | 07-28-21 A
NDET3-125 | GRP-2021-ND3.79.3.2 | 2021 GRP - North Detroit 3 | Install Main -Mitchell St (2) (ANO 7 Mile Rd & 7 Mile Rd) | 170 | 07-19-21 A | 07-19-21 A
RR1 52970 | GRP-2021-RR1.50.4.2 | 2021 GRP - River Rouge | Install Main - Burke 1 (4' SNPL Coolidge Hwy & 2' NSPL Coolidge Hwy) | 5 | 07-20-21 A | 08-16-21 A
RR1 52810 | GRP-2021-RR1.50.2.2 | 2021 GRP - River Rouge | Install Main - Burke 1 (3' SNPL Delisle St & 4' SNPL Coolidge Hwy) | 985 | 07-21-21 A | 08-16-21 A
NDET3-5370 | GRP-2021-ND3.34.1.2 | 2021 GRP - North Detroit 3 | Install Main - Hasse Ave (E Outer Dr & ANO 7 Mile Rd) | 2445 | 07-21-21 A | 07-27-21 A
NDET3-7275 | GRP-2021-ND3.82.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Revere Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 2370 | 07-21-21 A | 07-27-21 A
WCDET1-10660 | GRP-2021-WCDet1.17.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 4 (Buena Vista & Buena Vista) | 50 | 07-23-21 A | 07-23-21 A
RR1 56890 | GRP-2021-RR1.42.3.2 | 2021 GRP - River Rouge | Install Main - Genessee 1 (Coolidge Hwy & E Great Lakes St) | 1910 | 07-23-21 A | 09-07-21 A
RR1 590 | GRP-2021-RR1.31.1.2 | 2021 GRP - River Rouge | Install Main - Nieman (Haltiner & W Jefferson) | 735 | 07-23-21 A | 07-28-21 A
AA4 21438 | GRP-2021-AA4.13.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - 5th St (W Madison St & Davis Ave) | 1275 | 07-23-21 A | 08-26-21 A
WCDET1-4985 | GRP-2021-WCDet1.48.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 2 (Bourke & Doris) | 1963 | 07-26-21 A | 08-10-21 A
SWDET2-6030 | PROJ-0951-SWDET2.56.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Beard (ASO W Vernor & Cahalan) | 1194 | 07-26-21 A | 08-06-21 A
WCDET1-10980 | GRP-2021-WCDet1.48.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 2 (Intervale & Ewald) Start after Filer gas up | 766 | 07-26-21 A | 08-16-21 A
RR1 6901 | GRP-2021-RR.20.1.2 | 2021 GRP - Risk Rank | Install Main - ANO E Grand (John R & Melrose) | 2415 | 07-26-21 A | 08-26-21 A
NDET3-335 | GRP-2021-ND3.28.3.2 | 2021 GRP - North Detroit 3 | Install Main - Dwyer St (ANO 7 Mile Rd & 7 Mile Rd) - Install as necessary | 110 | 07-26-21 A | 07-26-21 A
RR1 11161 | GRP-2021-FR.59.3.2 | 2021 GRP - Field Recommendation | Install Main - Mack (2' NSPL Mack & 17' NSPL Mack @ Belvidere) | 18 | 07-26-21 A | 07-26-21 A
NDET3-8440 | GRP-2021-ND3.88.2.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Gallagher St & Gallagher St) | 115 | 07-26-21 A | 07-26-21 A
NDET3-9070 | GRP-2021-ND3.9.12.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Dwyer St & Dwyer St) | 110 | 07-26-21 A | 07-26-21 A
WCDET1-10820 | GRP-2021-WCDet1.48.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 2 (Livernois & Livernois) (Crossing at Intervale) | 112 | 07-26-21 A | 07-26-21 A
RR1 11081 | GRP-2021-FR.59.2.2 | 2021 GRP - Field Recommendation | Install Main - Mack (3' NSPL Mack & 17' NSPL Mack @ Belvidere) | 17 | 07-27-21 A | 07-27-21 A
Ypsi 3-7560 | PROJ-0951-YSP3.23.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Jeff (Desoto & Mary Catherine) | 1210 | 07-27-21 A | 07-29-21 A
Ypsi 3-6070 | PROJ-0951-YSP3.17.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Studebaker (Chevrolet & Tyler) | 1115 | 07-27-21 A | 08-02-21 A
RR1 51296 | GRP-2021-RR1.65.1.2 | 2021 GRP - River Rouge | Install Main - Abbott (EOM @ 261' WWPL Genessee St & Genessee St) | 310 | 07-28-21 A | 07-30-21 A
NCDET - 23835 | NEWPROJ-6.4.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Cheyenne (Puritan & Fenkell) | 2607 | 07-28-21 A | 08-03-21 A
NDET3-5950 | GRP-2021-ND3.42.1.2 | 2021 GRP - North Detroit 3 | Install Main - Shields St (E Outer Dr & ANO 7 Mile Rd) | 2445 | 07-28-21 A | 08-03-21 A
RR1 9721 | GRP-2021-FR.56.1.2 | 2021 GRP - Field Recommendation | Install Main - 24th (37' SSPL Fort & 147' SSPL Fort) | 119 | 07-29-21 A | 08-03-21 A
SWDET2-1012 | GRP-2021-WCDet1.52.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Quincy 2 (ANO Fenkell& Bourke) | 1584 | 07-29-21 A | 08-09-21 A
RR1 575 | GRP-2021-RR1.26.1.2 | 2021 GRP - River Rouge | Install Main - Haltiner St (108' NNPL Louis St & 50' NNPL Cora St) | 1660 | 07-29-21 A | 08-19-21 A
NDET3-4255 | GRP-2021-ND3.74.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Klinger St (1) (8 Mile Rd (M102) & E Outer Dr) | 2334 | 07-29-21 A | 08-03-21 A
WCDET1-12350 | GRP-2021-WCDet1.40.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Buena Vista 2 (Livernois & Broadstreet) | 355 | 07-30-21 A | 08-30-21 A
RR1 54170 | GRP-2021-RR1.15.3.2 | 2021 GRP - River Rouge | Install Main - Cora (4' EWPL Haltiner St & 5' WEPL Haltiner St) | 50 | 07-30-21 A | 09-09-21 A
SWDET2-4510 | PROJ-0951-SWDET2.37.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Rathbone (Woodmere & Lawndale) | 1798 | 08-02-21 A | 08-13-21 A
RR1 9001 | GRP-2021-RR.47.1.2 | 2021 GRP - Risk Rank | Install Main - Minden (Conner & Gunston) | 2114 | 08-02-21 A | 08-17-21 A
NDET3-6905 | GRP-2021-ND3.43.1.2 | 2021 GRP - North Detroit 3 | Install Main - Sunset St (2) (E Outer Dr & ANO 7 Mile Rd) | 2450 | 08-02-21 A | 08-05-21 A
RR1 5171 | GRP-2021-RR1.58.1.2 | 2021 GRP - River Rouge | Install Main - Coolidge Hwy 2 (W Jefferson & Burke St) | 240 | 08-02-21 A | 08-16-21 A
Ypsi 3-5820 | PROJ-0951-YSP3.16.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Buick (Tyler & Chevrolet) | 1175 | 08-02-21 A | 08-04-21 A
NDET3-4365 | GRP-2021-ND3.88.1.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Harned St & Mitchell St) | 305 | 08-03-21 A | 08-03-21 A
NDET3-6235 | GRP-2021-ND3.29.1.2 | 2021 GRP - North Detroit 3 | Install Main - Dean Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 2450 | 08-04-21 A | 08-10-21 A
RR1 8121 | GRP-2021-RR.36.1.2 | 2021 GRP - Risk Rank | Install Main - Canton (EOM 100' NNPL Farnsworth & Gration) | 1462 | 08-05-21 A | 08-10-21 A
RR1 52650 | GRP-2021-RR1.50.3.2 | 2021 GRP - River Rouge | Install Main - Burke 1 (4' SNPL E Pleasant St & 3' SNPL Delisle St) | 160 | 08-05-21 A | 08-16-21 A
RR1 5135 | GRP-2021-RR1.50.1.2 | 2021 GRP - River Rouge | Install Main - Burke 1 (E James St & E Pleasant St) | 225 | 08-05-21 A | 09-14-21 A
RR1 56410 | GRP-2021-RR1.44.2.2 | 2021 GRP - River Rouge | Install Main - E Pleasasnt North (4' EWPL Burke St & 8' WEPL Genessee St) | 1175 | 08-05-21 A | 2021-09-20
NDET3-4235 | GRP-2021-ND3.70.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Gallagher (1) (8 Mile Rd (M102) & E Outer Dr) | 2342 | 08-05-21 A | 08-10-21 A
SWDET2-5950 | PROJ-0951-SWDET2.55.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Whitaker 1 (Mullane & Springwells) | 765 | 08-09-21 A | 08-16-21 A
RR1 5701 | GRP-2021-RR.4.1.2 | 2021 GRP - Risk Rank | Install Main - Manistique (E Jefferson & Essex) | 2300 | 08-09-21 A | 08-31-21 A
NDET3-170 | GRP-2021-ND3.80.1.2 | 2021 GRP - North Detroit 3 | Install Main - Tie-ins - Norwood At 8 Mile Rd | 14 | 08-09-21 A | 08-09-21 A
NDET3-8510 | GRP-2021-ND3.88.4.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Revere St & Revere St) | 130 | 08-09-21 A | 08-09-21 A
NDET3-9280 | GRP-2021-ND3.9.15.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (At Albany Ave) | 220 | 08-09-21 A | 08-09-21 A
SWDET2-9646 | GRP-2021-WCDet1.52.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Quincy 2 (Bourke & EOM) | 503 | 08-09-21 A | 08-10-21 A
RR1 51306 | GRP-2021-RR1.66.1.2 | 2021 GRP - River Rouge | Install Main - Alexander 1 (139' SSPL E Great Lakes St & Abbott St) | 550 | 08-10-21 A | 08-12-21 A
RR1 60540 | GRP-2021-RR1.2.9.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (4' WEPL W Jefferson Ave & 0' WWPL W Jefferson Ave) | 120 | 08-10-21 A | 08-12-21 A
AA4 20382 | GRP-2021-AA4.8.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Liberty St (54' EEPL Crest Ave & 21' WWPL S 7Th St) | 1165 | 08-10-21 A | 09-16-21 A
WCDET1-15570 | GRP-2021-WCDet1.61.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Bourke (North) (Livernois & Quincy) | 549 | 08-11-21 A | 08-11-21 A
NDET3-6725 | GRP-2021-ND3.41.2.2 | 2021 GRP - North Detroit 3 | Install Main - Ryan Rd (2) (Emery St & ANO 7 Mile Rd) | 935 | 08-11-21 A | 08-16-21 A
Ypsi 3-1950 | PROJ-0951-YSP3.2.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Desoto (State & Tyler) | 2465 | 08-11-21 A | 08-30-21 A
RR1 53850 | GRP-2021-RR1.58.3.2 | 2021 GRP - River Rouge | Install Main - Coolidge Hwy 2 (Burke St & Richter St) | 1970 | 08-12-21 A | 2021-11-04
RR1 5183 | GRP-2021-RR1.62.1.2 | 2021 GRP - River Rouge | Install Main - E Oak St (W Jefferson & 4' EWPL Burke St) | 135 | 08-12-21 A | 08-12-21 A
NDET3-6500 | GRP-2021-ND3.41.1.2 | 2021 GRP - North Detroit 3 | Install Main - Ryan Rd (2) (E Outer Dr & Emery St) | 1510 | 08-12-21 A | 08-16-21 A
NDET3-6940 | GRP-2021-ND3.65.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Charest St (1) (8 Mile Rd (M102) & E Outer Dr) | 2352 | 08-12-21 A | 08-17-21 A
WCDET1-15650 | GRP-2021-WCDet1.27.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Stoepel 1 (Ewald & Oakman) | 502 | 08-12-21 A | 08-17-21 A
Ypsi 3-12240 | PROJ-0951-YSP3.45.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - US-12 (Gill & Gates) | 365 | 08-12-21 A | 08-17-21 A
RR1 5621 | GRP-2021-RR.3.1.2 | 2021 GRP - Risk Rank | Install Main - Wayburn (Berkshire & Evanston) | 1990 | 08-13-21 A | 08-23-21 A
RR1 60460 | GRP-2021-RR1.2.8.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (Coolidge Hwy & Oak St) | 345 | 08-13-21 A | 08-17-21 A
NDET3-3695 | GRP-2021-ND3.57.1.2 | 2021 GRP - North Detroit 3 | Install Main - Hamlet St (1) (Ryan Rd & Sunset St) - Removed from the scope | 0 | 08-16-21 A | 08-17-21 A
NDET3-110 | GRP-2021-ND3.73.1.2 | 2021 GRP - North Detroit 3 | Install Main - Harned St (2) (At E Outer Dr) | 60 | 08-16-21 A | 08-17-21 A
NDET3-155 | GRP-2021-ND3.81.1.2 | 2021 GRP - North Detroit 3 | Install Main - Tie-ins - (Norwood St & Outer Dr) | 7 | 08-16-21 A | 08-17-21 A
NDET3-160 | GRP-2021-ND3.81.1.2 | 2021 GRP - North Detroit 3 | Install Main - Tie-ins - (Norwood St & ANO 7 Mile Rd) | 27 | 08-16-21 A | 08-17-21 A
NDET3-165 | GRP-2021-ND3.81.1.2 | 2021 GRP - North Detroit 3 | Install Main - Tie-ins - (Norwood St & 7 Mile Rd) | 4 | 08-16-21 A | 08-17-21 A
NDET3-175 | GRP-2021-ND3.80.1.2 | 2021 GRP - North Detroit 3 | Install Main - Tie-ins - Norwood At E Outer | 10 | 08-16-21 A | 08-17-21 A
NDET3-3130 | GRP-2021-ND3.2.1.2 | 2021 GRP - North Detroit 3 | Install Main - Girardin Ave (Tie-in at 7 Mile Rd) - Removed from the scope | 0 | 08-16-21 A | 08-17-21 A
NDET3-8580 | GRP-2021-ND3.88.5.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Norwood St & Norwood St) | 140 | 08-16-21 A | 08-17-21 A
NDET3-8650 | GRP-2021-ND3.12.6.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Sunset St & Shields St) | 160 | 08-16-21 A | 08-17-21 A
NDET3-8720 | GRP-2021-ND3.12.7.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Justine Ave & Eureka St) | 130 | 08-16-21 A | 08-17-21 A
NDET3-8790 | GRP-2021-ND3.12.8.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Healy St & Lamont Ave) | 290 | 08-16-21 A | 08-17-21 A
NDET3-8860 | GRP-2021-ND3.12.9.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Lamont Ave & Fenelon Ave) | 60 | 08-16-21 A | 08-17-21 A
NDET3-8930 | GRP-2021-ND3.12.10.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Conley Ave & Keys&ne Ave) | 115 | 08-16-21 A | 08-17-21 A
NDET3-9000 | GRP-2021-ND3.12.11.2 | 2021 GRP - North Detroit 3 | Install Main - 7 Mile Rd (1) (Keystone Ave) | 82 | 08-16-21 A | 08-17-21 A
WCDET1-3305 | GRP-2021-WCDet1.27.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Stoepel 1 (Ewald & Ewald) | 256 | 08-16-21 A | 08-16-21 A
SWDET2-6670 | PROJ-0951-SWDET2.64.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Whitaker 2 (Springwells & Central) | 906 | 08-16-21 A | 08-20-21 A
WCDET1-12030 | GRP-2021-WCDet1.30.4.2 | 2021 GRP - West Central Detroit 1 | Install Main - Buena Vista 1 (Stoepel & Livernois) | 214 | 08-16-21 A | 08-16-21 A
NDET3-105 | GRP-2021-ND3.73.1.2 | 2021 GRP - North Detroit 3 | Install Main - Harned St (2) (At 7 Mile Rd) | 80 | 08-16-21 A | 08-16-21 A
NDET3-145 | GRP-2021-ND3.65.1.2 | 2021 GRP - North Detroit 3 | Install Main - Tie-ins Charest St (1) (8 Mile Rd & 8 Mile) | 24 | 08-16-21 A | 08-16-21 A
NDET3-150 | GRP-2021-ND3.65.1.2 | 2021 GRP - North Detroit 3 | Install Main - Tie-ins Charest St (1) (Outer & Outer) | 24 | 08-16-21 A | 08-16-21 A
NDET3-7800 | GRP-2021-ND3.8.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - E Remington St (Norwood & Yonka) | 280 | 08-16-21 A | 08-16-21 A
WCDET1-11710 | GRP-2021-WCDet1.30.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Buena Vista 1 (Turner & Ewald) | 639 | 08-16-21 A | 08-23-21 A
WCDET1-11870 | GRP-2021-WCDet1.30.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Buena Vista 1 (Ewald & Stoepel) | 1268 | 08-16-21 A | 08-19-21 A
WCDET1-1785 | GRP-2021-WCDet1.7.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Broadstreet (Waverly & Buena Vista) | 814 | 08-16-21 A | 08-18-21 A
Milestone 1 | GRP-2021-ND3.23 | 2021 GRP - North Detroit 3 | Install Main Finish Milestone | 0 |  | 08-17-21 A
SWDET2-4910 | PROJ-0951-SWDET2.42.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Logan 1 (Mullane & Springwells) | 705 | 08-17-21 A | 08-18-21 A
NDET3-6705 | GRP-2021-ND3.41.3.2 | 2021 GRP - North Detroit 3 | Install Main - Ryan Rd (2) (Ryan Rd & Ryan Rd) | 55 | 08-17-21 A | 08-17-21 A
RR1 5120 | GRP-2021-RR1.42.1.2 | 2021 GRP - River Rouge | Install Main - Genessee 1 (E Pleasant St & Coolidge Hwy) | 1180 | 08-17-21 A | 2021-10-07
RR1 51307 | GRP-2021-RR1.67.1.2 | 2021 GRP - River Rouge | Install Main - Catherine St (Alexander St & 179' WWPL Ironton St) | 460 | 08-18-21 A | 08-19-21 A
WCDET1-9860 | GRP-2021-WCDet1.27.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Stoepel 1 (Oakman & Buena Vista) | 2125 | 08-18-21 A | 09-01-21 A
WCDET1-3065 | GRP-2021-WCDet1.13.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald Cr North 1 (Schoolcraft & Livernois) | 1920 | 08-18-21 A | 09-07-21 A
RR1 11081 | GRP-2021-RR.11.1.2 | 2021 GRP - Risk Rank | Install Main - Novara (Crusade & Kelly) | 2911 | 08-18-21 A | 2021-10-04
NCDET - 24225 | NEWPROJ-6.16.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Ward (Puritan & Fenkell) | 2581 | 08-18-21 A | 08-26-21 A
SWDET2-19805 | PROJ-0951-SWDET2.36.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Longworth (Tie-in & Lawndale) | 690 | 08-19-21 A | 08-24-21 A
WCDET1-1625 | GRP-2021-WCDet1.5.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Waverly (Broadstreet & Dexter) | 2405 | 08-19-21 A | 08-27-21 A
AA4 20774 | GRP-2021-AA4.32.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - 8th St (W Liberty St & EOM) | 660 | 08-19-21 A | 08-19-21 A
NDET3-7400 | GRP-2021-ND3.78.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Mitchell St (1) (8 Mile Rd (M102) & E Outer Dr) | 2367 | 08-19-21 A | 08-24-21 A
RR1 53610 | GRP-2021-RR1.4.3.2 | 2021 GRP - River Rouge | Install Main - Coolidge Hwy 1 (Division St & W Jefferson Ave) | 680 | 08-20-21 A | 2021-10-01
NWDET-21780 | PROJ-0951-NWDET1CO.29.3.2 | 2021 GRP - North West Detroit 1b | Elevate Main - Artesian (3) (SO Glendale & EEOM Artesian) | 359 | 08-23-21 A | 08-24-21 A
SWDET2-14875 | PROJ-0951-SWDET2.64.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Whitaker 2 (Central & Green) | 929 | 08-23-21 A | 08-25-21 A
RR1 6821 | GRP-2021-RR.19.1.2 | 2021 GRP - Risk Rank | Install Main - McDougall (Davison & Carpenter) | 2460 | 08-23-21 A | 09-08-21 A
RR1 9561 | GRP-2021-FR.54.1.2 | 2021 GRP - Field Recommendation | Install Main - 16th (65' NNPL Lafayette & Lafayette) | 168 | 08-23-21 A | 08-31-21 A
RR1 9161 | GRP-2021-FR.49.1.2 | 2021 GRP - Field Recommendation | Install Main - St Anne (Lafayette & Fort) | 553 | 08-23-21 A | 08-31-21 A
Ypsi 3-3090 | PROJ-0951-YSP3.4.3.2 | 2021 GRP - Ypsilanti 3 | Install Main - Nash 2 (Tyler & State) | 2685 | 08-23-21 A | 09-13-21 A
RR1 9401 | GRP-2021-FR.52.1.2 | 2021 GRP - Field Recommendation | Install Main - Lafayette (3' WWPL 17Th & 16Th) | 298 | 08-23-21 A | 08-31-21 A
RR1 10651 | GRP-2021-FR.52.1.2 | 2021 GRP - Field Recommendation | Install Main - Lafayette (St. Anne & 110' EEPL St. Anne) | 115 | 08-23-21 A | 08-31-21 A
AA4 26908 | GRP-2021-AA4.28.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Jefferson St South (1' WEPL S 7Th St & S 1St St) | 1240 | 08-23-21 A | 09-09-21 A
NWDET-21840 | PROJ-0951-NWDET1CO.29.3.2 | 2021 GRP - North West Detroit 1b | Elevate Main - Artesian (4) (Artesian & EOM) | 2077 | 08-24-21 A | 08-24-21 A
WCDET1-12190 | GRP-2021-WCDet1.40.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Buena Vista 2 (Broadstreet & Petoskey) | 1149 | 08-24-21 A | 08-30-21 A
SWDET2-20125 | PROJ-0951-SWDET2.36.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Longworth (Tie-in & Springwells) | 600 | 08-25-21 A | 08-25-21 A
RR1 5141 | GRP-2021-RR1.48.1.2 | 2021 GRP - River Rouge | Install Main - Delisle (W Jefferson & Burke) | 380 | 08-25-21 A | 2021-09-23
RR1 55850 | GRP-2021-RR1.53.4.2 | 2021 GRP - River Rouge | Install Main - E James South (3' WEPL Burke St & 8' EWPL Harris St) 2" | 1365 | 08-25-21 A | 09-02-21 A
WCDET1-1705 | GRP-2021-WCDet1.6.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Tyler (Broadstreet & Dexter) | 2440 | 08-26-21 A | 09-08-21 A
AA4 20526 | GRP-2021-AA4.13.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - 5th St (W Jefferson St & W Madison St) | 749 | 08-26-21 A | 2021-09-21
NDET3-4245 | GRP-2021-ND3.72.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Harned St (1) (8 Mile Rd (M102) & E Outer Dr) | 2329 | 08-26-21 A | 08-31-21 A
RR1 587 | GRP-2021-RR1.30.1.2 | 2021 GRP - River Rouge | Install Main - Myrtle (Division & W Jefferson) | 590 | 08-26-21 A | 08-30-21 A
RR1 58610 | GRP-2021-RR1.56.3.2 | 2021 GRP - River Rouge | Install Main - Richter (Maple St & E Great Lakes St) | 1080 | 08-27-21 A | 09-02-21 A
SWDET2-15035 | PROJ-0951-SWDET2.64.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Whitaker 2 (Green & Beard) | 737 | 08-27-21 A | 08-30-21 A
Ypsi 3-2200 | PROJ-0951-YSP3.42.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - State (McCartney & Desoto) | 1105 | 08-30-21 A | 09-07-21 A
WCDET1-3545 | GRP-2021-WCDet1.30.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Buena Vista 1 (Turner & Turner) Start | 113 | 08-30-21 A | 08-30-21 A
AA4 20377 | GRP-2021-AA4.2.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Pauline Blvd (Redeemer & S 7th Stt) | 1241 | 08-30-21 A | 09-15-21 A
WCDET1-9460 | GRP-2021-WCDet1.16.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Santa Rosa 2 (Buena Vista & Elmhurst) | 2897 | 08-30-21 A | 09-16-21 A
SWDET2-17685 | PROJ-0951-SWDET2.61.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Senator 2 (Springwells & Central) | 905 | 08-30-21 A | 09-08-21 A
RR1 58110 | GRP-2021-RR1.54.3.2 | 2021 GRP - River Rouge | Install Main - Leroy (Genessee St & Richter St) | 755 | 08-30-21 A | 2021-09-22
RR1 55290 | GRP-2021-RR1.45.2.2 | 2021 GRP - River Rouge | Install Main - E Henry (33' EEPL Genessee St & 110' WWPL Richter St) | 610 | 08-30-21 A | 2021-11-04
RR1 55610 | GRP-2021-RR1.53.80.2 | 2021 GRP - River Rouge | Install Main - E James South (W Jefferson & 4' EWPL Burke St) 2" | 395 | 08-30-21 A | 09-02-21 A
RR1 55690 | GRP-2021-RR1.53.2.2 | 2021 GRP - River Rouge | Install Main - E James South (4' EWPL Burke St & 3' WEPL Burke St) 3" | 40 | 08-30-21 A | 09-02-21 A
RR1 57290 | GRP-2021-RR1.41.2.2 | 2021 GRP - River Rouge | Install Main - Harris (18' NNPL E James St & 18' NNPL E Pleasant St) | 425 | 08-31-21 A | 09-03-21 A
RR1 10921 | GRP-2021-RR.61.1.2 | 2021 GRP - Risk Rank | Install Main - Carpenter (McDougall & Charest) | 230 | 08-31-21 A | 09-08-21 A
RR1 57210 | GRP-2021-RR1.41.3.2 | 2021 GRP - River Rouge | Install Main - Harris (E Cicotte St & 18' NNPL E James St) | 275 | 08-31-21 A | 09-03-21 A
RR1 5185 | GRP-2021-RR1.63.1.2 | 2021 GRP - River Rouge | Install Main - Pine St (Burke St & Genessee St) | 1140 | 09-01-21 A | 2021-10-26
RR1 58450 | GRP-2021-RR1.63.3.2 | 2021 GRP - River Rouge | Install Main - Pine St (Genessee St & Richter St) | 790 | 09-01-21 A | 2021-11-02
RR1 10581 | GRP-2021-FR.58.2.2 | 2021 GRP - Field Recommendation | Install Main - Jefferson (21St & 15Th) | 1641 | 09-01-21 A | 2021-10-08
RR1 5117 | GRP-2021-RR1.41.1.2 | 2021 GRP - River Rouge | Install Main - Harris (4' SSPL E Anchor St & E Cicotte St) | 260 | 09-02-21 A | 09-03-21 A
RR1 60300 | GRP-2021-RR1.2.6.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (3' WEPL W Jefferson Ave & 0' WWPL W Jefferson Ave) | 115 | 09-02-21 A | 09-02-21 A
RR1 60220 | GRP-2021-RR1.2.5.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (Myrtle St & 12' SSPL Myrtle St) | 25 | 09-02-21 A | 09-02-21 A
NCDET - 24705 | NEWPROJ-6.15.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Sorrento (Puritan & Fenkell) | 2565 | 09-02-21 A | 09-15-21 A
WCDET1-4105 | GRP-2021-WCDet1.37.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Stoepel 2 (Buena Vista & Fullerton) | 1009 | 09-02-21 A | 09-08-21 A
WCDET1-4825 | GRP-2021-WCDet1.46.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Santa Rosa 1 (Ewald & Ewald) | 343 | 09-02-21 A | 09-02-21 A
NDET3-4250 | GRP-2021-ND3.73.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Harned St (2) (E Outer Dr & ANO 7 Mile Rd) | 2478 | 09-02-21 A | 09-08-21 A
RR1 10751 | GRP-2021-FR.49.1.2 | 2021 GRP - Field Recommendation | Install Main - St Anne (Fort & Jefferson) | 289 | 09-02-21 A | 09-03-21 A
RR1 5156 | GRP-2021-RR1.53.1.2 | 2021 GRP - River Rouge | Install Main - E James North (W Jefferson & 3' WEPL Burke St) 3" | 435 | 09-02-21 A | 09-14-21 A
RR1 60140 | GRP-2021-RR1.2.4.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (42' NNPL Myrtle St & Myrtle St) | 95 | 09-03-21 A | 2021-11-26
NCDET - 3560 | NEWPROJ-6.14.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Steel (Puritan & ANO Fenkell) | 2567 | 09-07-21 A | 09-17-21 A
SWDET2-18245 | PROJ-0951-SWDET2.34.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Homer (Lawndale & Springwells) | 1643 | 09-07-21 A | 2021-09-27
RR1 63170 | GRP-2021-RR1.103.1.2 | 2021 GRP - River Rouge | Install Main - E Glenwood Ave (W Jefferson Ave & Ironton Ave) | 1100 | 09-07-21 A | 09-15-21 A
RR1 55770 | GRP-2021-RR1.53.3.2 | 2021 GRP - River Rouge | Install Main - E James North (3' WEPL Burke St & 8' EWPL Harris St) 3" | 1300 | 09-07-21 A | 09-14-21 A
RR1 545 | GRP-2021-RR1.15.1.2 | 2021 GRP - River Rouge | Install Main - Cora (5' WEPL Haltiner St & 11' EWPL W Jefferson Ave) | 795 | 09-08-21 A | 09-09-21 A
WCDET1-5065 | GRP-2021-WCDet1.49.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Schoolcraft (Ewald & Ewald) | 580 | 09-08-21 A | 09-08-21 A
RR1 54410 | GRP-2021-RR1.16.2.2 | 2021 GRP - River Rouge | Install Main - Division (10' NSPL W Pleasant St & Linden St) | 525 | 09-09-21 A | 2021-09-28
WCDET1-12670 | GRP-2021-WCDet1.50.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Fullerton (Stoepel & AWO Livernois) | 132 | 09-09-21 A | 09-09-21 A
WCDET1-1945 | GRP-2021-WCDet1.9.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - AWO Livernois (Fullerton & Elmhurst) | 2816 | 09-09-21 A | 2021-10-04
WCDET1-3225 | GRP-2021-WCDet1.26.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Monica West 1 (Ewald & Ewald) | 223 | 09-09-21 A | 09-09-21 A
WCDET1-6720 | GRP-2021-WCDet1.14.4.2 | 2021 GRP - West Central Detroit 1 | Install Main - Prairie 1 (Ewald & Ewald) | 302 | 09-09-21 A | 09-09-21 A
RR1 5165 | GRP-2021-RR1.56.1.2 | 2021 GRP - River Rouge | Install Main - Richter (E Pleasant St & Leroy St) | 255 | 09-10-21 A | 2021-09-27
NDET3-7470 | GRP-2021-ND3.66.1.2 | 2021 GRP - North Detroit 3 | Install main Main - Charest St (2) (E Outer Dr & ANO 7 Mile Rd) | 2622 | 09-10-21 A | 09-15-21 A
NDET3-4240 | GRP-2021-ND3.71.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Gallagher St (2) (E Outer Dr & ANO 7 Mile Rd) | 2216 | 09-10-21 A | 09-14-21 A
WCDET1-6880 | GRP-2021-WCDet1.14.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Prairie 1 (Ewald Circle & Oakman Blvd) | 363 | 09-10-21 A | 09-15-21 A
Ypsi 3-9050 | PROJ-0951-YSP3.29.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Woodglen (Tyler & Cedarcliff) | 1875 | 09-10-21 A | 2021-10-14
SWDET2-6430 | PROJ-0951-SWDET2.61.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Senator 2 (Central & Green) | 931 | 09-10-21 A | 09-14-21 A
RR1 560 | GRP-2021-RR1.20.1.2 | 2021 GRP - River Rouge | Install Main - Emiline St (EOM & Haltiner) | 125 | 09-13-21 A | 09-13-21 A
WCDET1-3145 | GRP-2021-WCDet1.25.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman North 1 (Prairie & Santa Rosa) | 977 | 09-13-21 A | 09-14-21 A
WCDET1-7440 | GRP-2021-WCDet1.45.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd West 2 (Prairie & Davison) | 859 | 09-13-21 A | 2021-09-23
AA4 27148 | GRP-2021-AA4.8.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Liberty St (26' NNPL W Liberty St & 8' NSPL W Liberty St) | 95 | 09-13-21 A | 09-14-21 A
SWDET2-17605 | PROJ-0951-SWDET2.61.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Senator 2 (Green & Beard) | 373 | 09-13-21 A | 2021-09-22
WCDET1-8240 | GRP-2021-WCDet1.10.4.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd West (Stoepel & Stoepel) Crossing @Stoepel | 51 | 09-13-21 A | 09-13-21 A
RR1 54970 | GRP-2021-RR1.59.3.2 | 2021 GRP - River Rouge | Install Main - E Great Lakes St (4' WEPL Richter St & 4' WEPL AWO Goodell St) | 120 | 09-13-21 A | 2021-09-22
RR1 52170 | GRP-2021-RR1.6.3.2 | 2021 GRP - River Rouge | Install Main - AWO Goodell St (Maple St & E Great Lakes) | 1105 | 09-13-21 A | 2021-10-08
AA4 20527 | GRP-2021-AA4.14.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - 6th St (W Jefferson St & W Madison St) | 680 | 09-13-21 A | 2021-10-06
WCDET1-1555155 | GRP-2021-WCDet1.54.12.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald East 2 (Davison & Buena Vista) | 764 | 09-14-21 A | 09-14-21 A
Ypsi 3-11650 | PROJ-0951-YSP3.3.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - S Outerlane Dr (8' SSPL State St & EOM) | 500 | 09-14-21 A | 09-14-21 A
RR1 563 | GRP-2021-RR1.21.1.2 | 2021 GRP - River Rouge | Install Main - Fairmont (Nieman & Cora) | 865 | 09-15-21 A | 09-16-21 A
RR1 593 | GRP-2021-RR1.32.1.2 | 2021 GRP - River Rouge | Install Main - Summit St (2' NSPL Nieman St & 4' SNPL Cora St) | 860 | 09-15-21 A | 09-17-21 A
WCDET1-6320 | GRP-2021-WCDet1.53.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald Cr West 2 (Buena Vista & Davison) | 832 | 09-15-21 A | 2021-11-01
WCDET1-4025 | GRP-2021-WCDet1.36.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Monica West 2 (Buena Vista & Elmhurst) | 2888 | 09-15-21 A | 2021-10-08
WCDET1-2985 | GRP-2021-WCDet1.22.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Tuller (Schoolcraft & Schoolcratf) | 456 | 09-15-21 A | 2021-10-21
AA4 20525 | GRP-2021-AA4.12.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - 4th St (W Jefferson St & W Madison St) | 675 | 09-16-21 A | 2021-09-21
NDET3-7150 | GRP-2021-ND3.77.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Klinger St (2) (E Outer Dr& 7 Mile Rd) | 2125 | 09-16-21 A | 2021-10-05
WCDET1-4585 | GRP-2021-WCDet1.43.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - San Juan (Ewald & Ewald) | 360 | 09-16-21 A | 09-16-21 A
RR1 253 | GRP-2021-RR1.6.1.2 | 2021 GRP - River Rouge | Install Main - AWO Goodell St (Maple St & Coolidge Hwy) | 760 | 09-16-21 A | 2021-10-01
SWDET2-2110 | PROJ-0951-SWDET2.6.1.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor (Dix & Detroit City Limit) | 764 | 09-16-21 A | 2021-10-01
NCDET - 3490 | NEWPROJ-6.1.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Appoline (Puritan & Fenkell) | 2571 | 09-17-21 A | 2021-09-30
RR1 250 | GRP-2021-RR1.2.1.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (70' NNPL E Anchor St & 40' NNPL E James St) | 600 | 09-17-21 A | 2021-10-27
RR1 56490 | GRP-2021-RR1.44.4.2 | 2021 GRP - River Rouge | Install Main - E Pleasasnt North (8' WEPL Genesse St & Harris St) | 495 | 09-17-21 A | 2021-11-03
AA4 20540 | GRP-2021-AA4.28.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Jefferson St North (12' EWPL 5Th St & S 1St St) | 1320 | 09-17-21 A | 2021-09-24
Milestone 2 | GRP-2021-CDet2.23 | 2021 GRP - Central Detroit 2 | Elevate Main Finish Milestone | 0 |  | 09-20-21*
Milestone 1 | GRP-2021-CDet2.23 | 2021 GRP - Central Detroit 2 | Install Main Finish Milestone | 0 |  | 09-20-21*
Milestone 1 | GRP-2021-SCDet1.23 | 2021 GRP - South Central Detroit 1 | Install Main Finish Milestone | 0 |  | 09-20-21*
Milestone 2 | GRP-2021-SCDet1.23 | 2021 GRP - South Central Detroit 1 | Elevate Main Finish Milestone | 0 |  | 09-20-21*
Milestone 2 | GRP-2021-ED1.23 | 2021 GRP - East Detroit 1 | Elevate Main Finish Milestone | 0 |  | 09-20-21*
SWDET2-10935 | PROJ-0951-SWDET2.70.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Springwells 2 (Tie-In & W Vernor) | 46 | 2021-09-20 | 2021-09-20
SWDET2-11335 | PROJ-0951-SWDET2.14.3.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Central 2 (Dix & W Vernor) | 1823 | 09-20-21* | 2021-09-30
WCDET1-8160 | GRP-2021-WCDet1.10.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd South 1 (Stoepel & EOM) | 120 | 2021-09-20 | 2021-09-20
AA4 25588 | GRP-2021-AA4.5.2.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - S 1st St (12' NNPL W Davis Ave & 4' NSPL W Davis Ave) | 58 | 09-20-21* | 2021-09-20
RR1 54330 | GRP-2021-RR1.16.3.2 | 2021 GRP - River Rouge | Install Main - Division (W Cicotte St & 10' NSPL W Pleasant St) | 560 | 09-20-21* | 2021-09-22
RR1 54810 | GRP-2021-RR1.46.3.2 | 2021 GRP - River Rouge | Install Main - E Cicotte (Burke St & Harris St) | 1135 | 2021-09-20 | 2021-09-27
WCDET1-13170 | GRP-2021-WCDet1.31.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Elmhurst (AWO Livernois & American) | 1337 | 2021-09-20 | 2021-09-22
WCDET1-13330 | GRP-2021-WCDet1.31.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Elmhurst (American & AWO Livernois) | 89 | 2021-09-20 | 2021-09-20
Ypsi 3-11860 | PROJ-0951-YSP3.40.1.2 | 2021 GRP - Ypsilanti 3 | Elevate Main - S Pasadena Ave (Coolidge & State) | 795 | 2021-09-20 | 2021-09-23
SWDET2-10132 | GRP-2021-WCDet1.56.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Quincy 1 (EOM & John C Lodge Services Dr) | 380 | 2021-09-20 | 2021-09-20
RR1 5941 | GRP-2021-RR.7.1.2 | 2021 GRP - Risk Rank | Install Main - Mayfield (Chalmers & Kelly) | 3460 | 2021-09-20 | 2021-10-12
RR1 8681 | GRP-2021-RR.43.1.2 | 2021 GRP - Risk Rank | Install Main - Outer (Eaton & Kendall) | 2488 | 2021-09-20 | 2021-11-01
RR1 10291 | GRP-2021-FR.51.1.2 | 2021 GRP - Field Recommendation | Install Main - Fort (267' WWPL Anne & Anne) | 273 | 2021-09-20 | 2021-09-27
WCDET1-1555235 | GRP-2021-WCDet1.54.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald East 2 (Oakman & Buena Vista) | 2094 | 09-20-21* | 2021-09-24
Ypsi 3-12180 | PROJ-0951-YSP3.44.1.2 | 2021 GRP - Ypsilanti 3 | Elevate Main - Beverly St (Coolidge & State) | 1306 | 2021-09-20 | 2021-09-24
Ypsi 3-12310 | PROJ-0951-YSP3.45.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Gill (456' SSPL Service Dr & US-12) | 155 | 2021-09-20 | 2021-09-20
CDET1 7000475 | PROJ-0951-CDET1-2.16 | 2020 GRP - Carry Over - Central Detroit 1 | Install Main Finish Milestone | 0 |  | 09-20-21*
GP5-701100 | PROJ-0951-GP 5 -3.23 | 2020 GRP - Carry Over - GP 5 | Install Main Finish Milestone | 0 |  | 09-20-21*
Milestone 2 | PROJ-0951-WDET9-4.53 | 2020 GRP - Carry Over - West Detroit 9 | Elevate Main Finish Milestone | 0 |  | 09-20-21*
Milestone 1 | PROJ-0951-NDET2-2.54 | 2020 GRP - Carry Over - North Detroit 2 | Install Main Finish Milestone | 0 |  | 09-20-21*
WCDET1-1556095 | GRP-2021-WCDet1.28.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 5 (Fullerton & Elmhurst) optional | 1883 | 09-20-21* | 2021-09-20
Muni12070 | PROJ-0951-MUN-2.32.3.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (24' EWPL Archdale St & 4' WEPL Archdale St) | 40 | 09-20-21* | 2021-09-20
Ypsi 3-12460 | PROJ-0951-YSP3.10.3.2 | 2021 GRP - Ypsilanti 3 | Install Main - Calder (94 Service Drive) | 30 | 2021-09-20 | 2021-09-20
Milestone 2 | Proj-WDET3PLH | West Detroit 3 - Pull Ahead 2021 | Elevate Main Finish Milestone | 0 |  | 09-20-21*
GP5-701080 | PROJ-0951-GP 5 -3.23 | 2020 GRP - Carry Over - GP 5 | Elevate Main Finish Milestone | 0 |  | 09-20-21*
RR1 60380 | GRP-2021-RR1.2.7.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (56' NNPL Coolidge Hwy & 4' SNPL Coolidge Hwy) | 85 | 2021-09-21 | 2021-09-21
WCDET1-1556175 | GRP-2021-WCDet1.28.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 5 (Elmhurst & Burlingame) optional | 932 | 2021-09-21 | 2021-09-22
Muni11590 | PROJ-0951-MUN-2.26.2.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Archdale St & Clayburn St) | 850 | 2021-09-22 | 2021-09-27
WCDET1-3625 | GRP-2021-WCDet1.31.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Elmhurst (Bryden & American) | 243 | 2021-09-22 | 2021-09-22
Milestone 2 | PROJ-0951-NDET2-2.54 | 2020 GRP - Carry Over - North Detroit 2 | Elevate Main Finish Milestone | 0 |  | 09-22-21*
WCDET1-4265 | GRP-2021-WCDet1.39.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Bryden (Utica & Elmhurst) | 365 | 2021-09-23 | 2021-09-23
RR1 52490 | GRP-2021-RR1.25.1.2 | 2021 GRP - River Rouge | Install Main - Burke 2 (Louis St & Nieman St) | 550 | 2021-09-23 | 2021-09-28
WCDET1-14830 | GRP-2021-WCDet1.33.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Utica (Bryden & American) | 240 | 2021-09-23 | 2021-09-23
Ypsi 3-3340 | PROJ-0951-YSP3.6.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Coolidge (McCartney & Pasadena) | 305 | 2021-09-24 | 2021-09-24
RR1 548 | GRP-2021-RR1.16.1.2 | 2021 GRP - River Rouge | Install Main - Division (Victoria St & W Cicotte St) | 530 | 2021-09-24 | 2021-09-28
RR1 5180 | GRP-2021-RR1.61.1.2 | 2021 GRP - River Rouge | Install Main - Maple St (Richter & Goodell) | 235 | 2021-09-24 | 2021-09-27
SWDET2-6510 | PROJ-0951-SWDET2.62.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Stratton 1 (Beard & Waterman) | 724 | 2021-09-24 | 2021-09-28
WCDET1-7200 | GRP-2021-WCDet1.35.3.4 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd East 2 (Prairie & Davison) | 912 | 2021-09-24 | 2021-09-27
WCDET1-10020 | GRP-2021-WCDet1.37.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Stoepel 2 (Fullerton & Elmhurst) | 1878 | 2021-09-24 | 2021-09-29
NCDET - 3495 | NEWPROJ-6.3.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Birwood (Pilgrim & ANO Fenkell) | 1802 | 2021-09-27 | 2021-10-01
WCDET1-7680 | GRP-2021-WCDet1.15.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd 3 (American & American) | 185 | 2021-09-27 | 2021-09-27
Muni12230 | PROJ-0951-MUN-2.52.2.2 | 2021 GRP - Municipality | Install Main - Longacre St (2) (ANO W Warren Ave & W Warren Ave) | 115 | 09-27-21* | 2021-09-27
WCDET1-11200 | GRP-2021-WCDet1.29.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - American (Oakman & Tuxedo) | 1070 | 2021-09-27 | 2021-10-04
WCDET1-1556455 | GRP-2021-WCDet1.29.2.2 | 2021 GRP - West Central Detroit 1 | Elevate Main - American (Tuxedo & Burlingame) | 791 | 2021-09-27 | 2021-09-30
WCDET1-7920 | GRP-2021-WCDet1.10.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd South 1 (Monica & Santa Rosa) to Prairie | 540 | 2021-09-28 | 2021-09-29
RR1 551 | GRP-2021-RR.17.1.2 | 2021 GRP - Risk Rank | Install Main - Corbett 1 (Annsbury & Coplin) | 2445 | 09-28-21* | 2021-10-15
RR1 9241 | GRP-2021-FR.50.1.2 | 2021 GRP - Field Recommendation | Install Main - Church (Woodward & John) | 770 | 09-28-21* | 2021-10-05
RR1 5147 | GRP-2021-RR1.51.1.2 | 2021 GRP - River Rouge | Install Main - Brownlee (E Anchor St & E Cicotte St) | 255 | 2021-09-29 | 2021-09-30
AA4 20541 | GRP-2021-AA4.29.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Madison St 2 (S 7Th St & S 1St St) | 2058 | 2021-09-29 | 2021-10-09
SWDET2-3310 | PROJ-0951-SWDET2.21.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Bank (Springwells & EOM) | 135 | 2021-09-29 | 2021-09-30
AA4 26588 | GRP-2021-AA4.9.4.2 | 2021 GRP - Ann Arbor 4 | Install Main - S Main (62' NNPL E Hoover Ave & E Hoover Ave) | 900 | 09-29-21* | 2021-10-02
Muni11670 | PROJ-0951-MUN-2.26.3.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Clayburn St & Woodmont Ave) | 1305 | 2021-09-29 | 2021-10-05
Muni12310 | PROJ-0951-MUN-2.47.2.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (201' WWPL Longacre St & 13' EEPL Clayburn St) | 840 | 2021-09-29 | 2021-10-01
Ypsi 3-12630 | PROJ-0951-YSP3.42.3.2 | 2021 GRP - Ypsilanti 3 | Elevate Main - State (McCartney & Beverly) | 432 | 2021-09-29 | 2021-09-30
WCDET1-8080 | GRP-2021-WCDet1.10.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd South 1 (Santa Rosa & Stoepel) | 327 | 2021-09-29 | 2021-09-30
NCDET - 3540 | NEWPROJ-6.10.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Meyers (Puritan & Keeler) | 1984 | 09-30-21* | 2021-10-08
RR1 596 | GRP-2021-RR1.33.1.2 | 2021 GRP - River Rouge | Install Main - Victoria St (Division & W Jefferson) | 525 | 2021-09-30 | 2021-10-04
AA4 20384 | GRP-2021-AA4.10.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - 2nd St (W Jefferson St & W Madison St) | 735 | 2021-09-30 | 2021-10-01
SWDET2-6590 | PROJ-0951-SWDET2.63.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Waterman 1 (W Vernor & EOM) | 726 | 2021-09-30 | 2021-10-04
WCDET1-12830 | GRP-2021-WCDet1.50.4.2 | 2021 GRP - West Central Detroit 1 | Install Main - Fullerton (AWO Livernois & Livernois) Optional | 80 | 09-30-21* | 2021-09-30
RR1 54490 | GRP-2021-RR1.16.4.2 | 2021 GRP - River Rouge | Install Main - Division (Linden St & Coolidge Hwy) | 675 | 2021-09-30 | 2021-10-01
RR1 11671 | GRP-2021-FR.51.1.2 | 2021 GRP - Field Recommendation | Install Main - Fort (EOM 45' WWPL St Anne & St Anne) | 48 | 2021-09-30 | 2021-10-06
Muni12150 | PROJ-0951-MUN-2.51.2.2 | 2021 GRP - Municipality | Install Main - Clayburn St (1) (ANO W Warren Ave & W Warren Ave) | 110 | 09-30-21* | 2021-09-30
WCDET1-9140 | GRP-2021-WCDet1.46.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Santa Rosa 1 (Oakman & Davison) | 997 | 2021-09-30 | 2021-10-04
RR1 5105 | GRP-2021-RR1.36.1.2 | 2021 GRP - River Rouge | Install Main - W Great Lakes (Burke & W Jefferson) | 420 | 2021-10-01 | 2021-10-05
SWDET2-8805 | PROJ-0951-SWDET2.16.2.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Dix 4 (At Central) | 45 | 2021-10-01 | 2021-10-01
WCDET1-13520 | GRP-2021-WCDet1.41.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Tuxedo (American & EOM) Optional | 85 | 10-01-21* | 2021-10-05
SWDET2-1032 | GRP-2021-WCDet1.56.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Quincy 1 (Hughes & Fenkell) | 1020 | 10-01-21* | 2021-10-21
AA4 27958 | GRP-2021-AA4.13.4.2 | 2021 GRP - Ann Arbor 4 | Install Main - 5th St (W Jefferson St & Tie-in) | 64 | 2021-10-01 | 2021-10-01
NCDET - 3505 | NEWPROJ-6.5.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Griggs 2 (James couzens & Fenkell) | 1578 | 2021-10-04 | 2021-10-07
SWDET2-1710 | PROJ-0951-SWDET2.4.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - ENO Pitt (Central & EOM) | 5 | 2021-10-04 | 2021-10-04
SWDET2-3710 | PROJ-0951-SWDET2.27.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Mint (Springwells & EOM) | 109 | 2021-10-04 | 2021-10-05
SWDET2-8165 | PROJ-0951-SWDET2.1.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 1 (Railroad & W Vernor) | 1528 | 2021-10-04 | 2021-10-26
WCDET1-9300 | GRP-2021-WCDet1.46.2.2 | 2021 GRP - West Central Detroit 1 | Elevate Main - Santa Rosa 1 (Davison & Davison) Mis | 110 | 10-04-21* | 2021-10-04
RR1 58280 | GRP-2021-RR1.28.3.2 | 2021 GRP - River Rouge | Install Main - Linden (4' EWPL Division St & 5' WEPL Division St) | 40 | 2021-10-04 | 2021-10-04
WCDET1-8660 | GRP-2021-WCDet1.26.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Monica West 1 (Oakman & Buena Vista) | 1825 | 2021-10-04 | 2021-10-06
WCDET1-1556505 | GRP-2021-WCDet1.11.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Burlingame (AWO Livernois & Livernois) | 55 | 2021-10-04 | 2021-10-05
Milestone 2 | PROJ-0951-YSP3.43 | 2021 GRP - Ypsilanti 3 | Elevate Main Finish Milestone | 0 |  | 10-04-21*
AA4 25258 | GRP-2021-AA4.45.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - Redeemer Ave (Pauline Blvd & Hewett Rd) | 415 | 10-05-21* | 2021-10-06
RR1 54650 | GRP-2021-RR1.47.3.2 | 2021 GRP - River Rouge | Install Main - E Anchor (Burke St & Brownlee St) | 655 | 2021-10-05 | 2021-10-07
SWDET2-18405 | PROJ-0951-SWDET2.67.3.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Honorah (EOM & Dix) | 648 | 2021-10-05 | 2021-10-06
NDET3-6945 | GRP-2021-ND3.83.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Revere Ave (2) (E Outer Dr & 7 Mile Rd) | 2528 | 2021-10-05 | 2021-10-08
WCDET1-3465 | GRP-2021-WCDet1.29.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - American (Burlingame & ANO Grand River) | 791 | 2021-10-05 | 2021-10-08
RR1 581 | GRP-2021-RR1.28.1.2 | 2021 GRP - River Rouge | Install Main - Linden (4' WEPL Division St & 43' WWPL W Jefferson Ave) | 540 | 2021-10-06 | 2021-10-06
SWDET2-5230 | PROJ-0951-SWDET2.46.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Cahalan 2 (EOM & Central) | 401 | 2021-10-06 | 2021-10-07
SWDET2-5710 | PROJ-0951-SWDET2.52.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Navy 1 (Lawndale & Springwells) | 1606 | 2021-10-06 | 2021-10-15
WCDET1-8500 | GRP-2021-WCDet1.45.4.2 | 2021 GRP - West Central Detroit 1 | Elevate Main - Oakman Blvd West 2 (Davison & Davison) | 60 | 10-06-21* | 2021-10-06
NDET3-6795 | GRP-2021-ND3.79.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Mitchell St (2) (E Outer Dr & ANO 7 Mile Rd) | 2510 | 10-06-21* | 2021-10-14
Muni12390 | PROJ-0951-MUN-2.47.3.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (150' WWPL Longacre St & 215' Longacre St) | 430 | 2021-10-06 | 2021-10-07
WCDET1-1050 | GRP-2021-WCDet1.4.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Turner (Schoolcraft & Davison) | 821 | 2021-10-06 | 2021-10-07
RR1 584 | GRP-2021-RR1.29.1.2 | 2021 GRP - River Rouge | Install Main - Louis (Burke St & W Jefferson Ave) | 325 | 2021-10-07 | 2021-10-08
SWDET2-2590 | PROJ-0951-SWDET2.12.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - W Vernor 4 (Central & EOM) | 2355 | 2021-10-07 | 2021-10-20
Muni11750 | PROJ-0951-MUN-2.26.4.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Asbury Park & St Marys St) | 540 | 2021-10-07 | 2021-10-12
WCDET1-13790 | GRP-2021-WCDet1.11.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Burlingame (American & American) | 79 | 2021-10-07 | 2021-10-08
RR1 599 | GRP-2021-RR1.34.1.2 | 2021 GRP - River Rouge | Install Main - W Anchor St (Division St & 7' WWPL W Jefferson Ave) | 520 | 2021-10-08 | 2021-10-12
WCDET1-2745 | GRP-2021-WCDet1.19.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Davison North 1 (Turner & Ewald) | 574 | 2021-10-08 | 2021-10-11
RR1 5159 | GRP-2021-RR1.54.1.2 | 2021 GRP - River Rouge | Install Main - Leroy (W Jefferson Ave & Burke St) | 365 | 10-08-21* | 2021-10-08
SWDET2-10775 | PROJ-0951-SWDET2.70.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Springwells 2 (At Dix) | 5 | 2021-10-08 | 2021-10-08
RR1 61940 | GRP-2021-RR1.39.4.2 | 2021 GRP - River Rouge | Install Main - W Pleasasnt (120' WWPL Division St & Division St) | 130 | 2021-10-08 | 2021-10-11
WCDET1-4425 | GRP-2021-WCDet1.41.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Tuxedo (American & AWO Livernois) | 1341 | 2021-10-08 | 2021-10-13
NCDET - 3535 | NEWPROJ-6.10.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Meyers (Keeler & Fenkell) | 574 | 2021-10-11 | 2021-10-12
RR1 5144 | GRP-2021-RR1.49.1.2 | 2021 GRP - River Rouge | Install Main - Byron (E Pleasant St & Leroy St) | 335 | 10-11-21* | 2021-10-11
AA4 20537 | GRP-2021-AA4.25.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Tuner Park Ct (W Madison St & EOM) | 560 | 2021-10-11 | 2021-10-12
AA4 20781 | GRP-2021-AA4.38.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Hewett Rd (Russett Rd & Russell Rd) | 970 | 2021-10-11 | 2021-10-14
RR1 54010 | GRP-2021-RR1.58.4.2 | 2021 GRP - River Rouge | Install Main - Coolidge Hwy 2 (Goodell St & AEO Goodell St) | 115 | 2021-10-11 | 2021-10-18
RR1 55130 | GRP-2021-RR1.45.1.2 | 2021 GRP - River Rouge | Install Main - E Henry (Burke St & 85' WWPL Byron St) | 480 | 2021-10-11 | 2021-10-11
SWDET2-15245 | PROJ-0951-SWDET2.46.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Cahalan 2 (Central & Green) | 888 | 2021-10-11 | 2021-10-14
NDET3-7345 | GRP-2021-ND3.81.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Norwood St (2) (E Outer Dr & 7 Mile Rd) | 2364 | 2021-10-11 | 2021-10-14
RR1 9321 | GRP-2021-FR.51.1.2 | 2021 GRP - Field Recommendation | Install Main - Fort (EOM 78' WWPL Anne & 15Th) | 1152 | 2021-10-11 | 2021-10-29
Muni10630 | PROJ-0951-MUN-2.38.1.2 | 2021 GRP - Municipality | Install Main - Longacre St (3) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-10-11 | 2021-10-11
WCDET1-2105 | GRP-2021-WCDet1.11.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Burlingame (American & Livernois) | 1314 | 2021-10-11 | 2021-10-18
WCDET1-3785 | GRP-2021-WCDet1.22.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Tuller (Schoolcraft & Davision) | 821 | 2021-10-11 | 2021-10-12
WCDET1-14850 | GRP-2021-WCDet1.34.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - ANO Grand River (American & Prairie) | 328 | 2021-10-11 | 2021-10-12
AA4 26508 | GRP-2021-AA4.9.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - S Main (4' EWPL S Main St & 3' WEPL S Main St) | 80 | 2021-10-12 | 2021-10-14
RR1 61860 | GRP-2021-RR1.39.2.2 | 2021 GRP - River Rouge | Install Main - W Pleasasnt (107' WWPL Dwight St & 1' WWPL Charles St) | 385 | 2021-10-12 | 2021-10-14
RR1 11231 | GRP-2021-FR.63.1.2 | 2021 GRP - Field Recommendation | Install Main - Easement (Church & Candler) | 326 | 2021-10-12 | 2021-10-18
WCDET1-1556525 | GRP-2021-WCDet1.14.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Prairie 3 (Grand River & Grand River) | 169 | 2021-10-12 | 2021-10-12
WCDET1-11260 | GRP-2021-WCDet1.49.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Schoolcraft (Ewald & Ewald) | 73 | 2021-10-13 | 2021-10-13
RR1 11181 | GRP-2021-FR.55.1.2 | 2021 GRP - Field Recommendation | Install Main - 18th (9'WEPL 18th & 3' WWPL 18th) | 18 | 2021-10-13 | 2021-10-14
Muni10950 | PROJ-0951-MUN-2.42.1.2 | 2021 GRP - Municipality | Install Main - Rutland St (1) (ANO W Warren Ave & W Warren Ave) | 110 | 2021-10-13 | 2021-10-13
WCDET1-2265 | GRP-2021-WCDet1.53.54.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald Cr West 2 (Schoolcraft & Davison) | 819 | 2021-10-13 | 2021-10-15
WCDET1-13680 | GRP-2021-WCDet1.51.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Webb (American & AWO Livernois) | 1342 | 2021-10-13 | 2021-10-18
WCDET1-14400 | GRP-2021-WCDet1.58.59.2 | 2021 GRP - West Central Detroit 1 | Install Main - Grand River Ave N (Stoepel & EOM) livernios | 387 | 2021-10-13 | 2021-10-15
Ypsi 3-7810 | PROJ-0951-YSP3.24.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Ponderosa (Woodglen & EOM) | 610 | 10-14-21* | 2021-10-15
Ypsi 3-9300 | PROJ-0951-YSP3.30.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Sunnyglen (Glengrove & Nash) | 740 | 10-14-21* | 2021-10-15
Muni11990 | PROJ-0951-MUN-2.32.2.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (Archdale St & St Marys St) | 2950 | 2021-10-14 | 2021-11-02
RR1 5153 | GRP-2021-RR1.40.1.2 | 2021 GRP - River Rouge | Install Main - W James (EOM @ 40' EEPL Dwight St & 4' EWPL Division St) | 385 | 2021-10-15 | 2021-10-18
RR1 5188 | GRP-2021-RR1.64.1.2 | 2021 GRP - River Rouge | Install Main - Walnut St (W Jefferson Ave & Genessee St) | 920 | 10-15-21* | 2021-10-18
AA4 25928 | GRP-2021-AA4.5.5.2 | 2021 GRP - Ann Arbor 4 | Install Main - S 1st St (Nob Hill Pl & 12' NNPL W Davis Ave) | 255 | 2021-10-15 | 2021-10-15
SWDET2-19325 | PROJ-0951-SWDET2.42.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Logan 1 (At Lawndale) | 5 | 10-15-21* | 2021-10-15
NDET3-7650 | GRP-2021-ND3.7.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Yonka (2) (7 Mile Rd & E Outer Dr) | 2550 | 2021-10-15 | 2021-10-20
Muni12470 | PROJ-0951-MUN-2.47.4.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' WEPL Ruthland St & 158' EEPL Ruthland St) | 165 | 2021-10-15 | 2021-10-15
WCDET1-14080 | GRP-2021-WCDet1.58.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Grand River Ave N (Monica & Stoepel) | 314 | 2021-10-15 | 2021-10-18
WCDET1-1555075 | GRP-2021-WCDet1.54.55.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald East 2 (Schoolcraft & EOM) | 641 | 2021-10-15 | 2021-10-18
AA4 20383 | GRP-2021-AA4.9.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - S Main (Hill St & W Hoover St) | 779 | 2021-10-16 | 2021-10-21
AA4 20544 | GRP-2021-AA4.34.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - 3rd St (W Jefferson St & W Madison St) | 675 | 2021-10-16 | 2021-10-18
NCDET - 3515 | NEWPROJ-6.8.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Manor (Puritan & Fenkell) | 2477 | 2021-10-18 | 2021-10-28
AA4 27308 | GRP-2021-AA4.29.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Madison St 2 (S 1St St & 88' EEPL S Main St) | 495 | 2021-10-18 | 2021-10-19
SWDET2-24285 | PROJ-0951-SWDET2.74.5.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Lawndale 2 (Woodmere & W Vernor) | 1079 | 10-18-21* | 2021-10-25
RR1 9481 | GRP-2021-FR.53.1.2 | 2021 GRP - Field Recommendation | Install Main - 15th (Fort & Jefferson) | 262 | 2021-10-18 | 2021-10-21
WCDET1-2665 | GRP-2021-WCDet1.18.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 6 (Burlingame & Grand River) | 1684 | 2021-10-18 | 2021-10-21
WCDET1-4505 | GRP-2021-WCDet1.42.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Davison South 1 (Stoepel & Livernois) | 239 | 2021-10-18 | 2021-10-18
WCDET1-14240 | GRP-2021-WCDet1.58.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Grand River Ave N (Burnette & Prairie) | 260 | 2021-10-18 | 2021-10-19
RR1 551 | GRP-2021-RR1.17.1.2 | 2021 GRP - River Rouge | Install Main - Dwight (Linden & W Pleasant) | 495 | 2021-10-19 | 2021-10-20
SWDET2-6270 | PROJ-0951-SWDET2.59.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Navy 2 (Springwells & Central) | 905 | 2021-10-19 | 2021-10-22
WCDET1-7280 | GRP-2021-WCDet1.35.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd East 2 (Davison & Buena Vista) | 922 | 10-19-21* | 2021-10-21
WCDET1-12980 | GRP-2021-WCDet1.19.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Davison North 1 (Stoepel & Livernois) | 229 | 2021-10-19 | 2021-10-19
WCDET1-13750 | GRP-2021-WCDet1.51.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Webb (American & EOM) Optional | 85 | 10-19-21* | 2021-10-19
SWDET2-15325 | PROJ-0951-SWDET2.46.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Cahalan 2 (Green & Beard) | 733 | 2021-10-19 | 2021-10-21
SWDET2-20895 | PROJ-0951-SWDET2.45.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Mullane (At Homer) | 53 | 2021-10-19 | 2021-10-19
RR1 5461 | GRP-2021-RR.1.1.2 | 2021 GRP - Risk Rank | Install Main - Corbett 2 (Coplin & Chalmers) | 1605 | 2021-10-19 | 2021-10-29
WCDET1-1555325 | GRP-2021-WCDet1.55.10.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald Cr South 1 (Schoolcraft & Prairie) | 506 | 2021-10-19 | 2021-10-19
Muni11030 | PROJ-0951-MUN-2.43.1.2 | 2021 GRP - Municipality | Install Main - Rutland St (2) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-10-19 | 2021-10-19
WCDET1-2585 | GRP-2021-WCDet1.17.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois 4 (Davison & Davison) | 339 | 2021-10-19 | 2021-10-20
AA4 20534 | GRP-2021-AA4.21.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Nob Hill Pl (S 1st St & Nob Hill Ct) | 160 | 2021-10-19 | 2021-10-20
WCDET1-13920 | GRP-2021-WCDet1.58.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Grand River Ave N (Burnette & Prairie) | 281 | 2021-10-19 | 2021-10-20
RR1 5177 | GRP-2021-RR1.60.1.2 | 2021 GRP - River Rouge | Install Main - Elm St (W Jefferson & Genesse St) | 1020 | 2021-10-20 | 2021-10-25
RR1 59810 | GRP-2021-RR1.40.3.2 | 2021 GRP - River Rouge | Install Main - W James (4' EWPL Division St & 0' WEPL W Jefferson Ave) | 570 | 2021-10-20 | 2021-10-21
WCDET1-15250 | GRP-2021-WCDet1.59.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Bourke (East) (Burnette & EOM Burnette) Optional | 181 | 10-20-21* | 2021-10-20
WCDET1-1555405 | GRP-2021-WCDet1.55.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald Cr South 1 (Monica & Prairie) | 642 | 2021-10-20 | 2021-10-20
Muni9510 | PROJ-0951-MUN-2.24.1.2 | 2021 GRP - Municipality | Install Main - Abington Ave (1) (ANO W Warren Ave & W Warren Ave) | 100 | 2021-10-20 | 2021-10-20
WCDET1-1545 | GRP-2021-WCDet1.3.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Burnette (Grand River & I-96 Service Rd) | 336 | 2021-10-20 | 2021-10-21
WCDET1-1555505 | GRP-2021-WCDet1.38.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Livernois - EAS (Livernois & Livernois) | 567 | 2021-10-20 | 2021-10-21
AA4 20789 | GRP-2021-AA4.46.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Russell Rd (Russett Rd & Hewett Dr) | 525 | 2021-10-21 | 2021-10-22
SWDET2-9945 | PROJ-0951-SWDET2.12.5.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor 4 (Tie-in & Dix) | 84 | 2021-10-21 | 2021-10-22
RR1 62020 | GRP-2021-RR1.39.5.2 | 2021 GRP - River Rouge | Install Main - W Pleasasnt (Division St & 117' WWPL W Jefferson Ave) | 455 | 2021-10-21 | 2021-10-25
SWDET2-19485 | PROJ-0951-SWDET2.42.2.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Logan 1 (Lawndale & Mullane) | 922 | 2021-10-21 | 2021-10-27
NDET3-7460 | GRP-2021-ND3.85.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Wexford (2) (E Outer Dr & 7 Mile Rd) | 2371 | 2021-10-21 | 2021-10-26
Muni12550 | PROJ-0951-MUN-2.47.5.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (189' WWPL Abington Ave & Abington Ave) | 195 | 2021-10-21 | 2021-10-21
WCDET1-2505 | GRP-2021-WCDet1.46.24.2 | 2021 GRP - West Central Detroit 1 | Install Main - Santa Rosa 1 (Davison & Buena Vista) | 870 | 2021-10-21 | 2021-10-26
WCDET1-2905 | GRP-2021-WCDet1.21.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Annland (Stoepel & Livernois) | 381 | 2021-10-21 | 2021-10-22
WCDET1-1555955 | GRP-2021-WCDet1.63.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - ASO Grand River Ave (Burnette & Jeffries) | 181 | 2021-10-21 | 2021-10-22
WCDET1-1556415 | GRP-2021-WCDet1.44.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Stearns (Livernois & LIvernois) | 24 | 2021-10-21 | 2021-10-21
AA4 22488 | GRP-2021-AA4.56.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - EWO Main St (170' WWPL S Main St & S Main St) | 180 | 2021-10-22 | 2021-10-25
SWDET2-9685 | GRP-2021-WCDet1.56.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Quincy 1 (Huges & John C Lodge Service) | 189 | 10-22-21* | 2021-10-22
WCDET1-15020 | GRP-2021-WCDet1.57.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Burlingame (Grand River & Jeffries Fawy) | 336 | 2021-10-22 | 2021-10-22
RR1 10311 | GRP-2021-FR.51.1.2 | 2021 GRP - Field Recommendation | Install Main - Fort (6' EWPL 15Th & 137' EEPL 15Th) | 220 | 2021-10-22 | 2021-11-01
WCDET1-3705 | GRP-2021-WCDet1.32.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Georgeland (Stoepel & Livernois) | 200 | 2021-10-22 | 2021-10-22
AA4 20533 | GRP-2021-AA4.20.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Nob Hill Ct (Nob Hill Pl & Nob Hill Pl) | 235 | 2021-10-22 | 2021-10-26
WCDET1-1556055 | GRP-2021-WCDet1.63.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - ASO Grand River Ave (Burnette & Burnette) | 155 | 2021-10-22 | 2021-10-25
WCDET1-1385 | GRP-2021-WCDet1.1.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Barr (Stoepel & Livernois) | 382 | 2021-10-25 | 2021-10-26
WCDET1-2425 | GRP-2021-WCDet1.15.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd 3 (Jeffries & American) | 324 | 2021-10-25 | 2021-10-25
SWDET2-5550 | PROJ-0951-SWDET2.50.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Lane 2 (Evans & Central) | 590 | 2021-10-25 | 2021-10-27
AA4 21198 | GRP-2021-AA4.34.3.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - 3rd St (W Madison St & W Mosley St) | 583 | 2021-10-25 | 2021-10-28
WCDET1-15110 | GRP-2021-WCDet1.2.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Grand River Ave S (Prairie & Monica) Eleminate | 0 | 2021-10-25 | 2021-10-26
WCDET1-1555735 | GRP-2021-WCDet1.62.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - The Lodge (Quincy & Livernois) | 572 | 2021-10-25 | 2021-10-26
Muni12630 | PROJ-0951-MUN-2.47.6.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (114' WWPL Abington Ave & 160' EEPL Abington Ave) | 335 | 2021-10-25 | 2021-10-25
WCDET1-7760 | GRP-2021-WCDet1.15.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd 3 (American & Prairie) | 376 | 2021-10-25 | 2021-10-25
WCDET1-8980 | GRP-2021-WCDet1.12.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Monica East 3 (Grand River & EOM) | 198 | 2021-10-25 | 2021-10-26
Ypsi 3-8060 | PROJ-0951-YSP3.25.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Pineridge (Woodglen & EOM) | 610 | 2021-10-26 | 2021-10-28
SWDET2-11665 | PROJ-0951-SWDET2.74.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 2 (Woodmere & Tie-in) | 28 | 2021-10-26 | 2021-10-26
WCDET1-7040 | GRP-2021-WCDet1.14.5.2 | 2021 GRP - West Central Detroit 1 | Install Main - Prairie 2 (Cortland & Elmhurst) | 1060 | 2021-10-26 | 2021-10-29
AA4 26098 | GRP-2021-AA4.5.6.2 | 2021 GRP - Ann Arbor 4 | Install Main - S 1st St (48' NNPL W Jefferson St & W Madison St) | 840 | 2021-10-26 | 2021-10-30
RR1 62100 | GRP-2021-RR1.39.6.2 | 2021 GRP - River Rouge | Install Main - W Pleasasnt (11' SNPL W Pleasant St & 4' NSPL W Pleasant St) | 35 | 2021-10-26 | 2021-10-26
SWDET2-21075 | PROJ-0951-SWDET2.59.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Navy 2 (Central & Green) | 933 | 2021-10-26 | 2021-10-29
WCDET1-2345 | GRP-2021-WCDet1.14.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Prairie 3 (ANO Grand River & Burlingame) | 900 | 2021-10-26 | 2021-10-28
WCDET1-7520 | GRP-2021-WCDet1.45.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd West 2 (Davison & Buena Vista) | 827 | 2021-10-26 | 2021-10-28
WCDET1-15130 | GRP-2021-WCDet1.2.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Grand River Ave S (Monica & Monica) Eleminate | 0 | 2021-10-26 | 2021-10-27
SWDET2-9785 | PROJ-0951-SWDET2.12.4.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor 4 (Tee to Tee at Waterman) | 31 | 2021-10-27 | 2021-10-27
RR1 62180 | GRP-2021-RR1.39.7.2 | 2021 GRP - River Rouge | Install Main - W Pleasasnt (117' WWPL W Jefferson Ave & W Jefferson Ave) | 125 | 2021-10-27 | 2021-10-28
SWDET2-24365 | PROJ-0951-SWDET2.74.4.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 2 (Tie-In & W Vernor) | 40 | 2021-10-27 | 2021-10-27
NDET3-7295 | GRP-2021-ND3.64.1.2 | 2021 GRP - North Detroit 3 | Elevate Main - Binder St (2) (E Outer Dr & ANO 7 Mile Rd) | 2570 | 2021-10-27 | 2021-11-01
Muni9590 | PROJ-0951-MUN-2.25.1.2 | 2021 GRP - Municipality | Install Main - Abington Ave (2) (W Warren Ave & ASO W Warren Ave) | 110 | 2021-10-27 | 2021-10-27
WCDET1-4905 | GRP-2021-WCDet1.47.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Stoepel 3 (Burlingame & Grand River) | 1463 | 2021-10-27 | 2021-11-02
WCDET1-15410 | GRP-2021-WCDet1.60.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Bourke (West) (Burnette & EOM Burnette) | 155 | 2021-10-27 | 2021-10-27
WCDET1-1555795 | GRP-2021-WCDet1.8.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Dexter (Pasadena & Pasadena) | 94 | 2021-10-27 | 2021-10-27
Ypsi 3-9550 | PROJ-0951-YSP3.31.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Glengrove (State & Sunnyglen) | 575 | 2021-10-28 | 2021-10-29
SWDET2-8325 | PROJ-0951-SWDET2.1.5.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 1 (At Ferney) | 103 | 2021-10-28 | 2021-10-29
AA4 24768 | GRP-2021-AA4.58.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Nob Hill Apts (EOM & S Main St) | 255 | 2021-10-28 | 2021-10-28
RR1 56570 | GRP-2021-RR1.44.5.2 | 2021 GRP - River Rouge | Install Main - E Pleasasnt South (Harris St & Richter St) | 330 | 10-28-21* | 2021-10-29
SWDET2-15725 | PROJ-0951-SWDET2.66.2.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Casper (Belle & Pitt) | 975 | 2021-10-28 | 2021-11-03
SWDET2-20655 | PROJ-0951-SWDET2.45.3.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Mullane (Logan & Longworth) | 335 | 2021-10-28 | 2021-10-28
WCDET1-14720 | GRP-2021-WCDet1.8.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Dexter West (Pasadena & Pasadena) | 94 | 2021-10-28 | 2021-10-29
NCDET - 3545 | NEWPROJ-6.11.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Monte Vista (Puritan & Fenkell) | 2619 | 2021-10-29 | 2021-11-09
RR1 5129 | GRP-2021-RR1.47.1.2 | 2021 GRP - River Rouge | Install Main - E Anchor (W Jefferson Ave & Burke St) | 440 | 2021-10-29 | 2021-11-01
SWDET2-7630 | PROJ-0951-SWDET2.75.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Norman (Woodmere & ANO W Vernor) | 1811 | 10-29-21* | 2021-11-08
SWDET2-10585 | PROJ-0951-SWDET2.9.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Springwells 1 (W Vernor & ASO Vernor) | 127 | 2021-10-29 | 2021-11-01
AA4 21028 | GRP-2021-AA4.10.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - 2nd St (W Madison St & W Mosely St) | 405 | 2021-10-29 | 2021-10-29
WCDET1-8820 | GRP-2021-WCDet1.12.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Monica (East) 3 (Burlingame & Grand River) | 1317 | 2021-10-29 | 2021-11-02
RR1 56330 | GRP-2021-RR1.44.3.2 | 2021 GRP - River Rouge | Install Main - E Pleasasnt South (W Jefferson Ave & Burke St) | 390 | 10-29-21* | 2021-11-01
RR1 61430 | GRP-2021-RR1.2.20.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (0' SSPL Linden St & 4' NSPL W Henry St) | 170 | 2021-10-29 | 2021-10-29
SWDET2-14785 | PROJ-0951-SWDET2.72.5.2 | 2021 GRP - South West Detroit 2 | Install Main - Cabot (W Vernor & ASO Vernor) | 108 | 2021-10-29 | 2021-11-01
SWDET2-20815 | PROJ-0951-SWDET2.45.2.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Mullane (Longworth & Homer) | 401 | 2021-10-29 | 2021-10-29
SWDET2-24535 | PROJ-0951-SWDET2.50.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Lane 2 (Central & Green) | 891 | 2021-10-29 | 2021-11-03
Muni11110 | PROJ-0951-MUN-2.44.1.2 | 2021 GRP - Municipality | Install Main - Southfield Fwy (M-39) (66' EEPL Ashton Ave & 112' WWPL Archdale St) | 545 | 10-29-21* | 2021-11-08
Muni12710 | PROJ-0951-MUN-2.47.7.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Grandmont Ave & 149' EEPL Grandmont Ave) | 155 | 2021-10-29 | 2021-10-29
Muni9766 | PROJ-0951-MUN-2.1.1.2 | 2021 GRP - Municipality | Install Main - Southfield Fwy (M-39) (66' EEPL Ashton Ave & 112' WWPL Archdale St) | 545 | 10-29-21* | 2021-11-08
AA4 20790 | GRP-2021-AA4.47.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Russett Rd (Russell Rd & Hewett Dr) | 520 | 2021-10-30 | 2021-11-01
RR1 5123 | GRP-2021-RR1.43.1.2 | 2021 GRP - River Rouge | Install Main - Goodell (Francis Riopelle Ave & 31' NNPL Coolidge Hwy) | 990 | 2021-11-01 | 2021-11-03
SWDET2-9625 | PROJ-0951-SWDET2.12.2.2 | 2021 GRP - South West Detroit 2 | Install Main - W Vernor 4 (Central & Waterman) | 2343 | 11-01-21* | 2021-11-12
WCDET1-5360 | GRP-2021-WCDet1.22.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Tuller (Buena Vista & Buena Vista) | 498 | 2021-11-01 | 2021-11-01
SWDET2-19965 | PROJ-0951-SWDET2.36.2.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Longworth (Tie-in & Tie-in) | 347 | 2021-11-01 | 2021-11-01
RR1 6101 | GRP-2021-RR.9.1.2 | 2021 GRP - Risk Rank | Install Main - Spring Garden 1 (Chalmers & Hayes) | 2715 | 2021-11-01 | 2021-11-18
RR1 10331 | GRP-2021-FR.51.1.2 | 2021 GRP - Field Recommendation | Install Main - Fort (6' NSPL Fort & 34' NSPL Fort @ 17th) | 28 | 2021-11-01 | 2021-11-01
NCET4-60 | Proj-NCDET43-1 PA.21.2 | NCDET4 Pull Ahead | Install main - ASO McNichols (4) (Snowden & Steel) | 1800 | 11-01-21* | 2021-11-08
NCET4-70 | Proj-NCDET43-1 PA.40.1 | NCDET4 Pull Ahead | Install main - Prest (McNichols & Puritan) | 2558 | 11-01-21* | 2021-11-08
RFordMMO105 | Proj-Redford PA.12.1.1 | Redford - Pull Ahead | Install Main - Centralia St (Curtis St & Santa Maria Ave) | 1765 | 11-01-21* | 2021-11-04
WD3PH-5640 | Proj-WDET3PLH.1.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Main - Paul (Archdale & Abington) | 1750 | 11-01-21* | 2021-12-09
WD3PH-5720 | Proj-WDET3PLH.2.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Main - Longacre (ASO Warren & Paul) | 2500 | 11-01-21* | 2021-12-09
WD3PH-5800 | Proj-WDET3PLH.5.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Main - Rutland (ASO Warren & Paul) | 2450 | 11-01-21* | 2021-12-09
WD3PH-5880 | Proj-WDET3PLH.6.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Main - Abgington (ASO Warren & Paul) | 2400 | 11-01-21* | 2021-12-09
Milestone 2 | GRP-2021-ND3.23 | 2021 GRP - North Detroit 3 | Elevate Main Finish Milestone | 0 |  | 11-01-21*
Milestone 1 | GRP-2021-FR.23 | 2021 GRP - Field Recommendation | Install Main Finish Milestone | 0 |  | 11-01-21*
RR1 5108 | GRP-2021-RR1.37.1.2 | 2021 GRP - River Rouge | Install Main - W Henry (Division St & 4' WWPL W Jefferson Ave) | 620 | 2021-11-02 | 2021-11-04
WCDET1-2185 | GRP-2021-WCDet1.4.10.2 | 2021 GRP - West Central Detroit 1 | Install Main - Turner (EOM & Buena Vista) | 611 | 2021-11-02 | 2021-11-03
SWDET2-5310 | PROJ-0951-SWDET2.47.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Evans (Gartner & Pershing) | 1030 | 2021-11-02 | 2021-11-05
SWDET2-8085 | PROJ-0951-SWDET2.1.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 1 (At Railroad) | 440 | 2021-11-02 | 2021-11-15
WCDET1-10500 | GRP-2021-WCDet1.17.3.2 | 2021 GRP - West Central Detroit 1 | Elevate Main - Livernois 4 (Davison & EOM) | 913 | 11-02-21* | 2021-11-05
SWDET2-21155 | PROJ-0951-SWDET2.59.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Navy 2 (Green & Beard) | 737 | 2021-11-02 | 2021-11-04
SWDET2-21315 | PROJ-0951-SWDET2.75.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Norman (ANO Vernor & W Vernor) | 108 | 2021-11-02 | 2021-11-04
Muni10470 | PROJ-0951-MUN-2.36.1.2 | 2021 GRP - Municipality | Install Main - Grandmont Ave (2) (W Warren Ave & ASO W Warren Ave) | 110 | 2021-11-02 | 2021-11-02
Ypsi 3-8800 | PROJ-0951-YSP3.28.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Cedarcliff (Woodglen & EOM) | 510 | 2021-11-03 | 2021-11-03
RR1 5126 | GRP-2021-RR1.46.1.2 | 2021 GRP - River Rouge | Install Main - E Cicotte (W Jefferson Ave & Burke St) | 435 | 2021-11-03 | 2021-11-08
RR1 5138 | GRP-2021-RR1.44.1.2 | 2021 GRP - River Rouge | Install Main - E Pleasasnt North (W Jefferson Ave & 4' EWPL Burke St) | 390 | 2021-11-03 | 2021-11-04
WCDET1-5145 | GRP-2021-WCDet1.50.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Fullerton (Tuller & Ewald) | 233 | 2021-11-03 | 2021-11-03
AA4 26428 | GRP-2021-AA4.9.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - S Main (S Main St & 58' EEPL S Main St) | 140 | 2021-11-03 | 2021-11-05
WCDET1-5520 | GRP-2021-WCDet1.22.4.2 | 2021 GRP - West Central Detroit 1 | Install Main - Tuller (Buena Vista & Fullerton) | 1046 | 2021-11-03 | 2021-11-05
AA4 25758 | GRP-2021-AA4.5.4.2 | 2021 GRP - Ann Arbor 4 | Install Main - S 1st St (114' NNPL Nob Hill Pl & Nob Hill Pl) | 155 | 2021-11-03 | 2021-11-04
WCDET1-5840 | GRP-2021-WCDet1.53.2.2 | 2021 GRP - West Central Detroit 1 | Install Main - Ewald Cr West 2 (Buena Vista & Cortland) | 2094 | 2021-11-04 | 2021-11-09
RR1 56090 | GRP-2021-RR1.62.2.2 | 2021 GRP - River Rouge | Install Main - E Oak St (25' EEPL Byron St & Genessee St) | 550 | 2021-11-04 | 2021-11-08
SWDET2-22835 | PROJ-0951-SWDET2.69.2.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Pitt (Casper & Central) | 370 | 2021-11-04 | 2021-11-05
Muni10150 | PROJ-0951-MUN-2.32.1.2 | 2021 GRP - Municipality | Install Main - ASO W Warren Ave (1) (Southfield Rd & Archdale St) | 275 | 2021-11-04 | 2021-11-04
Muni12790 | PROJ-0951-MUN-2.47.8.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (213' WWPL Woodmont Ave & 4' EWPL Woodmont Ave) | 220 | 2021-11-04 | 2021-11-04
RFordMMO110 | Proj-Redford PA.19.1.1 | Redford - Pull Ahead | Install Main - Norborne St (Curtis St & Bennett St) | 800 | 2021-11-04 | 2021-11-09
RFordMMO115 | Proj-Redford PA.12.1.1 | Redford - Pull Ahead | Install Main - Centralia St (Tie-In At 6 Mile Rd) | 25 | 2021-11-04 | 2021-11-04
RR1 536 | GRP-2021-RR1.12.1.2 | 2021 GRP - River Rouge | Install Main - AWO W Jefferson (W Henry & EOM) | 130 | 2021-11-05 | 2021-11-05
SWDET2-5630 | PROJ-0951-SWDET2.51.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Logan 2 (Central & EOM) | 756 | 2021-11-05 | 2021-11-10
RR1 251 | GRP-2021-RR1.3.1.2 | 2021 GRP - River Rouge | Install Main - Francis Riopelle Ave (Richter St & EOM) | 425 | 2021-11-05 | 2021-11-05
SWDET2-17125 | PROJ-0951-SWDET2.78.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Sharon (W Vernor & ASO Vernor) | 106 | 2021-11-05 | 2021-11-08
ND2-25840 | PROJ-0951-WDET9-4.35.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Install Main - Vista Marian School (Warren & EOM) | 1045 | 11-05-21* | 2021-11-10
WCDET1-1555045 | GRP-2021-WCDet1.51.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - WCDET1 Street (Cross Street) | 0 | 2021-11-05 | 2021-11-10
AA4 20788 | GRP-2021-AA4.45.1.2 | 2021 GRP - Ann Arbor 4 | Install Main - Redeemer Ave (Rusell Rd & Hewett Rd) | 520 | 2021-11-06 | 2021-11-08
AA4 25418 | GRP-2021-AA4.5.3.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - S 1st St (W Mosely St & 114' NNPL Nob Hill Pl) | 528 | 2021-11-06 | 2021-11-09
Ypsi 3-8300 | PROJ-0951-YSP3.26.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Briardale (Woodglen & EOM) | 610 | 2021-11-08 | 2021-11-09
Ypsi 3-9800 | PROJ-0951-YSP3.32.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Ravinewood (Nash & Glengrove) | 735 | 2021-11-08 | 2021-11-09
RR1 5150 | GRP-2021-RR1.52.1.2 | 2021 GRP - River Rouge | Install Main - Batavia (Burke St & Genessee St) | 1185 | 2021-11-08 | 2021-11-11
SWDET2-5390 | PROJ-0951-SWDET2.48.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Gartner 1 (Lawndale & Springwells) | 1670 | 2021-11-08 | 2021-11-16
RR1 55450 | GRP-2021-RR1.45.4.2 | 2021 GRP - River Rouge | Install Main - E Henry (110' WWPL Richter St & Richter St) | 120 | 2021-11-08 | 2021-11-08
SWDET2-22675 | PROJ-0951-SWDET2.69.3.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Pitt (Springwells & Casper) | 306 | 2021-11-08 | 2021-11-09
SWDET2-24205 | PROJ-0951-SWDET2.82.4.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Lawndale 1W (Chamberlain & Witt) | 961 | 2021-11-08 | 2021-11-11
Muni11910 | PROJ-0951-MUN-2.27.2.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (4) (EOM Penrod St & Rosemont Ave) | 280 | 11-08-21* | 2021-11-10
Muni12950 | PROJ-0951-MUN-2.47.10.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' WEPL Asbury Park & 95' EEPL Asbury Park) | 100 | 2021-11-08 | 2021-11-08
Muni9757 | PROJ-0951-MUN-2.52.1.2 | 2021 GRP - Municipality | Install Main - Longacre St (2) (EOM & ANO W Warren Ave) | 290 | 2021-11-08 | 2021-11-08
RR1 5132 | GRP-2021-RR1.45.80.2 | 2021 GRP - River Rouge | Install Main - E Henry (W Jefferson Ave & Burke St) | 335 | 2021-11-09 | 2021-11-10
AA4 21278 | GRP-2021-AA4.34.2.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - 3rd St (W Mosley St & W Davis Ave) | 931 | 2021-11-09 | 2021-11-15
WCDET1-8410 | GRP-2021-WCDet1.25.3.2 | 2021 GRP - West Central Detroit 1 | Elevate Main - Oakman Blvd West (Davison & Davison) | 130 | 11-09-21* | 2021-11-09
RR1 56170 | GRP-2021-RR1.62.4.2 | 2021 GRP - River Rouge | Install Main - E Oak St (4' WEPL Genessee St & Richer St) | 790 | 2021-11-09 | 2021-11-12
SWDET2-18595 | PROJ-0951-SWDET2.68.3.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Inglis (Woodmere & W Vernor) | 2042 | 2021-11-09 | 2021-11-18
NCET4-100 | Proj-NCDET43-1 PA.37.1 | NCDET4 Pull Ahead | Install main - Whitcomb (McNichols & Puritan) | 2460 | 2021-11-09 | 2021-11-16
RFordMMO120 | Proj-Redford PA.19.1.1 | Redford - Pull Ahead | Install Main - Norborne St (Tie-In At 6 Mile Rd) | 15 | 2021-11-09 | 2021-11-16
Milestone 2 | GRP-2021-WCDet1.23 | 2021 GRP - West Central Detroit 1 | Elevate Main Finish Milestone | 0 |  | 11-09-21*
NCDET - 3555 | NEWPROJ-6.12.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Pinehurst (Puritan & ANO Fenkell) | 2552 | 2021-11-10 | 2021-11-19
RR1 52 | GRP-2021-RR1.4.1.2 | 2021 GRP - River Rouge | Install Main - Coolidge Hwy 1 (332' WWPL Division St & Division St) | 400 | 2021-11-10 | 2021-11-11
SWDET2-7070 | PROJ-0951-SWDET2.69.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Pitt (EOM & Springwells) | 87 | 2021-11-10 | 2021-11-10
WCDET1-12510 | GRP-2021-WCDet1.50.3.2 | 2021 GRP - West Central Detroit 1 | Install Main - Fullerton (Ewald Circle & Oakman Blvd) | 250 | 2021-11-10 | 2021-11-10
RR1 6181 | GRP-2021-RR.10.1.2 | 2021 GRP - Risk Rank | Install Main - Spring Garden 2 (Hayes & Kelly) | 1920 | 2021-11-10 | 2021-11-19
AA4 27798 | GRP-2021-AA4.9.5.2 | 2021 GRP - Ann Arbor 4 | Install Main - S Main (Hill & Tie-in) | 9 | 2021-11-10 | 2021-11-11
Muni13030 | PROJ-0951-MUN-2.47.11.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (108' WWPL Asbury Park & Asbury Park) | 200 | 2021-11-10 | 2021-11-10
Muni9753 | PROJ-0951-MUN-2.51.1.2 | 2021 GRP - Municipality | Install Main - Clayburn St (1) (23' NNPL ANO W Warren Ave & 5' NSPL ANO W Warren Ave) | 45 | 2021-11-10 | 2021-11-10
WCDET1-4745 | GRP-2021-WCDet1.45.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd West 2 (Buena Vista & Cortland) | 1800 | 2021-11-10 | 2021-11-15
AA4 23298 | GRP-2021-AA4.18.3.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Koch Ave (96' WWPL S 1st St & 49' EEPL S 1st St) | 185 | 2021-11-10 | 2021-11-13
SWDET2-7230 | PROJ-0951-SWDET2.70.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Springwells 2 (Dix & W Vernor) | 2163 | 2021-11-11 | 2021-11-23
SWDET2-11825 | PROJ-0951-SWDET2.74.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Lawndale 2 (ANO W Vernor & W Vernor) | 20 | 2021-11-11 | 2021-11-11
RFordMMO125 | Proj-Redford PA.16.1.1 | Redford - Pull Ahead | Install Main - Kinloch St (Curtis St & Santa Maria Ave) | 1695 | 2021-11-11 | 2021-11-17
Ypsi 3-1480 | PROJ-0951-YSP3.38.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - McCartney (State & I-94) | 1225 | 2021-11-12 | 2021-11-19
SWDET2-3550 | PROJ-0951-SWDET2.25.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Elsmere 2 (At Rathbone) | 33 | 2021-11-12 | 2021-11-12
SWDET2-8925 | PROJ-0951-SWDET2.3.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - EWO Woodmere (At W Vernor) | 861 | 2021-11-12 | 2021-11-17
RR1 53930 | GRP-2021-RR1.58.2.2 | 2021 GRP - River Rouge | Install Main - Coolidge Hwy 2 (Richter St & Goodell St) | 265 | 2021-11-12 | 2021-11-15
RR1 55370 | GRP-2021-RR1.45.3.2 | 2021 GRP - River Rouge | Install Main - E Henry (4' NSPL E Henry St & 4' SNPL E Henry St) | 45 | 2021-11-12 | 2021-11-12
SWDET2-21475 | PROJ-0951-SWDET2.75.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Norman (Tie-In & ANO Vernor) | 5 | 2021-11-12 | 2021-11-12
Muni9750 | PROJ-0951-MUN-2.27.1.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (4) (Rosemont Ave & 25' EEPL Ashton Ave) | 395 | 2021-11-12 | 2021-11-17
Muni11830 | PROJ-0951-MUN-2.26.5.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (Southfield Rd & 18' WWPL Archdale St) | 185 | 11-12-21* | 2021-11-12
Muni13110 | PROJ-0951-MUN-2.47.12.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Asbury Park & 209' EEPL Asbury Park) | 215 | 2021-11-12 | 2021-11-12
AA4 20542 | GRP-2021-AA4.30.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - W Mosley St (3rd St & S Ashley St) | 947 | 2021-11-13 | 2021-11-18
NCDET - 3530 | NEWPROJ-6.9.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Mendota (Pilgrim & ANO Fenkell) | 1802 | 2021-11-15 | 2021-11-19
SWDET2-6750 | PROJ-0951-SWDET2.65.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Carson (Dix & W Vernor) | 2248 | 11-15-21* | 2021-11-23
RR1 52330 | GRP-2021-RR1.52.3.2 | 2021 GRP - River Rouge | Install Main - Batavia (Genessee St & Richer St) | 795 | 2021-11-15 | 2021-11-16
RR1 53690 | GRP-2021-RR1.4.2.2 | 2021 GRP - River Rouge | Install Main - Coolidge Hwy 1 (Division St & 400' EEPL Division St) | 400 | 2021-11-15 | 2021-11-15
AA4 27858 | GRP-2021-AA4.9.6.2 | 2021 GRP - Ann Arbor 4 | Install Main - S Main (Moseley & Tie-in) | 8 | 2021-11-15 | 2021-11-17
Muni9761 | PROJ-0951-MUN-2.50.1.2 | 2021 GRP - Municipality | Install Main - Woodmont Ave (1) (ANO W Warren Ave & W Warren Ave) | 115 | 11-15-21* | 2021-11-15
WCDET1-3945 | GRP-2021-WCDet1.35.1.2 | 2021 GRP - West Central Detroit 1 | Install Main - Oakman Blvd East 2 (Buena Vista & Cortland) | 1829 | 2021-11-16 | 2021-11-19
AA4 20531 | GRP-2021-AA4.18.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - Koch Ave (3rd St & 50' EEPL 3rd St) | 5 | 2021-11-16 | 2021-11-17
RR1 60060 | GRP-2021-RR1.2.2.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (4' NNPL Leroy St & Coolidge Hwy) | 815 | 2021-11-16 | 2021-11-18
Muni9670 | PROJ-0951-MUN-2.26.1.2 | 2021 GRP - Municipality | Install Main - ANO W Warren Ave (1) (26' WWPL Archdale St & Archdale St) | 75 | 2021-11-16 | 2021-11-16
Muni10070 | PROJ-0951-MUN-2.31.1.2 | 2021 GRP - Municipality | Install Main - Asbury Park (3) (W Waren Ave & ASO W Warren Ave) | 115 | 2021-11-16 | 2021-11-16
Muni10870 | PROJ-0951-MUN-2.41.1.2 | 2021 GRP - Municipality | Install Main - Mettetal St (3) (W Warren Ave & ASO W Warren Ave) | 115 | 2021-11-16 | 2021-11-16
Muni13190 | PROJ-0951-MUN-2.47.13.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (Mettetal St & 266' EEPL Mettetal St) | 270 | 2021-11-16 | 2021-11-16
NWDET-22770 | PROJ-0951-NWDET1CO.29.3.2 | 2021 GRP - North West Detroit 1b | Elevate Main - Kendall (1) (Evergreen & Artesian) | 2681 | 11-16-21* | 2021-11-17
WD3PH-3480 | Proj-WDET3PLH.4.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Main - Archdale (Warren & Paul) | 2600 | 11-16-21* | 2021-12-28
Muni12870 | PROJ-0951-MUN-2.47.9.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (4' EWPL Woodmont Ave & 4' WEPL Asbury Park) | 385 | 2021-11-17 | 2021-11-19
Ypsi 3-8550 | PROJ-0951-YSP3.27.1.2 | 2021 GRP - Ypsilanti 3 | Install Main - Brooktree (Woodglen & EOM) | 620 | 2021-11-18 | 2021-11-19
NCDET - 3525 | NEWPROJ-6.9.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Mendota (ASO Puritan & Pilgrim) | 562 | 2021-11-18 | 2021-11-19
SWDET2-4670 | PROJ-0951-SWDET2.39.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Cahalan 1 (Mullane & Springwells) | 815 | 2021-11-18 | 2021-11-26
SWDET2-6110 | PROJ-0951-SWDET2.57.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Gartner 2 (Springwells & Central) | 922 | 2021-11-18 | 2021-11-23
AA4 23378 | GRP-2021-AA4.18.2.2 | 2021 GRP - Ann Arbor 4 | Install Main - Koch Ave (50' EEPL 3rd St & 96' WWPL S 1st St) | 335 | 2021-11-18 | 2021-11-19
SWDET2-15065 | PROJ-0951-SWDET2.39.3.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Cahalan 1 (Lawndale & Mullane) | 790 | 2021-11-18 | 2021-11-23
Muni9830 | PROJ-0951-MUN-2.28.1.2 | 2021 GRP - Municipality | Install Main - Archdale St (2) (ANO W Warren Ave & W Warren Ave) | 105 | 2021-11-18 | 2021-11-18
NWDET-22780 | PROJ-0951-NWDET1CO.29.3.2 | 2021 GRP - North West Detroit 1b | Elevate Main - Kendall (2) (Artesian & Ashton) | 1590 | 2021-11-18 | 2021-11-18
AA4 27708 | GRP-2021-AA4.30.3.2 | 2021 GRP - Ann Arbor 4 | Install Main - W Mosley St (S Ashley St & S Main St) | 140 | 2021-11-18 | 2021-11-19
NCDET - 3550 | NEWPROJ-6 | 2020 GRP - Carry Over - North Central Detroit 3 | Elevate Main - Pilgrim 1 (Mendota & Birwood) | 320 | 2021-11-19 | 2021-11-19
SWDET2-14385 | PROJ-0951-SWDET2.55.2.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Whitaker 1 (Lawndale & Mullane) | 807 | 2021-11-19 | 2021-11-23
RR1 5541 | GRP-2021-RR.2.1.2 | 2021 GRP - Risk Rank | Install Main - Fairview (E Warren & E Canfield) | 1975 | 2021-11-19 | 2021-12-03
NCET4-110 | Proj-NCDET43-1 PA.36.1 | NCDET4 Pull Ahead | Install main - sussex (McNichols & Puritan) | 2499 | 2021-11-19 | 2021-12-02
Milestone 1 | GRP-2021-WCDet1.23 | 2021 GRP - West Central Detroit 1 | Install Main Finish Milestone | 0 |  | 11-19-21*
Milestone 1 | GRP-2021-ED1.23 | 2021 GRP - East Detroit 1 | Install Main Finish Milestone | 0 |  | 11-19-21*
SWDET2-1790 | PROJ-0951-SWDET2.1.1.2 | 2021 GRP - South West Detroit 2 | Install Main - Dix 1 (Miller & Railroad) | 839 | 11-22-21* | 2021-11-29
Ypsi 3-11150 | PROJ-0951-YSP3.38.3.2 | 2021 GRP - Ypsilanti 3 | Install Main - McCartney (Coolidge & William) | 445 | 2021-11-22 | 2021-11-23
RR1 59980 | GRP-2021-RR1.2.3.2 | 2021 GRP - River Rouge | Install Main - W Jefferson Ave (1) (12' NSPL E Pleasant St & Delisle St) | 200 | 2021-11-22 | 2021-11-22
Muni11350 | PROJ-0951-MUN-2.47.1.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (0' SNPL W Warren Ave & 0' NSPL W Warren Ave) | 100 | 2021-11-22 | 2021-11-22
Muni9990 | PROJ-0951-MUN-2.30.1.2 | 2021 GRP - Municipality | Install Main - Asbury Park (2) (ANO W Warren Ave & W Warren Ave) | 105 | 2021-11-23 | 2021-11-23
SWDET2-14225 | PROJ-0951-SWDET2.55.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Whitaker 1 (At Lawndale) | 84 | 2021-11-24 | 2021-11-24
Muni9910 | PROJ-0951-MUN-2.29.1.2 | 2021 GRP - Municipality | Install Main - Archdale St (3) (W Warren Ave & ASO W Warren Ave) | 105 | 2021-11-24 | 2021-11-24
SWDET2-5870 | PROJ-0951-SWDET2.54.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Senator 1 (EOM & Mullane) | 610 | 2021-11-26 | 2021-11-26
SWDET2-17445 | PROJ-0951-SWDET2.54.3.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Senator 1 (Mullane & Springwells) | 968 | 11-26-21* | 2021-11-29
SWDET2-17835 | PROJ-0951-SWDET2.57.3.2 | 2021 GRP - South West Detroit 2 | Install Main - Gartner 2 (Central & Green) | 937 | 2021-11-26 | 2021-12-01
Muni9772 | PROJ-0951-MUN-2.23.1.2 | 2021 GRP - Municipality | Install Main - St Marys St (2) (ANO W Warren Ave & W Warren Ave) | 95 | 2021-11-26 | 2021-11-26
Milestone 1 | GRP-2021-RR1.23 | 2021 GRP - River Rouge | Install Main Finish Milestone | 0 |  | 11-26-21*
SWDET2-5150 | PROJ-0951-SWDET2.45.1.2 | 2021 GRP - South West Detroit 2 | Elevate Main - Mullane (At Cahalan) | 161 | 2021-11-29 | 2021-11-30
Muni13270 | PROJ-0951-MUN-2.47.14.2 | 2021 GRP - Municipality | Install Main - W Warren Ave (1) (0' SNPL W Warren Ave & 0' Sspl W Warren Ave) | 110 | 2021-11-29 | 2021-11-29
Ypsi 3-11380 | PROJ-0951-YSP3.38.2.2 | 2021 GRP - Ypsilanti 3 | Install Main - McCartney (3' EWPL McCartney Ave & 90' EWPL McCartney Ave) | 90 | 2021-11-30 | 2021-11-30
AA4 23458 | GRP-2021-AA4.18.4.2 | 2021 GRP - Ann Arbor 4 | Install Main - Koch Ave (49' EEPL S 1st St & S Main St) | 360 | 2021-11-30 | 2021-12-03
RFordMMO130 | Proj-Redford PA.16.1.1 | Redford - Pull Ahead | Install Main - Kinloch St (Tie-In At 6 Mile Rd North Side) | 16 | 2021-11-30 | 2021-11-30
RFordMMO135 | Proj-Redford PA.7.1.1 | Redford - Pull Ahead | Install Main - Bennett St (1) (MacArthur & Kinloch St) | 670 | 2021-11-30 | 2021-12-01
Muni9762 | PROJ-0951-MUN-2.8.1.2 | 2021 GRP - Municipality | Install Main - St Marys St (3) (W Warren Ave & ASO W Warren Ave) | 105 | 2021-11-30 | 2021-11-30
Milestone 2 | PROJ-0951-SWDET2.23 | 2021 GRP - South West Detroit 2 | Elevate Main Finish Milestone | 0 |  | 11-30-21*
Milestone 1 | PROJ-0951-YSP3.43 | 2021 GRP - Ypsilanti 3 | Install Main Finish Milestone | 0 |  | 11-30-21*
AA5-107 | Proj-AA5-PLH.1.1 | Ann Arbor 5 - Pull Ahead 2021 | Install Main - AA 5 | 7830 | 12-01-21* | 2021-12-30
RFordMMO140 | Proj-Redford PA.16.1.1 | Redford - Pull Ahead | Install Main - Kinloch St (Tie-In At 6 Mile Rd South Side) | 19 | 2021-12-02 | 2021-12-02
SWDET2-17915 | PROJ-0951-SWDET2.57.2.2 | 2021 GRP - South West Detroit 2 | Install Main - Gartner 2 (Green & Beard) | 737 | 2021-12-03 | 2021-12-07
RFordMMO145 | Proj-Redford PA.18.1.1 | Redford - Pull Ahead | Install Main - MacArthur (6 Mile Rd & 6 Mile Rd) | 605 | 2021-12-03 | 2021-12-07
Milestone 1 | GRP-2021-AA4.23 | 2021 GRP - Ann Arbor 4 | Install Main Finish Milestone | 0 |  | 12-03-21*
Milestone 1 | GRP-2021-RR.23 | 2021 GRP - Risk Rank | Install Main Finish Milestone | 0 |  | 12-03-21*
NCET4-125 | Proj-NCDET43-1 PA.35.1 | NCDET4 Pull Ahead | Install main - Robson (McNichols & Puritan) | 2408 | 2021-12-06 | 2021-12-14
Milestone 1 | PROJ-0951-SWDET2.23 | 2021 GRP - South West Detroit 2 | Install Main Finish Milestone | 0 |  | 12-07-21*
AA4 20379 | GRP-2021-AA4.5.1.2 | 2021 GRP - Ann Arbor 4 | Elevate Main - S 1st St (2' NSPL W Madison St & W Mosley St) | 455 | 2021-12-13 | 2021-12-14
Milestone 2 | GRP-2021-AA4.23 | 2021 GRP - Ann Arbor 4 | Elevate Main Finish Milestone | 0 |  | 12-14-21*
Milestone 1 | Proj-WDET3PLH | West Detroit 3 - Pull Ahead 2021 | Install Main Finish Milestone | 0 |  | 12-30-21*

## Service (hidden)
Activity ID | WBS | Project Name | Activity Name | Budgeted Units | Start | Finish
CDET-1350 | PROJ-0951-CDET1-2.36.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Sturtevant (1) (Linwood & Dexter) | 48 | 11-16-20 A | 03-01-21 A
RedfMMO1030 | PROJ-0951-MMORedford-1.1.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | MMO - 7 Mile Rd (Inkster & Gaylord) | 14 | 11-17-20 A | 12-31-20 A
CDET-2410 | PROJ-0951-CDET1-2.25.2.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Buena Vista (1) (AEO Dexter & Linwood) | 60 | 12-07-20 A | 03-09-21 A
Muni7370 | PROJ-0951-MUN-3.31.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - Laslle (Longfellow & EOM) | 1 | 12-26-20 A | 12-29-20 A
CDET-1175 | PROJ-0951-CDET1-2.6.2.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Clements (2) (Livernois & Dexter) | 16 | 12-28-20 A | 01-21-21 A
Muni7840 | PROJ-0951-MUN-3.34.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - linwood (Off Joy) | 1 | 12-29-20 A | 12-30-20 A
Muni4450 | PROJ-0951-MUN-3.18.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - Rosa Parks (W Philadelphia & Longfellow) West and East | 7 | 12-30-20 A | 12-30-20 A
Muni5370 | PROJ-0951-MUN-3.21.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - Joy (Linwood & Dexter) | 5 | 12-30-20 A | 12-30-20 A
Muni7800 | PROJ-0951-MUN-3.33.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - Dexter (Off Joy) | 0 | 12-30-20 A | 12-30-20 A
CDET-10385 | PROJ-0951-CDET1-2.53.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Ewald (2) (Livernois & Dexter) | 14 | 01-07-21 A | 02-16-21 A
AA4 21868 | GRP-2021-AA4.36.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - Eberwhite Blvd West (Lutz & W Madison) | 9 | 01-11-21 A | 02-01-21 A
AA4 23978 | GRP-2021-AA4.40.4.2 | 2021 GRP - Ann Arbor 4 | Install Services - Lutz Ave (Eberwhite Blvd & S 7th St) | 12 | 01-11-21 A | 01-25-21 A
SCDet-4625 | GRP-2021-SCDet1.34.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Northlawn (Joy & Tireman) | 127 | 01-11-21 A | 02-08-21 A
CDET-215 | PROJ-0951-CDET1-2.5.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Clements (1) (Linwood & Dexter) | 70 | 01-11-21 A | 02-08-21 A
AA4 21788 | GRP-2021-AA4.36.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Eberwhite Blvd West (W Liberty & Lutz) | 5 | 01-12-21 A | 03-10-21 A
AA4 20828 | GRP-2021-AA4.37.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Elder Blvd (11' WWPL Crest Ave & Eberwhite Blvd) | 3 | 01-14-21 A | 01-25-21 A
AA4 26288 | GRP-2021-AA4.6.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 7th St (Jefferson Ct & W Madison St) | 27 | 01-18-21 A | 03-10-21 A
EDET1 50764 | GRP-2021-ED1.37.1.2 | 2021 GRP - East Detroit 1 | Install Services - Yorkshire Rd (2) (Waveney St & Mack Ave) | 95 | 01-19-21 A | 02-22-21 A
AA4 23158 | GRP-2021-AA4.39.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - Jefferson Ct (272' WWPL S 7th St & 16' WWPL S 7th St) | 8 | 01-19-21 A | 01-27-21 A
AA4 23808 | GRP-2021-AA4.40.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - Lutz Ave (11' EWPL Crest Ave & Eberwhite Blvd) | 6 | 01-21-21 A | 02-04-21 A
AA4 22188 | GRP-2021-AA4.37.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Elder Blvd (Eberwhite Blvd & EOM 280' EEPL Eberwhite Blvd) | 5 | 01-22-21 A | 01-29-21 A
SCDet-4465 | GRP-2021-SCDet1.32.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Wisconsin (Joy & Tireman) | 88 | 01-25-21 A | 02-03-21 A
EDET1 50758 | GRP-2021-ED1.31.1.2 | 2021 GRP - East Detroit 1 | Install Services - Kensington Ave (2) (Waveney St & Mack Ave) | 79 | 01-25-21 A | 03-16-21 A
AA4 24478 | GRP-2021-AA4.44.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Mt Vernon Ave (Mt Pleasant Ave & Manhattan Ave) | 18 | 01-27-21 A | 02-26-21 A
SCDet-2865 | GRP-2021-SCDet1.12.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Carlin (Joy & Tireman) | 100 | 02-01-21 A | 02-25-21 A
SCDet-4385 | GRP-2021-SCDet1.31.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Indiana (Joy & Tireman) | 105 | 02-01-21 A | 02-24-21 A
AP 1760 | PROJ-0951-MMOAllen.9.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Becker 1 (Bellaire & Goddard) | 1 | 02-01-21 A | 02-01-21 A
AP 1820 | PROJ-0951-MMOAllen.12.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Bellaire (Reeck & 975 Feet East Of Becker) | 3 | 02-01-21 A | 03-08-21 A
NWDET-19990 | PROJ-0951-NWDET1CO.53.3.2 | 2021 GRP - North West Detroit 1b | Install Services - Penrod (2) (Schoolcraft & Davison) | 30 | 02-01-21 A | 03-09-21 A
NWDET-17660 | PROJ-0951-NWDET1CO.52.3.2 | 2021 GRP - North West Detroit 1b | Install Services - Faust (2) (Schoolcraft & Davison) | 29 | 02-01-21 A | 03-09-21 A
EDET1 50750 | GRP-2021-ED1.22.1.2 | 2021 GRP - East Detroit 1 | Install Services - Bishop St (2) (Waveney St & Mack Ave) | 114 | 02-01-21 A | 03-09-21 A
EDET1 50754 | GRP-2021-ED1.27.1.2 | 2021 GRP - East Detroit 1 | Install Services - Grayton St (2) (Waveney St & Mack Ave) | 106 | 02-01-21 A | 02-08-21 A
CDET-125 | PROJ-0951-CDET1-2.2.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Doris (1) (Linwood & Livernois) | 58 | 02-01-21 A | 02-03-21 A
CDET-170 | PROJ-0951-CDET1-2.3.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - W Grand 1 (Dexter & Linwood) | 44 | 02-01-21 A | 02-02-21 A
CDET-300 | PROJ-0951-CDET1-2.8.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Fleet (1) (Linwood & Oakman) | 2 | 02-01-21 A | 02-03-21 A
CDET-390 | PROJ-0951-CDET1-2.11.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Oakman (1) (Fleet & Dexter) | 53 | 02-01-21 A | 03-17-21 A
CDET-435 | PROJ-0951-CDET1-2.15.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Oakman Ct (Linwood & Oakman) | 31 | 02-01-21 A | 02-03-21 A
CDET-695 | PROJ-0951-CDET1-2.26.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Livernois (1) (Doris & Davison) | 7 | 02-01-21 A | 03-08-21 A
CDET-1045 | PROJ-0951-CDET1-2.13.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Oakman (3) (Dexter & Linwood) | 9 | 02-01-21 A | 03-08-21 A
CDET-1220 | PROJ-0951-CDET1-2.10.3.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Pasadena (2) (Dexter & Livernois) | 84 | 02-01-21 A | 02-02-21 A
CDET-11985 | PROJ-0951-CDET1-2.60.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Dexter (5) (Tyler & Buena Vista) | 3 | 02-01-21 A | 03-08-21 A
GP-43950 | PROJ-0951-GP 5 -3.138.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - Lakepointe 1 (Kercheval & Mack) | 14 | 02-01-21 A | 02-02-21 A
AA4 26768 | GRP-2021-AA4.49.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Soule Blvd (102' SSPL Wakefield Ave & 373' SSPL Lutz Ave) | 11 | 02-01-21 A | 03-10-21 A
AP 4580 | PROJ-0951-MMOAllen.71.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Reeck 1 (Promenade & Goddard) | 19 | 02-02-21 A | 2021-09-23
AA4 23638 | GRP-2021-AA4.40.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Lutz Ave (14' WEPL Soule Blvd & 11' EWPL Crest Ave) | 4 | 02-02-21 A | 03-02-21 A
AP 4330 | PROJ-0951-MMOAllen.66.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Pleasant (Reeck & Park) | 20 | 02-03-21 A | 03-02-21 A
AP 4730 | PROJ-0951-MMOAllen.74.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Rose (Reeck & Park) | 20 | 02-03-21 A | 02-03-21 A
AP 4380 | PROJ-0951-MMOAllen.67.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Promenade (Reeck & Park) | 17 | 02-03-21 A | 03-02-21 A
AA4 27568 | GRP-2021-AA4.52.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Madison St (6' WEPL Eberwhite Blvd & Madison Pl) | 9 | 02-03-21 A | 03-10-21 A
AA4 20846 | GRP-2021-AA4.55.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Woodbridge Blvd (Eberwhite Blvd & EOM) | 1 | 02-03-21 A | 02-26-21 A
AA4 20827 | GRP-2021-AA4.36.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Eberwhite Blvd East (Woodbridge & Elder) | 14 | 02-03-21 A | 02-10-21 A
SCDet-4545 | GRP-2021-SCDet1.33.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Ohio (Joy & Tireman) | 85 | 02-04-21 A | 03-16-21 A
AA4 20842 | GRP-2021-AA4.51.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Virginia St (Bemidji St & W Liberty St) | 0 | 02-04-21 A | 02-04-21 A
SCDet-4705 | GRP-2021-SCDet1.35.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Cloverlawn (Joy & Tireman) | 77 | 02-08-21 A | 03-08-21 A
CDET-865 | PROJ-0951-CDET1-2.31.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Glendale (1) (Linwood & AEO Dexter) | 71 | 02-08-21 A | 03-08-21 A
EDET1 50755 | GRP-2021-ED1.28.1.2 | 2021 GRP - East Detroit 1 | Install Services - Harvard Rd (2) (Waveney St & Mack Ave) | 102 | 02-08-21 A | 03-18-21 A
EDET1 501210 | GRP-2021-ED1.68.1.2 | 2021 GRP - East Detroit 1 | Install Services - 3 Mile Rd (2) (Waveney St & ANO Mack Ave) | 86 | 02-15-21 A | 03-18-21 A
CDET-21030 | PROJ-0951-CDET1-2.32.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Ewald N (1) (Petoskey & Petoskey ) | 1 | 02-17-21 A | 02-17-21 A
NWDET-15570 | PROJ-0951-NWDET1CO.25.2.2 | 2021 GRP - North West Detroit 1b | Install Services - ASO Schoolcraft (1) (Artesian & Stahelin) | 1 | 02-22-21 A | 02-22-21 A
SCDet-5825 | GRP-2021-SCDet1.49.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Mackenzie 1 (Hartwell & Littlefield) | 3 | 02-22-21 A | 03-08-21 A
AP 2760 | PROJ-0951-MMOAllen.59.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Old Goddard (Goddard Rd & Pheasant Run) | 2 | 02-22-21 A | 2021-09-20
NWDET-18520 | PROJ-0951-NWDET1CO.49.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Piedmont (2) (Schoolcraft & Davison) | 8 | 02-22-21 A | 02-23-21 A
NWDET-17430 | PROJ-0951-NWDET1CO.51.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Greenview (2) (Davison & EOM) | 14 | 02-22-21 A | 02-23-21 A
NWDET-17200 | PROJ-0951-NWDET1CO.51.3.2 | 2021 GRP - North West Detroit 1b | Install Services - Greenview (2) (Schoolcraft & Davison) | 25 | 02-22-21 A | 03-01-21 A
NWDET-16970 | PROJ-0951-NWDET1CO.47.5.2 | 2021 GRP - North West Detroit 1b | Install Services - Minock (2) (ASO Schoolcraft & Davison) | 14 | 02-22-21 A | 02-23-21 A
NWDET-15230 | PROJ-0951-NWDET1CO.32.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Stahelin (2) (Schoolcraft & EOM) | 12 | 02-22-21 A | 02-23-21 A
NWDET-15140 | PROJ-0951-NWDET1CO.32.3.2 | 2021 GRP - North West Detroit 1b | Install Services - Stahelin (2) (Schoolcraft & Davison) | 22 | 02-22-21 A | 02-26-21 A
NWDET-14420 | PROJ-0951-NWDET1CO.34.3.2 | 2021 GRP - North West Detroit 1b | Install Services - Ashton (2) (Schoolcraft & EOM) | 48 | 02-22-21 A | 03-02-21 A
NWDET-11190 | PROJ-0951-NWDET1CO.20.4.2 | 2021 GRP - North West Detroit 1b | Install Services - Rosemont (2) (Davison & EOM) | 18 | 02-22-21 A | 02-24-21 A
NWDET-11100 | PROJ-0951-NWDET1CO.20.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Rosemont (2) (Schoolcraft & Davison) | 34 | 02-22-21 A | 02-26-21 A
NWDET-9230 | PROJ-0951-NWDET1CO.56.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Glastonbury (4) (Davison & EOM) | 5 | 02-22-21 A | 02-22-21 A
NWDET-8990 | PROJ-0951-NWDET1CO.56.3.2 | 2021 GRP - North West Detroit 1b | Install Services - Glastonbury (4) (Schoolcraft & Davison) | 25 | 02-22-21 A | 03-02-21 A
NWDET-7370 | PROJ-0951-NWDET1CO.24.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Auburn (1) (Glendale & EOM) | 7 | 02-22-21 A | 02-22-21 A
NWDET-7280 | PROJ-0951-NWDET1CO.24.55.2 | 2021 GRP - North West Detroit 1b | Install Services - Auburn (1) (Schoolcraft & Glendale) | 10 | 02-22-21 A | 02-23-21 A
NWDET-2955 | PROJ-0951-NWDET1CO.29.1.2 | 2021 GRP - North West Detroit 1b | Install Services - Artesian (3) (Schoolcraft & SO Glendale) | 12 | 02-22-21 A | 06-02-21 A
NWDET-3000 | PROJ-0951-NWDET1CO.17.1.2 | 2021 GRP - North West Detroit 1b | Install Services - Davison (1) (Auburn & Artesian) | 17 | 02-22-21 A | 02-24-21 A
NWDET-20110 | PROJ-0951-NWDET1CO.50.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Warwick (2) (ASO Schoolcraft & Davison) | 3 | 02-22-21 A | 03-01-21 A
NWDET-15470 | PROJ-0951-NWDET1CO.25.3.2 | 2021 GRP - North West Detroit 1b | Install Services - ASO Schoolcraft (1) (Auburn & Artesian) | 18 | 02-22-21 A | 02-24-21 A
AA4 28488 | GRP-2021-AA4.6.6.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 7th St (Jefferson & Jefferson Ct) | 2 | 02-22-21 A | 03-10-21 A
NWDET-20510 | PROJ-0951-NWDET1CO.61.7.2 | 2021 GRP - North West Detroit 1b | Install Services - Schoolcraft (3) (Glastonbury & Ashton) | 12 | 02-22-21 A | 02-22-21 A
CDET2-3065 | GRP-2021-CDet2.22.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Taylor 1 (Dexter & Linwood) | 57 | 02-22-21 A | 04-15-21 A
CDET-260 | PROJ-0951-CDET1-2.7.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Kendall (1) (Linwood & Oakman) | 59 | 02-22-21 A | 03-01-21 A
CDET-10165 | PROJ-0951-CDET1-2.1.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Kendall (2) (Dexter & Livernois) | 50 | 02-22-21 A | 03-01-21 A
AA4 20606 | GRP-2021-AA4.19.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Madison Pl (W Madison St & EOM) | 20 | 02-22-21 A | 03-10-21 A
SCDet-4865 | GRP-2021-SCDet1.37.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Greenlawn (Joy & Tireman) | 76 | 02-23-21 A | 03-08-21 A
AP 2200 | PROJ-0951-MMOAllen.31.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Goddard (Allen & 500' East Of Becker) | 10 | 02-23-21 A | 03-30-21 A
SCDet-4785 | GRP-2021-SCDet1.36.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Roselawn (Joy & Tireman) | 78 | 02-24-21 A | 03-08-21 A
SCDet-9850 | GRP-2021-SCDet1.49.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Mackenzie 1 (Littlefield & Oakman Blvd) | 16 | 02-25-21 A | 03-10-21 A
CDET-10835 | PROJ-0951-CDET1-2.55.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Tuxedo (1) (Dexter & AWO Linwood) | 3 | 02-26-21 A | 03-08-21 A
AP 1660 | PROJ-0951-MMOAllen.4.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Andrews 1 (Southway & Goddard) | 3 | 02-26-21 A | 02-26-21 A
AP 2060 | PROJ-0951-MMOAllen.24.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Crescent (Reeck & Park) | 24 | 02-26-21 A | 03-02-21 A
AA4 24148 | GRP-2021-AA4.40.5.2 | 2021 GRP - Ann Arbor 4 | Install Services - Lutz Ave (EOM 215' WWPL Soule Blvd & 3' WWPL Soule Blvd) | 4 | 02-26-21 A | 02-26-21 A
SCDet-9190 | GRP-2021-SCDet1.11.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Decatur (Belton & 309' NNPL Tireman) | 10 | 02-28-21 A | 03-04-21 A
NWDET-3060 | PROJ-0951-NWDET1CO.18.1.2 | 2021 GRP - North West Detroit 1b | Install Services - Glendale (1) (Auburn & Artesian) | 5 | 02-28-21 A | 03-24-21 A
NWDET-3070 | PROJ-0951-NWDET1CO.18.1.2 | 2021 GRP - North West Detroit 1b | Install Services - Glendale (1) (Auburn & Artesian) | 4 | 02-28-21 A | 03-24-21 A
EDET1 50748 | GRP-2021-ED1.20.1.2 | 2021 GRP - East Detroit 1 | Install Services - Audubon Rd (1) (Waveney St & Mack Ave) | 81 | 03-01-21 A | 03-15-21 A
EDET1 50752 | GRP-2021-ED1.25.1.2 | 2021 GRP - East Detroit 1 | Install Services - Courville St (2) (Waveney St & Mack Ave) | 86 | 03-01-21 A | 03-08-21 A
CDET2-1865 | GRP-2021-CDet2.7.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Chicago Blvd 1 (Dexter & Wildemere) | 2 | 03-01-21 A | 03-01-21 A
CDET2-2025 | GRP-2021-CDet2.9.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Chicago Blvd 2 (Wildemere & Genessee) | 1 | 03-01-21 A | 03-01-21 A
CDET2-4825 | GRP-2021-CDet2.45.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Genessee (Chicago & Joy) | 12 | 03-01-21 A | 03-03-21 A
CDET2-7530 | GRP-2021-CDet2.39.38.2 | 2021 GRP - Central Detroit 2 | Install Services - Wildemere 2 (W Chicago & Joy) | 29 | 03-01-21 A | 03-08-21 A
EDET1 507656 | GRP-2021-ED1.6.1.2 | 2021 GRP - East Detroit 1 | Install Services - Harvard Rd (1) (Waveney & ANO Warren) | 83 | 03-01-21 A | 03-18-21 A
CDET-1090 | PROJ-0951-CDET1-2.14.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Oakman (4) (Livernois & Dexter) | 87 | 03-01-21 A | 03-15-21 A
CDET-1395 | PROJ-0951-CDET1-2.37.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Ewald (1) (Dexter & Kendall) | 59 | 03-01-21 A | 03-10-21 A
CDET2-3225 | GRP-2021-CDet2.25.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Hazelwood 1 (Dexter & Linwood) | 55 | 03-02-21 A | 03-11-21 A
AP 5130 | PROJ-0951-MMOAllen.81.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Seavitt 2 (Moore & Allen) | 21 | 03-02-21 A | 03-08-21 A
NCDET - 6875 | NEWPROJ-6.5.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Griggs 2 (James couzens & Fenkell) | 42 | 03-02-21 A | 03-09-21 A
SCDet-2625 | GRP-2021-SCDet1.9.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Littlefield 1 (Joy & Sorrento) | 41 | 03-02-21 A | 03-10-21 A
AP 2680 | PROJ-0951-MMOAllen.55.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Moore 2 (Manor & Park) | 9 | 03-02-21 A | 03-02-21 A
AP 2620 | PROJ-0951-MMOAllen.52.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Melbourne 3 (Moore & 380' South Of Maylawn Ave) | 25 | 03-02-21 A | 03-08-21 A
AP 2640 | PROJ-0951-MMOAllen.53.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Midway (Buckingham & Seavitt) | 5 | 03-02-21 A | 03-02-21 A
AP 2580 | PROJ-0951-MMOAllen.50.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Melbourne 1 (Southway & Goddard) | 1 | 03-02-21 A | 03-02-21 A
AP 1900 | PROJ-0951-MMOAllen.16.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Buckingham (Moore & Allen) | 28 | 03-02-21 A | 04-06-21 A
AP 1680 | PROJ-0951-MMOAllen.5.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Andrews 2 (Allen & Midway) | 15 | 03-02-21 A | 03-02-21 A
AP 1720 | PROJ-0951-MMOAllen.7.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Balfour 1 (Southway & Goddard) | 4 | 03-02-21 A | 2021-09-21
SCDet-9350 | GRP-2021-SCDet1.11.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Decatur (309' NNPL Tireman & Tireman) | 3 | 03-07-21 A | 03-12-21 A
NWDET-13550 | PROJ-0951-NWDET1CO.13.3.2 | 2021 GRP - North West Detroit 1b | Install Services - Westwood (1) (ASO Schoolcraft & Davison) | 9 | 03-08-21 A | 03-15-21 A
CDET2-3385 | GRP-2021-CDet2.27.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Gladstone 1 (Dexter & Lawton) | 29 | 03-08-21 A | 03-15-21 A
CDET2-2505 | GRP-2021-CDet2.15.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Edison 2 (Linwood & Rosa Parks) | 101 | 03-08-21 A | 04-15-21 A
EDET1 50753 | GRP-2021-ED1.26.1.2 | 2021 GRP - East Detroit 1 | Install Services - Grayton St (1) (E Warrern Ave & Waveney St) | 77 | 03-08-21 A | 04-01-21 A
EDET1 501212 | GRP-2021-ED1.70.1.2 | 2021 GRP - East Detroit 1 | Install Services - Bedford St West (2) (Waveney St & Mack Ave) | 94 | 03-08-21 A | 03-24-21 A
SCDet-7820 | GRP-2021-SCDet1.28.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Normile (Esper & Belton) | 43 | 03-08-21 A | 04-09-21 A
NWDET-20070 | PROJ-0951-NWDET1CO.53.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Penrod (2) (Davison & EOM) | 7 | 03-08-21 A | 03-08-21 A
NWDET-17740 | PROJ-0951-NWDET1CO.52.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Faust (2) (Davison & EOM) | 18 | 03-08-21 A | 03-10-21 A
NWDET-13640 | PROJ-0951-NWDET1CO.13.2.2 | 2021 GRP - North West Detroit 1b | Install Services - Westwood (1) (Davison & Glendale) | 7 | 03-08-21 A | 04-16-21 A
RR1 7821 | GRP-2021-RR.32.1.2 | 2021 GRP - Risk Rank | Install Services - Lamphere (Fenkell & Eaton) | 18 | 03-08-21 A | 03-11-21 A
CDET-565 | PROJ-0951-CDET1-2.20.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Linwood (1) (Davison & Cortland) | 4 | 03-08-21 A | 03-08-21 A
CDET-1530 | PROJ-0951-CDET1-2.40.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Davison (3) South (Linwood & Dexter) | 3 | 03-08-21 A | 03-15-21 A
CDET-1665 | PROJ-0951-CDET1-2.21.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Linwood (2) (Monterey & Elmhurst) | 1 | 03-08-21 A | 03-08-21 A
CDET-1845 | PROJ-0951-CDET1-2.42.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Cortland (1) (Linwood & AWO Linwood) | 14 | 03-08-21 A | 03-09-21 A
CDET-11065 | PROJ-0951-CDET1-2.56.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Linwood (3) (Monterey & Richton) | 4 | 03-08-21 A | 05-23-21 A
CDET-13345 | PROJ-0951-CDET1-2.66.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Dexter (6) (Leslie & Glendale) | 1 | 03-08-21 A | 03-08-21 A
CDET-13575 | PROJ-0951-CDET1-2.67.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Dexter (7) (Clairmount & Collingwood) | 8 | 03-08-21 A | 04-05-21 A
SCDet-4145 | GRP-2021-SCDet1.28.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Normile (Belton & Tireman) | 35 | 03-08-21 A | 03-11-21 A
AP 4680 | PROJ-0951-MMOAllen.73.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Reeck 3 (Moore & Midway) | 28 | 03-08-21 A | 06-01-21 A
AP 4480 | PROJ-0951-MMOAllen.69.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Quandt 2 (260' North Moore Ave & Midway Ave) | 28 | 03-08-21 A | 03-08-21 A
AP 4230 | PROJ-0951-MMOAllen.64.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Pelham 2 (450' South Conrail Rr & Goddard) | 3 | 03-08-21 A | 03-08-21 A
AP 2700 | PROJ-0951-MMOAllen.56.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Moore 3 (Fox & Allen Park Corporate Limits) | 3 | 03-08-21 A | 03-08-21 A
AP 2380 | PROJ-0951-MMOAllen.40.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Kolb 2 (Midway & Northway) | 6 | 03-08-21 A | 03-08-21 A
AP 2520 | PROJ-0951-MMOAllen.47.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Manor 2 (Moore & Midway) | 24 | 03-08-21 A | 03-30-21 A
AP 2360 | PROJ-0951-MMOAllen.39.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Kolb 1 (Southway & Goddard) | 12 | 03-08-21 A | 03-08-21 A
AA4 22918 | GRP-2021-AA4.1.5.2 | 2021 GRP - Ann Arbor 4 | Install Services - Hutchins Ave (Potter Ave & W Stadium Blvd) | 1 | 03-09-21 A | 08-10-21 A
AA4 24318 | GRP-2021-AA4.43.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Mt Pleasant Ave (Manhattan Dr & Sunnyside Blvd) | 17 | 03-09-21 A | 03-10-21 A
CDET-1485 | PROJ-0951-CDET1-2.39.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Davison (2) (Dexter & Linwood) | 10 | 03-10-21 A | 03-11-21 A
AA4 29028 | GRP-2021-AA4.19.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Madison Pl (W Madison St & EOM) | 8 | 03-10-21 A | 04-08-21 A
AA4 29018 | GRP-2021-AA4.43.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Mt Pleasant Ave (Manhattan Dr & Sunnyside Blvd) | 15 | 03-11-21 A | 05-20-21 A
CDET2-1545 | GRP-2021-CDet2.2.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Glynn 1 (Dexter & Linwood) | 63 | 03-11-21 A | 04-12-21 A
AP 2660 | PROJ-0951-MMOAllen.54.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Moore 1 (107' West Of Buckingham Ave & Marlborough) | 14 | 03-12-21 A | 2021-09-27
AP 2560 | PROJ-0951-MMOAllen.49.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Maylawn (Reeck & Becker) | 0 | 03-12-21 A | 03-12-21 A
CDET2-4585 | GRP-2021-CDet2.42.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Wildemere 1 (Glynn & W Chicago) | 2 | 03-14-21 A | 03-31-21 A
SCDet-3105 | GRP-2021-SCDet1.15.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Hartwell (Joy & Tireman) | 106 | 03-15-21 A | 03-16-21 A
SCDet-5425 | GRP-2021-SCDet1.44.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Van Buren (Meadowdale & Schaefer) | 2 | 03-15-21 A | 03-15-21 A
CDET2-2265 | GRP-2021-CDet2.12.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Longfellow 1 (Dexter & Lawton) | 3 | 03-15-21 A | 03-15-21 A
CDET2-2425 | GRP-2021-CDet2.14.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Edison 1 (Dexter & Savery) | 8 | 03-15-21 A | 03-16-21 A
CDET2-2665 | GRP-2021-CDet2.17.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Atkinson 1 (Dexter & Savery) | 4 | 03-15-21 A | 03-15-21 A
CDET2-4745 | GRP-2021-CDet2.44.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Savery (Chicago & Joy) | 8 | 03-15-21 A | 03-16-21 A
CDET2-6170 | GRP-2021-CDet2.21.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Clairmount 2 (La Salle & Rosa Parks) | 43 | 03-15-21 A | 07-27-21 A
CDET2-10210 | GRP-2021-CDet2.21.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Clairmount 2 (Linwood & La Salle) | 13 | 03-15-21 A | 07-27-21 A
CDET-20330 | PROJ-0951-CDET1-2.17.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Dexter (1) (Collingwood & Leslie) | 7 | 03-15-21 A | 03-15-21 A
CDET2-2585 | GRP-2021-CDet2.16.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Wagner (Dexter & Savery) | 3 | 03-16-21 A | 03-22-21 A
AA4 20455 | GRP-2021-AA4.4.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Franklin Blvd (S 7th St & Hutchins Ave) | 1 | 03-17-21 A | 08-10-21 A
AA4 20841 | GRP-2021-AA4.50.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Sunnyside Blvd (EOM & S 7th St) | 26 | 03-18-21 A | 05-17-21 A
AA4 22838 | GRP-2021-AA4.1.4.2 | 2021 GRP - Ann Arbor 4 | Install Services - Hutchins Ave (Pauline Bvd & Potter Ave) | 1 | 03-19-21 A | 06-16-21 A
CDET2-8610 | GRP-2021-CDet2.5.2.2 | 2021 GRP - Central Detroit 2 | Install Services - W Boston Blvd 1 (Wildemere & EOM) | 3 | 03-19-21 A | 04-14-21 A
CDET2-2745 | GRP-2021-CDet2.18.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Atkinson 2 (Linwood & Rosa Parks) | 103 | 03-22-21 A | 05-19-21 A
CDET2-4105 | GRP-2021-CDet2.36.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Euclid 1 (Dexter & Linwood) | 29 | 03-22-21 A | 05-04-21 A
CDET2-4185 | GRP-2021-CDet2.37.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Euclid 2 (Linwood & 14th) | 24 | 03-22-21 A | 03-24-21 A
RR1 6681 | GRP-2021-RR.16.1.2 | 2021 GRP - Risk Rank | Install Services - Patton (Tireman & Sawyer) | 54 | 03-22-21 A | 03-31-21 A
RR1 7981 | GRP-2021-RR.34.1.2 | 2021 GRP - Risk Rank | Install Services - Appoline (Santa Clara & Mcnichols) | 46 | 03-22-21 A | 03-31-21 A
EDET1 506736 | GRP-2021-ED1.76.2.2 | 2021 GRP - East Detroit 1 | Install Services - Devonshire Rd (2) (Bremen St & Brunswick St) | 44 | 03-22-21 A | 03-24-21 A
CDET-1440 | PROJ-0951-CDET1-2.38.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Davison (1) (Livernois & Dexter) | 39 | 03-22-21 A | 08-16-21 A
CDET-14035 | PROJ-0951-CDET1-2.69.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Dexter (9) (Clarimount & Virgina Park) | 23 | 03-22-21 A | 2021-09-22
EDET1 50749 | GRP-2021-ED1.21.1.2 | 2021 GRP - East Detroit 1 | Install Services - Bishop St (1) (E Warrern Ave & Waveney St) | 1 | 03-22-21 A | 03-30-21 A
EDET1 501546 | GRP-2021-ED1.21.3.2 | 2021 GRP - East Detroit 1 | Install Services - Bishop St (1) (ASO E Warrern Ave & Waveney St) | 78 | 03-22-21 A | 03-24-21 A
SCDet-3185 | GRP-2021-SCDet1.16.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Bingham (Littlefield & Tireman) | 73 | 03-22-21 A | 03-28-21 A
EDET1 506576 | GRP-2021-ED1.76.3.2 | 2021 GRP - East Detroit 1 | Install Services - Devonshire Rd (2) (Brunswick St & Mack Ave) | 16 | 03-24-21 A | 03-24-21 A
EDET1 50763 | GRP-2021-ED1.36.1.2 | 2021 GRP - East Detroit 1 | Install Services - Yorkshire Rd (1) (E Warrern Ave & Waveney St) | 71 | 03-24-21 A | 03-31-21 A
CDET2-10930 | GRP-2021-CDet2.37.3 | 2021 GRP - Central Detroit 2 | Install Services - Euclid (14th & Rosa Parks) | 6 | 03-24-21 A | 03-24-21 A
AA4 20832 | GRP-2021-AA4.41.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Manhattan Dr (Mt Vernon Ave& Mt Pleasant Dr) | 3 | 03-24-21 A | 04-23-21 A
EDET1 501220 | GRP-2021-ED1.78.1.2 | 2021 GRP - East Detroit 1 | Install Services - Haverhill St (2) (Waveney St& ANO Mack Ave) | 73 | 03-25-21 A | 04-27-21 A
AA4 20460 | GRP-2021-AA4.6.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 7th St (12' SNPL W Madison St & 6' NNPL Pauline Blvd) | 49 | 03-25-21 A | 04-19-21 A
NWDET-13730 | PROJ-0951-NWDET1CO.13.4.2 | 2021 GRP - North West Detroit 1b | Install Services - Westwood (1) (Glendale & EOM) | 5 | 03-26-21 A | 03-29-21 A
SCDet-4065 | GRP-2021-SCDet1.4.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Freda (Esper & Tireman) | 75 | 03-29-21 A | 04-07-21 A
SCDet-4305 | GRP-2021-SCDet1.30.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Kentucky (Joy & Tireman) | 105 | 03-29-21 A | 03-30-21 A
SCDet-4945 | GRP-2021-SCDet1.38.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Steel (Tireman & Oakman) | 16 | 03-29-21 A | 03-30-21 A
EDET1 50747 | GRP-2021-ED1.19.1.2 | 2021 GRP - East Detroit 1 | Install Services - Audubon Rd (2) (E Warrern Ave & Waveney St) | 64 | 03-29-21 A | 05-03-21 A
SCDet-6500 | GRP-2021-SCDet1.8.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Esper (Manor & Mendota) | 6 | 03-29-21 A | 03-30-21 A
SCDet-6660 | GRP-2021-SCDet1.8.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Esper (Mendota & Joy) | 52 | 03-29-21 A | 03-30-21 A
RR1 7581 | GRP-2021-RR.29.1.2 | 2021 GRP - Risk Rank | Install Services - Fielding (McNichols & Grand River) | 50 | 03-29-21 A | 04-27-21 A
CDET-1800 | PROJ-0951-CDET1-2.19.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - Dexter (3) (Davison & Doris) | 9 | 03-29-21 A | 03-30-21 A
Muni1230 | PROJ-0951-MUN-3.27.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - Linwood (Davison & Doris) | 6 | 03-29-21 A | 2021-09-20
AA4 28658 | GRP-2021-AA4.2.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Pauline Blvd (S 7th St & Hutchinst) | 7 | 03-29-21 A | 06-15-21 A
AP 5180 | PROJ-0951-MMOAllen.82.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Sterling (Moore & Pennsylvania) | 42 | 03-30-21 A | 03-30-21 A
AP 5030 | PROJ-0951-MMOAllen.79.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Ruth 2 (200' South Moore & Midway Ave) | 39 | 03-30-21 A | 2021-10-20
AP 2020 | PROJ-0951-MMOAllen.22.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Chatham (Wick & 420' South Of Maylawn Ave) | 37 | 03-30-21 A | 04-06-21 A
AP 2320 | PROJ-0951-MMOAllen.37.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Hubert 2 (Moore & Conrail Rr) | 27 | 03-30-21 A | 2021-10-12
CDET2-11020 | GRP-2021-CDet2.19.1.2 | 2021 GRP - Central Detroit 2 | Install Services - ANO Joy (Savery & Savery) | 1 | 03-31-21 A | 03-31-21 A
EDET1 501218 | GRP-2021-ED1.76.1.2 | 2021 GRP - East Detroit 1 | Install Services - Devonshire Rd (2) (Waveney Ave & Bremen St) | 26 | 03-31-21 A | 03-31-21 A
AA4 20843 | GRP-2021-AA4.52.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Madison St (Soule Blvd & Eberwhite Blvd) | 13 | 04-01-21 A | 04-01-21 A
CDET2-8530 | GRP-2021-CDet2.50.3.2 | 2021 GRP - Central Detroit 2 | Install Services - LaSalle 1 (Gladstone & W Euclid) | 30 | 04-04-21 A | 04-08-21 A
SCDet-2065 | GRP-2021-SCDet1.1.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Oakman Blvd W 3 (Joy & Birwood) | 9 | 04-05-21 A | 04-13-21 A
SCDet-2145 | GRP-2021-SCDet1.2.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Oakman Blvd N 2 (Steel & Birwood) | 15 | 04-05-21 A | 04-13-21 A
EDET1 50751 | GRP-2021-ED1.24.1.2 | 2021 GRP - East Detroit 1 | Install Services - Courville St (1) (E Warrern Ave & Waveney St) | 59 | 04-05-21 A | 06-15-21 A
SCDet-8470 | GRP-2021-SCDet1.29.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Wyoming Ave West (Joy & Tireman) | 51 | 04-05-21 A | 05-05-21 A
CDET-21080 | PROJ-0951-CDET1-2.28.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - AWO Linwood (1) (Cortland & Collingwood) | 4 | 04-05-21 A | 04-05-21 A
AA4 22758 | GRP-2021-AA4.1.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - Hutchins Ave (W Davis St & Pauline Blvd) | 17 | 04-06-21 A | 04-20-21 A
Ypsi 3-10330 | PROJ-0951-YSP3.34.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Olds (Hudson & Desoto) | 0 | 04-06-21 A | 2021-09-23
AP 2420 | PROJ-0951-MMOAllen.42.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Laurence 2 (Moore & Pennsylvania) | 22 | 04-06-21 A | 04-27-21 A
AP 1940 | PROJ-0951-MMOAllen.18.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Carter 2 (550' North Moore Ave & Midway) | 36 | 04-06-21 A | 2021-10-07
Ypsi 3-10580 | PROJ-0951-YSP3.35.2.2 | 2021 GRP - Ypsilanti 3 | Install Services - Hudson (Ecorse & Olds) | 4 | 04-07-21 A | 06-16-21 A
AA4 29038 | GRP-2021-AA4.52.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Madison St (6' WEPL Eberwhite Blvd & Madison Pl) | 1 | 04-08-21 A | 04-08-21 A
AA4 20612 | GRP-2021-AA4.26.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Davis Ave (S 7th St & Hutchins) | 7 | 04-09-21 A | 04-09-21 A
CDET2-5225 | GRP-2021-CDet2.50.1.2 | 2021 GRP - Central Detroit 2 | Install Services - LaSalle 1 (Clairmount & Gladstone) | 27 | 04-11-21 A | 04-15-21 A
GP-7700 | PROJ-0951-GP 5 -3.131.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - Mack North 2 (Balfour & Cadieux)-GP4 | 10 | 04-12-21 A | 09-20-21 A
CDET2-6330 | GRP-2021-CDet2.24.57.2 | 2021 GRP - Central Detroit 2 | Install Services - Taylor 2 (Linwood & La Salle) | 13 | 04-12-21 A | 04-15-21 A
CDET2-6490 | GRP-2021-CDet2.26.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Hazelwood 2 (La Salle & Rosa Parks) | 50 | 04-12-21 A | 05-11-21 A
EDET1 503776 | GRP-2021-ED1.69.3.2 | 2021 GRP - East Detroit 1 | Install Services - Bedford St (1) (E Warren Ave & Waveney St) | 65 | 04-12-21 A | 05-19-21 A
CDET2-10850 | GRP-2021-CDet2.24.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Taylor 2 (La Salle & Rosa Parks) | 55 | 04-12-21 A | 05-11-21 A
Ypsi 3-5600 | PROJ-0951-YSP3.15.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Eugene (Tyler & 94 Service Drive) | 59 | 04-12-21 A | 2021-11-22
Ypsi 3-10930 | PROJ-0951-YSP3.37.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Nash 1 (Old Ecorse & Desoto) | 79 | 04-12-21 A | 08-26-21 A
SCDet-3025 | GRP-2021-SCDet1.14.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Schaefer Hwy W 1 (Joy & Tireman) | 30 | 04-12-21 A | 04-15-21 A
SCDet-3425 | GRP-2021-SCDet1.19.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Sorrento (Joy & Mackenzie) | 19 | 04-13-21 A | 04-20-21 A
Ypsi 3-4620 | PROJ-0951-YSP3.11.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Fox (94 Service Drive & Tyler) | 38 | 04-14-21 A | 2021-10-13
Ypsi 3-2890 | PROJ-0951-YSP3.41.3.2 | 2021 GRP - Ypsilanti 3 | Install Services - Desoto (Old Ecorse & Dodge) | 37 | 04-14-21 A | 06-16-21 A
CDET2-10010 | GRP-2021-CDet2.28.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Gladstone 2 (Linwood & Rosa Parks) | 79 | 04-15-21 A | 04-15-21 A
SCDet-2945 | GRP-2021-SCDet1.13.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Schaefer Hwy E 1 (Joy & Tireman) | 62 | 04-18-21 A | 04-25-21 A
CDET2-1045 | GRP-2021-CDet2.4.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Calvert 1 (Dexter & Linwood) | 85 | 04-18-21 A | 06-15-21 A
SCDet-2305 | GRP-2021-SCDet1.5.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Oakman Blvd E 3 (Joy & Birwood) | 15 | 04-19-21 A | 04-20-21 A
SCDet-3265 | GRP-2021-SCDet1.17.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Cheyenne (Joy & Littlefield) | 26 | 04-19-21 A | 05-06-21 A
SCDet-5665 | GRP-2021-SCDet1.47.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Tireman 1 (Decatur & Appoline) | 20 | 04-19-21 A | 04-20-21 A
SCDet-10330 | GRP-2021-SCDet1.3.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Oakman Blvd W 1 (Belton & Tireman) | 9 | 04-19-21 A | 04-20-21 A
SCDet-10920 | GRP-2021-SCDet1.19.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Sorrento (Mackenzie & Tireman) | 38 | 04-19-21 A | 04-20-21 A
Ypsi 3-12330 | PROJ-0951-YSP3.36.3.2 | 2021 GRP - Ypsilanti 3 | Install Services - Old Ecorse (Nash & Onandaga) | 1 | 04-19-21 A | 04-19-21 A
NCDET - 20455 | NEWPROJ-6.2.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Ardmore (Puritan & Fenkell) | 63 | 04-20-21 A | 04-26-21 A
AA4 22678 | GRP-2021-AA4.1.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Hutchins Ave (Princeton Ave & 23' NNPL W Davis Ave) | 29 | 04-22-21 A | 05-12-21 A
AA4 20834 | GRP-2021-AA4.43.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Mt Pleasant Ave (Mt Vernon Ave & Manhattan Dr) | 18 | 04-23-21 A | 04-28-21 A
SCDet-3585 | GRP-2021-SCDet1.21.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Meyers (Joy & Oakman) | 23 | 04-25-21 A | 04-29-21 A
CDET2-6850 | GRP-2021-CDet2.30.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Blaine 1 (Wildemere & Linwood) | 14 | 04-25-21 A | 05-06-21 A
CDET2-9640 | GRP-2021-CDet2.31.2.2 | 2021 GRP - Central Detroit 2 | Install Services - Blaine (Dexter & Wildemere) | 13 | 04-25-21 A | 05-04-21 A
SCDet-2225 | GRP-2021-SCDet1.3.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Oakman Blvd W 1 (Mackenzie & Belton) | 9 | 04-26-21 A | 04-27-21 A
SCDet-2385 | GRP-2021-SCDet1.6.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Oakman Blvd S 2 (Steel & Birwood) | 12 | 04-26-21 A | 04-27-21 A
SCDet-2465 | GRP-2021-SCDet1.7.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Oakman Blvd E 1 (Mackenzie & Tireman) | 13 | 04-26-21 A | 04-27-21 A
SCDet-2785 | GRP-2021-SCDet1.11.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Decatur (Belton & EOM) | 5 | 04-26-21 A | 04-26-21 A
EDET1 501132 | GRP-2021-ED1.56.1.2 | 2021 GRP - East Detroit 1 | Install Services - Chatsworth St (2) (Bremen St & Mack Ave) | 61 | 04-26-21 A | 06-15-21 A
EDET1 501138 | GRP-2021-ED1.62.1.2 | 2021 GRP - East Detroit 1 | Install Services - Somerset Ave (2) (Waveney St & Mack Ave) | 86 | 04-26-21 A | 05-19-21 A
EDET1 501214 | GRP-2021-ED1.72.1.2 | 2021 GRP - East Detroit 1 | Install Services - Berkshire St (2) (Bremen St & Mack Ave) | 65 | 04-26-21 A | 04-27-21 A
EDET1 501215 | GRP-2021-ED1.73.1.2 | 2021 GRP - East Detroit 1 | Install Services - Buckingham Ave (1) (E Warrern Ave & Waveney St) | 49 | 04-26-21 A | 08-18-21 A
SCDet-9030 | GRP-2021-SCDet1.17.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Cheyenne (Littlefield & Tireman) | 53 | 04-26-21 A | 04-29-21 A
CDET2-9000 | GRP-2021-CDet2.3.57.2 | 2021 GRP - Central Detroit 2 | Install Services - ANO Chicago (La Salle & Rosa Parks) | 24 | 04-26-21 A | 08-16-21 A
WCDET1-7300 | GRP-2021-WCDet1.35.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd East 2 (Davison & Cortland) | 15 | 04-26-21 A | 04-28-21 A
WCDET1-7780 | GRP-2021-WCDet1.15.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd 3 (American & Prairie) | 6 | 04-26-21 A | 04-26-21 A
RR1 8061 | GRP-2021-RR.35.1.2 | 2021 GRP - Risk Rank | Install Services - Stoepel (8 Mile & Pembroke) | 0 | 04-26-21 A | 05-19-21 A
EDET1 502246 | GRP-2021-ED1.67.2.2 | 2021 GRP - East Detroit 1 | Install Services - 3 Mile Rd (1) (E Warrern Ave & Waveney St) | 50 | 04-26-21 A | 04-27-21 A
EDET1 503926 | GRP-2021-ED1.75.3.2 | 2021 GRP - East Detroit 1 | Install Services - Devonshire Rd (1) (ASO E Warren Ave & Waveney Ave) | 72 | 04-26-21 A | 05-19-21 A
EDET1 507276 | GRP-2021-ED1.5.1.2 | 2021 GRP - East Detroit 1 | Install Services - Kensington Ave (ASO E Warren & Waveney) | 79 | 04-26-21 A | 04-27-21 A
RedfMMO3800 | PROJ-0951-MMORedford-1.30.1 | 2020 GRP - Carry Over - MMO 6382 Redford | MMO - Denby (Curtis & Vassar) | 75 | 04-26-21 A | 04-26-21 A
RedfMMO3860 | PROJ-0951-MMORedford-1.31.1 | 2020 GRP - Carry Over - MMO 6382 Redford | MMO - Fox (Pembroke & Grand River) | 19 | 04-26-21 A | 04-28-21 A
RedfMMO3960 | PROJ-0951-MMORedford-1.33.1 | 2020 GRP - Carry Over - MMO 6382 Redford | MMO - Indiana (7 Mile Rd & St Martins ave) | 53 | 04-26-21 A | 04-30-21 A
RedfMMO4160 | PROJ-0951-MMORedford-1.37.1 | 2020 GRP - Carry Over - MMO 6382 Redford | MMO - Poinnciana (7 Mile & Vassar) | 6 | 04-26-21 A | 04-26-21 A
CDET-1130 | PROJ-0951-CDET1-2.4.3.2 | 2020 GRP - Carry Over - Central Detroit 1 | Install Services - W Grand 2 (Dexter & Livernois) | 33 | 04-26-21 A | 04-29-21 A
GP-7895 | PROJ-0951-GP 5 -3.110.1.3 | 2020 GRP - Carry Over - GP 5 | Install Services - Westchester 1 (Essex & Fairfax) | 29 | 04-26-21 A | 04-30-21 A
NDET1-6810 | PROJ-0951-NDET1-1.16.1 | 2019 GRP - Carry Over - North Detroit 1 | Install Services - Outer Dr E (Rayalt & 7 Mile) | 15 | 04-26-21 A | 04-28-21 A
HMT 2-14750 | PROJ-0951-HMT-1.6.6.2 | 2019 GRP - Carry Over - Hamtramck 2 | Install Services - Caniff Ave (Nagel & Mackay) | 4 | 04-26-21 A | 04-27-21 A
Muni8210 | PROJ-0951-MUN-3.22.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - Lawton (Grand Blvd & EOM) | 1 | 04-26-21 A | 04-26-21 A
Muni8630 | PROJ-0951-MUN-3.39.1.2 | 2020 GRP - Carry Over - Municipality | Install Services - Lawton (Grand Blvd & EOM) | 3 | 04-26-21 A | 04-26-21 A
AP 5630 | PROJ-0951-MMOAllen.90.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Yost 2 (Vine & Joseph) | 5 | 04-27-21 A | 06-01-21 A
AP 2720 | PROJ-0951-MMOAllen.57.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Niver 1 (Englewood Ave & 100' North Moore) | 40 | 04-27-21 A | 06-01-21 A
AP 5580 | PROJ-0951-MMOAllen.89.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Yost 1 (Vine & Joseph) | 10 | 04-27-21 A | 06-01-21 A
AP 2180 | PROJ-0951-MMOAllen.30.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Fox 2 (Moore & Pennsylvania) | 28 | 04-27-21 A | 2021-10-29
AP 2340 | PROJ-0951-MMOAllen.38.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Joseph (N Yost Ave & S Yost Ave) | 13 | 04-27-21 A | 2021-10-19
AP 5230 | PROJ-0951-MMOAllen.83.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Vine 1 (Champaign & Englewood) | 6 | 04-27-21 A | 06-15-21 A
Ypsi 3-4370 | PROJ-0951-YSP3.10.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Calder (Tyler & 94 Service Drive) | 55 | 04-28-21 A | 2021-10-18
SCDet-8710 | GRP-2021-SCDet1.20.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Appoline (Oakman & Civic) | 47 | 05-03-21 A | 05-17-21 A
SCDet-9520 | GRP-2021-SCDet1.10.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Littlefield 2 (Oakman & Appoline) | 5 | 05-03-21 A | 05-10-21 A
SCDet-11080 | GRP-2021-SCDet1.18.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Ward (Mackenzie & Littlefield) | 8 | 05-03-21 A | 05-04-21 A
SCDet-11490 | GRP-2021-SCDet1.55.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Mackenzie 2 (Oakman Blvd & Morrow Circle) | 2 | 05-03-21 A | 05-03-21 A
CDET2-3705 | GRP-2021-CDet2.31.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Blaine 2 (Linwood & La Salle) | 16 | 05-03-21 A | 05-10-21 A
SCDet-10010 | GRP-2021-SCDet1.21.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Meyers (Oakman & Civic) | 59 | 05-03-21 A | 05-11-21 A
CDET2-6690 | GRP-2021-CDet2.31.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Blaine 2 (La Salle & Rosa Parks) | 18 | 05-03-21 A | 05-19-21 A
AA4 20824 | GRP-2021-AA4.11.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Crest Ave (W Liberty St & Luts Ave) | 22 | 05-07-21 A | 05-14-21 A
SCDet-2705 | GRP-2021-SCDet1.10.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Littlefield 2 (Belton & Oakman) | 3 | 05-10-21 A | 05-10-21 A
SCDet-3505 | GRP-2021-SCDet1.20.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Appoline (Joy & Oakman) | 18 | 05-10-21 A | 05-17-21 A
CDET2-3305 | GRP-2021-CDet2.26.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Hazelwood 2 (Linwood & La Salle) | 24 | 05-10-21 A | 05-19-21 A
SCDet-11320 | GRP-2021-SCDet1.20.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Appoline (Civic & Tireman) | 5 | 05-10-21 A | 05-10-21 A
Ypsi 3-5120 | PROJ-0951-YSP3.13.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Gates (94 Service Drive & Tyler) | 22 | 05-10-21 A | 05-19-21 A
AA4 29008 | GRP-2021-AA4.6.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 7th St (Jefferson Ct & W Madison St) | 4 | 05-10-21 A | 05-19-21 A
SCDet-5905 | GRP-2021-SCDet1.50.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Civic (Appoline & Manor) | 1 | 05-10-21 A | 05-10-21 A
NDET3-3855 | GRP-2021-ND3.61.1.2 | 2021 GRP - North Detroit 3 | Install Services - Sunset St (1) (8 Mile Rd (M102) & E Outer Dr) | 47 | 05-11-21 A | 05-11-21 A
Ypsi 3-10080 | PROJ-0951-YSP3.33.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Dodge (Desoto & Nash) | 4 | 05-11-21 A | 05-24-21 A
SCDet-7500 | GRP-2021-SCDet1.26.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Middlepointe (Esper & Tireman) | 1 | 05-11-21 A | 05-17-21 A
CDET2-3145 | GRP-2021-CDet2.3.6.2 | 2021 GRP - Central Detroit 2 | Install Services - ANO Chicago (Linwood & La Salle) | 51 | 05-12-21 A | 05-18-21 A
EDET1 50959 | GRP-2021-ED1.48.1.2 | 2021 GRP - East Detroit 1 | Install Services - Wayburn Ave (2) (Waveney St & Mack Ave) | 63 | 05-12-21 A | 05-19-21 A
Ypsi 3-11460 | PROJ-0951-YSP3.41.2.2 | 2021 GRP - Ypsilanti 3 | Install Services - Desoto (Tyler & Nash) | 45 | 05-12-21 A | 09-17-21 A
Ypsi 3-4870 | PROJ-0951-YSP3.12.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Dorset (Tyler & 94 Service Drive) | 26 | 05-12-21 A | 2021-12-10
SCDet-3825 | GRP-2021-SCDet1.25.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Mendota (Esper & Tireman) | 22 | 05-14-21 A | 05-18-21 A
SCDet-7330 | GRP-2021-SCDet1.25.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Mendota (Oakman & Esper) | 25 | 05-14-21 A | 05-19-21 A
AA4 25118 | GRP-2021-AA4.22.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Princeton Ave (S 7th St & 5th St) | 11 | 05-14-21 A | 06-14-21 A
SCDet-5105 | GRP-2021-SCDet1.40.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Griggs (Joy & Oakman) | 4 | 05-17-21 A | 05-17-21 A
SWDET2-2760 | PROJ-0951-SWDET2.14.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Central 2 (NO Dix & Dix) | 8 | 05-17-21 A | 08-03-21 A
SWDET2-2840 | PROJ-0951-SWDET2.15.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Dix 3 (Woodmere & Casper) | 7 | 05-17-21 A | 06-01-21 A
CDET2-8770 | GRP-2021-CDet2.1.1.2 | 2021 GRP - Central Detroit 2 | Install Services - ASO Chicago (14th & Rosa Parks) | 27 | 05-17-21 A | 05-18-21 A
NDET3-3690 | GRP-2021-ND3.55.1.2 | 2021 GRP - North Detroit 3 | Install Services - Dean Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 98 | 05-17-21 A | 05-26-21 A
SCDet-6145 | GRP-2021-SCDet1.53.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Westover (Mendota & Middlepointe) | 8 | 05-17-21 A | 05-18-21 A
Ypsi 3-4120 | PROJ-0951-YSP3.9.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Onandaga (Old Ecorse & Oswego) | 37 | 05-17-21 A | 2021-10-29
RR1 7741 | GRP-2021-RR.31.1.2 | 2021 GRP - Risk Rank | Install Services - Whitney (Grand River & Dexter) | 0 | 05-17-21 A | 05-18-21 A
GP-7210 | PROJ-0951-GP 5 -3.8.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - Alter 3 (Jefferson & Hampton) | 4 | 05-17-21 A | 05-19-21 A
RR1 7161 | GRP-2021-RR.24.1.2 | 2021 GRP - Risk Rank | Install Services - Spokane (Beechwood & Colfax) | 44 | 05-19-21 A | 05-26-21 A
EDET1 50756 | GRP-2021-ED1.29.1.2 | 2021 GRP - East Detroit 1 | Install Services - Haverhill St (1) (E Warrern Ave & Waveney St) | 61 | 05-23-21 A | 05-23-21 A
EDET1 501213 | GRP-2021-ED1.71.1.2 | 2021 GRP - East Detroit 1 | Install Services - Berkshire St (1) (ASO E Warrern Ave & Waveney St) | 63 | 05-23-21 A | 05-23-21 A
NCDET - 22765 | NEWPROJ-6.6.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Hartwell (Puritan & Fenkell) | 86 | 05-24-21 A | 05-25-21 A
SWDET2-6200 | PROJ-0951-SWDET2.58.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Lonyo 1 (EOM & Dix) | 2 | 05-24-21 A | 05-31-21 A
AA4 28738 | GRP-2021-AA4.2.15.2 | 2021 GRP - Ann Arbor 4 | Install Services - Pauline Blvd (Hutchins & S Main Stt) | 31 | 05-24-21 A | 08-10-21 A
AP 5480 | PROJ-0951-MMOAllen.87.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Wick 1 (Pelham & Becker) | 34 | 05-25-21 A | 2021-10-21
AP 5530 | PROJ-0951-MMOAllen.88.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Wick 2 (Pelham & Vine) | 46 | 05-25-21 A | 2021-11-15
AP 5330 | PROJ-0951-MMOAllen.85.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Vine 3 (Moore & Conrail Rr) | 13 | 05-25-21 A | 2021-11-03
AP 5430 | PROJ-0951-MMOAllen.86.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Vine 4 (Vine Ave & 146' East Of Vine Ave) | 10 | 05-25-21 A | 06-01-21 A
AP 4880 | PROJ-0951-MMOAllen.77.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Rosedale 3 (Moore & Conrail Rr) | 45 | 05-25-21 A | 08-16-21 A
AP 4280 | PROJ-0951-MMOAllen.65.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Pennsylvania (Colwell & Fox) | 17 | 05-25-21 A | 08-16-21 A
AP 2140 | PROJ-0951-MMOAllen.28.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Englewood 3 (200' East Of Fox Ave & Vine) | 8 | 05-25-21 A | 2021-11-17
AP 2300 | PROJ-0951-MMOAllen.36.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Hubert 1 (Englewood & Moore Ave) | 27 | 05-25-21 A | 2021-10-29
AA4 21628 | GRP-2021-AA4.13.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - 5th St (W Davis Ave & Pauline Blvd) | 13 | 05-26-21 A | 05-26-21 A
NDET3-7290 | GRP-2021-ND3.40.1.2 | 2021 GRP - North Detroit 3 | Install Services - Ryan Rd (1) (8 Mile Rd (M102) & E Outer Dr) | 72 | 05-26-21 A | 05-26-21 A
Ypsi 3-3870 | PROJ-0951-YSP3.8.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Oswego (Onandaga & Eugene) | 31 | 05-27-21 A | 2021-10-05
SWDET2-1880 | PROJ-0951-SWDET2.2.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Dix 2 (Lonyo & Woodmere) | 0 | 05-31-21 A | 05-31-21 A
SWDET2-3080 | PROJ-0951-SWDET2.18.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 1 (At Dix) | 0 | 05-31-21 A | 06-21-21 A
SWDET2-3160 | PROJ-0951-SWDET2.19.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 2 (Richard & EO Oakdale) | 15 | 05-31-21 A | 06-15-21 A
SWDET2-3880 | PROJ-0951-SWDET2.29.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Richard (EOM & Woodmere) | 2 | 05-31-21 A | 06-07-21 A
SWDET2-4040 | PROJ-0951-SWDET2.31.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 3 (Richard & ANO W Vernor) | 13 | 05-31-21 A | 06-09-21 A
SWDET2-7880 | PROJ-0951-SWDET2.78.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Sharon (NO Woodmere & Woodmere) | 11 | 05-31-21 A | 06-08-21 A
SWDET2-8505 | PROJ-0951-SWDET2.2.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Dix 2 (EOM & Lonyo) | 1 | 05-31-21 A | 05-31-21 A
SWDET2-12335 | PROJ-0951-SWDET2.18.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 1 (Wendall & WO Cabot) | 16 | 05-31-21 A | 06-21-21 A
SWDET2-12495 | PROJ-0951-SWDET2.18.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 1 (Dix & Pearl) | 9 | 05-31-21 A | 06-21-21 A
SWDET2-12655 | PROJ-0951-SWDET2.18.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 1 (Wendall & Pearl) | 0 | 05-31-21 A | 06-21-21 A
SWDET2-12815 | PROJ-0951-SWDET2.31.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 3 (ANO W Vernor & W Vernor) | 0 | 05-31-21 A | 06-07-21 A
SWDET2-12975 | PROJ-0951-SWDET2.31.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 3 (W Vernor & ASO Vernor) | 0 | 05-31-21 A | 06-07-21 A
SWDET2-13135 | PROJ-0951-SWDET2.31.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 3 (ASO Vernor & Elsmere) | 9 | 05-31-21 A | 06-15-21 A
SWDET2-16985 | PROJ-0951-SWDET2.78.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Sharon (Woodmere & ANO W Vernor) | 26 | 05-31-21 A | 06-10-21 A
RR1 7241 | GRP-2021-RR.25.1.2 | 2021 GRP - Risk Rank | Install Services - Irvington (State Fair & 7 Mile) | 13 | 05-31-21 A | 06-02-21 A
Ypsi 3-7100 | PROJ-0951-YSP3.21.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Eileen (Tyler & Chevrolet) | 28 | 06-01-21 A | 2021-10-04
Ypsi 3-3620 | PROJ-0951-YSP3.7.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Cayuga (Eugene & Onandaga) | 13 | 06-02-21 A | 06-22-21 A
RR1 7401 | GRP-2021-RR.27.1.2 | 2021 GRP - Risk Rank | Install Services - Burt (Westfield & Joy) East | 29 | 06-02-21 A | 06-23-21 A
RR1 10171 | GRP-2021-RR.27.2.2 | 2021 GRP - Risk Rank | Install Services - Burt (Westfield & Joy) West | 33 | 06-02-21 A | 06-23-21 A
AP 2040 | PROJ-0951-MMOAllen.23.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Cowell (Moore & Pennsylvania Ave) | 56 | 06-03-21 A | 06-15-21 A
AA4 28888 | GRP-2021-AA4.26.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Davis Ave (Hutchins & 5th) | 6 | 06-03-21 A | 06-03-21 A
EDET1 50951 | GRP-2021-ED1.40.1.2 | 2021 GRP - East Detroit 1 | Install Services - Lakepointe Sr (2) (Waveney St & Mack Ave) | 41 | 06-07-21 A | 06-08-21 A
EDET1 50952 | GRP-2021-ED1.41.1.2 | 2021 GRP - East Detroit 1 | Install Services - Lakepointe St (1) (E Warrern Ave & Waveney St) | 32 | 06-07-21 A | 06-08-21 A
EDET1 50955 | GRP-2021-ED1.44.1.2 | 2021 GRP - East Detroit 1 | Install Services - Maryland St (2) (Waveney St & Mack Ave) | 59 | 06-07-21 A | 06-18-21 A
EDET1 501127 | GRP-2021-ED1.51.1.2 | 2021 GRP - East Detroit 1 | Install Services - Beaconsfield St (1) (E Warrern Ave & Waveney St) | 0 | 06-07-21 A | 07-20-21 A
CDET2-9320 | GRP-2021-CDet2.1.2.2 | 2021 GRP - Central Detroit 2 | Install Services - ASO Chicago (Linwood & 14th) | 53 | 06-07-21 A | 06-08-21 A
EDET1 503446 | GRP-2021-ED1.11.4.2 | 2021 GRP - East Detroit 1 | Install Services - ASO E Warren Ave (3) (Harvard Rd & Cadieux Rd) | 3 | 06-07-21 A | 2021-09-20
EDET1 504486 | GRP-2021-ED1.16.4.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (1) (Balfour Rd & Balfour Rd) | 0 | 06-07-21 A | 2021-09-20
Ypsi 3-11920 | PROJ-0951-YSP3.39.2.2 | 2021 GRP - Ypsilanti 3 | Install Services - Tyler (EOM & Desoto) | 33 | 06-08-21 A | 2021-10-08
AP 1960 | PROJ-0951-MMOAllen.19.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Champaign 1 (Pelham & Allen) | 30 | 06-09-21 A | 06-15-21 A
AA4 22028 | GRP-2021-AA4.17.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Edgewood Pl (W Davis Ave & EOM) | 9 | 06-09-21 A | 06-17-21 A
SCDet-8140 | GRP-2021-SCDet1.24.3.2 | 2021 GRP - South Central Detroit 1 | Install Service - Pinehurst (Oakman & Esper) | 32 | 06-10-21 A | 06-15-21 A
AP 2120 | PROJ-0951-MMOAllen.27.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Englewood 2 (Allen & 200' East Of Fox Ave) | 29 | 06-10-21 A | 06-15-21 A
SCDet-3665 | GRP-2021-SCDet1.22.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Manor (Esper & Tireman) | 19 | 06-11-21 A | 06-15-21 A
SCDet-3745 | GRP-2021-SCDet1.24.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Pinehurst (Joy & Oakman) | 22 | 06-11-21 A | 06-15-21 A
SCDet-5025 | GRP-2021-SCDet1.39.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Birwood (Joy & Oakman) | 17 | 06-11-21 A | 06-15-21 A
SCDet-6820 | GRP-2021-SCDet1.22.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Manor West (Oakman & Civic) | 20 | 06-11-21 A | 06-15-21 A
SCDet-6900 | GRP-2021-SCDet1.22.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Manor East (Oakman & Belton) | 22 | 06-11-21 A | 06-15-21 A
SCDet-7250 | GRP-2021-SCDet1.25.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Mendota (Joy & Oakman) | 20 | 06-11-21 A | 06-15-21 A
AP 1920 | PROJ-0951-MMOAllen.17.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Carter 1 (Englewood & 550' North Moore) | 22 | 06-11-21 A | 06-15-21 A
AP 4930 | PROJ-0951-MMOAllen.78.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Ruth 1 (Englewood & 200' South Moore Ave) | 24 | 06-11-21 A | 06-15-21 A
AP 5280 | PROJ-0951-MMOAllen.84.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Vine 2 (Wick & Moore) | 17 | 06-11-21 A | 06-15-21 A
SCDet-6980 | GRP-2021-SCDet1.22.4.2 | 2021 GRP - South Central Detroit 1 | Install Services - Manor West (Joy & Oakman) | 15 | 06-14-21 A | 06-15-21 A
SCDet-7060 | GRP-2021-SCDet1.22.5.2 | 2021 GRP - South Central Detroit 1 | Install Services - Manor East (Joy & Oakman) | 13 | 06-14-21 A | 06-15-21 A
AP 1740 | PROJ-0951-MMOAllen.8.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Balfour 2 (Midway & Northway) | 8 | 06-14-21 A | 06-15-21 A
AP 2240 | PROJ-0951-MMOAllen.33.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Helen (559' West Of Louise Ave & Louise Ave) | 12 | 06-14-21 A | 06-15-21 A
AP 2600 | PROJ-0951-MMOAllen.51.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Melbourne 2 (Chatham & Moore) | 14 | 06-14-21 A | 06-15-21 A
RR1 51718 | GRP-2021-RR1.105.1.2 | 2021 GRP - River Rouge | MMO - E Josephine (W Jefferson & EOM) | 14 | 06-14-21 A | 06-15-21 A
EDET1 50949 | GRP-2021-ED1.38.1.2 | 2021 GRP - East Detroit 1 | Install Services - Barham St (1) (E Warrern Ave & Waveney St) | 5 | 06-14-21 A | 06-14-21 A
EDET1 50950 | GRP-2021-ED1.39.1.2 | 2021 GRP - East Detroit 1 | Install Services - Barham St (2) (Waveney St & Mack Ave) | 0 | 06-14-21 A | 06-14-21 A
EDET1 50954 | GRP-2021-ED1.43.1.2 | 2021 GRP - East Detroit 1 | Install Services - Maryland St (1) (E Warrern Ave & Waveney St) | 21 | 06-14-21 A | 06-17-21 A
EDET1 501137 | GRP-2021-ED1.61.1.2 | 2021 GRP - East Detroit 1 | Install Services - Somerset Ave (1) (E Warrern Ave & Waveney St) | 33 | 06-14-21 A | 07-20-21 A
SCDet-8300 | GRP-2021-SCDet1.24.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Pinehurst (Esper & Tireman) | 15 | 06-14-21 A | 06-15-21 A
RR1 63090 | GRP-2021-RR1.14.1.2 | 2021 GRP - River Rouge | MMO - Charles (19' NSPL W Pleasant St & 8' NSPL W Pleasant St) | 2 | 06-14-21 A | 06-15-21 A
GP-7610 | PROJ-0951-GP 5 -3.64.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - Kercheval (Balfour & Alter) | 7 | 06-14-21 A | 06-15-21 A
GP-7235 | PROJ-0951-GP 5 -3.114.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - ASO Kercheval (Balfour & Alter) | 15 | 06-14-21 A | 06-15-21 A
Ypsi 3-12340 | PROJ-0951-YSP3.14.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - 94 Service Drive (Eugene & Gates) | 1 | 06-14-21 A | 06-16-21 A
AA4 20604 | GRP-2021-AA4.17.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Edgewood Pl (W Hoover Ave & W Davis Ave) | 10 | 06-14-21 A | 06-14-21 A
AA4 20613 | GRP-2021-AA4.27.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Hoover Ave (5th St & S Main St) | 34 | 06-14-21 A | 07-16-21 A
SCDet-5585 | GRP-2021-SCDet1.46.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Belton 2 (Mendota & Middlepointe) | 5 | 06-15-21 A | 06-15-21 A
SCDet-5985 | GRP-2021-SCDet1.51.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Blowers (Mendota & Middlepointe) | 6 | 06-15-21 A | 06-15-21 A
AA4 28988 | GRP-2021-AA4.36.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Eberwhite Blvd West (W Liberty & Lutz) | 1 | 06-15-21 A | 06-16-21 A
RR1 51561 | GRP-2021-RR1.98.1.2 | 2021 GRP - River Rouge | MMO - W Josephine St (EOM & W Jefferson) | 1 | 06-15-21 A | 06-15-21 A
Ypsi 3-3010 | PROJ-0951-YSP3.37.2.2 | 2021 GRP - Ypsilanti 3 | Install Services - Nash 1 (Desoto & Tyler) | 0 | 06-16-21 A | 06-16-21 A
Ypsi 3-12190 | PROJ-0951-YSP3.44.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Beverly St (Coolidge & State) | 0 | 06-16-21 A | 06-16-21 A
AA4 28948 | GRP-2021-AA4.26.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Davis Ave (5th & Main) | 32 | 06-17-21 A | 07-08-21 A
SCDet-3345 | GRP-2021-SCDet1.18.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Ward (Joy & Mackenzie) | 25 | 06-18-21 A | 06-21-21 A
SCDet-3985 | GRP-2021-SCDet1.27.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Morrow (Esper & Tireman) | 60 | 06-18-21 A | 06-21-21 A
SCDet-4225 | GRP-2021-SCDet1.29.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Wyoming Ave East (Joy & Tireman) | 36 | 06-18-21 A | 06-21-21 A
SCDet-5745 | GRP-2021-SCDet1.48.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Tireman 2 (Manor & Wisconsin) | 30 | 06-18-21 A | 06-21-21 A
RR1 51556 | GRP-2021-RR1.93.1.2 | 2021 GRP - River Rouge | Install Services - Sunnyside St (Salliotte Rd & 157' SSPL Salliotte Rd) | 5 | 06-18-21 A | 08-30-21 A
EDET1 501129 | GRP-2021-ED1.53.1.2 | 2021 GRP - East Detroit 1 | Install Services - Bremen St (2) (Balfour Rd & Buckingham Ave) | 1 | 06-18-21 A | 06-21-21 A
EDET1 501216 | GRP-2021-ED1.74.1.2 | 2021 GRP - East Detroit 1 | Install Services - Buckingham Ave (2) (Waveney St & Mack Ave) | 80 | 06-18-21 A | 06-21-21 A
SWDET2-3240 | PROJ-0951-SWDET2.20.1.2 | 2021 GRP - South West Detroit 2 | Install Services - AEO Distel (Olivet & EOM) | 4 | 06-18-21 A | 06-21-21 A
SCDet-6290 | GRP-2021-SCDet1.43.3.2 | 2021 GRP - South Central Detroit 1 | Install Services - Joy 3 (Ohio & Greenlawn) | 2 | 06-18-21 A | 06-21-21 A
SCDet-5345 | GRP-2021-SCDet1.43.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Joy 3 (Wyoming & Ohio) | 4 | 06-18-21 A | 06-21-21 A
SCDet-5265 | GRP-2021-SCDet1.42.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Joy 2 (Manor & Wyoming) | 7 | 06-18-21 A | 06-21-21 A
SCDet-5185 | GRP-2021-SCDet1.41.1.2 | 2021 GRP - South Central Detroit 1 | Install Services - Joy 1 (Schaefer & Manor) | 5 | 06-18-21 A | 06-21-21 A
SCDet-11240 | GRP-2021-SCDet1.18.2.2 | 2021 GRP - South Central Detroit 1 | Install Services - Ward (Littlefield & Tireman) | 46 | 06-18-21 A | 06-29-21 A
RR1 57470 | GRP-2021-RR1.83.3.2 | 2021 GRP - River Rouge | Install Services - High St 2 (Cicotte St & Southfield Rd) | 11 | 06-18-21 A | 08-16-21 A
RR1 59110 | GRP-2021-RR1.92.4.2 | 2021 GRP - River Rouge | Install Services - Salliotte St (5' EEPL High St & W Jefferson Ave) | 21 | 06-18-21 A | 08-16-21 A
NDET3-4220 | GRP-2021-ND3.63.1.2 | 2021 GRP - North Detroit 3 | Install Services - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 87 | 06-18-21 A | 06-21-21 A
EDET1 508166 | GRP-2021-ED1.7.1.2 | 2021 GRP - East Detroit 1 | Install Services - ANO Mack Ave 2 (Courville & Courville) | 1 | 06-18-21 A | 06-21-21 A
EDET1 508486 | GRP-2021-ED1.8.3.2 | 2021 GRP - East Detroit 1 | Install Services - ANO Mack Ave (3) (Yorkshire & Yorkshire) | 0 | 06-18-21 A | 06-21-21 A
GP-7695 | PROJ-0951-GP 5 -3.132.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - Mack North 1 (Balfour & Cadieux)-GP4 | 9 | 06-21-21 A | 09-20-21 A
CDET2-7870 | GRP-2021-CDet2.48.2.2 | 2021 GRP - Central Detroit 2 | Install Services - Linwood 1 (Longfellow & Atkinson) | 0 | 06-21-21 A | 06-21-21 A
CDET2-8030 | GRP-2021-CDet2.49.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Linwood 2 (Gladstone & Carter) | 0 | 06-21-21 A | 06-21-21 A
RR1 58950 | GRP-2021-RR1.92.3.2 | 2021 GRP - River Rouge | Install Services - Salliotte St (96' WWPL Drennan St & High St) | 3 | 06-21-21 A | 08-16-21 A
RR1 59030 | GRP-2021-RR1.92.2.2 | 2021 GRP - River Rouge | Install Services - Salliotte St (141' WWPL High St & 1' WWPL High St) | 2 | 06-21-21 A | 08-16-21 A
RR1 61620 | GRP-2021-RR1.10.3.2 | 2021 GRP - River Rouge | Install Services - Outer Dr (High St & 252' EEPL High St) | 6 | 06-21-21 A | 06-21-21 A
GP-42530 | PROJ-0951-GP 5 -3.133.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - Mack South (Alter & Balfour) | 20 | 06-21-21 A | 09-20-21 A
GP-46920 | PROJ-0951-GP 5 -3.7.1.2 | 2020 GRP - Carry Over - GP 5 | Install Services - Alter (Klenk & Detroit City Limit) | 1 | 06-21-21 A | 06-21-21 A
Ypsi 3-11440 | PROJ-0951-YSP3.1.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Carol Ann (Eileen & Mary Catherine) | 20 | 06-21-21 A | 06-22-21 A
AA4 20844 | GRP-2021-AA4.54.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Wakefield Ave (Hutchins & Prescott) | 7 | 06-21-21 A | 06-21-21 A
AA4 20840 | GRP-2021-AA4.49.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Soule Blvd (4' SSPL W Liberty St & 19' NNPL Lutz Ave) | 19 | 06-21-21 A | 07-09-21 A
EDET1 504166 | GRP-2021-ED1.2.3.2 | 2021 GRP - East Detroit 1 | Install Services - E Outer Dr (W) (ASO E Warren Ave & Waveney Ave) | 28 | 06-22-21 A | 07-15-21 A
AA4 20617 | GRP-2021-AA4.31.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Wilder Pl (W Davis Ave & W Hoover Ave) | 16 | 06-23-21 A | 07-06-21 A
Ypsi 3-12700 | PROJ-0951-YSP3.9.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Onandaga (Eugene & Oswego) | 8 | 06-24-21 A | 08-23-21 A
NDET3-5750 | GRP-2021-ND3.45.3.2 | 2021 GRP - North Detroit 3 | Install Services - 8 Mile Rd (Dwyer St & Elliot St) | 2 | 06-24-21 A | 08-31-21 A
RR1 10711 | GRP-2021-RR.37.2.2 | 2021 GRP - Risk Rank | Install Services - Varjo (Cliff & Van Dyke) | 4 | 06-28-21 A | 08-16-21 A
Ypsi 3-7340 | PROJ-0951-YSP3.22.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Mary Catherine (Woodglen & Eileen) | 47 | 07-01-21 A | 2021-10-14
AA4 20833 | GRP-2021-AA4.42.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Maxwell Ave (EOM & Soule Blvd) | 7 | 07-01-21 A | 07-01-21 A
RR1 6601 | GRP-2021-RR.50.1.2 | 2021 GRP - Risk Rank | Install Services - Rademacher (Lafayette & 157' SSPL Lafayette) | 6 | 07-05-21 A | 08-18-21 A
RR1 6281 | GRP-2021-RR.13.1.2 | 2021 GRP - Risk Rank | Install Services - Lafayette (Rademacher & Campbell) | 13 | 07-06-21 A | 08-12-21 A
Ypsi 3-6850 | PROJ-0951-YSP3.20.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Chevrolet (Tyler & Desoto) | 3 | 07-06-21 A | 09-20-21 A
NDET3-6640 | GRP-2021-ND3.51.1.2 | 2021 GRP - North Detroit 3 | Install Services - Caldwell St (1) (8 Mile Rd (M102) & Hamlet St) | 3 | 07-06-21 A | 07-06-21 A
NDET3-6840 | GRP-2021-ND3.51.3.2 | 2021 GRP - North Detroit 3 | Install Services - Caldwell St (1) (Hamlet St & Amrad St) | 11 | 07-06-21 A | 07-07-21 A
Ypsi 3-6600 | PROJ-0951-YSP3.19.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Lori (Mary Catherine & Tyler) | 31 | 07-06-21 A | 2021-10-05
NCDET - 23455 | NEWPROJ-6.7.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Littlefield (Puritan & Fenkell) | 0 | 07-07-21 A | 07-20-21 A
RR1 5801 | GRP-2021-RR.5.1.2 | 2021 GRP - Risk Rank | Install Services - Bringard (Reno & Regent) | 82 | 07-07-21 A | 07-20-21 A
NDET3-7475 | GRP-2021-ND3.80.1.2 | 2021 GRP - North Detroit 3 | Install Services - Norwood St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 07-08-21 A | 07-20-21 A
NDET3-7280 | GRP-2021-ND3.84.1.2 | 2021 GRP - North Detroit 3 | Install Services - Wexford (1) (8 Mile Rd & E Outer Dr) | 0 | 07-08-21 A | 07-20-21 A
CDET2-3545 | GRP-2021-CDet2.29.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Carter (Dexter & Linwood) | 0 | 07-09-21 A | 07-20-21 A
EDET1 501125 | GRP-2021-ED1.49.1.4 | 2021 GRP - East Detroit 1 | Install Services - Balfour Rd (ASO E Warren Ave & Waveney Ave) | 0 | 07-09-21 A | 07-20-21 A
RR1 8541 | GRP-2021-RR.41.1.2 | 2021 GRP - Risk Rank | Install Services - 8th (Southfield & W Outer) | 64 | 07-12-21 A | 07-20-21 A
RR1 8621 | GRP-2021-RR.42.1.2 | 2021 GRP - Risk Rank | Install Services - Coram (Gratiot & Hayes) | 65 | 07-12-21 A | 07-20-21 A
NDET3-555 | GRP-2021-ND3.86.1.2 | 2021 GRP - North Detroit 3 | Install Services - Yonka (1) (8 Mile Rd (M102) & E Remington Ave) | 0 | 07-12-21 A | 07-20-21 A
Ypsi 3-6350 | PROJ-0951-YSP3.18.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Zephyr (Tyler & Chevrolet) | 33 | 07-12-21 A | 2021-10-04
SWDET2-4360 | PROJ-0951-SWDET2.35.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Lafayette (Woodmere & Lawndale) | 69 | 07-12-21 A | 08-04-21 A
SWDET2-11515 | PROJ-0951-SWDET2.17.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 1E (Chamberlain & Witt) | 6 | 07-12-21 A | 07-12-21 A
SWDET2-24145 | PROJ-0951-SWDET2.82.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 1W (At Witt) | 0 | 07-12-21 A | 07-12-21 A
EDET1 504246 | GRP-2021-ED1.2.4.2 | 2021 GRP - East Detroit 1 | Install Services - E Outer Dr (W) (Waveney St & Mack Ave) | 35 | 07-12-21 A | 07-15-21 A
NDET3-5660 | GRP-2021-ND3.13.1.2 | 2021 GRP - North Detroit 3 | Install Services - Dwyer St (1) (8 Mile Rd (M102) & Hamlet St) | 40 | 07-12-21 A | 07-12-21 A
CDET2-3945 | GRP-2021-CDet2.34.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Philadelphia 1 (Dexter & Linwood) | 0 | 07-13-21 A | 07-20-21 A
RR1 6761 | GRP-2021-RR.18.1.2 | 2021 GRP - Risk Rank | Install Services - St Marys (Chicago & Plymouth) | 52 | 07-13-21 A | 07-20-21 A
CDET2-2905 | GRP-2021-CDet2.20.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Clairmount 1 (Dexter & Linwood) | 0 | 07-13-21 A | 07-20-21 A
CDET2-3785 | GRP-2021-CDet2.32.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Pingree 1 (Dexter & Linwood) | 0 | 07-14-21 A | 07-20-21 A
EDET1 504086 | GRP-2021-ED1.1.3.2 | 2021 GRP - East Detroit 1 | Install Services - E Outer Dr (E) (Waveney Ave & Mack Ave) | 0 | 07-14-21 A | 07-20-21 A
RR1 6361 | GRP-2021-RR.14.1.2 | 2021 GRP - Risk Rank | Install Services - Casgrain (40' NNPL Lafayette & 131' NNPL Lafayette) | 7 | 07-14-21 A | 07-21-21 A
EDET1 50848 | GRP-2021-ED1.1.1.2 | 2021 GRP - East Detroit 1 | Install Services - E Outer Dr (E) (E Warren Ave & Waveney Ave) | 32 | 07-15-21 A | 08-16-21 A
EDET1 50958 | GRP-2021-ED1.47.1.2 | 2021 GRP - East Detroit 1 | Install Services - Wayburn Ave (1) (E Warrern Ave & Waveney St) | 0 | 07-15-21 A | 07-20-21 A
EDET1 501136 | GRP-2021-ED1.60.1.2 | 2021 GRP - East Detroit 1 | Install Services - Nottingham Rd (2) (Waveney St & Mack Ave) | 0 | 07-15-21 A | 07-20-21 A
SWDET2-5480 | PROJ-0951-SWDET2.49.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Green (Dix & W Vernor) | 0 | 07-15-21 A | 07-20-21 A
AP 2440 | PROJ-0951-MMOAllen.43.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Leslie (1361' West Of Allen Road & Allen Rd) | 0 | 07-15-21 A | 07-20-21 A
AA4 24628 | GRP-2021-AA4.57.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Myron Ct (W Hoover & EOM) | 4 | 07-15-21 A | 07-15-21 A
SWDET2-4920 | PROJ-0951-SWDET2.42.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Logan 1 (Mullane & Springwells) | 18 | 07-15-21 A | 07-15-21 A
SWDET2-19505 | PROJ-0951-SWDET2.42.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Logan 1 (Lawndale & Mullane) | 29 | 07-15-21 A | 07-15-21 A
SWDET2-19825 | PROJ-0951-SWDET2.36.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Longworth (Tie-in & Lawndale) | 22 | 07-15-21 A | 07-15-21 A
SWDET2-19985 | PROJ-0951-SWDET2.36.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Longworth (Tie-in & Tie-in) | 2 | 07-15-21 A | 07-15-21 A
SWDET2-20145 | PROJ-0951-SWDET2.36.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Longworth (Tie-in & Springwells) | 17 | 07-15-21 A | 07-15-21 A
SWDET2-20675 | PROJ-0951-SWDET2.45.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Mullane (Logan & Longworth) | 3 | 07-15-21 A | 07-15-21 A
SWDET2-23465 | PROJ-0951-SWDET2.45.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Mullane (Longworth & Homer) | 6 | 07-15-21 A | 07-15-21 A
SWDET2-24225 | PROJ-0951-SWDET2.82.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 1W (Chamberlain & Witt) | 8 | 07-15-21 A | 07-15-21 A
EDET1 501135 | GRP-2021-ED1.59.1.2 | 2021 GRP - East Detroit 1 | Install Services - Nottingham Rd (1) (E Warrern Ave & Waveney St) | 0 | 07-16-21 A | 07-20-21 A
SWDET2-6360 | PROJ-0951-SWDET2.60.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Rieden 1 (Pitt & W Vernor) | 23 | 07-16-21 A | 07-20-21 A
AP 2280 | PROJ-0951-MMOAllen.35.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Herrick 2 (1080 West Of Cortland Ave & Cortland Ave) | 0 | 07-16-21 A | 07-20-21 A
AP 2480 | PROJ-0951-MMOAllen.45.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Lucy (885' West Of Marlborough Ave & Marlborough) | 0 | 07-16-21 A | 07-20-21 A
NDET3-6615 | GRP-2021-ND3.62.3.2 | 2021 GRP - North Detroit 3 | Install Services - Syracuse Ave (1) (Hamlet St & Amrad St) | 0 | 07-16-21 A | 07-20-21 A
CDET2-1945 | GRP-2021-CDet2.7.2.2 | 2021 GRP - Central Detroit 2 | Install Services - Chicago Blvd 1 (Lawton & Linwood) | 0 | 07-19-21 A | 07-20-21 A
CDET2-3865 | GRP-2021-CDet2.33.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Pingree 2 (Linwood & La Salle) | 0 | 07-19-21 A | 07-20-21 A
AP 2100 | PROJ-0951-MMOAllen.26.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Englewood 1 (402' West Of Louise Ave & Louise) | 0 | 07-19-21 A | 07-20-21 A
CDET2-1705 | GRP-2021-CDet2.5.1.2 | 2021 GRP - Central Detroit 2 | Install Services - W Boston Blvd 1 (Linwood & Lawton) | 0 | 07-19-21 A | 07-20-21 A
CDET2-4025 | GRP-2021-CDet2.35.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Philadelphia 2 (Linwood & La Salle) | 0 | 07-19-21 A | 07-20-21 A
CDET2-7170 | GRP-2021-CDet2.35.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Philadelphia 2 (La Salle & 14th) | 0 | 07-19-21 A | 07-20-21 A
NDET3-6450 | GRP-2021-ND3.62.1.2 | 2021 GRP - North Detroit 3 | Install Services - Syracuse Ave (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 07-19-21 A | 07-20-21 A
CDET2-2185 | GRP-2021-CDet2.11.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Rochester (Dexter & Wildemere) | 0 | 07-20-21 A | 07-20-21 A
CDET2-5065 | GRP-2021-CDet2.48.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Linwood 1 (Collingwood & Longfellow) | 0 | 07-20-21 A | 07-20-21 A
CDET2-5145 | GRP-2021-CDet2.49.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Linwood 2 (Carter & Euclid) | 0 | 07-20-21 A | 07-20-21 A
CDET2-7010 | GRP-2021-CDet2.33.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Pingree 2 (La Salle & 14th) | 0 | 07-20-21 A | 07-20-21 A
CDET2-8190 | GRP-2021-CDet2.49.2.2 | 2021 GRP - Central Detroit 2 | Install Services - Linwood 2 (Joy & Euclid) | 0 | 07-20-21 A | 07-20-21 A
CDET2-8350 | GRP-2021-CDet2.49.4.2 | 2021 GRP - Central Detroit 2 | Install Services - Linwood 2 (Atkinson & Gladstone) | 0 | 07-20-21 A | 07-20-21 A
NDET3-7810 | GRP-2021-ND3.8.1.2 | 2021 GRP - North Detroit 3 | Install Services - E Remington St (Norwood & Yonka) | 0 | 07-20-21 A | 07-20-21 A
CDET2-11150 | GRP-2021-CDet2.51.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Wildemere 3 (Pingree & Pingree) | 0 | 07-20-21 A | 07-20-21 A
CDET2-11310 | GRP-2021-CDet2.53.1.2 | 2021 GRP - Central Detroit 2 | Install Services - AEO Linwood (Clairmount & Clairmount) | 0 | 07-20-21 A | 07-20-21 A
RR1 6441 | GRP-2021-RR.15.1.2 | 2021 GRP - Risk Rank | Install Services - Crawford (56' NNPL Lafayette & 124' SSPL Lafayette) | 6 | 07-21-21 A | 07-26-21 A
AA4 27088 | GRP-2021-AA4.8.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Liberty St (Soule Blvd & Crest Ave) | 10 | 07-22-21 A | 09-14-21 A
NDET3-4980 | GRP-2021-ND3.22.1.2 | 2021 GRP - North Detroit 3 | Install Services - St Louis Ave (E Outer Dr & ANO 7 Mile Rd) | 71 | 07-26-21 A | 09-01-21 A
NDET3-7370 | GRP-2021-ND3.82.1.2 | 2021 GRP - North Detroit 3 | Install Services - Revere Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 78 | 07-26-21 A | 07-27-21 A
AA4 21458 | GRP-2021-AA4.13.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - 5th St (W Madison St & Davis Ave) | 44 | 07-26-21 A | 08-31-21 A
AP 1980 | PROJ-0951-MMOAllen.20.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Champaign 2 (Allen & Fox) | 65 | 07-27-21 A | 08-09-21 A
NDET3-795 | GRP-2021-ND3.65.1.2 | 2021 GRP - North Detroit 3 | Install Services - Charest St (1) (8 Mile Rd (M102) & E Outer Dr) | 84 | 07-27-21 A | 09-01-21 A
NDET3-15 | GRP-2021-ND3.70.1.2 | 2021 GRP - North Detroit 3 | Install Services - Gallagher (1) (8 Mile Rd (M102) & E Outer Dr) | 86 | 07-27-21 A | 08-10-21 A
NDET3-40 | GRP-2021-ND3.74.1.2 | 2021 GRP - North Detroit 3 | Install Services - Klinger St (1) (8 Mile Rd (M102) & E Outer Dr) | 95 | 07-27-21 A | 08-03-21 A
RR1 6521 | GRP-2021-RR.49.1.2 | 2021 GRP - Risk Rank | Install Services - Livernois (EOM & W Lafayette) | 3 | 07-27-21 A | 07-30-21 A
SWDET2-6920 | PROJ-0951-SWDET2.67.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Honorah (Dix & W Vernor) | 50 | 08-02-21 A | 08-16-21 A
AP 2000 | PROJ-0951-MMOAllen.21.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Champaign 3 (Fox & Vine) | 25 | 08-02-21 A | 08-11-21 A
AP 2400 | PROJ-0951-MMOAllen.41.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Laurence 1 (Englewood & Moore) | 18 | 08-02-21 A | 08-06-21 A
SWDET2-21975 | PROJ-0951-SWDET2.76.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Oakdale (ASO W Vernor & Mandale) | 29 | 08-02-21 A | 08-13-21 A
RR1 5881 | GRP-2021-RR.6.1.2 | 2021 GRP - Risk Rank | Install Services - Iowa (Sherwood & School) | 35 | 08-02-21 A | 08-16-21 A
RR1 7901 | GRP-2021-RR.33.1.2 | 2021 GRP - Risk Rank | Install Services - Florence (Hamilton & Woodward) | 44 | 08-02-21 A | 08-16-21 A
RR1 8781 | GRP-2021-RR.44.1.2 | 2021 GRP - Risk Rank | Install Services - Kenmoor (Conner & Gunston) | 92 | 08-02-21 A | 08-16-21 A
RR1 63160 | GRP-2021-RR1.11.1.2 | 2021 GRP - River Rouge | Install Services - Cherrygrove St (W Jefferson Ave & EOM) | 23 | 08-02-21 A | 08-16-21 A
Ypsi 3-7590 | PROJ-0951-YSP3.23.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Jeff (Desoto & Mary Catherine) | 33 | 08-03-21 A | 09-15-21 A
NDET3-65 | GRP-2021-ND3.78.1.2 | 2021 GRP - North Detroit 3 | Install Services - Mitchell St (1) (8 Mile Rd (M102) & E Outer Dr) | 93 | 08-04-21 A | 09-01-21 A
Ypsi 3-6100 | PROJ-0951-YSP3.17.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Studebaker (Chevrolet & Tyler) | 16 | 08-05-21 A | 2021-10-21
Ypsi 3-5850 | PROJ-0951-YSP3.16.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Buick (Tyler & Chevrolet) | 34 | 08-06-21 A | 08-26-21 A
RR1 51543 | GRP-2021-RR1.79.1.2 | 2021 GRP - River Rouge | Install Services - E Alexis Ave (W Jefferson & Eliza) | 21 | 08-09-21 A | 08-16-21 A
RR1 51547 | GRP-2021-RR1.83.1.2 | 2021 GRP - River Rouge | Install Services - High St 2 (W Josephine St & Cicotte St) | 16 | 08-09-21 A | 08-16-21 A
RR1 51562 | GRP-2021-RR1.99.1.2 | 2021 GRP - River Rouge | Install Services - W Woodward Ave (EOM High St) | 12 | 08-09-21 A | 08-16-21 A
RR1 51563 | GRP-2021-RR1.100.1.2 | 2021 GRP - River Rouge | Install Services - W Westfield St (EOM & High) | 14 | 08-09-21 A | 08-16-21 A
RR1 51715 | GRP-2021-RR1.102.1.2 | 2021 GRP - River Rouge | Install Services - E Charlotte Ave (W Jefferson Ave & Eliza St) | 23 | 08-09-21 A | 08-16-21 A
CDET2-6010 | GRP-2021-CDet2.11.3.2 | 2021 GRP - Central Detroit 2 | Install Services - Rochester (Wildemere & lawton) | 3 | 08-09-21 A | 08-13-21 A
RR1 59540 | GRP-2021-RR1.112.1.2 | 2021 GRP - River Rouge | MMO - W Auburn Ave (High St & W Jefferson Ave) | 15 | 08-09-21 A | 08-16-21 A
SWDET2-17305 | PROJ-0951-SWDET2.78.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Sharon (ASO W Vernor & Mandale) | 24 | 08-09-21 A | 08-16-21 A
SWDET2-21815 | PROJ-0951-SWDET2.76.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Oakdale (Woodmere & ANO W Vernor) | 26 | 08-09-21 A | 08-16-21 A
RR1 8221 | GRP-2021-RR.37.1.2 | 2021 GRP - Risk Rank | Install Services - Varjo (Sherwood & Cliff) | 20 | 08-09-21 A | 08-13-21 A
RR1 8301 | GRP-2021-RR.38.1.2 | 2021 GRP - Risk Rank | Install Services - Cliff (Varjo & EOM 181' SSPL Varjo) | 3 | 08-09-21 A | 08-16-21 A
RR1 10801 | GRP-2021-RR.22.1.2 | 2021 GRP - Risk Rank | Install Services - Bloom (7 Mile & Nevada) West | 37 | 08-09-21 A | 08-16-21 A
AP 4780 | PROJ-0951-MMOAllen.75.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Rosedale 1 (Belmont & Englewood) | 7 | 08-09-21 A | 08-10-21 A
RR1 63070 | GRP-2021-RR1.77.1.2 | 2021 GRP - River Rouge | MMO - Broadway Ave (High & EOM) | 21 | 08-09-21 A | 08-16-21 A
RR1 63130 | GRP-2021-RR1.100.1.2 | 2021 GRP - River Rouge | MMO - W Westfield St (High & W Jefferson) | 17 | 08-09-21 A | 08-16-21 A
RR1 63140 | GRP-2021-RR1.99.1.2 | 2021 GRP - River Rouge | MMO - W Woodward Ave (High & W Jefferson) | 13 | 08-09-21 A | 08-13-21 A
RR1 51552 | GRP-2021-RR1.88.1.2 | 2021 GRP - River Rouge | MMO - Ridge St (High & W Jefferson) | 24 | 08-10-21 A | 08-16-21 A
RR1 51720 | GRP-2021-RR1.107.1.2 | 2021 GRP - River Rouge | Install Services - Joseph St (W Jefferson Ave & Eliza St) | 5 | 08-10-21 A | 08-16-21 A
SWDET2-7160 | PROJ-0951-SWDET2.71.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Stair (Dix & W Vernor) | 46 | 08-10-21 A | 08-16-21 A
NDET3-6555 | GRP-2021-ND3.49.3.2 | 2021 GRP - North Detroit 3 | Install Services - Bloom St (1) (Hamlet St & E Outer Dr) | 16 | 08-10-21 A | 08-16-21 A
AA4 20462 | GRP-2021-AA4.8.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Liberty St (54' EEPL Crest Ave & 21' WWPL S 7Th St) | 34 | 08-10-21 A | 09-16-21 A
RR1 51545 | GRP-2021-RR1.81.1.2 | 2021 GRP - River Rouge | MMO - Elton St (High & W Jefferson) | 7 | 08-12-21 A | 08-16-21 A
NDET3-7030 | GRP-2021-ND3.50.4.2 | 2021 GRP - North Detroit 3 | Install Services - Buffalo St (1) (Hamlet St & Amrad St) | 19 | 08-12-21 A | 08-16-21 A
NDET3-6380 | GRP-2021-ND3.46.1.2 | 2021 GRP - North Detroit 3 | Install Services - Albany Ave (1) (Hamlet & Amrad St) | 7 | 08-16-21 A | 08-16-21 A
NDET3-6275 | GRP-2021-ND3.46.3.2 | 2021 GRP - North Detroit 3 | Install Services - Albany Ave (1) (Hamlet St & EOM) | 6 | 08-16-21 A | 08-16-21 A
RR1 5255 | GRP-2021-RR1.10.1.2 | 2021 GRP - River Rouge | Install Services - Outer Dr (162' WWPL High St & High St) | 2 | 08-16-21 A | 08-16-21 A
RR1 51564 | GRP-2021-RR1.101.1.2 | 2021 GRP - River Rouge | Install Services - Webster St (Labadie St & EOM @ 158' SSPL Labadie St) | 3 | 08-16-21 A | 08-16-21 A
SWDET2-7720 | PROJ-0951-SWDET2.76.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Oakdale (NO Woodmere & Woodmere) | 6 | 08-16-21 A | 08-16-21 A
AA3-5650 | GRP-2021-RR1.8.1.2 | 2021 GRP - River Rouge | Install Services - Eliza St (35' NNPL E Charlotte Ave & 4' NSPL E Charlotte Ave) | 1 | 08-16-21 A | 08-16-21 A
AA3-5720 | GRP-2021-RR1.9.1.2 | 2021 GRP - River Rouge | Install Services - Florence St 2 (Joseph st & E Charlotte Ave) | 3 | 08-16-21 A | 08-16-21 A
AA3-5860 | GRP-2021-RR1.8.2.2 | 2021 GRP - River Rouge | Install Services - Eliza St (E Charlotte Ave & EOM @ 108' SSPL E Alexis Ave) | 1 | 08-16-21 A | 08-16-21 A
RR1 59690 | GRP-2021-RR1.97.3.2 | 2021 GRP - River Rouge | MMO Services - W Glenwood Ave (High & 420' WWPL W Jefferson Ave) | 2 | 08-16-21 A | 08-16-21 A
SWDET2-16155 | PROJ-0951-SWDET2.71.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Stair (EOM & Dix) | 2 | 08-16-21 A | 08-16-21 A
SWDET2-23015 | PROJ-0951-SWDET2.69.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Pitt (Honorah & EOM) | 1 | 08-16-21 A | 08-16-21 A
RR1 9101 | GRP-2021-RR.48.1.2 | 2021 GRP - Risk Rank | Install Services - Gunston (Nashville & Gunston) | 4 | 08-16-21 A | 08-16-21 A
NDET3-6600 | GRP-2021-ND3.49.1.2 | 2021 GRP - North Detroit 3 | Install Services - Bloom St (1) (8 Mile Rd (M102) & Hamlet St) | 36 | 08-16-21 A | 08-16-21 A
NDET3-6910 | GRP-2021-ND3.50.1.2 | 2021 GRP - North Detroit 3 | Install Services - Buffalo St (1) (8 Mile Rd (M102) & Hamlet St) | 7 | 08-16-21 A | 08-16-21 A
NDET3-6785 | GRP-2021-ND3.60.3.2 | 2021 GRP - North Detroit 3 | Install Services - Moenart St (1) (Hamlet St & E Outer Dr) | 66 | 08-16-21 A | 08-19-21 A
Ypsi 3-1980 | PROJ-0951-YSP3.2.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Desoto (State & Tyler) | 75 | 08-18-21 A | 2021-10-21
Ypsi 3-3120 | PROJ-0951-YSP3.4.3.2 | 2021 GRP - Ypsilanti 3 | Install Services - Nash 2 (Tyler & State) | 8 | 08-24-21 A | 2021-10-25
AA4 26928 | GRP-2021-AA4.28.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Jefferson St South (1' WEPL S 7Th St & S 1St St) | 34 | 08-26-21 A | 2021-09-20
AA4 20823 | GRP-2021-AA4.32.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - 8th St (W Liberty St & EOM) | 22 | 08-27-21 A | 09-10-21 A
NCDET - 23845 | NEWPROJ-6.4.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Cheyenne (Puritan & Fenkell) | 88 | 08-30-21 A | 09-01-21 A
NCDET - 24235 | NEWPROJ-6.16.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Ward (Puritan & Fenkell) | 109 | 08-30-21 A | 09-01-21 A
RR1 51540 | GRP-2021-RR1.76.1.2 | 2021 GRP - River Rouge | Install Services - Bell St (High & Visgar) | 1 | 08-30-21 A | 08-30-21 A
RR1 51541 | GRP-2021-RR1.77.1.2 | 2021 GRP - River Rouge | Install Services - Broadway Ave (High & W Jefferson) | 7 | 08-30-21 A | 08-30-21 A
RR1 51548 | GRP-2021-RR1.84.1.2 | 2021 GRP - River Rouge | MMO - Knox St (High & W Jefferson) | 24 | 08-30-21 A | 09-02-21 A
RR1 51549 | GRP-2021-RR1.85.1.2 | 2021 GRP - River Rouge | Install Services - Labadie St (55' WWPL Webster St & High St) | 1 | 08-30-21 A | 08-30-21 A
RR1 51554 | GRP-2021-RR1.91.1.2 | 2021 GRP - River Rouge | MMO - Ruth St (High & W Jefferson) | 5 | 08-30-21 A | 08-30-21 A
RR1 51559 | GRP-2021-RR1.96.1.2 | 2021 GRP - River Rouge | Install Services - W Charlotte (14' EEPL High St & 5' WWPL W Jefferson Ave) | 22 | 08-30-21 A | 08-31-21 A
RR1 51723 | GRP-2021-RR1.110.1.2 | 2021 GRP - River Rouge | Install Services - W Alexis Ave (8' EEPL High St & 9' WWPL W Jefferson Ave) | 22 | 08-30-21 A | 08-31-21 A
RR1 59410 | GRP-2021-RR1.80.1.2 | 2021 GRP - River Rouge | MMO - Visgar Rd (EOM & W Jefferson Ave) | 4 | 08-30-21 A | 08-30-21 A
RR1 6041 | GRP-2021-RR.8.1.2 | 2021 GRP - Risk Rank | Install Services - Westphalia (7 Mile & Greiner) | 67 | 08-30-21 A | 09-01-21 A
RR1 7081 | GRP-2021-RR.22.1.2 | 2021 GRP - Risk Rank | Install Services - Bloom (7 Mile & Nevada) East | 51 | 08-30-21 A | 09-01-21 A
RR1 8861 | GRP-2021-RR.45.1.2 | 2021 GRP - Risk Rank | Install Services - Engleside (Conner & Gunston) | 87 | 08-30-21 A | 09-01-21 A
RR1 8941 | GRP-2021-RR.46.1.2 | 2021 GRP - Risk Rank | Install Services - College (Conner & Gunston) | 82 | 08-30-21 A | 09-01-21 A
RR1 10251 | GRP-2021-RR.46.2.2 | 2021 GRP - Risk Rank | Install Services - College (Gunston & Devon) | 63 | 08-30-21 A | 09-01-21 A
NDET3-5290 | GRP-2021-ND3.56.1.2 | 2021 GRP - North Detroit 3 | Install Services - Fenelon Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 42 | 08-30-21 A | 08-31-21 A
NDET3-6835 | GRP-2021-ND3.59.1.2 | 2021 GRP - North Detroit 3 | Install Services - Keystone St (1) (8 Mile Rd (M102) & Hamlet St) | 18 | 08-30-21 A | 09-01-21 A
NDET3-6650 | GRP-2021-ND3.60.1.2 | 2021 GRP - North Detroit 3 | Install Services - Moenart St (1) (8 Mile Rd (M102) & Hamlet St) | 67 | 08-30-21 A | 09-01-21 A
NDET3-725 | GRP-2021-ND3.59.3.2 | 2021 GRP - North Detroit 3 | Install Services - Keystone St (1) (Hamlet St & E Outer Dr) | 72 | 08-30-21 A | 09-01-21 A
Muni8050 | PROJ-0951-MUN-2.12.1.2 | 2021 GRP - Municipality | Install Services - Pinehurst (Chicago & Joy) | 94 | 08-30-21 A | 09-01-21 A
Muni8130 | PROJ-0951-MUN-2.7.1.2 | 2021 GRP - Municipality | Install Services - Ash (Vinewood & Roosevelt) | 0 | 08-30-21 A | 09-01-21 A
AA4 20457 | GRP-2021-AA4.2.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Pauline Blvd (Redeemer & S 7th Stt) | 28 | 08-30-21 A | 2021-09-28
AP 1780 | PROJ-0951-MMOAllen.10.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Becker 2 (Englewood & Wick) | 35 | 08-31-21 A | 09-01-21 A
AP 2160 | PROJ-0951-MMOAllen.29.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Fox 1 (Englewood & Moore) | 33 | 08-31-21 A | 09-01-21 A
AA4 20600 | GRP-2021-AA4.13.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - 5th St (W Jefferson St & W Madison St) | 16 | 09-02-21 A | 2021-09-30
Ypsi 3-2230 | PROJ-0951-YSP3.42.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - State (McCartney & Desoto) | 11 | 09-10-21 A | 09-16-21 A
NDET3-6915 | GRP-2021-ND3.52.1.2 | 2021 GRP - North Detroit 3 | Install Services - Conley Ave (1) (8 Mile Rd (M102) & Hamlet St) | 40 | 09-13-21 A | 09-14-21 A
NDET3-7090 | GRP-2021-ND3.52.3.2 | 2021 GRP - North Detroit 3 | Install Services - Conley Ave (1) (Hamlet St & E Outer Dr) | 44 | 09-13-21 A | 09-14-21 A
NDET3-5440 | GRP-2021-ND3.31.2.2 | 2021 GRP - North Detroit 3 | Install Services - Mound Rd (Mound & Mound) | 3 | 09-13-21 A | 09-13-21 A
Ypsi 3-11670 | PROJ-0951-YSP3.3.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - S Outerlane Dr (8' SSPL State St & EOM) | 9 | 09-14-21 A | 09-15-21 A
Ypsi 3-9080 | PROJ-0951-YSP3.29.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Woodglen (Tyler & Cedarcliff) | 50 | 09-20-21 A | 2021-11-02
Ypsi 3-1740 | PROJ-0951-YSP3.39.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Tyler (Desoto & McCartney) | 1 | 2021-09-20 | 2021-09-20
NCDET - 6735 | NEWPROJ-6.3.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Birwood (Puritan & Fenkell) | 54 | 2021-09-20 | 2021-09-24
NCDET - 7035 | NEWPROJ-6.8.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Manor (Puritan & Fenkell) | 20 | 2021-09-20 | 2021-10-15
NCDET - 7405 | NEWPROJ-6.14.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Steel (Puritan & ANO Fenkell) | 81 | 2021-09-20 | 2021-10-22
NCDET - 23065 | NEWPROJ-6.13.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Snowden (Puritan & Fenkell) | 78 | 2021-09-20 | 2021-10-11
NCDET - 24715 | NEWPROJ-6.15.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Sorrento (Puritan & Fenkell) | 97 | 2021-09-20 | 2021-10-22
Milestone 4 | GRP-2021-SCDet1.23 | 2021 GRP - South Central Detroit 1 | Service Finish Milestone | 0 |  | 09-20-21*
RR1 5259 | GRP-2021-RR1.15.1.2 | 2021 GRP - River Rouge | Install Services - Cora (5' WEPL Haltiner St & 11' EWPL W Jefferson Ave) | 7 | 2021-09-20 | 2021-09-21
RR1 5266 | GRP-2021-RR1.22.1.2 | 2021 GRP - River Rouge | MMO - Florence St (W Jefferson & Haltiner) | 6 | 09-20-21* | 2021-09-20
RR1 5269 | GRP-2021-RR1.26.1.2 | 2021 GRP - River Rouge | Install Services - Haltiner St (108' NNPL Louis St & 50' NNPL Cora St) | 29 | 2021-09-20 | 2021-09-24
RR1 5270 | GRP-2021-RR1.27.1.2 | 2021 GRP - River Rouge | MMO - Le Blanc (Haltiner & W Jefferson) | 1 | 09-20-21* | 2021-09-20
RR1 5274 | GRP-2021-RR1.31.1.2 | 2021 GRP - River Rouge | Install Services - Nieman (Haltiner & W Jefferson) | 8 | 2021-09-20 | 2021-09-21
RR1 5278 | GRP-2021-RR1.35.1.2 | 2021 GRP - River Rouge | MMO - W Cicotte St (Dwight & W Jefferson) | 8 | 09-20-21* | 2021-09-20
RR1 5281 | GRP-2021-RR1.38.1.2 | 2021 GRP - River Rouge | MMO - Oak St (EOM & W Jefferson) | 1 | 09-20-21* | 2021-09-20
WCDET1-1635 | GRP-2021-WCDet1.5.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Waverly (Broadstreet & Dexter) | 39 | 2021-09-20 | 2021-09-27
WCDET1-1715 | GRP-2021-WCDet1.6.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Tyler (Broadstreet & Dexter) | 91 | 2021-09-20 | 2021-10-06
WCDET1-1795 | GRP-2021-WCDet1.7.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Broadstreet (Waverly & Buena Vista) | 17 | 2021-09-20 | 2021-09-22
WCDET1-1875 | GRP-2021-WCDet1.8.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Dexter E (Davison & Buena Vista) | 3 | 2021-09-20 | 2021-09-20
WCDET1-3075 | GRP-2021-WCDet1.13.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald Cr North 1 (Schoolcraft & San Juan) | 24 | 2021-09-20 | 2021-09-23
WCDET1-3155 | GRP-2021-WCDet1.25.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd North 1(Prairie & Stoepel) | 11 | 2021-09-20 | 2021-09-21
WCDET1-4355 | GRP-2021-WCDet1.40.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Buena Vista 2 (Livernois & Dexter) | 52 | 2021-09-20 | 2021-09-29
WCDET1-4995 | GRP-2021-WCDet1.48.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois 2 (Bourke & Doris) | 1 | 2021-09-20 | 2021-09-20
CDET2-4425 | GRP-2021-CDet2.40.1.2 | 2021 GRP - Central Detroit 2 | Install Services - Dexter 1 (Longfellow & Euclid) | 0 | 09-20-21* | 2021-09-20
RR1 5304 | GRP-2021-RR1.61.1.2 | 2021 GRP - River Rouge | MMO - Maple St (W Jefferson & Goodell) | 53 | 09-20-21* | 2021-09-30
RR1 51476 | GRP-2021-RR1.66.1.2 | 2021 GRP - River Rouge | Install Services - Alexander 1 (139' SSPL E Great Lakes St & Abbott St) | 13 | 2021-09-20 | 2021-09-22
RR1 51480 | GRP-2021-RR1.70.1.2 | 2021 GRP - River Rouge | Install Services - Hill St (Genessee St & 27' WWPL Alexander St) | 27 | 2021-09-20 | 2021-09-24
RR1 51482 | GRP-2021-RR1.72.1.2 | 2021 GRP - River Rouge | Install Services - Orcahard St (W Jefferson & Ecorse City Limit) | 26 | 2021-09-20 | 2021-09-24
RR1 51483 | GRP-2021-RR1.73.1.2 | 2021 GRP - River Rouge | Install Services - Perrin St (E Great Lakes & Abbott) | 21 | 09-20-21* | 2021-09-23
RR1 51546 | GRP-2021-RR1.82.1.2 | 2021 GRP - River Rouge | MMO - High St 1 (River Rouge City Limits & W Josephine St) | 3 | 09-20-21* | 2021-09-20
RR1 51557 | GRP-2021-RR1.94.1.2 | 2021 GRP - River Rouge | MMO - Union St (High & W Jefferson) | 5 | 09-20-21* | 2021-09-20
RR1 51560 | GRP-2021-RR1.97.1.2 | 2021 GRP - River Rouge | Install Services - W Glenwood Ave (420' WWPL W Jefferson Ave & 12' WWPL W Jefferson Ave) | 5 | 2021-09-20 | 2021-09-20
RR1 51714 | GRP-2021-RR1.90.1.2 | 2021 GRP - River Rouge | Install Services - E Auburn Ave (W Jefferson Ave & Ironton Ave) | 32 | 2021-09-20 | 2021-09-27
RR1 51716 | GRP-2021-RR1.103.1.2 | 2021 GRP - River Rouge | Install Services - E Glenwood Ave (W Jefferson Ave & Ironton Ave) | 37 | 2021-09-20 | 2021-09-27
RR1 51717 | GRP-2021-RR1.104.1.2 | 2021 GRP - River Rouge | Install Services - E Rockwood Ave (W Jefferson Ave & Ironton Ave) | 12 | 2021-09-20 | 2021-09-21
EDET1 50847 | GRP-2021-ED1.4.1.2 | 2021 GRP - East Detroit 1 | Install Services - ANO Mack Ave (1) (Alter Rd & Nottingham Rd) | 17 | 2021-09-20 | 2021-09-20
EDET1 50582 | GRP-2021-ED1.9.1.2 | 2021 GRP - East Detroit 1 | Install Services - ASO E Warren Ave (1) (Alter Rd& Chatsworth St) | 9 | 2021-09-20 | 2021-09-21
EDET1 50583 | GRP-2021-ED1.10.1.2 | 2021 GRP - East Detroit 1 | Install Services - ASO E Warren Ave (2) (Chatsworth St & E Outer Dr) | 17 | 2021-09-20 | 2021-09-22
EDET1 50584 | GRP-2021-ED1.11.1.2 | 2021 GRP - East Detroit 1 | Install Services - ASO E Warren Ave (3) (E Outer Dr & Bishop St) | 10 | 2021-09-20 | 2021-09-21
EDET1 50591 | GRP-2021-ED1.18.1.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) S (Bishop St & Grayton St) | 2 | 2021-09-20 | 2021-09-20
EDET1 501128 | GRP-2021-ED1.52.1.2 | 2021 GRP - East Detroit 1 | Install Services - Beaconsfield St (2) (Waveney St & Mack Ave) | 14 | 2021-09-20 | 2021-09-22
EDET1 501131 | GRP-2021-ED1.55.1.2 | 2021 GRP - East Detroit 1 | Install Services - Chatsworth St (1) (E Warrern Ave & Waveney St) | 45 | 2021-09-20 | 2021-09-28
SWDET2-1960 | PROJ-0951-SWDET2.3.1.2 | 2021 GRP - South West Detroit 2 | Install Services - EWO Woodmere (At W Vernor) | 1 | 2021-09-20 | 2021-09-20
SWDET2-2040 | PROJ-0951-SWDET2.5.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Fort (Woodmere & Distel) | 0 | 2021-09-20 | 2021-09-20
SWDET2-2200 | PROJ-0951-SWDET2.7.1.2 | 2021 GRP - South West Detroit 2 | Install Services - ANO W Vernor (Woodmere & Norman) | 12 | 2021-09-20 | 2021-09-21
SWDET2-2280 | PROJ-0951-SWDET2.8.1.2 | 2021 GRP - South West Detroit 2 | Install Services - ASO W Vernor 1 (Woodmere & Lawndale) | 4 | 2021-09-20 | 2021-09-20
SWDET2-2360 | PROJ-0951-SWDET2.9.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Springwells 1 (ASO Vernor & Rathbone) | 39 | 2021-09-20 | 2021-09-28
SWDET2-2440 | PROJ-0951-SWDET2.10.1.2 | 2021 GRP - South West Detroit 2 | Install Services - W Vernor 2 (Dearborn City Limit & Woodmere) | 0 | 2021-09-20 | 2021-09-20
SWDET2-2520 | PROJ-0951-SWDET2.11.1.2 | 2021 GRP - South West Detroit 2 | Install Services - W Vernor 3 (Inglis & Central) North | 16 | 2021-09-20 | 2021-09-22
SWDET2-2680 | PROJ-0951-SWDET2.13.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Central 1 W (ASO Vernor & Logan) | 22 | 2021-09-20 | 2021-09-23
SWDET2-2920 | PROJ-0951-SWDET2.16.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Dix 4 (Central & W Vernor) | 20 | 2021-09-20 | 2021-09-23
SWDET2-3000 | PROJ-0951-SWDET2.17.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 1E (ASO Vernor & Chamberlain) | 34 | 2021-09-20 | 2021-09-27
SWDET2-3400 | PROJ-0951-SWDET2.22.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Distel (Olivet & Fort) | 17 | 2021-09-20 | 2021-09-22
SWDET2-3480 | PROJ-0951-SWDET2.24.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Elsmere 1 (Woodmere & Avis) | 12 | 2021-09-20 | 2021-09-21
SWDET2-3640 | PROJ-0951-SWDET2.26.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Fulton (EOM & Elsmere) | 6 | 2021-09-20 | 2021-09-20
SWDET2-3800 | PROJ-0951-SWDET2.28.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Olivet (Woodmere & Lawndale) | 30 | 2021-09-20 | 2021-09-24
SWDET2-3960 | PROJ-0951-SWDET2.30.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Witt (EOM & Elsmere) | 11 | 2021-09-20 | 2021-09-21
SWDET2-4120 | PROJ-0951-SWDET2.32.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 4 (Mandale & Avis) | 2 | 2021-09-20 | 2021-09-20
SWDET2-4200 | PROJ-0951-SWDET2.33.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Chamberlain (Woodmere & Lawndale) | 68 | 2021-09-20 | 2021-10-05
SWDET2-4280 | PROJ-0951-SWDET2.34.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Homer (Woodmere & Lawndale) | 64 | 2021-09-20 | 2021-10-04
SWDET2-4440 | PROJ-0951-SWDET2.36.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Longworth (Woodmere & Lawndale) | 58 | 2021-09-20 | 2021-10-01
SWDET2-4520 | PROJ-0951-SWDET2.37.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Rathbone (Woodmere & Lawndale) | 60 | 2021-09-20 | 2021-10-01
SWDET2-4600 | PROJ-0951-SWDET2.38.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Avis (Woodmere & Elsmere) | 27 | 2021-09-20 | 2021-09-24
SWDET2-4760 | PROJ-0951-SWDET2.40.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Falcon (Woodmere & Lawndale) | 66 | 2021-09-20 | 2021-10-04
SWDET2-4840 | PROJ-0951-SWDET2.41.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Lane 1 (Woodmere & Elsmere) | 17 | 2021-09-20 | 2021-09-22
SWDET2-5000 | PROJ-0951-SWDET2.43.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Mandale (Woodmere & Elsemere) | 10 | 2021-09-20 | 2021-09-21
SWDET2-5080 | PROJ-0951-SWDET2.44.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Mason (Woodmere & Elsemere) | 23 | 2021-09-20 | 2021-09-23
SWDET2-5160 | PROJ-0951-SWDET2.45.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Mullane (At Cahalan) | 0 | 2021-09-20 | 2021-09-20
SWDET2-5800 | PROJ-0951-SWDET2.53.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Pershing (Springwells & Central) | 2 | 2021-09-20 | 2021-09-20
SWDET2-5880 | PROJ-0951-SWDET2.54.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Senator 1 (EOM & Mullane) | 27 | 2021-09-20 | 2021-09-24
SWDET2-5960 | PROJ-0951-SWDET2.55.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Whitaker 1 (Mullane & Springwells) | 28 | 2021-09-20 | 2021-09-24
SWDET2-6040 | PROJ-0951-SWDET2.56.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Beard (W Vernor & Cahalan) | 23 | 2021-09-20 | 2021-09-23
SWDET2-6440 | PROJ-0951-SWDET2.61.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Senator 2 (Central & Green) | 37 | 2021-09-20 | 2021-09-28
SWDET2-6680 | PROJ-0951-SWDET2.64.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Whitaker 2 (Springwells & Central) | 26 | 2021-09-20 | 2021-09-24
SWDET2-6760 | PROJ-0951-SWDET2.65.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Carson (Dix & W Vernor) | 78 | 2021-09-20 | 2021-10-06
SWDET2-6840 | PROJ-0951-SWDET2.66.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Casper (Dix & Tie-In) | 18 | 2021-09-20 | 2021-09-23
SWDET2-7000 | PROJ-0951-SWDET2.68.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Inglis (ANO W Vernor & W Vernor) | 0 | 2021-09-20 | 2021-09-20
SWDET2-7080 | PROJ-0951-SWDET2.69.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Pitt (EOM & Springwells) | 1 | 2021-09-20 | 2021-09-20
SWDET2-7400 | PROJ-0951-SWDET2.72.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Cabot (NO Woodmere & Woodmere) | 6 | 2021-09-20 | 2021-09-20
SWDET2-7480 | PROJ-0951-SWDET2.73.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Ferris (Woodmere & ANO W Vernor) | 55 | 2021-09-20 | 2021-10-01
SWDET2-7560 | PROJ-0951-SWDET2.74.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 2 (NO Woodmere & Woodmere) | 1 | 2021-09-20 | 2021-09-20
SWDET2-7640 | PROJ-0951-SWDET2.75.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Norman (Woodmere & ANO W Vernor) | 68 | 2021-09-20 | 2021-10-05
SWDET2-7960 | PROJ-0951-SWDET2.79.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Wendell (Woodmere & W Vernor) | 46 | 2021-09-20 | 2021-09-29
RR1 259 | GRP-2021-RR1.3.1.2 | 2021 GRP - River Rouge | Install Services - Francis Riopelle Ave (Richter St & EOM) | 1 | 2021-09-20 | 2021-09-20
AA3-4825 | GRP-2021-RR1.7.1.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (2) (River Rouge City Limits & E Glenwood) | 12 | 2021-09-20 | 2021-09-21
SWDET2-8665 | PROJ-0951-SWDET2.16.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Dix 4 (Casper & Central) | 1 | 2021-09-20 | 2021-09-20
SWDET2-8825 | PROJ-0951-SWDET2.16.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Dix 4 (At Central) | 0 | 2021-09-20 | 2021-09-20
SWDET2-8975 | PROJ-0951-SWDET2.5.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Fort (EO Distal & Elsmere) | 3 | 2021-09-20 | 2021-09-20
SWDET2-9055 | PROJ-0951-SWDET2.5.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Fort (Elsmere & EOM) | 1 | 2021-09-20 | 2021-09-20
SWDET2-9485 | PROJ-0951-SWDET2.12.3.2 | 2021 GRP - South West Detroit 2 | Install Services - W Vernor 4 (At Central) | 0 | 2021-09-20 | 2021-09-20
SWDET2-10285 | PROJ-0951-SWDET2.8.3.2 | 2021 GRP - South West Detroit 2 | Install Services - ASO W Vernor 1 (Lawndale & Central) | 16 | 2021-09-20 | 2021-09-23
SWDET2-10445 | PROJ-0951-SWDET2.9.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Springwells 1 (Rathbone & Chamberlain) | 0 | 2021-09-20 | 2021-09-20
SWDET2-11115 | PROJ-0951-SWDET2.13.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Central 1 W (Logan & Pershing) | 1 | 2021-09-20 | 2021-09-20
SWDET2-11195 | PROJ-0951-SWDET2.13.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Central 1 E (W Vernor & ASO Vernor) | 0 | 2021-09-20 | 2021-09-20
SWDET2-11355 | PROJ-0951-SWDET2.14.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Central 2 (Dix & W Vernor) | 32 | 2021-09-20 | 2021-09-20
SWDET2-13295 | PROJ-0951-SWDET2.32.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Woodmere 4 (Avis & Fort) | 42 | 2021-09-20 | 2021-09-28
SWDET2-13455 | PROJ-0951-SWDET2.26.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Fulton (Elsmere & EOM) | 10 | 2021-09-20 | 2021-09-21
RR1 51890 | GRP-2021-RR1.65.3.2 | 2021 GRP - River Rouge | Install Services - Abbott (Genessee St & Ironton Ave) | 45 | 2021-09-20 | 2021-09-29
WCDET1-10520 | GRP-2021-WCDet1.17.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois 4 (Davison & EOM) | 4 | 09-20-21* | 2021-09-20
WCDET1-11000 | GRP-2021-WCDet1.48.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois 2 (Intervale & Ewald) | 4 | 2021-09-20 | 2021-09-20
WCDET1-12210 | GRP-2021-WCDet1.40.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Buena Vista 2 (Broadstreet & Petoskey) | 43 | 2021-09-20 | 2021-09-28
WCDET1-12370 | GRP-2021-WCDet1.40.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Buena Vista 2 (Livernois & Broadstreet) | 11 | 2021-09-20 | 2021-09-21
RR1 54990 | GRP-2021-RR1.59.3.2 | 2021 GRP - River Rouge | MMO - E Great Lakes St (W Jefferson Ave & Goodell St) | 11 | 09-20-21* | 2021-09-21
RR1 55790 | GRP-2021-RR1.53.3.2 | 2021 GRP - River Rouge | Install Services - E James North (3' WEPL Burke St & 8' EWPL Harris St) 3" | 16 | 2021-09-20 | 2021-09-23
RR1 55870 | GRP-2021-RR1.53.4.2 | 2021 GRP - River Rouge | Install Services - E James South (3' WEPL Burke St & 8' EWPL Harris St) 2" | 19 | 2021-09-20 | 2021-09-22
RR1 58790 | GRP-2021-RR1.56.2.2 | 2021 GRP - River Rouge | MMO - Richter (Lorey St & Maple St) | 17 | 09-20-21* | 2021-09-22
RR1 59270 | GRP-2021-RR1.74.3.2 | 2021 GRP - River Rouge | Install Services - Stone St (Genessee St & Ironton Ave) | 48 | 2021-09-20 | 2021-09-29
AP 1620 | PROJ-0951-MMOAllen.2.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Allen 1 (Pelham & 150' North Of Moore) | 24 | 2021-09-20 | 2021-09-24
RR1 60800 | GRP-2021-RR1.2.12.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (4' NSPL Burke St & W Great Lakes St) | 10 | 2021-09-20 | 2021-09-21
RR1 61120 | GRP-2021-RR1.2.16.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (Neiman St & 118' NNPL Cora St) | 5 | 2021-09-20 | 2021-09-20
RR1 61200 | GRP-2021-RR1.2.17.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (Stoner St & Forest St) | 6 | 2021-09-20 | 2021-09-20
RR1 61360 | GRP-2021-RR1.2.19.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (Forest St & River Rouge City Limits) | 5 | 2021-09-20 | 2021-09-20
AA3-5930 | GRP-2021-RR1.7.3.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (2) (W Glenwood & knox) | 3 | 2021-09-20 | 2021-09-20
AA3-6000 | GRP-2021-RR1.7.2.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (2) (82' NNPL Ridge & 265' NNPL W Charlotte) | 6 | 2021-09-20 | 2021-09-20
AA3-6070 | GRP-2021-RR1.7.4.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (2) (32' SSPL Knox & 8' SSPL W Alexis) | 19 | 2021-09-20 | 2021-09-23
SWDET2-13615 | PROJ-0951-SWDET2.80.1.2 | 2021 GRP - South West Detroit 2 | Install Services - ASO W Vernor 2 (Central & Beard) | 0 | 2021-09-20 | 2021-09-20
SWDET2-13765 | PROJ-0951-SWDET2.30.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Witt (Lawndale & EOM) | 0 | 2021-09-20 | 2021-09-20
SWDET2-13925 | PROJ-0951-SWDET2.30.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Witt (Elsmere & Lawndale) | 15 | 2021-09-20 | 2021-09-22
SWDET2-13845 | PROJ-0951-SWDET2.38.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Avis (Elsmere & Lawndale) | 23 | 2021-09-20 | 2021-09-23
SWDET2-14405 | PROJ-0951-SWDET2.55.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Whitaker 1 (Lawndale & Mullane) | 33 | 2021-09-20 | 2021-09-27
SWDET2-14565 | PROJ-0951-SWDET2.72.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Cabot (Woodmere & ANO W Vernor) | 24 | 2021-09-20 | 2021-09-23
SWDET2-14645 | PROJ-0951-SWDET2.72.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Cabot (ANO Vernor & W Vernor) | 0 | 2021-09-20 | 2021-09-20
SWDET2-14725 | PROJ-0951-SWDET2.72.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Cabot (ASO Vernor & Mandale) | 29 | 2021-09-20 | 2021-09-24
SWDET2-14895 | PROJ-0951-SWDET2.64.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Whitaker 2 (Central & Green) | 31 | 2021-09-20 | 2021-09-27
SWDET2-15055 | PROJ-0951-SWDET2.64.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Whitaker 2 (Green & Beard) | 25 | 2021-09-20 | 2021-09-24
SWDET2-15105 | PROJ-0951-SWDET2.39.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Cahalan 1 (Lawndale & Mullane) | 27 | 2021-09-20 | 2021-09-24
SWDET2-15665 | PROJ-0951-SWDET2.66.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Casper (Tie-In & W Vernor) | 32 | 2021-09-20 | 2021-09-27
SWDET2-15905 | PROJ-0951-SWDET2.13.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Central 1 E (ASO Vernor & Logan) | 20 | 2021-09-20 | 2021-09-23
SWDET2-16075 | PROJ-0951-SWDET2.33.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Chamberlain (Lawndale & Springwells) | 37 | 2021-09-20 | 2021-09-28
SWDET2-16315 | PROJ-0951-SWDET2.25.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Elsmere 2 (Lafayette & Olivet) | 0 | 2021-09-20 | 2021-09-20
SWDET2-16475 | PROJ-0951-SWDET2.25.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Elsmere 2 (Olivet & Witt) | 2 | 2021-09-20 | 2021-09-20
SWDET2-16635 | PROJ-0951-SWDET2.25.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Elsmere 2 (Witt & Fort) | 1 | 2021-09-20 | 2021-09-20
SWDET2-16825 | PROJ-0951-SWDET2.73.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Ferris (ANO Vernor & EOM) | 0 | 2021-09-20 | 2021-09-20
SWDET2-17705 | PROJ-0951-SWDET2.61.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Senator 2 (Springwells & Central) | 32 | 2021-09-20 | 2021-09-27
SWDET2-18105 | PROJ-0951-SWDET2.49.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Green (W Vernor & EOM) | 41 | 2021-09-20 | 2021-09-28
SWDET2-18615 | PROJ-0951-SWDET2.68.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Inglis (Woodmere & W Vernor) | 77 | 2021-09-20 | 2021-10-06
SWDET2-18695 | PROJ-0951-SWDET2.37.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Rathbone (Lawndale & Springwells) | 49 | 2021-09-20 | 2021-09-30
SWDET2-18855 | PROJ-0951-SWDET2.35.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Lafayette (Lawndale & EOM) | 28 | 2021-09-20 | 2021-09-24
SWDET2-19025 | PROJ-0951-SWDET2.41.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Lane 1 (Elsmere & Lawndale) | 47 | 2021-09-20 | 2021-09-29
SWDET2-19185 | PROJ-0951-SWDET2.41.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Lane 1 (Lawndale & Springwells) | 51 | 2021-09-20 | 2021-09-30
SWDET2-19665 | PROJ-0951-SWDET2.51.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Logan 2 (EOM & Central) | 0 | 2021-09-20 | 2021-09-20
SWDET2-20345 | PROJ-0951-SWDET2.44.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Mason (Elsemere & Lawndale) | 46 | 2021-09-20 | 2021-09-29
SWDET2-20505 | PROJ-0951-SWDET2.43.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Mandale (Elsemere & Lawndale) | 35 | 2021-09-20 | 2021-09-27
SWDET2-21655 | PROJ-0951-SWDET2.75.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Norman (ANO Vernor & ANO Vernor) | 0 | 2021-09-20 | 2021-09-20
SWDET2-22215 | PROJ-0951-SWDET2.28.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Olivet (Lawndale & EOM) | 11 | 2021-09-20 | 2021-09-21
SWDET2-22535 | PROJ-0951-SWDET2.77.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Pearl (Tie-In & ANO Vernor) | 82 | 2021-09-20 | 2021-10-07
SWDET2-22695 | PROJ-0951-SWDET2.69.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Pitt (Springwells & Casper) | 2 | 2021-09-20 | 2021-09-20
SWDET2-23975 | PROJ-0951-SWDET2.82.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 1W (W Vernor & ASO Vernor) | 0 | 2021-09-20 | 2021-09-20
SWDET2-24055 | PROJ-0951-SWDET2.82.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 1W (ASO Vernor & Chamberlain) | 32 | 2021-09-20 | 2021-09-27
SWDET2-24425 | PROJ-0951-SWDET2.1.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Dix 1 (Railroad & W Vernor) | 3 | 2021-09-20 | 2021-09-27
RR1 5481 | GRP-2021-RR.1.1.2 | 2021 GRP - Risk Rank | Install Services - Corbett 2 (Coplin & Chalmers) | 33 | 2021-09-20 | 2021-09-24
RR1 5641 | GRP-2021-RR.3.1.2 | 2021 GRP - Risk Rank | Install Services - Wayburn (Berkshire & Evanston) | 76 | 2021-09-20 | 2021-10-04
RR1 5721 | GRP-2021-RR.4.1.2 | 2021 GRP - Risk Rank | Install Services - Manistique (E Jefferson & Essex) | 22 | 2021-09-20 | 2021-09-23
RR1 6121 | GRP-2021-RR.9.1.2 | 2021 GRP - Risk Rank | Install Services - Spring Garden 1 (Chalmers & Hayes) | 30 | 2021-09-20 | 2021-09-29
RR1 6841 | GRP-2021-RR.19.1.2 | 2021 GRP - Risk Rank | Install Services - McDougall (Davison & Carpenter) | 30 | 2021-09-20 | 2021-09-24
RR1 6921 | GRP-2021-RR.20.1.2 | 2021 GRP - Risk Rank | Install Services - ANO E Grand (John R & Melrose) | 12 | 2021-09-20 | 2021-09-22
RR1 7001 | GRP-2021-RR.21.1.2 | 2021 GRP - Risk Rank | Install Services - Dwyer (Charles & Casemere) | 18 | 2021-09-20 | 2021-09-22
RR1 7321 | GRP-2021-RR.26.1.2 | 2021 GRP - Risk Rank | Install Services - Alger (Woodward & Beaubien) | 24 | 2021-09-20 | 2021-09-23
RR1 7501 | GRP-2021-RR.28.1.2 | 2021 GRP - Risk Rank | Install Services - Calvert (Hamilton & Woodward) | 70 | 2021-09-20 | 2021-10-04
RR1 7661 | GRP-2021-RR.30.1.2 | 2021 GRP - Risk Rank | Install Services - Grand River (61' NNPL Whitney & Whitney) | 1 | 2021-09-20 | 2021-09-20
RR1 8141 | GRP-2021-RR.36.1.2 | 2021 GRP - Risk Rank | Install Services - Canton (EOM 100' NNPL Farnsworth & Gration) | 24 | 2021-09-20 | 2021-09-23
RR1 8381 | GRP-2021-RR.39.1.2 | 2021 GRP - Risk Rank | Install Services - Fairport (E McNichols & Gratiot) | 12 | 2021-09-20 | 2021-09-21
RR1 8461 | GRP-2021-RR.40.1.2 | 2021 GRP - Risk Rank | Install Services - Glenwood (Gratiot & Chalmers) | 22 | 2021-09-20 | 2021-09-23
RR1 9021 | GRP-2021-RR.47.1.2 | 2021 GRP - Risk Rank | Install Services - Minden (Conner & Gunston) | 70 | 2021-09-20 | 2021-10-06
EDET1 502886 | GRP-2021-ED1.4.3.2 | 2021 GRP - East Detroit 1 | Install Services - ANO Mack Ave (1) (Somerset Ave & Balfour Rd) | 2 | 2021-09-20 | 2021-09-20
EDET1 503366 | GRP-2021-ED1.11.3.2 | 2021 GRP - East Detroit 1 | Install Services - ASO E Warren Ave (3) (Grayton St & Harvard Rd) | 1 | 2021-09-20 | 2021-09-20
EDET1 503526 | GRP-2021-ED1.11.5.2 | 2021 GRP - East Detroit 1 | Install Services - ASO E Warren Ave (3) (E Warren Ave & Woodshall St) | 17 | 2021-09-20 | 2021-09-22
EDET1 503606 | GRP-2021-ED1.11.6.2 | 2021 GRP - East Detroit 1 | Install Services - ASO E Warren Ave (3) (Neff Ave & Hereford St) | 3 | 2021-09-20 | 2021-09-20
EDET1 504576 | GRP-2021-ED1.18.3.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Cadieux Rd) | 0 | 2021-09-20 | 2021-09-20
EDET1 504656 | GRP-2021-ED1.18.4.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) (Cadieux Rd & ANO E Warren Ave) | 0 | 2021-09-20 | 2021-09-20
EDET1 504736 | GRP-2021-ED1.18.5.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) (Cadieux Dr & ASO E Warren Ave) | 1 | 2021-09-20 | 2021-09-20
EDET1 504816 | GRP-2021-ED1.18.6.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Woodhall St) | 1 | 2021-09-20 | 2021-09-20
EDET1 504896 | GRP-2021-ED1.18.7.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) (E Warren Ave & ASO E Warren Ave @ Woodhall St (West Side)) | 0 | 2021-09-20 | 2021-09-20
EDET1 504976 | GRP-2021-ED1.18.8.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) (Caduiex St & Neff Ave) | 2 | 2021-09-20 | 2021-09-20
EDET1 505056 | GRP-2021-ED1.18.9.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) S (Woodhall St & Neff Ave) | 1 | 2021-09-20 | 2021-09-20
EDET1 505216 | GRP-2021-ED1.18.11.2 | 2021 GRP - East Detroit 1 | Install Services - E Warren Ave (3) S (Bishop St & Grayton St) | 0 | 2021-09-20 | 2021-09-20
NDET3-5110 | GRP-2021-ND3.4.1.2 | 2021 GRP - North Detroit 3 | Install Services - E Outer Dr (North) - (Anglin St & Mt Elliot St) | 76 | 2021-09-20 | 2021-10-05
NDET3-7410 | GRP-2021-ND3.1.1.2 | 2021 GRP - North Detroit 3 | Install Services - 8 Mile Rd (M102) (1) (Harned St & Sunset St) | 19 | 2021-09-20 | 2021-09-20
NDET3-4930 | GRP-2021-ND3.3.1.2 | 2021 GRP - North Detroit 3 | Install Services - E Outer Dr (South) - (Anglin St & Mt Elliott St) | 73 | 2021-09-20 | 2021-10-04
NDET3-6440 | GRP-2021-ND3.10.1.2 | 2021 GRP - North Detroit 3 | Install Services - ANO 7 Mile Rd (2) (Ryan Rd & Bloom St) | 13 | 2021-09-20 | 2021-09-21
NDET3-6400 | GRP-2021-ND3.11.1.2 | 2021 GRP - North Detroit 3 | Install Services - ANO 7 Mile Rd (3) (Bloom & Mound Rd)) | 4 | 2021-09-20 | 2021-09-20
NDET3-5005 | GRP-2021-ND3.14.1.2 | 2021 GRP - North Detroit 3 | Install Services - Dwyer St (2) (E Outer Dr & ANO 7 Mile Rd) | 73 | 2021-09-20 | 2021-10-04
NDET3-6680 | GRP-2021-ND3.18.1.2 | 2021 GRP - North Detroit 3 | Install Services - Filer Ave (2) (Emery St & ANO 7 Mile Rd) | 9 | 2021-09-20 | 2021-09-21
NDET3-5195 | GRP-2021-ND3.19.1.2 | 2021 GRP - North Detroit 3 | Install Services - Gable Ave (E Outer Dr & ANO 7 Mile Rd) | 74 | 2021-09-20 | 2021-10-04
NDET3-4615 | GRP-2021-ND3.21.1.2 | 2021 GRP - North Detroit 3 | Install Services - Mt Elliote St (2) (E Outer Dr & ANO 7 Mile Rd) | 21 | 2021-09-20 | 2021-09-23
NDET3-5585 | GRP-2021-ND3.24.1.2 | 2021 GRP - North Detroit 3 | Install Services - Albany Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 40 | 2021-09-20 | 2021-09-27
NDET3-6900 | GRP-2021-ND3.25.1.2 | 2021 GRP - North Detroit 3 | Install Services - Bloom St (2) (E Outer Dr & E Lantz Ave) | 3 | 2021-09-20 | 2021-09-20
NDET3-6325 | GRP-2021-ND3.26.1.2 | 2021 GRP - North Detroit 3 | Install Services - Buffalo St (2) (E Outer Dr & ANO 7 Mile Rd) | 82 | 2021-09-20 | 2021-10-05
NDET3-5925 | GRP-2021-ND3.27.1.2 | 2021 GRP - North Detroit 3 | Install Services - Caldwell St (2) (E Outer Dr & Emery St) | 51 | 2021-09-20 | 2021-09-29
NDET3-4985 | GRP-2021-ND3.28.1.2 | 2021 GRP - North Detroit 3 | Install Services - Conley Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 97 | 2021-09-20 | 2021-10-08
NDET3-6495 | GRP-2021-ND3.29.1.2 | 2021 GRP - North Detroit 3 | Install Services - Dean Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 82 | 2021-09-20 | 2021-10-05
NDET3-5735 | GRP-2021-ND3.32.1.2 | 2021 GRP - North Detroit 3 | Install Services - Eureka St (E Outer Dr & ANO 7 Mile Rd) | 56 | 2021-09-20 | 2021-09-30
NDET3-5025 | GRP-2021-ND3.33.1.2 | 2021 GRP - North Detroit 3 | Install Services - Fenelon Ave (2) (E Outer Dr & 7 Mile Rd) | 67 | 2021-09-20 | 2021-10-01
NDET3-5555 | GRP-2021-ND3.34.1.2 | 2021 GRP - North Detroit 3 | Install Services - Hasse Ave (E Outer Dr & ANO 7 Mile Rd) | 66 | 2021-09-20 | 2021-10-01
NDET3-5375 | GRP-2021-ND3.35.1.2 | 2021 GRP - North Detroit 3 | Install Services - Healy St (E Outer Dr & ANO 7 Mile Rd) | 74 | 2021-09-20 | 2021-10-04
NDET3-5945 | GRP-2021-ND3.36.1.2 | 2021 GRP - North Detroit 3 | Install Services - Justine Ave (E Outer Dr & 7 Mile Rd) | 81 | 2021-09-20 | 2021-10-05
NDET3-7240 | GRP-2021-ND3.37.1.2 | 2021 GRP - North Detroit 3 | Install Services - Keystone St (2) (E Lantz St & ANO 7 Mile Rd) | 70 | 2021-09-20 | 2021-10-04
NDET3-5205 | GRP-2021-ND3.38.1.2 | 2021 GRP - North Detroit 3 | Install Services - Lamont Ave (E Outer Dr & 7 Mile Rd) | 68 | 2021-09-20 | 2021-10-04
NDET3-7315 | GRP-2021-ND3.39.1.2 | 2021 GRP - North Detroit 3 | Install Services - Moenart St (2) (EOM & E Lantz Ave) | 6 | 2021-09-20 | 2021-09-27
NDET3-7020 | GRP-2021-ND3.41.1.2 | 2021 GRP - North Detroit 3 | Install Services - Ryan Rd (2) (E Outer Dr & Emery St) | 71 | 2021-09-20 | 2021-09-20
NDET3-6245 | GRP-2021-ND3.42.1.2 | 2021 GRP - North Detroit 3 | Install Services - Shields St (E Outer Dr & ANO 7 Mile Rd) | 78 | 2021-09-20 | 2021-10-05
NDET3-7170 | GRP-2021-ND3.43.1.2 | 2021 GRP - North Detroit 3 | Install Services - Sunset St (2) (E Outer Dr & ANO 7 Mile Rd) | 92 | 2021-09-20 | 2021-10-07
NDET3-5780 | GRP-2021-ND3.44.1.2 | 2021 GRP - North Detroit 3 | Install Services - Syracuse Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 49 | 2021-09-20 | 2021-09-29
NDET3-5480 | GRP-2021-ND3.58.1.2 | 2021 GRP - North Detroit 3 | Install Services - Hamlet St (2) (Fenelon Ave & Mound Rd) | 0 | 2021-09-20 | 2021-09-20
NDET3-30 | GRP-2021-ND3.72.1.2 | 2021 GRP - North Detroit 3 | Install Services - Harned St (1) (8 Mile Rd (M102) & E Outer Dr) | 75 | 2021-09-20 | 2021-10-05
NDET3-55 | GRP-2021-ND3.77.1.2 | 2021 GRP - North Detroit 3 | Install Services - Klinger St (2) (E Outer Dr& 7 Mile Rd) | 75 | 2021-09-20 | 2021-10-04
NDET3-4380 | GRP-2021-ND3.88.1.2 | 2021 GRP - North Detroit 3 | Install Services - 7 Mile Rd (1) (Harned St & Mitchell St) | 4 | 2021-09-20 | 2021-09-20
NDET3-6515 | GRP-2021-ND3.91.1.2 | 2021 GRP - North Detroit 3 | Install Services - ANO 7 Mile Rd (1) (Mitchell St & Ryan St) | 13 | 2021-09-20 | 2021-09-21
NDET3-6065 | GRP-2021-ND3.45.1.2 | 2021 GRP - North Detroit 3 | Install Services - 8 Mile Rd (2) (Mound Rd & Dwyer St) | 0 | 2021-09-20 | 2021-09-20
NDET3-6890 | GRP-2021-ND3.25.3.2 | 2021 GRP - North Detroit 3 | Install Services - Bloom St (2) (E Lantz Ave & ANO 7Mile Rd) | 67 | 2021-09-20 | 2021-10-01
NDET3-6370 | GRP-2021-ND3.27.3.2 | 2021 GRP - North Detroit 3 | Install Services - Caldwell St (2) (Emery St & ANO 7 Mile Rd) | 8 | 2021-09-20 | 2021-09-21
NDET3-5535 | GRP-2021-ND3.58.3.2 | 2021 GRP - North Detroit 3 | Install Services - Hamlet St (2) (Mound Rd & Dwyer St) | 0 | 2021-09-20 | 2021-09-20
NDET3-7340 | GRP-2021-ND3.39.3.2 | 2021 GRP - North Detroit 3 | Install Services - Moenart St (2) (E Outer Dr & ANO 7 Mile Rd) | 10 | 2021-09-20 | 2021-09-27
NDET3-4530 | GRP-2021-ND3.4.2.2 | 2021 GRP - North Detroit 3 | Install Services - E Outer Dr (North) - (Mt Elliot St & Conrail) | 1 | 2021-09-20 | 2021-09-20
NDET3-6990 | GRP-2021-ND3.41.3.2 | 2021 GRP - North Detroit 3 | Install Services - Ryan Rd (2) (Ryan Rd & Ryan Rd) | 0 | 2021-09-20 | 2021-09-20
NDET3-6960 | GRP-2021-ND3.41.2.2 | 2021 GRP - North Detroit 3 | Install Services - Ryan Rd (2) (Emery St & ANO 7 Mile Rd) | 27 | 2021-09-20 | 2021-09-20
NDET3-5380 | GRP-2021-ND3.31.1.2 | 2021 GRP - North Detroit 3 | Install Services - Mound Rd (E. Outer Dr. & ANO 7 Mile Rd) | 10 | 2021-09-20 | 2021-09-21
NDET3-715 | GRP-2021-ND3.3.10.2 | 2021 GRP - North Detroit 3 | Install Services - E Outer Dr (South) - (Mt Elliot St & Filer Ave) | 0 | 2021-09-20 | 2021-09-20
NDET3-720 | GRP-2021-ND3.3.11.2 | 2021 GRP - North Detroit 3 | Install Services - E Outer Dr (South) - (Filer Ave & EOM) | 1 | 2021-09-20 | 2021-09-20
NDET3-6375 | GRP-2021-ND3.11.3.2 | 2021 GRP - North Detroit 3 | Install Services - ANO 7 Mile Rd (3) (Mound Rd & Mt Elliott) | 3 | 2021-09-20 | 2021-09-20
NDET3-6285 | GRP-2021-ND3.11.2.2 | 2021 GRP - North Detroit 3 | Install Services - ANO 7 Mile Rd (3) (Mt Elliott & Filer Ave) | 4 | 2021-09-20 | 2021-09-20
NCDET - 6675 | NEWPROJ-6.59.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - ANO Fenkell 4 (Hubbell & Stansbury) | 4 | 2021-09-20 | 2021-09-21
RR1 11391 | GRP-2021-FR.65.1.2 | 2021 GRP - Field Recommendation | Install Services - Rohns (Mack & Goethe) | 11 | 2021-09-20 | 2021-09-20
RR1 10861 | GRP-2021-FR.59.1.2 | 2021 GRP - Field Recommendation | Install Services - Mack (Crane & McClellan) | 1 | 2021-09-20 | 2021-09-20
RR1 63080 | GRP-2021-RR1.25.1.2 | 2021 GRP - River Rouge | MMO - Burke 2 (Ruloff St & Louis St) | 3 | 09-20-21* | 2021-09-20
RR1 63100 | GRP-2021-RR1.43.1.2 | 2021 GRP - River Rouge | MMO - Goodell (Coolidge Hwy & E Great Lakes) | 13 | 09-20-21* | 2021-09-22
RR1 63110 | GRP-2021-RR1.70.1.2 | 2021 GRP - River Rouge | MMO - Hill St (Ironton St & Alexander St) | 6 | 09-20-21* | 2021-09-20
RR1 63120 | GRP-2021-RR1.54.1.2 | 2021 GRP - River Rouge | MMO - Leroy (Bruke St & Genessee St) | 3 | 09-20-21* | 2021-09-20
RR1 63150 | GRP-2021-RR1.64.1.2 | 2021 GRP - River Rouge | MMO - Walnut St (Genessee St & Richter) | 27 | 09-20-21* | 2021-09-24
EDET1 507336 | GRP-2021-ED1.35.1.2 | 2021 GRP - East Detroit 1 | Install Services - ANO E Warren Ave (1) (Devonshire Rd & E Outer Dr) | 18 | 2021-09-20 | 2021-09-22
EDET1 507346 | GRP-2021-ED1.80.2.2 | 2021 GRP - East Detroit 1 | Install Services - ANO E Warren Ave (2) (Neff Ave & Hereford St) | 4 | 2021-09-20 | 2021-09-20
EDET1 507356 | GRP-2021-ED1.80.3.2 | 2021 GRP - East Detroit 1 | Install Services - ANO E Warren Ave (2) (E Warren Ave & Woodhall St) | 11 | 2021-09-20 | 2021-09-21
EDET1 507366 | GRP-2021-ED1.80.1.2 | 2021 GRP - East Detroit 1 | Install Services - ANO E Warren Ave (2) (E Outer Dr & Cadiuex Rd) | 14 | 2021-09-20 | 2021-09-22
RR1 11141 | GRP-2021-RR.62.1.2 | 2021 GRP - Risk Rank | Install Services - Nevada (WO Moenart & Bloom) | 0 | 2021-09-20 | 2021-09-20
WCDET1-1555295 | GRP-2021-WCDet1.30.4.2 | 2021 GRP - West Central Detroit 1 | Install Services - Buena Vista 1 (Stoepel & Livernois) | 0 | 2021-09-20 | 2021-09-20
Milestone 4 | PROJ-0951-WDET9-4.53 | 2020 GRP - Carry Over - West Detroit 9 | Install Service Finish Milestone | 0 |  | 09-20-21*
NDET3-7980 | GRP-2021-ND3.9.1.2 | 2021 GRP - North Detroit 3 | Install Services - 7 Mile Rd (3) (Sherwood & Conrail RR) | 0 | 2021-09-20 | 2021-09-20
WCDET1-1556245 | GRP-2021-WCDet1.52.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Quincy 2 (ANO Fenkell& Bourke) | 38 | 2021-09-20 | 2021-09-20
Muni7250 | PROJ-0951-MUN-2.2.1.2 | 2021 GRP - Municipality | Install Services - Chicago 2 (Wyoming & EOM) | 1 | 2021-09-20 | 2021-09-20
Muni7330 | PROJ-0951-MUN-2.3.1.2 | 2021 GRP - Municipality | Install Services - Wyoming (ANO Chicago & Chicago) | 1 | 2021-09-20 | 2021-09-20
Muni7410 | PROJ-0951-MUN-2.4.1.2 | 2021 GRP - Municipality | Install Services - ANO Chicago (Griggs & Wyoming) | 1 | 2021-09-20 | 2021-09-20
Muni7490 | PROJ-0951-MUN-2.5.1.2 | 2021 GRP - Municipality | Install Services - Griggs (ANO Chicago & Chicago) | 1 | 2021-09-20 | 2021-09-20
Muni7570 | PROJ-0951-MUN-2.6.1.2 | 2021 GRP - Municipality | Install Services - W Chicago 1 (Pinehurst & Griggs) | 9 | 2021-09-20 | 2021-09-20
Muni7730 | PROJ-0951-MUN-2.6.2.2 | 2021 GRP - Municipality | Install Services - W Chicago 1 (Pinehurst & Birwood) | 4 | 2021-09-20 | 2021-09-20
Muni7810 | PROJ-0951-MUN-2.9.1.2 | 2021 GRP - Municipality | Install Services - Mendota (Chicago & ASO Chicago) | 10 | 2021-09-20 | 2021-09-20
Muni7890 | PROJ-0951-MUN-2.10.1.2 | 2021 GRP - Municipality | Install Services - Birwood (Chicago & ASO Chicago) | 1 | 2021-09-20 | 2021-09-20
Muni7970 | PROJ-0951-MUN-2.11.1.2 | 2021 GRP - Municipality | Install Services - ASO Chicago (Pinehurst & Birwood) | 1 | 2021-09-20 | 2021-09-20
Muni8210 | PROJ-0951-MUN-2.13.1.2 | 2021 GRP - Municipality | Install Services - Magnolia (Vinewood & Mckinley) | 3 | 2021-09-20 | 2021-10-01
Muni8370 | PROJ-0951-MUN-2.15.1.2 | 2021 GRP - Municipality | Install Services - West Grand Blvd (1) (West Grand Blvd & EOM) | 2 | 2021-09-20 | 2021-10-01
Muni8530 | PROJ-0951-MUN-2.17.1.2 | 2021 GRP - Municipality | Install Services - Hubbard (West Grand Blvd & Michigan) | 4 | 2021-09-20 | 2021-10-01
Muni8610 | PROJ-0951-MUN-2.18.1.2 | 2021 GRP - Municipality | Install Services - Mckinley (NO Magnolia & Magnolia) | 3 | 2021-09-20 | 2021-10-01
Muni8690 | PROJ-0951-MUN-2.19.1.2 | 2021 GRP - Municipality | Install Services - Vinewood (Magnolia & Michigan) | 9 | 2021-09-20 | 2021-10-01
Muni8770 | PROJ-0951-MUN-2.20.1.2 | 2021 GRP - Municipality | Install Services - Lahser (Santa Clara & Mcnichols) | 30 | 2021-09-20 | 2021-10-01
Muni9090 | PROJ-0951-MUN-2.15.2.2 | 2021 GRP - Municipality | Install Services - West Grand Blvd (1) (West Grand Blvd & Vinewood) | 1 | 2021-09-20 | 2021-10-01
Muni9170 | PROJ-0951-MUN-2.15.3.2 | 2021 GRP - Municipality | Install Services - West Grand Blvd (1) (EOM & Mckinley) | 1 | 2021-09-20 | 2021-10-01
Muni9250 | PROJ-0951-MUN-2.22.4.2 | 2021 GRP - Municipality | Install Services - West Grand Blvd (2) (Mckinley & Ash) | 1 | 2021-09-20 | 2021-10-01
Muni9330 | PROJ-0951-MUN-2.18.2.2 | 2021 GRP - Municipality | Install Services - Mckinley (Magnolia & West Grand Blvd) | 6 | 2021-09-20 | 2021-10-01
Ypsi 3-12750 | PROJ-0951-YSP3.39.3.2 | 2021 GRP - Ypsilanti 3 | Install Services - Tyler (Nevada & Desoto) | 1 | 2021-09-20 | 2021-09-20
AA4 29338 | GRP-2021-AA4.6.6.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 7th St (Jefferson & Jefferson Ct) | 1 | 2021-09-20 | 2021-09-20
Milestone 65 | PROJ-0951-NDET2-2.54 | 2020 GRP - Carry Over - North Detroit 2 | Services Finish Milestone | 0 |  | 09-20-21*
Milestone 4 | GRP-2021-CDet2.23 | 2021 GRP - Central Detroit 2 | Service Finish Milestone | 0 |  | 09-20-21*
RR1 5301 | GRP-2021-RR1.58.1.2 | 2021 GRP - River Rouge | Install Services - Coolidge Hwy 2 (W Jefferson & Burke St) | 1 | 2021-09-21 | 2021-09-21
RR1 51479 | GRP-2021-RR1.69.1.2 | 2021 GRP - River Rouge | Install Services - Genenssee St 2 (12' NSPL E Great Lakes St & 5' SNPL Forest St) | 24 | 2021-09-21 | 2021-09-24
WCDET1-9480 | GRP-2021-WCDet1.16.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Santa Rosa 2 (Buena Vista & Elmhurst) | 107 | 2021-09-21 | 2021-10-12
RR1 52670 | GRP-2021-RR1.50.3.2 | 2021 GRP - River Rouge | Install Services - Burke 1 (4' SNPL E Pleasant St & 3' SNPL Delisle St) | 1 | 2021-09-21 | 2021-09-21
RR1 52830 | GRP-2021-RR1.50.2.2 | 2021 GRP - River Rouge | Install Services - Burke 1 (3' SNPL Delisle St & 4' SNPL Coolidge Hwy) | 8 | 2021-09-21 | 2021-09-22
RR1 53150 | GRP-2021-RR1.50.5.2 | 2021 GRP - River Rouge | Install Services - Burke 1 (2' NSPL Coolidge Hwy & 2' NSPL W Oak St) | 4 | 2021-09-21 | 2021-09-21
RR1 53310 | GRP-2021-RR1.50.6.2 | 2021 GRP - River Rouge | Install Services - Burke 1 (2' NSPL W Oak St & 3' NSPL Maple St) | 3 | 2021-09-21 | 2021-09-21
RR1 56750 | GRP-2021-RR1.68.3.2 | 2021 GRP - River Rouge | Install Services - Forest St (Genessee St & Ironton Ave) | 51 | 2021-09-21 | 2021-10-01
RR1 60480 | GRP-2021-RR1.2.8.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (Coolidge Hwy & Oak St) | 3 | 2021-09-21 | 2021-09-21
RR1 60720 | GRP-2021-RR1.2.11.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (Maple St & E Great Lakes St) | 2 | 2021-09-21 | 2021-09-21
NDET3-4230 | GRP-2021-ND3.66.1.2 | 2021 GRP - North Detroit 3 | Install Services - Charest St (2) (E Outer Dr & ANO 7 Mile Rd) | 62 | 2021-09-21 | 2021-10-01
NDET3-7135 | GRP-2021-ND3.83.1.2 | 2021 GRP - North Detroit 3 | Install Services - Revere Ave (2) (E Outer Dr & 7 Mile Rd) | 77 | 2021-09-21 | 2021-10-04
RR1 11461 | GRP-2021-FR.66.1.2 | 2021 GRP - Field Recommendation | Install Services - Holcomb (Mack & 74' SSPL Mack) | 1 | 2021-09-21 | 2021-09-21
WCDET1-3555 | GRP-2021-WCDet1.30.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Buena Vista 1 (Turner & Turner) | 1 | 2021-09-21 | 2021-09-22
WCDET1-4115 | GRP-2021-WCDet1.37.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Stoepel 2 (Buena Vista & Fullerton) | 35 | 2021-09-21 | 2021-09-28
WCDET1-8180 | GRP-2021-WCDet1.10.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd South 1 (Stoepel & EOM) | 0 | 2021-09-21 | 2021-09-22
WCDET1-9880 | GRP-2021-WCDet1.27.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Stoepel 1 (Oakman & Buena Vista) | 79 | 2021-09-21 | 2021-10-06
WCDET1-1556115 | GRP-2021-WCDet1.28.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois 5 (Fullerton & Elmhurst) | 7 | 2021-09-21 | 2021-09-23
WCDET1-1556265 | GRP-2021-WCDet1.56.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Quincy 1 (EOM & John C Lodge Services Dr) | 0 | 2021-09-21 | 2021-09-22
RR1 5273 | GRP-2021-RR1.30.1.2 | 2021 GRP - River Rouge | Install Services - Myrtle (Division & W Jefferson) | 9 | 2021-09-22 | 2021-09-23
RR1 51477 | GRP-2021-RR1.67.1.2 | 2021 GRP - River Rouge | Install Services - Cattherine St (Alexander St & 179' WWPL Ironton St) | 16 | 2021-09-22 | 2021-09-24
RR1 56430 | GRP-2021-RR1.44.2.2 | 2021 GRP - River Rouge | Install Services - E Pleasasnt North (4' EWPL Burke St & 8' WEPL Genessee St) | 26 | 2021-09-22 | 2021-09-28
Ypsi 3-11880 | PROJ-0951-YSP3.40.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - S Pasadena Ave (Coolidge & State) | 14 | 2021-09-22 | 2021-09-23
AP 5080 | PROJ-0951-MMOAllen.80.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Seavitt 1 (Highland & Seavitt) | 0 | 2021-09-22 | 2021-09-22
NDET3-35 | GRP-2021-ND3.73.1.2 | 2021 GRP - North Detroit 3 | Install Services - Harned St (2) (E Outer Dr & ANO 7 Mile Rd) | 68 | 2021-09-22 | 2021-10-05
RR1 11531 | GRP-2021-FR.67.1.2 | 2021 GRP - Field Recommendation | Install Services - Belvidere (Mack & Charlevoix) | 16 | 2021-09-22 | 2021-09-24
CDET1 7000515 | PROJ-0951-CDET1-2.16 | 2020 GRP - Carry Over - Central Detroit 1 | Service Finish Milestone | 0 |  | 09-22-21*
GP5-701120 | PROJ-0951-GP 5 -3.23 | 2020 GRP - Carry Over - GP 5 | Service Finish Milestone | 0 |  | 09-22-21*
RR1 5265 | GRP-2021-RR1.21.1.2 | 2021 GRP - River Rouge | Install Services - Fairmont (Nieman & Cora) | 32 | 2021-09-23 | 2021-09-30
RR1 5275 | GRP-2021-RR1.32.1.2 | 2021 GRP - River Rouge | Install Services - Summit St (2' NSPL Nieman St & 4' SNPL Cora St) | 27 | 2021-09-23 | 2021-09-29
AA4 20599 | GRP-2021-AA4.12.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - 4th St (W Jefferson St & W Madison St) | 19 | 2021-09-23 | 2021-09-29
WCDET1-13400 | GRP-2021-WCDet1.31.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Elmhurst (American & AWO Livernois) | 14 | 2021-09-23 | 2021-09-23
WCDET1-13410 | GRP-2021-WCDet1.31.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Elmhurst (AWO Livernois & American) | 0 | 2021-09-23 | 2021-09-24
RR1 56910 | GRP-2021-RR1.42.3.2 | 2021 GRP - River Rouge | Install Services - Genessee 1 (Coolidge Hwy & E Great Lakes St) | 5 | 2021-09-23 | 2021-09-23
RR1 60400 | GRP-2021-RR1.2.7.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (56' NNPL Coolidge Hwy & 4' SNPL Coolidge Hwy) | 1 | 2021-09-23 | 2021-09-23
NDET3-4260 | GRP-2021-ND3.79.1.2 | 2021 GRP - North Detroit 3 | Install Services - Mitchell St (2) (E Outer Dr & ANO 7 Mile Rd) | 60 | 2021-09-23 | 2021-10-05
WCDET1-1556195 | GRP-2021-WCDet1.28.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois 5 (Elmhurst & Burlingame) | 5 | 2021-09-23 | 2021-09-24
WCDET1-4275 | GRP-2021-WCDet1.39.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Bryden (Utica & Elmhurst) | 4 | 2021-09-24 | 2021-09-24
RR1 54350 | GRP-2021-RR1.16.3.2 | 2021 GRP - River Rouge | Install Services - Division (W Cicotte St & 10' NSPL W Pleasant St) | 6 | 2021-09-24 | 2021-09-24
RR1 58130 | GRP-2021-RR1.54.3.2 | 2021 GRP - River Rouge | Install Services - Leroy (Genessee St & Richter St) | 35 | 2021-09-24 | 2021-10-01
RR1 58630 | GRP-2021-RR1.56.3.2 | 2021 GRP - River Rouge | Install Services - Richter (Maple St & E Great Lakes St) | 39 | 2021-09-24 | 2021-10-04
SWDET2-17625 | PROJ-0951-SWDET2.61.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Senator 2 (Green & Beard) | 18 | 2021-09-24 | 2021-09-28
AP 4130 | PROJ-0951-MMOAllen.62.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Park 3 (Moore & Midway) | 33 | 2021-09-24 | 2021-10-04
NDET3-7440 | GRP-2021-ND3.81.1.2 | 2021 GRP - North Detroit 3 | Install Services - Norwood St (2) (E Outer Dr & 7 Mile Rd) | 73 | 2021-09-24 | 2021-10-08
WCDET1-7460 | GRP-2021-WCDet1.45.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd West 2 (Prairie & Davison) | 17 | 2021-09-24 | 2021-09-29
RR1 5291 | GRP-2021-RR1.48.1.2 | 2021 GRP - River Rouge | Install Services - Delisle (W Jefferson & Burke) | 4 | 2021-09-27 | 2021-09-27
AP 1800 | PROJ-0951-MMOAllen.11.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Becker 3 (Wick & Midway) | 45 | 2021-09-27 | 2021-10-08
RR1 11321 | GRP-2021-FR.64.1.2 | 2021 GRP - Field Recommendation | Install Services - Rolfs (571' NNPL Mack & Mack) | 2 | 2021-09-27 | 2021-09-27
Ypsi 3-3370 | PROJ-0951-YSP3.6.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Coolidge (McCartney & Pasadena) | 1 | 2021-09-28 | 2021-09-28
RR1 5299 | GRP-2021-RR1.56.1.2 | 2021 GRP - River Rouge | Install Services - Richter (E Pleasant St & Leroy St) | 6 | 2021-09-28 | 2021-09-28
AA4 20614 | GRP-2021-AA4.28.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Jefferson St North (12' EWPL 5Th St & S 1St St) | 4 | 2021-09-28 | 2021-09-28
WCDET1-1555255 | GRP-2021-WCDet1.54.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald East 2 (Oakman & Buena Vista) East adresses only | 55 | 2021-09-28 | 2021-10-07
WCDET1-7220 | GRP-2021-WCDet1.35.3.4 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd East 2 (Prairie & Davison) | 16 | 2021-09-28 | 2021-09-29
RR1 54830 | GRP-2021-RR1.46.3.2 | 2021 GRP - River Rouge | Install Services - E Cicotte (Burke St & Harris St) | 25 | 2021-09-29 | 2021-10-05
SWDET2-18265 | PROJ-0951-SWDET2.34.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Homer (Lawndale & Springwells) | 63 | 2021-09-29 | 2021-10-13
NDET3-20 | GRP-2021-ND3.71.1.2 | 2021 GRP - North Detroit 3 | Install Services - Gallagher St (2) (E Outer Dr & ANO 7 Mile Rd) | 79 | 2021-09-29 | 2021-10-14
Muni11570 | PROJ-0951-MUN-2.26.2.2 | 2021 GRP - Municipality | Install Services - ANO W Warren Ave (1) (Archdale St & Clayburn St) | 10 | 2021-09-29 | 2021-10-12
RR1 5260 | GRP-2021-RR1.16.1.2 | 2021 GRP - River Rouge | Install Services - Division (Victoria St & W Cicotte St) | 1 | 2021-09-30 | 2021-09-30
SWDET2-6520 | PROJ-0951-SWDET2.62.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Stratton 1 (Beard & Waterman) | 0 | 2021-09-30 | 2021-09-30
WCDET1-7940 | GRP-2021-WCDet1.10.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd South 1 (Monica & Santa Rosa) | 4 | 2021-09-30 | 2021-10-01
WCDET1-10040 | GRP-2021-WCDet1.37.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Stoepel 2 (Fullerton & Elmhurst) | 44 | 2021-09-30 | 2021-10-07
RR1 52510 | GRP-2021-RR1.25.1.2 | 2021 GRP - River Rouge | Install Services - Burke 2 (Louis St & Nieman St) | 11 | 2021-09-30 | 2021-10-01
RR1 54430 | GRP-2021-RR1.16.2.2 | 2021 GRP - River Rouge | Install Services - Division (10' NSPL W Pleasant St & Linden St) | 6 | 2021-09-30 | 2021-09-30
NDET3-7660 | GRP-2021-ND3.7.1.2 | 2021 GRP - North Detroit 3 | Install Services - Yonka (2) (7 Mile Rd & E Outer Dr) | 75 | 2021-09-30 | 2021-10-14
WCDET1-1556495 | GRP-2021-WCDet1.29.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - American (Tuxedo & Burlingame) | 0 | 2021-09-30 | 2021-10-01
NCDET - 6690 | NEWPROJ-6.1.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Appoline (Puritan & Fenkell) | 96 | 2021-10-01 | 2021-11-04
NCDET - 7155 | NEWPROJ-6.11.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Monte Vista (Puritan & Fenkell) | 107 | 2021-10-01 | 2021-10-28
AA4 20615 | GRP-2021-AA4.29.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Madison St 2 (S 7Th St & S 1St St) | 36 | 2021-10-01 | 2021-10-09
WCDET1-8100 | GRP-2021-WCDet1.10.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd South 1 (Santa Rosa & Stoepel) | 5 | 2021-10-01 | 2021-10-01
RR1 5293 | GRP-2021-RR1.51.1.2 | 2021 GRP - River Rouge | Install Services - Brownlee (E Anchor St & E Cicotte St) | 6 | 2021-10-04 | 2021-10-04
AA4 20464 | GRP-2021-AA4.10.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - 2nd St (W Jefferson St & W Madison St) | 20 | 2021-10-04 | 2021-10-11
SWDET2-1720 | PROJ-0951-SWDET2.4.1.2 | 2021 GRP - South West Detroit 2 | Install Services - ENO Pitt (Central & EOM) | 1 | 2021-10-04 | 2021-10-04
SWDET2-3320 | PROJ-0951-SWDET2.21.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Bank (Springwells & EOM) | 0 | 2021-10-04 | 2021-10-04
RR1 54510 | GRP-2021-RR1.16.4.2 | 2021 GRP - River Rouge | Install Services - Division (Linden St & Coolidge Hwy) | 1 | 2021-10-04 | 2021-10-04
WCDET1-1555635 | GRP-2021-WCDet1.50.4.2 | 2021 GRP - West Central Detroit 1 | Install Services - Fullerton (AWO Livernois & Livernois) | 0 | 2021-10-04 | 2021-10-04
SWDET2-2120 | PROJ-0951-SWDET2.6.1.2 | 2021 GRP - South West Detroit 2 | Install Services - W Vernor (Dix & Detroit City Limit) | 4 | 2021-10-05 | 2021-10-05
WCDET1-9160 | GRP-2021-WCDet1.46.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Santa Rosa 1 (Oakman & Davison) | 42 | 2021-10-05 | 2021-10-13
AA4 29348 | GRP-2021-AA4.9.4.2 | 2021 GRP - Ann Arbor 4 | Install Services - S Main (62' NNPL E Hoover Ave & Hill) | 10 | 2021-10-05 | 2021-10-11
WCDET1-1556285 | GRP-2021-WCDet1.29.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - American (Oakman & Tuxedo) | 5 | 2021-10-05 | 2021-10-06
RR1 5276 | GRP-2021-RR1.33.1.2 | 2021 GRP - River Rouge | Install Services - Victoria St (Division & W Jefferson) | 4 | 2021-10-06 | 2021-10-06
SWDET2-3720 | PROJ-0951-SWDET2.27.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Mint (Springwells & EOM) | 0 | 2021-10-06 | 2021-10-06
SWDET2-6600 | PROJ-0951-SWDET2.63.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Waterman 1 (W Vernor & EOM) | 5 | 2021-10-06 | 2021-10-06
NDET3-70 | GRP-2021-ND3.85.1.2 | 2021 GRP - North Detroit 3 | Install Services - Wexford (2) (E Outer Dr & 7 Mile Rd) | 73 | 2021-10-06 | 2021-10-20
RR1 9261 | GRP-2021-FR.50.1.2 | 2021 GRP - Field Recommendation | Install Services - Church (Woodward & John) | 6 | 2021-10-06 | 2021-10-11
RR1 11101 | GRP-2021-RR.11.1.2 | 2021 GRP - Risk Rank | Install Services - Novara (Crusade & Kelly) | 59 | 2021-10-06 | 2021-10-20
RR1 5279 | GRP-2021-RR1.36.1.2 | 2021 GRP - River Rouge | Install Services - W Great Lakes (Burke & W Jefferson) | 14 | 2021-10-07 | 2021-10-11
WCDET1-8680 | GRP-2021-WCDet1.26.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Monica West 1 (Oakman & Buena Vista) | 75 | 2021-10-07 | 2021-10-21
Muni11650 | PROJ-0951-MUN-2.26.3.2 | 2021 GRP - Municipality | Install Services - ANO W Warren Ave (1) (Clayburn St & Woodmont Ave) | 10 | 2021-10-07 | 2021-10-20
WCDET1-1955 | GRP-2021-WCDet1.9.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - AWO Livernois (Fullerton & Elmhurst) | 0 | 2021-10-07 | 2021-10-07
RR1 5271 | GRP-2021-RR1.28.1.2 | 2021 GRP - River Rouge | Install Services - Linden (4' WEPL Division St & 43' WWPL W Jefferson Ave) | 15 | 2021-10-08 | 2021-10-12
RR1 53630 | GRP-2021-RR1.4.3.2 | 2021 GRP - River Rouge | Install Services - Coolidge Hwy 1 (Division St & W Jefferson Ave) | 3 | 2021-10-08 | 2021-10-08
AP 2740 | PROJ-0951-MMOAllen.58.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Niver 2 (100' North Moore Ave & Midway) | 18 | 2021-10-08 | 2021-10-13
WCDET1-1060 | GRP-2021-WCDet1.4.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Turner (Schoolcraft & Davison) | 10 | 2021-10-08 | 2021-10-12
Milestone 4 | GRP-2021-ND3.23 | 2021 GRP - North Detroit 3 | Service Finish Milestone | 0 |  | 10-08-21*
AA4 20601 | GRP-2021-AA4.14.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - 6th St (W Jefferson St & W Madison St) | 17 | 2021-10-09 | 2021-10-15
AA4 25278 | GRP-2021-AA4.45.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Redeemer Ave (Pauline Blvd & Hewett Rd) | 3 | 2021-10-09 | 2021-10-09
NCDET - 7115 | NEWPROJ-6.10.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Meyers (Puritan & Fenkell) | 79 | 2021-10-11 | 2021-11-12
RR1 5284 | GRP-2021-RR1.42.1.2 | 2021 GRP - River Rouge | Install Services - Genessee 1 (E Pleasant St & Coolidge Hwy) | 2 | 2021-10-11 | 2021-10-11
WCDET1-4035 | GRP-2021-WCDet1.36.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Monica West 2 (Buena Vista & Elmhurst) | 108 | 2021-10-11 | 2021-11-01
SWDET2-5240 | PROJ-0951-SWDET2.46.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Cahalan 2 (EOM & Central) | 13 | 2021-10-11 | 2021-10-13
RR1 261 | GRP-2021-RR1.6.1.2 | 2021 GRP - River Rouge | Install Services - AWO Goodell St (Maple St & Coolidge Hwy) | 15 | 2021-10-11 | 2021-10-13
RR1 52190 | GRP-2021-RR1.6.3.2 | 2021 GRP - River Rouge | Install Services - AWO Goodell St (Maple St & E Great Lakes) | 14 | 2021-10-11 | 2021-10-13
RR1 54670 | GRP-2021-RR1.47.3.2 | 2021 GRP - River Rouge | Install Services - E Anchor (Burke St & Harris St) | 14 | 2021-10-11 | 2021-10-13
WCDET1-1556275 | GRP-2021-WCDet1.29.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - American (Burlingame & ANO Grand River) | 5 | 2021-10-11 | 2021-10-12
RR1 5272 | GRP-2021-RR1.29.1.2 | 2021 GRP - River Rouge | Install Services - Louis (Burke St & W Jefferson Ave) | 10 | 2021-10-12 | 2021-10-13
RR1 5300 | GRP-2021-RR1.57.1.2 | 2021 GRP - River Rouge | Install Services - Chestnut St (W Jefferson & 489' WWPL Genessee St) | 11 | 2021-10-12 | 2021-10-13
RR1 61960 | GRP-2021-RR1.39.4.2 | 2021 GRP - River Rouge | Install Services - W Pleasasnt (120' WWPL Division St & Division St) | 2 | 2021-10-12 | 2021-10-12
NDET3-4225 | GRP-2021-ND3.64.1.2 | 2021 GRP - North Detroit 3 | Install Services - Binder St (2) (E Outer Dr & ANO 7 Mile Rd) | 71 | 2021-10-12 | 2021-10-26
AA4 28978 | GRP-2021-AA4.49.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - Soule Blvd (102' SSPL Wakefield Ave & 373' SSPL Lutz Ave) | 1 | 2021-10-12 | 2021-10-14
SWDET2-7240 | PROJ-0951-SWDET2.70.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Springwells 2 (Dix & W Vernor) | 81 | 2021-10-13 | 2021-11-01
RR1 55150 | GRP-2021-RR1.45.1.2 | 2021 GRP - River Rouge | Install Services - E Henry (Burke St & 85' WWPL Byron St) | 16 | 2021-10-13 | 2021-10-15
RR1 5961 | GRP-2021-RR.7.1.2 | 2021 GRP - Risk Rank | Install Services - Mayfield (Chalmers & Kelly) | 37 | 2021-10-13 | 2021-10-20
WCDET1-3795 | GRP-2021-WCDet1.22.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Tuller (Schoolcraft & Davision) | 29 | 2021-10-13 | 2021-10-20
RR1 5277 | GRP-2021-RR1.34.1.2 | 2021 GRP - River Rouge | Install Services - W Anchor St (Division St & 7' WWPL W Jefferson Ave) | 8 | 2021-10-14 | 2021-10-14
WCDET1-4435 | GRP-2021-WCDet1.41.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Tuxedo (American & AWO Livernois) | 37 | 2021-10-14 | 2021-10-21
RR1 5297 | GRP-2021-RR1.54.1.2 | 2021 GRP - River Rouge | Install Services - Leroy (W Jefferson Ave & Burke St) | 3 | 2021-10-14 | 2021-10-14
Muni11730 | PROJ-0951-MUN-2.26.4.2 | 2021 GRP - Municipality | Install Services - ANO W Warren Ave (1) (Asbury Park & St Marys St) | 10 | 2021-10-14 | 2021-10-27
AA4 20611 | GRP-2021-AA4.25.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Tuner Park Ct (W Madison St & EOM) | 7 | 2021-10-15 | 2021-10-16
AA4 20829 | GRP-2021-AA4.38.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Hewett Rd (Russett Rd & Russell Rd) | 16 | 2021-10-16 | 2021-10-20
AA4 25948 | GRP-2021-AA4.5.5.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 1st St (Nob Hill Pl & 12' NNPL W Davis Ave) | 7 | 2021-10-16 | 2021-10-19
WCDET1-2275 | GRP-2021-WCDet1.53.54.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald Cr West 2 (Schoolcraft & Davison) | 10 | 2021-10-18 | 2021-10-19
Ypsi 3-7840 | PROJ-0951-YSP3.24.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Ponderosa (Woodglen & EOM) | 27 | 2021-10-19 | 2021-10-25
Ypsi 3-9330 | PROJ-0951-YSP3.30.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Sunnyglen (Glengrove & Nash) | 18 | 2021-10-19 | 2021-10-27
SWDET2-5720 | PROJ-0951-SWDET2.52.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Navy 1 (Lawndale & Springwells) | 63 | 2021-10-19 | 2021-11-02
WCDET1-13700 | GRP-2021-WCDet1.51.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Webb (American & AWO Livernois) | 40 | 2021-10-19 | 2021-10-26
SWDET2-15265 | PROJ-0951-SWDET2.46.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Cahalan 2 (Central & Green) | 23 | 2021-10-19 | 2021-10-22
RR1 5261 | GRP-2021-RR.17.1.2 | 2021 GRP - Risk Rank | Install Services - Corbett 1 (Annsbury & Coplin) | 86 | 2021-10-19 | 2021-11-05
WCDET1-2115 | GRP-2021-WCDet1.11.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Burlingame (American & Livernois) | 14 | 2021-10-19 | 2021-10-22
WCDET1-1555095 | GRP-2021-WCDet1.54.55.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald East 2 (Schoolcraft & EOM) East adresses only | 11 | 2021-10-19 | 2021-10-21
NCDET - 7260 | NEWPROJ-6.12.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Pinehurst (Puritan & ANO Fenkell) | 98 | 2021-10-20 | 2021-11-09
RR1 5295 | GRP-2021-RR1.40.1.2 | 2021 GRP - River Rouge | Install Services - W James (EOM @ 40' EEPL Dwight St & 4' EWPL Division St) | 9 | 2021-10-20 | 2021-10-20
RR1 5307 | GRP-2021-RR1.64.1.2 | 2021 GRP - River Rouge | Install Services - Walnut St (W Jefferson Ave & Genessee St) | 31 | 2021-10-20 | 2021-10-26
AA4 20620 | GRP-2021-AA4.34.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - 3rd St (W Jefferson St & W Madison St) | 21 | 2021-10-20 | 2021-10-25
AA4 27328 | GRP-2021-AA4.29.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Madison St 2 (S 1St St & 88' EEPL S Main St) | 10 | 2021-10-20 | 2021-10-23
WCDET1-14780 | GRP-2021-WCDet1.58.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Grand River Ave N (Monica & Monica) | 0 | 2021-10-20 | 2021-10-20
AP 4830 | PROJ-0951-MMOAllen.76.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Rosedale 2 (Englewood & Moore) | 27 | 2021-10-20 | 2021-10-26
WCDET1-1555345 | GRP-2021-WCDet1.55.10.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald Cr South 1 (Schoolcraft & Prairie) | 9 | 2021-10-20 | 2021-10-22
RR1 5261 | GRP-2021-RR1.17.1.2 | 2021 GRP - River Rouge | Install Services - Dwight (Linden & W Pleasant) | 9 | 2021-10-21 | 2021-10-22
WCDET1-2595 | GRP-2021-WCDet1.17.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois 4 (Davison & Davison) | 7 | 2021-10-21 | 2021-10-22
WCDET1-3235 | GRP-2021-WCDet1.26.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Monica West 1 (Ewald & Ewald) | 5 | 2021-10-21 | 2021-10-21
WCDET1-3315 | GRP-2021-WCDet1.27.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Stoepel 1 (Ewald & Ewald) | 1 | 2021-10-21 | 2021-10-21
WCDET1-4595 | GRP-2021-WCDet1.43.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - San Juan (Ewald & Ewald) | 12 | 2021-10-21 | 2021-10-22
AA4 20463 | GRP-2021-AA4.9.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - S Main (Hill St & W Hoover St) | 17 | 2021-10-21 | 2021-10-21
SWDET2-2600 | PROJ-0951-SWDET2.12.1.2 | 2021 GRP - South West Detroit 2 | Install Services - W Vernor 4 (Central & EOM) | 0 | 2021-10-21 | 2021-10-21
WCDET1-6740 | GRP-2021-WCDet1.14.4.2 | 2021 GRP - West Central Detroit 1 | Install Services - Prairie 1 (Ewald & Ewald) | 7 | 2021-10-21 | 2021-10-22
WCDET1-13940 | GRP-2021-WCDet1.58.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Grand River Ave N (Prairie & Monica) | 0 | 2021-10-21 | 2021-10-21
SWDET2-23445 | PROJ-0951-SWDET2.45.5.2 | 2021 GRP - South West Detroit 2 | Install Services - Mullane (At Whittaker) | 2 | 2021-10-21 | 2021-10-21
RR1 11251 | GRP-2021-FR.63.1.2 | 2021 GRP - Field Recommendation | Install Services - Easement (Church & Candler) | 4 | 2021-10-21 | 2021-10-28
WCDET1-4835 | GRP-2021-WCDet1.46.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Santa Rosa 1 (Ewald & Ewald) | 5 | 2021-10-21 | 2021-10-22
AA4 20608 | GRP-2021-AA4.21.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Nob Hill Pl (S 1st St & Nob Hill Ct) | 2 | 2021-10-21 | 2021-10-22
WCDET1-14100 | GRP-2021-WCDet1.58.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Grand River Ave N (Monica & Stoepel) | 3 | 2021-10-21 | 2021-10-22
WCDET1-1555425 | GRP-2021-WCDet1.55.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald Cr South 1 (Prairie & Ewald) | 14 | 2021-10-21 | 2021-10-25
WCDET1-1555 | GRP-2021-WCDet1.3.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Burnette (Grand River & I-96 Service Rd) | 3 | 2021-10-22 | 2021-10-22
WCDET1-2675 | GRP-2021-WCDet1.18.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois 6 (Burlingame & Grand River) | 5 | 2021-10-22 | 2021-10-22
WCDET1-2995 | GRP-2021-WCDet1.22.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Tuller (Schoolcraft & Schoolcratf) | 12 | 2021-10-22 | 2021-10-26
WCDET1-1556235 | GRP-2021-WCDet1.52.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Quincy 2 (Bourke & EOM) | 18 | 2021-10-22 | 2021-10-22
WCDET1-3715 | GRP-2021-WCDet1.32.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Georgeland (Stoepel & Livernois) | 5 | 2021-10-22 | 2021-10-25
WCDET1-1555475 | GRP-2021-WCDet1.38.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Livernois - Easment (Livernions & EOM) | 3 | 2021-10-22 | 2021-10-25
Ypsi 3-1050 | PROJ-0951-YSP3.5.4.1 | 2021 GRP - Ypsilanti 3 | Install Services - McCartney 1 (Tyler & EOM) | 1 | 2021-10-25 | 2021-10-25
WCDET1-2915 | GRP-2021-WCDet1.21.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Annland (Stoepel & Livernois) | 6 | 2021-10-25 | 2021-10-25
AA4 20837 | GRP-2021-AA4.46.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Russell Rd (Russett Rd & Hewett Dr) | 14 | 2021-10-25 | 2021-10-29
SWDET2-9645 | PROJ-0951-SWDET2.12.2.2 | 2021 GRP - South West Detroit 2 | Install Services - W Vernor 4 (Central & Waterman) | 31 | 2021-10-25 | 2021-11-01
RR1 59830 | GRP-2021-RR1.40.3.2 | 2021 GRP - River Rouge | Install Services - W James (4' EWPL Division St & 0' WEPL W Jefferson Ave) | 12 | 2021-10-25 | 2021-10-25
SWDET2-15345 | PROJ-0951-SWDET2.46.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Cahalan 2 (Green & Beard) | 10 | 2021-10-25 | 2021-10-26
WCDET1-1555915 | GRP-2021-WCDet1.63.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - ASO Grand River Ave (Burnette & Jeffries) | 1 | 2021-10-25 | 2021-10-25
RR1 11731 | GRP-2021-FR.53.1.2 | 2021 GRP - Field Recommendation | Install Services - 15th (Fort & Jefferson) | 0 | 2021-10-25 | 2021-10-29
WCDET1-2435 | GRP-2021-WCDet1.15.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd 3 (Jeffries & American) | 19 | 2021-10-26 | 2021-10-28
SWDET2-6280 | PROJ-0951-SWDET2.59.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Navy 2 (Springwells & Central) | 36 | 2021-10-26 | 2021-11-02
RR1 62040 | GRP-2021-RR1.39.5.2 | 2021 GRP - River Rouge | Install Services - W Pleasasnt (Division St & 117' WWPL W Jefferson Ave) | 7 | 2021-10-26 | 2021-10-27
WCDET1-15040 | GRP-2021-WCDet1.57.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Burlingame (Grand River & Jeffries Fawy) | 0 | 2021-10-26 | 2021-10-26
AA4 27768 | GRP-2021-AA4.56.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - EWO Main St (170' WWPL S Main St & S Main St) | 0 | 2021-10-26 | 2021-10-26
WCDET1-1556015 | GRP-2021-WCDet1.63.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - ASO Grand River Ave (Burnette & Burnette) | 3 | 2021-10-26 | 2021-10-26
WCDET1-2515 | GRP-2021-WCDet1.46.24.2 | 2021 GRP - West Central Detroit 1 | Install Services - Santa Rosa 1 (Davison & Buena Vista) | 27 | 2021-10-27 | 2021-11-02
RR1 5303 | GRP-2021-RR1.60.1.2 | 2021 GRP - River Rouge | Install Services - Elm St (W Jefferson & Genesse St) | 64 | 2021-10-27 | 2021-11-10
SWDET2-11685 | PROJ-0951-SWDET2.74.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 2 (Woodmere & Tie-in) | 0 | 2021-10-27 | 2021-10-27
WCDET1-9000 | GRP-2021-WCDet1.12.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Monica 3 (Grand River & EOM) | 4 | 2021-10-27 | 2021-10-27
AP 4030 | PROJ-0951-MMOAllen.61.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Park 2 (Englewood & Moore) | 39 | 2021-10-27 | 2021-11-08
WCDET1-1556255 | GRP-2021-WCDet1.56.3.2 | 2021 GRP - West Central Detroit 1 | Install Services - Quincy 1 (Hughes & Fenkell) | 16 | 2021-10-27 | 2021-10-27
WCDET1-1395 | GRP-2021-WCDet1.1.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Barr (Stoepel & Livernois) | 3 | 2021-10-27 | 2021-10-28
Milestone 4 | GRP-2021-WCDet1.23 | 2021 GRP - West Central Detroit 1 | Service Finish Milestone | 0 |  | 10-27-21*
RR1 5306 | GRP-2021-RR1.63.1.2 | 2021 GRP - River Rouge | Install Services - Pine St (Burke St & Genessee St) | 38 | 2021-10-28 | 2021-11-05
AA4 21218 | GRP-2021-AA4.34.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - 3rd St (W Madison St & W Mosley St) | 13 | 2021-10-28 | 2021-10-28
WCDET1-1475 | GRP-2021-WCDet1.2.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Grand River Ave South (Priarie & Livernois) | 0 | 2021-10-28 | 2021-10-29
AA4 20607 | GRP-2021-AA4.20.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Nob Hill Ct (Nob Hill Pl & Nob Hill Pl) | 14 | 2021-10-28 | 2021-11-03
SWDET2-5560 | PROJ-0951-SWDET2.50.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Lane 2 (Evans & Central) | 8 | 2021-10-29 | 2021-11-01
RR1 258 | GRP-2021-RR1.2.1.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (E Anchor St & E James St) | 3 | 2021-10-29 | 2021-10-29
WCDET1-7540 | GRP-2021-WCDet1.45.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd West 2 (Davison & Buena Vista) | 14 | 2021-10-29 | 2021-11-01
SWDET2-17855 | PROJ-0951-SWDET2.57.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Gartner 2 (Central & Green) | 39 | 10-29-21* | 2021-11-03
SWDET2-24385 | PROJ-0951-SWDET2.74.4.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 2 (Tie-In & W Vernor) | 0 | 2021-10-29 | 2021-10-29
WCDET1-1555175 | GRP-2021-WCDet1.54.12.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald East 2 (Davison & Buena Vista) East adresses only | 17 | 2021-10-29 | 2021-11-02
WCDET1-2355 | GRP-2021-WCDet1.14.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Prairie 3 (Burlingame & Grand River) | 7 | 2021-10-29 | 2021-11-02
AA4 24788 | GRP-2021-AA4.58.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Nob Hill Apts (EOM & S Main St) | 8 | 2021-10-30 | 2021-11-01
AA4 21048 | GRP-2021-AA4.10.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - 2nd St (W Madison St & W Mosely St) | 11 | 2021-11-01 | 2021-11-04
RR1 11741 | GRP-2021-FR.56.1.2 | 2021 GRP - Field Recommendation | Install Services - 24th (Fort & Jefferson) | 0 | 2021-11-01 | 2021-11-02
WCDET1-7060 | GRP-2021-WCDet1.14.5.2 | 2021 GRP - West Central Detroit 1 | Install Services - Prairie 2 (Oakman & Elmhurst) | 30 | 2021-11-01 | 2021-11-08
Ypsi 3-8090 | PROJ-0951-YSP3.25.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Pineridge (Woodglen & EOM) | 12 | 2021-11-02 | 2021-11-05
WCDET1-6340 | GRP-2021-WCDet1.53.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald Cr West 2 (Ewald & Buena Vista) | 17 | 2021-11-02 | 2021-11-04
RR1 56590 | GRP-2021-RR1.44.5.2 | 2021 GRP - River Rouge | Install Services - E Pleasasnt South (Harris St & Richter St) | 11 | 2021-11-02 | 2021-11-02
RR1 61450 | GRP-2021-RR1.2.20.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (0' SSPL Linden St & 4' NSPL W Henry St) | 7 | 2021-11-02 | 2021-11-03
SWDET2-21095 | PROJ-0951-SWDET2.59.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Navy 2 (Central & Green) | 34 | 2021-11-02 | 2021-11-09
WCDET1-5380 | GRP-2021-WCDet1.22.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Tuller (Buena Vista & Buena Vista) | 19 | 2021-11-02 | 2021-11-05
Ypsi 3-9580 | PROJ-0951-YSP3.31.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Glengrove (State & Sunnyglen) | 18 | 2021-11-03 | 2021-11-05
RR1 5287 | GRP-2021-RR1.47.1.2 | 2021 GRP - River Rouge | Install Services - E Anchor (W Jefferson Ave & Burke St) | 5 | 2021-11-03 | 2021-11-03
RR1 5290 | GRP-2021-RR1.44.1.2 | 2021 GRP - River Rouge | Install Services - E Pleasasnt North (W Jefferson Ave & 4' EWPL Burke St) | 4 | 2021-11-03 | 2021-11-03
AA4 26118 | GRP-2021-AA4.5.6.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 1st St (48' NNPL W Jefferson St & W Madison St) | 10 | 2021-11-03 | 2021-11-08
RR1 56350 | GRP-2021-RR1.44.3.2 | 2021 GRP - River Rouge | Install Services - E Pleasasnt South (W Jefferson Ave & Burke St) | 5 | 2021-11-03 | 2021-11-03
RR1 58470 | GRP-2021-RR1.63.3.2 | 2021 GRP - River Rouge | Install Services - Pine St (Genessee St & Richter St) | 21 | 2021-11-03 | 2021-11-08
RR1 9341 | GRP-2021-FR.51.1.2 | 2021 GRP - Field Recommendation | Install Services - Fort (15th & 21st) | 11 | 2021-11-03 | 2021-11-09
WCDET1-8840 | GRP-2021-WCDet1.12.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Monica 3 (Burlingame & Grand River) | 39 | 2021-11-03 | 2021-11-11
AA4 20838 | GRP-2021-AA4.47.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Russett Rd (Russell Rd & Hewett Dr) | 6 | 2021-11-04 | 2021-11-05
SWDET2-14805 | PROJ-0951-SWDET2.72.5.2 | 2021 GRP - South West Detroit 2 | Install Services - Cabot (W Vernor & ASO Vernor) | 0 | 2021-11-04 | 2021-11-04
SWDET2-15745 | PROJ-0951-SWDET2.66.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Casper (Belle & Pitt) | 35 | 2021-11-04 | 2021-11-11
SWDET2-22855 | PROJ-0951-SWDET2.69.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Pitt (Casper & Central) | 7 | 2021-11-04 | 2021-11-05
Muni11970 | PROJ-0951-MUN-2.32.2.2 | 2021 GRP - Municipality | Install Services - ASO W Warren Ave (1) (Archdale St & St Marys St) | 41 | 2021-11-04 | 2021-11-17
WCDET1-2195 | GRP-2021-WCDet1.4.10.2 | 2021 GRP - West Central Detroit 1 | Install Services - Turner (Buena Vista & EOM)) | 12 | 2021-11-04 | 2021-11-08
Ypsi 3-8830 | PROJ-0951-YSP3.28.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Cedarcliff (Woodglen & EOM) | 15 | 2021-11-05 | 2021-11-10
RR1 5285 | GRP-2021-RR1.43.1.2 | 2021 GRP - River Rouge | Install Services - Goodell (Francis Riopelle Ave & 31' NNPL Coolidge Hwy) | 29 | 2021-11-05 | 2021-11-11
WCDET1-4915 | GRP-2021-WCDet1.47.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Stoepel 3 (Burlingame & Grand River) | 23 | 2021-11-05 | 2021-11-10
SWDET2-5320 | PROJ-0951-SWDET2.47.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Evans (Gartner & Pershing) | 28 | 2021-11-05 | 2021-11-11
RR1 56510 | GRP-2021-RR1.44.4.2 | 2021 GRP - River Rouge | Install Services - E Pleasasnt North (8' WEPL Genessee St & Harris St) | 5 | 2021-11-05 | 2021-11-09
SWDET2-21335 | PROJ-0951-SWDET2.75.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Norman (ANO Vernor & W Vernor) | 1 | 2021-11-05 | 2021-11-05
SWDET2-24305 | PROJ-0951-SWDET2.74.5.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 2 (Woodmere & W Vernor) | 39 | 2021-11-05 | 2021-11-15
SWDET2-24555 | PROJ-0951-SWDET2.50.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Lane 2 (Central & Green) | 24 | 2021-11-05 | 2021-11-10
AA4 25778 | GRP-2021-AA4.5.4.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 1st St (114' NNPL Nob Hill Pl & Nob Hill Pl) | 4 | 2021-11-05 | 2021-11-06
RR1 5280 | GRP-2021-RR1.37.1.2 | 2021 GRP - River Rouge | Install Services - W Henry (Division St & 4' WWPL W Jefferson Ave) | 9 | 2021-11-08 | 2021-11-08
RR1 55310 | GRP-2021-RR1.45.2.2 | 2021 GRP - River Rouge | Install Services - E Henry (33' EEPL Genessee St & 110' WWPL Richter St) | 23 | 2021-11-08 | 2021-11-11
SWDET2-21175 | PROJ-0951-SWDET2.59.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Navy 2 (Green & Beard) | 22 | 2021-11-08 | 2021-11-11
Muni10130 | PROJ-0951-MUN-2.32.1.2 | 2021 GRP - Municipality | Install Services - ASO W Warren Ave (1) (Southfield Rd & Archdale St) | 10 | 2021-11-08 | 2021-11-19
WCDET1-5540 | GRP-2021-WCDet1.22.4.2 | 2021 GRP - West Central Detroit 1 | Install Services - Tuller (Buena Vista & Fullerton) | 19 | 2021-11-08 | 2021-11-11
RFordMMO175 | Proj-Redford PA.12.1.1 | Redford - Pull Ahead | Install Services - Centralia St (6 Mile Rd & Curtis St) | 0 | 2021-11-08 | 2021-11-09
RR1 53870 | GRP-2021-RR1.58.3.2 | 2021 GRP - River Rouge | Install Services - Coolidge Hwy 2 (Burke St & Richter St) | 52 | 2021-11-09 | 2021-11-19
RR1 56110 | GRP-2021-RR1.62.2.2 | 2021 GRP - River Rouge | Install Services - E Oak St (Burke St & Genessee St) | 27 | 2021-11-09 | 2021-11-15
AP 4630 | PROJ-0951-MMOAllen.72.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Reeck 2 (Allen & Moore) | 14 | 2021-11-09 | 2021-11-12
AA4 25438 | GRP-2021-AA4.5.3.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 1st St (W Mosely St & 114' NNPL Nob Hill Pl) | 12 | 2021-11-09 | 2021-11-10
NCET4-190 | Proj-NCDET43-1 PA.21.2 | NCDET4 Pull Ahead | Install Services - ASO McNichols (4) (Snowden & Steel) | 0 | 2021-11-09 | 2021-11-10
NCET4-80 | Proj-NCDET43-1 PA.40.1 | NCDET4 Pull Ahead | Install Services - Prest (McNichols & Puritan) | 100 | 2021-11-09 | 2021-11-10
RR1 5286 | GRP-2021-RR1.46.1.2 | 2021 GRP - River Rouge | Install Services - E Cicotte (W Jefferson Ave & Burke St) | 9 | 2021-11-10 | 2021-11-11
RR1 5289 | GRP-2021-RR1.50.1.2 | 2021 GRP - River Rouge | Install Services - Burke 1 (E James St & E Pleasant St) | 4 | 2021-11-10 | 2021-11-10
RR1 5296 | GRP-2021-RR1.53.1.2 | 2021 GRP - River Rouge | Install Services - E James North (W Jefferson & 3' WEPL Burke St) 3" | 6 | 2021-11-10 | 2021-11-10
AA4 20836 | GRP-2021-AA4.45.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - Redeemer Ave (Rusell Rd & Hewett Rd) | 13 | 2021-11-10 | 2021-11-15
RR1 55630 | GRP-2021-RR1.53.80.2 | 2021 GRP - River Rouge | Install Services - E James South (W Jefferson & 4' EWPL Burke St) 2" | 4 | 2021-11-10 | 2021-11-10
RR1 11771 | GRP-2021-FR.58.2.2 | 2021 GRP - Field Recommendation | Install Services - Jefferson (21St & 15Th) | 1 | 2021-11-10 | 2021-11-11
Muni9752 | PROJ-0951-MUN-2.52.1.2 | 2021 GRP - Municipality | Install Services - Longacre St (2) (EOM & ANO W Warren Ave) | 9 | 2021-11-10 | 2021-11-23
WCDET1-5860 | GRP-2021-WCDet1.53.2.2 | 2021 GRP - West Central Detroit 1 | Install Services - Ewald Cr West 2 (Buena Vista & Cortland) | 49 | 2021-11-10 | 2021-11-22
SWDET2-17145 | PROJ-0951-SWDET2.78.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Sharon (W Vernor & ASO Vernor) | 0 | 2021-11-11 | 2021-11-11
SWDET2-18425 | PROJ-0951-SWDET2.67.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Honorah (EOM & Dix) | 13 | 2021-11-11 | 2021-11-15
RFordMMO180 | Proj-Redford PA.19.1.1 | Redford - Pull Ahead | Install Services - Norborne St (Curtis St & Bennett St) | 0 | 2021-11-11 | 2021-11-12
Ypsi 3-8330 | PROJ-0951-YSP3.26.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Briardale (Woodglen & EOM) | 12 | 2021-11-12 | 2021-11-17
Ypsi 3-9830 | PROJ-0951-YSP3.32.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Ravinewood (Nash & Glengrove) | 1 | 2021-11-12 | 2021-11-19
RR1 5288 | GRP-2021-RR1.45.80.2 | 2021 GRP - River Rouge | Install Services - E Henry (W Jefferson Ave & Burke St) | 5 | 2021-11-12 | 2021-11-12
SWDET2-3560 | PROJ-0951-SWDET2.25.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Elsmere 2 (At Rathbone) | 1 | 2021-11-12 | 2021-11-12
SWDET2-5640 | PROJ-0951-SWDET2.51.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Logan 2 (Central & EOM) | 22 | 2021-11-12 | 2021-11-17
SWDET2-11845 | PROJ-0951-SWDET2.74.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Lawndale 2 (ANO W Vernor & W Vernor) | 2 | 2021-11-12 | 2021-11-12
SWDET2-21495 | PROJ-0951-SWDET2.75.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Norman (Tie-In & ANO Vernor) | 0 | 2021-11-12 | 2021-11-12
RR1 10601 | GRP-2021-FR.57.1.2 | 2021 GRP - Field Recommendation | Install Services - Jefferson (24Th & 95' EEPL 23Rd) | 1 | 2021-11-12 | 2021-11-12
Milestone 4 | GRP-2021-FR.23 | 2021 GRP - Field Recommendation | Service Finish Milestone | 0 |  | 11-12-21*
RR1 5294 | GRP-2021-RR1.52.1.2 | 2021 GRP - River Rouge | Install Services - Batavia (Burke St & Genessee St) | 35 | 2021-11-15 | 2021-11-22
AA4 21298 | GRP-2021-AA4.34.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - 3rd St (W Mosley St & W Davis Ave) | 20 | 2021-11-15 | 2021-11-15
RR1 56190 | GRP-2021-RR1.62.4.2 | 2021 GRP - River Rouge | Install Services - E Oak St (4' WEPL Genessee St & Richer St) | 26 | 2021-11-15 | 2021-11-19
AP 2460 | PROJ-0951-MMOAllen.44.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Louise (Englewood & Leslie) | 15 | 2021-11-15 | 2021-11-18
WCDET1-4755 | GRP-2021-WCDet1.45.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd West 2 (Buena Vista & Cortland) | 23 | 2021-11-16 | 2021-11-24
RR1 52350 | GRP-2021-RR1.52.3.2 | 2021 GRP - River Rouge | Install Services - Batavia (Genessee St & Richer St) | 20 | 2021-11-17 | 2021-11-22
AA4 20616 | GRP-2021-AA4.30.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - W Mosley St (3rd St & S Ashley St) | 19 | 2021-11-17 | 2021-11-18
NCET4-120 | Proj-NCDET43-1 PA.37.1 | NCDET4 Pull Ahead | Install Services - Whitcomb (McNichols & Puritan) | 100 | 2021-11-17 | 2021-11-18
SWDET2-4680 | PROJ-0951-SWDET2.39.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Cahalan 1 (Mullane & Springwells) | 9 | 2021-11-18 | 2021-11-19
SWDET2-5400 | PROJ-0951-SWDET2.48.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Gartner 1 (Lawndale & Springwells) | 65 | 2021-11-18 | 2021-12-03
AP 1700 | PROJ-0951-MMOAllen.6.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Aster (Allen & Rosedale) | 42 | 2021-11-18 | 2021-12-02
SWDET2-17465 | PROJ-0951-SWDET2.54.3.2 | 2021 GRP - South West Detroit 2 | Install Services - Senator 1 (Mullane & Springwells) | 28 | 2021-11-18 | 2021-11-26
AP 1840 | PROJ-0951-MMOAllen.13.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Bert (535 Feet West Of Louise & Louise) | 10 | 2021-11-19 | 2021-11-22
RR1 8701 | GRP-2021-RR.43.1.2 | 2021 GRP - Risk Rank | Install Services - Outer (Eaton & Kendall) | 0 | 2021-11-19 | 2021-11-24
Milestone 4 | GRP-2021-ED1.23 | 2021 GRP - East Detroit 1 | Service Finish Milestone | 0 |  | 11-19-21*
AA4 23398 | GRP-2021-AA4.18.2.2 | 2021 GRP - Ann Arbor 4 | Install Services - Koch Ave (50' EEPL 3rd St & 96' WWPL S 1st St) | 15 | 2021-11-22 | 2021-11-29
RR1 60080 | GRP-2021-RR1.2.2.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (4' NNPL Leroy St & Coolidge Hwy) | 5 | 2021-11-22 | 2021-11-22
RR1 6201 | GRP-2021-RR.10.1.2 | 2021 GRP - Risk Rank | Install Services - Spring Garden 2 (Hayes & Kelly) | 51 | 2021-11-22 | 2021-11-24
WCDET1-3955 | GRP-2021-WCDet1.35.1.2 | 2021 GRP - West Central Detroit 1 | Install Services - Oakman Blvd East 2 (Buena Vista & Cortland) | 33 | 2021-11-22 | 2021-11-30
Ypsi 3-8580 | PROJ-0951-YSP3.27.1.2 | 2021 GRP - Ypsilanti 3 | Install Services - Brooktree (Woodglen & EOM) | 12 | 2021-11-23 | 2021-11-30
AP 1880 | PROJ-0951-MMOAllen.15.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Brody 2 (1368 Feet West Of Allen Road & Allen) | 27 | 2021-11-23 | 2021-12-01
SWDET2-6120 | PROJ-0951-SWDET2.57.1.2 | 2021 GRP - South West Detroit 2 | Install Services - Gartner 2 (Springwells & Central) | 25 | 2021-11-26 | 2021-12-02
RR1 60000 | GRP-2021-RR1.2.3.2 | 2021 GRP - River Rouge | Install Services - W Jefferson Ave (1) (12' NSPL E Pleasant St & Delisle St) | 5 | 2021-11-26 | 2021-11-26
Milestone 4 | GRP-2021-RR1.23 | 2021 GRP - River Rouge | Service Finish Milestone | 0 |  | 11-26-21*
Ypsi 3-11490 | PROJ-0951-YSP3.38.2.2 | 2021 GRP - Ypsilanti 3 | Install Services - McCartney 1 (McCartney & EOM) | 1 | 2021-11-30 | 2021-11-30
RFordMMO185 | Proj-Redford PA.16.1.1 | Redford - Pull Ahead | Install Services - Kinloch St (Curtis St & Santa Maria Ave) | 0 | 2021-11-30 | 2021-11-30
AA5-103 | Proj-AA5-PLH.1.1 | Ann Arbor 5 - Pull Ahead 2021 | Install Services - Street (Cross St 1 & Cross St 2) | 37 | 2021-12-01 | 2021-12-30
AP 2220 | PROJ-0951-MMOAllen.32.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Grey (1018' West Of Marlborough & Marlborough Ave) | 24 | 2021-12-02 | 2021-12-08
AP 2780 | PROJ-0951-MMOAllen.60.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Park 1 (Champaign & Englewood) | 13 | 2021-12-03 | 2021-12-06
RFordMMO190 | Proj-Redford PA.7.1.1 | Redford - Pull Ahead | Install Services - Bennett St (1) (MacArthur & Kinloch St) | 0 | 2021-12-03 | 2021-12-06
NCET4-135 | Proj-NCDET43-1 PA.36.1 | NCDET4 Pull Ahead | Install Services - sussex (McNichols & Puritan) | 106 | 2021-12-06 | 2021-12-07
RR1 5561 | GRP-2021-RR.2.1.2 | 2021 GRP - Risk Rank | Install Services - Fairview (E Warren & E Canfield) | 26 | 2021-12-07 | 2021-12-15
AP 4430 | PROJ-0951-MMOAllen.68.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Quandt 1 (Englewood & 260' North Moore Ave) | 33 | 2021-12-07 | 2021-12-16
AA4 23478 | GRP-2021-AA4.18.4.2 | 2021 GRP - Ann Arbor 4 | Install Services - Koch Ave (49' EEPL S 1st St & S Main St) | 9 | 2021-12-08 | 2021-12-10
RFordMMO195 | Proj-Redford PA.18.1.1 | Redford - Pull Ahead | Install Services - MacArthur (6 Mile Rd & 6 Mile Rd) | 0 | 2021-12-08 | 2021-12-09
AP 2260 | PROJ-0951-MMOAllen.34.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Herrick 1 (745' East Of Pelham & Pelham Ave ) | 17 | 2021-12-09 | 2021-12-14
SWDET2-17935 | PROJ-0951-SWDET2.57.2.2 | 2021 GRP - South West Detroit 2 | Install Services - Gartner 2 (Green & Beard) | 24 | 2021-12-09 | 2021-12-14
Milestone 4 | PROJ-0951-YSP3.43 | 2021 GRP - Ypsilanti 3 | Service Finish Milestone | 0 |  | 12-10-21*
WD3PH-5660 | Proj-WDET3PLH.1.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Services - Paul (Archdale & Abington) | 0 | 2021-12-13 | 2021-12-13
WD3PH-5740 | Proj-WDET3PLH.2.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Services - Longacre (ASO Warren & Paul) | 0 | 2021-12-13 | 2021-12-13
WD3PH-5820 | Proj-WDET3PLH.5.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Services - Rutland (ASO Warren & Paul) | 0 | 2021-12-13 | 2021-12-13
WD3PH-5900 | Proj-WDET3PLH.6.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Services - Abgington (ASO Warren & Paul) | 0 | 2021-12-13 | 2021-12-13
AA4 20459 | GRP-2021-AA4.5.1.2 | 2021 GRP - Ann Arbor 4 | Install Services - S 1st St (2' NSPL W Madison St & W Mosley St) | 11 | 2021-12-14 | 2021-12-14
Milestone 4 | PROJ-0951-SWDET2.23 | 2021 GRP - South West Detroit 2 | Service Finish Milestone | 0 |  | 12-14-21*
Milestone 4 | GRP-2021-AA4.23 | 2021 GRP - Ann Arbor 4 | Service Finish Milestone | 0 |  | 12-14-21*
NCET4-145 | Proj-NCDET43-1 PA.35.1 | NCDET4 Pull Ahead | Install Services - Robson (McNichols & Puritan) | 105 | 2021-12-15 | 2021-12-15
Milestone 4 | GRP-2021-RR.23 | 2021 GRP - Risk Rank | Service Finish Milestone | 0 |  | 12-15-21*
AP 2500 | PROJ-0951-MMOAllen.46.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Manor 1 (Allen & Moore) | 27 | 2021-12-17 | 2021-12-28
AP 1640 | PROJ-0951-MMOAllen.3.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Allen 2 (150' North Of Moore & Champaign) | 53 | 2021-12-29 | 2022-01-14
Milestone 4 | Proj-WDET3PLH | West Detroit 3 - Pull Ahead 2021 | Service Finish Milestone | 0 |  | 12-30-21*
WD3PH-4825 | Proj-WDET3PLH.4.1.2 | West Detroit 3 - Pull Ahead 2021 | Install Services - Archdale (Warren & Paul) | 0 | 2021-12-30 | 2021-12-30
AP 4530 | PROJ-0951-MMOAllen.70.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Ray (826' West Of Louise Ave & Louise Ave) | 15 | 2022-01-18 | 2022-01-21
AP 2540 | PROJ-0951-MMOAllen.48.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Marlborough (Wick & Moore) | 23 | 2022-01-24 | 2022-01-28
AP 2080 | PROJ-0951-MMOAllen.25.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Dale (756' West Of Marlborough & Marlborough) | 15 | 2022-01-31 | 2022-02-03
AP 1860 | PROJ-0951-MMOAllen.14.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Brody 1 (Pelham & 949 Feet East Of Pelham Road) | 18 | 2022-02-04 | 2022-02-09
AP 4180 | PROJ-0951-MMOAllen.63.1.2 | 2021 GRP - Allen Park MMO | MMO Services - Pelham 1 (250' North Of Champaign & 450' South Conrail Rr) | 1 | 2022-02-10 | 2022-02-10
NCDET - 7075 | NEWPROJ-6.9.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Mendota (ASO Puritan & Pilgrim) | 51 | 2022-04-20 | 2022-05-10
NCDET - 25595 | NEWPROJ-6.9.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Install Services - Mendota (Pilgrim & ANO Fenkell) | 33 | 2022-04-20 | 2022-05-10

## Rest (hidden)
Activity ID | WBS | Project Name | Activity Name | Budgeted Units | Start | Finish
NDET1-4580 | PROJ-0951-NDET1-1.1.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - 7 Mile Rd (Outer Dr & Van Dyke) | 9 | 02-08-21 A | 02-12-21 A
NDET1-4660 | PROJ-0951-NDET1-1.2.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Anthos Garden Apts (Outer Dr E & EOM) | 0 | 02-08-21 A | 02-12-21 A
NDET1-4740 | PROJ-0951-NDET1-1.3.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Antwerp (7 Mile Rd and NO House) | 0 | 02-08-21 A | 02-12-21 A
NDET1-2240 | PROJ-0951-NDET1-1.4.8.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Bliss (Van Dyke & Outer Dr E) | 97 | 02-08-21 A | 02-12-21 A
NDET1-2330 | PROJ-0951-NDET1-1.5.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Conner (Outer Dr E & E State Fair) | 0 | 02-08-21 A | 02-12-21 A
NDET1-4310 | PROJ-0951-NDET1-1.10.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Outer Dr E 1 (Van Dyke & Conner) | 50 | 02-08-21 A | 02-12-21 A
NDET1-4220 | PROJ-0951-NDET1-1.11.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Outer Dr E 2 (Conner & Royalt) | 7 | 02-08-21 A | 02-12-21 A
NDET1-4490 | PROJ-0951-NDET1-1.6.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Lantz 2 (AEO Van Dyke & Van Dyke) | 53 | 02-08-21 A | 02-12-21 A
NDET1-4400 | PROJ-0951-NDET1-1.7.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - House (Antwerp & Van Dyke) | 52 | 02-08-21 A | 02-12-21 A
NDET1-4140 | PROJ-0951-NDET1-1.12.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Rolyat (Van Dyke & Outer Dr) | 52 | 02-08-21 A | 02-12-21 A
NDET1-4050 | PROJ-0951-NDET1-1.13.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Sirron (Outer Dr & Van Dyke) | 62 | 02-08-21 A | 02-12-21 A
NDET1-3960 | PROJ-0951-NDET1-1.14.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Suzanne (Antwerp & Van Dyke) | 37 | 02-08-21 A | 02-12-21 A
NDET1-3870 | PROJ-0951-NDET1-1.17.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Van Dyke 4 (Sirron & Outer Drive) | 7 | 02-08-21 A | 02-12-21 A
NDET1-3780 | PROJ-0951-NDET1-1.18.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Yolanda (Van Dyke & Outer Dr) | 80 | 02-08-21 A | 02-12-21 A
NDET1-1400 | PROJ-0951-NDET1-1.3.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Antwerp 2 (NO House & Suzanne) | 0 | 02-08-21 A | 02-12-21 A
NDET1-1600 | PROJ-0951-NDET1-1.20.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - AEO Van Dyke (7 Mile & Suzanne) | 7 | 02-08-21 A | 02-12-21 A
NDET1-1770 | PROJ-0951-NDET1-1.22.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Outer Dr Easement (Station & 7 Mile) | 22 | 02-08-21 A | 02-12-21 A
NDET1-5240 | PROJ-0951-NDET1-1.3.2.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Antwerp 3 (7 Mile & SO 7 Mile) | 0 | 02-08-21 A | 02-12-21 A
NDET1-5320 | PROJ-0951-NDET1-1.7.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - House (AEO Van Dyke & Van Dyke) | 52 | 02-08-21 A | 02-12-21 A
NDET1-5410 | PROJ-0951-NDET1-1.17.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Van Dyke 3 (Lantz & Rolyat) | 7 | 02-08-21 A | 02-12-21 A
NDET1-5500 | PROJ-0951-NDET1-1.17.2.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Van Dyke 2 (Bliss & Yolanda) | 7 | 02-08-21 A | 02-12-21 A
NDET1-5590 | PROJ-0951-NDET1-1.17.4.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Van Dyke 4 (Yolanda & Lantz) | 7 | 02-08-21 A | 02-12-21 A
NDET1-5680 | PROJ-0951-NDET1-1.17.5.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Van Dyke 1 (Suzanne & Bliss) | 7 | 02-08-21 A | 02-12-21 A
NDET1-5770 | PROJ-0951-NDET1-1.4.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Bliss (AEO Van Dyke & Van Dyke) | 97 | 02-08-21 A | 02-12-21 A
NDET1-5990 | PROJ-0951-NDET1-1.6.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Lantz 1 (Outer Dr & Van Dyke) | 53 | 02-08-21 A | 02-12-21 A
NDET1-6100 | PROJ-0951-NDET1-1.8.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - 7 Mile 1 (East of RR) | 9 | 02-08-21 A | 02-12-21 A
NDET1-6190 | PROJ-0951-NDET1-1.9.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - 7 Mile Steel (CN RR Crossing) | 9 | 02-08-21 A | 02-12-21 A
NDET1-1350 | PROJ-0951-NDET1-1.20.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - AEO Van Dyke (Bliss & Sirron) | 7 | 02-08-21 A | 02-12-21 A
NDET1-6310 | PROJ-0951-NDET1-1.14.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Suzanne (AEO Van Dyke & Van Dyke) | 37 | 02-08-21 A | 02-12-21 A
NDET1-6530 | PROJ-0951-NDET1-1.13.3.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Sirron (AEO Van Dyke & Van Dyke) | 50 | 02-08-21 A | 02-12-21 A
NDET1-6770 | PROJ-0951-NDET1-1.15.1.2 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - State Fair (Conner & EOM) | 52 | 02-08-21 A | 02-12-21 A
A29530 | PROJ-0951-NDET1-1.16.1 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Outer Dr E (Rayalt & Lappin) | 3 | 02-08-21 A | 02-12-21 A
NDET1-6790 | PROJ-0951-NDET1-1.19.1 | 2019 GRP - Carry Over - North Detroit 1 | Restoration - Soft Surface - Antwerp 3 (7 Mile & SO 7 Mile) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-4360 | PROJ-0951-HMT-1.1.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Belmont St (Conant & Buffalo) | 76 | 02-08-21 A | 02-12-21 A
HMT 2-8630 | PROJ-0951-HMT-1.34.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Zinow St (Fleming St & Joseph Campau Ave) | 91 | 02-08-21 A | 02-12-21 A
HMT 2-8730 | PROJ-0951-HMT-1.32.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Woodland Ave (Grand Haven St & Dequindre St) | 2 | 02-08-21 A | 02-12-21 A
HMT 2-9170 | PROJ-0951-HMT-1.28.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Pulaski St (Fleming St & Joseph Campau Ave) | 91 | 02-08-21 A | 02-12-21 A
HMT 2-9280 | PROJ-0951-HMT-1.27.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Norwalk St (Conant St & Buffalo St) | 35 | 02-08-21 A | 02-12-21 A
HMT 2-9380 | PROJ-0951-HMT-1.26.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Neibel St (Fleming St & Joseph Campau Ave) | 89 | 02-08-21 A | 02-12-21 A
HMT 2-9480 | PROJ-0951-HMT-1.25.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Nagel St (Caniff ave & Carpenter Ave) | 50 | 02-08-21 A | 02-12-21 A
HMT 2-9590 | PROJ-0951-HMT-1.23.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Lumpkin St (Carpenter Ave & Caniff Ave) | 164 | 02-08-21 A | 02-12-21 A
HMT 2-9690 | PROJ-0951-HMT-1.22.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Joseph Campau Ave (Carpenter Ave & Caniff Ave) | 96 | 02-08-21 A | 02-12-21 A
HMT 2-9800 | PROJ-0951-HMT-1.21.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Holmes St (Fleming & Mackay) | 135 | 02-08-21 A | 02-12-21 A
HMT 2-9910 | PROJ-0951-HMT-1.20.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Holbrook St (Conant St & Buffalo St) | 5 | 02-08-21 A | 02-12-21 A
HMT 2-10020 | PROJ-0951-HMT-1.19.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Grand Haven St (Commor Ave & Caniff St) | 15 | 02-08-21 A | 02-12-21 A
HMT 2-10230 | PROJ-0951-HMT-1.17.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Evaline St (Buffalo and EOM) | 41 | 02-08-21 A | 02-12-21 A
HMT 2-10440 | PROJ-0951-HMT-1.15.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Dyar St (Commor Ave & Caniff St) | 35 | 02-08-21 A | 02-12-21 A
HMT 2-10550 | PROJ-0951-HMT-1.14.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Doremus St (Conant St & Buffalo St) | 28 | 02-08-21 A | 02-12-21 A
HMT 2-10660 | PROJ-0951-HMT-1.13.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Dequindre St (Carpenter Ave & Caniff St) | 17 | 02-08-21 A | 02-12-21 A
HMT 2-10770 | PROJ-0951-HMT-1.12.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Conant St (Caniff St & Holbrook St) | 78 | 02-08-21 A | 02-12-21 A
HMT 2-10880 | PROJ-0951-HMT-1.11.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Comstock St (Conant St & Buffalo St) | 16 | 02-08-21 A | 02-12-21 A
HMT 2-10970 | PROJ-0951-HMT-1.10-1.36.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - 75 Crossing (Dequindre and Nagel) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-11070 | PROJ-0951-HMT-1.10.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Commor Ave 1 (Grand Haven & Dequindre) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-11280 | PROJ-0951-HMT-1.8.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Casmere Ave ((Joseph Campau & Mackay)) | 104 | 02-08-21 A | 02-12-21 A
HMT 2-11380 | PROJ-0951-HMT-1.7.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Carpenter Ave (Nagel St & Joseph Campau Ave) | 47 | 02-08-21 A | 02-12-21 A
HMT 2-11480 | PROJ-0951-HMT-1.6.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Caniff Ave (Nagel st and EOM) | 97 | 02-08-21 A | 02-12-21 A
HMT 2-11580 | PROJ-0951-HMT-1.5.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Burger St (Mackay & Fleming) | 37 | 02-08-21 A | 02-12-21 A
HMT 2-11690 | PROJ-0951-HMT-1.4.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Buffalo St (Holbrook & Edwin) | 10 | 02-08-21 A | 02-12-21 A
HMT 2-4270 | PROJ-0951-HMT-1.3.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Botsford St (Fleming St & Joseph Campau Ave) | 100 | 02-08-21 A | 02-12-21 A
HMT 2-1210 | PROJ-0951-HMT-1.6.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Caniff Ave (WO Joseph Campau & Joseph Campau) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-1440 | PROJ-0951-HMT-1.4.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Buffalo St (Edwin & No Caniff) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-1780 | PROJ-0951-HMT-1.17.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Evaline St (Conant and Buffalo) | 56 | 02-08-21 A | 02-12-21 A
HMT 2-1880 | PROJ-0951-HMT-1.1.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Belmont St (Buffalo and EOM) | 48 | 02-08-21 A | 02-12-21 A
HMT 2-2730 | PROJ-0951-HMT-1.6.2.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Caniff Ave (Nagel & WO Joseph Campau) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-2950 | PROJ-0951-HMT-1.6.4.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Caniff Ave (Vault and Caniff) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-3170 | PROJ-0951-HMT-1.6.5.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Caniff Ave Dequindre and Haven | 0 | 02-08-21 A | 02-12-21 A
HMT 2-3400 | PROJ-0951-HMT-1.10.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Commor Ave (Nagel and Fleming) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-3620 | PROJ-0951-HMT-1.10.2.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Commor Ave (Fleming St & Joseph Campau Ave) | 0 | 02-08-21 A | 02-12-21 A
HMT 2-3850 | PROJ-0951-HMT-1.5.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Burger St (Fleming & EO Fleming) | 0 | 02-08-21 A | 02-12-21 A
RR 250211 | PROJ-0951-HMT-1.9.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Moran (HMT Dual Main) (ANO Caniff & Carpenter) | 100 | 02-08-21 A | 02-12-21 A
HMT 2-11960 | PROJ-0951-HMT-1.2.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Mackay (Holmes & Holmes) | 33 | 02-08-21 A | 02-12-21 A
HMT 2-12200 | PROJ-0951-HMT-1.2.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Mackay (Burger & Casmere) | 33 | 02-08-21 A | 02-12-21 A
HMT 2-12310 | PROJ-0951-HMT-1.2.2.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Mackay (Whalen & Whalen) | 33 | 02-08-21 A | 02-12-21 A
HMT 2-12550 | PROJ-0951-HMT-1.21.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Holmes St Mackay (Mackay & Joseph Campau) | 135 | 02-08-21 A | 02-12-21 A
HMT 2-13030 | PROJ-0951-HMT-1.8.3.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Casmere Ave (Mackay & Fleming) | 105 | 02-08-21 A | 02-12-21 A
HMT 2-13380 | PROJ-0951-HMT-1.24.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Conant 4" HMT1 - (Harold & Caniff) | 20 | 02-08-21 A | 02-12-21 A
HMT 2-13610 | PROJ-0951-HMT-1.36.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Trowbridge Dual (North) - (Alpena & Conant) | 20 | 02-08-21 A | 02-12-21 A
HMT 2-13850 | PROJ-0951-HMT-1.37.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Conant 2 (Caniff & Casmere) | 35 | 02-08-21 A | 02-12-21 A
HMT 2-14220 | PROJ-0951-HMT-1.4.2.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Buffalo St (Talbot & Prescott)) | 2 | 02-08-21 A | 02-12-21 A
HMT 2-14330 | PROJ-0951-HMT-1.1.2.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Belmont St (Conant & Ellery) | 46 | 02-08-21 A | 02-12-21 A
HMT 2-14440 | PROJ-0951-HMT-1.6.6.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Caniff Ave (Nagel & Mackay) | 2 | 02-08-21 A | 02-12-21 A
HMT 2-14730 | PROJ-0951-HMT-1.38.1.2 | 2019 GRP - Carry Over - Hamtramck 2 | Restoration - Soft Surface - Gallager (Talbot & Caniff) | 35 | 02-08-21 A | 02-12-21 A
A26490 | PROJ-0951-GP 5 -3.129.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - ANO Kercheval (Balfour & Alter) | 0 | 03-04-21 A | 03-04-21 A
GP-14060 | PROJ-0951-GP 5 -3.114.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - ASO Kercheval (Balfour & Alter) | 0 | 03-04-21 A | 03-04-21 A
NWDET-20100 | PROJ-0951-NWDET1CO.53.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Penrod (2) (Davison & EOM) | 7 | 03-19-21 A | 05-24-21 A
RedfMMO3240 | PROJ-0951-MMORedford-1.27.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Denby 4 (Santa Maria & Curtis) | 0 | 03-19-21 A | 03-23-21 A
CDET-880 | PROJ-0951-CDET1-2.31.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Glendale (1) (Linwood & AEO Dexter) | 0 | 03-19-21 A | 06-02-21 A
Euclid 1800 | PROJ-0951-MUN-3.8.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Hubbell (W McNichols & Puritan) | 0 | 03-22-21 A | 03-25-21 A
Muni320 | PROJ-0951-MUN-3.23.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Conant (Carpenter & McNichols) | 0 | 03-23-21 A | 03-23-21 A
Muni550 | PROJ-0951-MUN-3.24.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Bagley 1 (20th & 17th) | 0 | 03-23-21 A | 03-23-21 A
Muni1030 | PROJ-0951-MUN-3.25.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Bagley 2 (21st & Trumbull) | 0 | 03-23-21 A | 03-23-21 A
Muni3790 | PROJ-0951-MUN-3.15.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Lawton (Grand Blvd & EOM) | 0 | 03-23-21 A | 03-23-21 A
NWDET-15500 | PROJ-0951-NWDET1CO.25.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - ASO Schoolcraft (1) (Auburn & Artesian) | 18 | 03-23-21 A | 06-01-21 A
NWDET-18550 | PROJ-0951-NWDET1CO.49.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Piedmont (2) (Schoolcraft & Davison) | 8 | 03-23-21 A | 03-23-21 A
SCDet-2880 | GRP-2021-SCDet1.12.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Carlin (Joy & Tireman) | 4 | 03-25-21 A | 03-25-21 A
Euclid 1320 | PROJ-0951-MUN-3.2.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - McNichols (Livernois & Greenlawn) | 0 | 03-25-21 A | 03-25-21 A
Euclid 1480 | PROJ-0951-MUN-3.4.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Clark St (Toledo & I-75 Service Dr) | 0 | 03-25-21 A | 03-25-21 A
Euclid 1560 | PROJ-0951-MUN-3.5.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Evergreen (Clarita & McNichols) | 0 | 03-25-21 A | 03-25-21 A
Euclid 1640 | PROJ-0951-MUN-3.6.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Scotten (Toledo & I-75 Service Dr) | 0 | 03-25-21 A | 03-25-21 A
CDET-1635 | PROJ-0951-CDET1-2.23.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Lawton (2) (Glendale & Leslie) | 0 | 03-25-21 A | 03-25-21 A
CDET-620 | PROJ-0951-CDET1-2.22.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Lawton (1) (Waverly & Davison) | 0 | 03-25-21 A | 03-25-21 A
WDET-1080 | PROJ-0951-WDET9-4.23.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Evergreen 2 (Ann Arbor Trail & Paul) | 0 | 03-25-21 A | 03-25-21 A
WDET-18370 | PROJ-0951-WDET9-4.23.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Evergreen 2 (Paul & Ford) | 0 | 03-25-21 A | 03-25-21 A
WDET-21860 | PROJ-0951-WDET9-4.34.29.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - River Oaks Apartments (Evergreen & Evergreen) | 3 | 03-25-21 A | 03-25-21 A
WDET-22110 | PROJ-0951-WDET9-4.34.30.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - River Oaks Apartments (Evergreen & EOM) | 3 | 03-25-21 A | 03-25-21 A
WDET-21360 | PROJ-0951-WDET9-4.34.24.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - River Oaks Apartments (Evergreen & Old Colony) | 3 | 03-25-21 A | 03-25-21 A
WDET-21610 | PROJ-0951-WDET9-4.34.25.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - River Oaks Apartments (Old Colony & Evergreen) | 3 | 03-25-21 A | 03-25-21 A
WDET-24450 | PROJ-0951-WDET9-4.1.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Evergreen 2 (ASO Warren & Ann Arbor Trail) | 44 | 03-25-21 A | 03-25-21 A
GP-14025 | PROJ-0951-GP 5 -3.6.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Alter 1 (Essex & Riverside) | 0 | 03-25-21 A | 03-25-21 A
GP-14100 | PROJ-0951-GP 5 -3.15.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Barrington 1 (ASO Jefferson & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-14105 | PROJ-0951-GP 5 -3.16.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Barrington 2 (Windmill Pointe & Essex) | 0 | 03-25-21 A | 2021-09-29
GP-14360 | PROJ-0951-GP 5 -3.56.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Essex (Balfour & Alter) | 0 | 03-25-21 A | 2021-09-29
GP-14465 | PROJ-0951-GP 5 -3.68.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Lakepointe 4 (Windmill Pointe & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-14475 | PROJ-0951-GP 5 -3.70.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Lakepointe 3 (ASO Jefferson & Essex) | 0 | 03-25-21 A | 03-25-21 A
NWDET-14450 | PROJ-0951-NWDET1CO.34.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Ashton (2) (Schoolcraft & EOM) | 80 | 03-25-21 A | 03-25-21 A
NWDET-11220 | PROJ-0951-NWDET1CO.20.4.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Rosemont (2) (Davison & EOM) | 18 | 03-25-21 A | 03-25-21 A
NWDET-11130 | PROJ-0951-NWDET1CO.20.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Rosemont (2) (Schoolcraft & Davison) | 34 | 03-25-21 A | 03-25-21 A
NWDET-17230 | PROJ-0951-NWDET1CO.51.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Greenview (2) (Schoolcraft & Davison) | 57 | 03-25-21 A | 05-24-21 A
WDET-495 | PROJ-0951-WDET9-4.10.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ashton 3 (Paul Ave & Kirkwood Ave) | 13 | 03-25-21 A | 03-25-21 A
WDET-4730 | PROJ-0951-WDET9-4.10.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ashton 3 (Paul & Dayton) | 3 | 03-25-21 A | 03-25-21 A
WDET-405 | PROJ-0951-WDET9-4.8.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ashton 1 (Paul & Whitlock) | 3 | 03-25-21 A | 03-25-21 A
WDET-4670 | PROJ-0951-WDET9-4.8.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ashton 1 (Whitlock ave & W Warren) | 3 | 03-25-21 A | 03-25-21 A
CDET-1320 | PROJ-0951-CDET1-2.35.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Fullerton (Livernois & Linwood) | 0 | 03-25-21 A | 2021-09-23
GP-14560 | PROJ-0951-GP 5 -3.83.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Middlesex East (Windmill Pointe & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-41920 | PROJ-0951-GP 5 -3.76.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Middlesex West(Windmill Pointe & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-14600 | PROJ-0951-GP 5 -3.87.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Nottingham 2 (St. Paul & EOM) | 0 | 03-25-21 A | 03-25-21 A
GP-14605 | PROJ-0951-GP 5 -3.88.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Nottingham 3 (ASO Jefferson & Halley) | 0 | 03-25-21 A | 2021-09-29
GP-43720 | PROJ-0951-GP 5 -3.137.1.3 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Nottingham Rd (Kerchavel & St Paul | 0 | 03-25-21 A | 2021-09-29
GP-43060 | PROJ-0951-GP 5 -3.135.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Pemberton 1 East (Jefferson & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-14610 | PROJ-0951-GP 5 -3.90.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Pemberton 2 East (Essex & Windmill Pointe) | 0 | 03-25-21 A | 03-25-21 A
GP-14615 | PROJ-0951-GP 5 -3.91.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Pemberton 2 West (Windmill Pointe & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-42810 | PROJ-0951-GP 5 -3.134.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Pemberton 1 West (Jefferson & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-14725 | PROJ-0951-GP 5 -3.111.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Westchester 2 (Windmill Pointe & Essex) | 0 | 03-25-21 A | 03-25-21 A
GP-14715 | PROJ-0951-GP 5 -3.110.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Westchester 1 (Jefferson & Fairfax) | 0 | 03-25-21 A | 03-25-21 A
GP-41630 | PROJ-0951-GP 5 -3.1.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Windmill Pointe Dr 3 (Barrington & Balfour) | 0 | 03-26-21 A | 03-26-21 A
GP-14730 | PROJ-0951-GP 5 -3.112.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Windmill Pointe Dr 1 (Balfour & Westchester) | 0 | 03-26-21 A | 03-26-21 A
GP-14735 | PROJ-0951-GP 5 -3.113.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Windmill Pointe Dr 2 (Westchester & Alter) | 0 | 03-26-21 A | 2021-09-29
GP-14755 | PROJ-0951-GP 5 -3.102.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface -Somerset 2 (Jefferson & St. Paul) | 0 | 03-26-21 A | 03-26-21 A
A26650 | PROJ-0951-GP 5 -3.5.4.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - ANO Kercheval 2 GP4 (Notre Dame & Cadieux)) | 0 | 03-26-21 A | 03-26-21 A
A26810 | PROJ-0951-GP 5 -3.5.5.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - ANO Kercheval 1 GP 4 (St. Clair & Notre Dame) | 0 | 03-26-21 A | 03-26-21 A
GP 41210 | PROJ-0951-GP 5 -3.77.76.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Kercheval PL (ASO Kercheval & Kerchval) GP4 | 0 | 03-26-21 A | 03-26-21 A
GP-46170 | PROJ-0951-GP 5 -3.9.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Kercheval North 2 GP4 (Neff & St. Clair) | 0 | 03-26-21 A | 03-26-21 A
GP-46250 | PROJ-0951-GP 5 -3.9.2.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Kercheval North 1 GP4 (Cadieux & Notre Dame) | 1 | 03-26-21 A | 03-26-21 A
GP-43320 | PROJ-0951-GP 5 -3.136.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Beaconsfield 3 (ASO Jefferson & Halley) | 0 | 03-26-21 A | 03-26-21 A
GP-44820 | PROJ-0951-GP 5 -3.2.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Riverside (Alter & Alter) | 0 | 03-26-21 A | 03-26-21 A
NCDET - 12635 | NEWPROJ-6.59.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - ANO Fenkell 4 (Hubbell & Stansbury) | 4 | 03-30-21 A | 03-30-21 A
ND2-13930 | PROJ-0951-NDET2-2.7.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - ANO 7 Mile Rd (Van Dyke & Sherwood) | 0 | 03-30-21 A | 03-30-21 A
ND2-1240 | PROJ-0951-NDET2-2.1.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - 7 Mile Rd (Sherwood & EOM) | 3 | 03-30-21 A | 03-30-21 A
ND2-13810 | PROJ-0951-NDET2-2.2.2.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - 8 Mile Rd (M102) (2) (Spencer & EOM) | 0 | 03-30-21 A | 03-30-21 A
ND2-13690 | PROJ-0951-NDET2-2.4.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - AEO Van Dyke Ave (M53) (8 Mile Rd & Milbank Greenway) | 0 | 03-30-21 A | 03-30-21 A
ND2-14050 | PROJ-0951-NDET2-2.8.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - AWO Van Dyke Ave (M53) (1) (8 Mile Rd & E Outer Drive) | 3 | 03-30-21 A | 03-30-21 A
ND2-18010 | PROJ-0951-NDET2-2.39.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Van Dyke Ave (M53) (1) (Outer Drive & Milbank Greenway) | 22 | 03-30-21 A | 03-30-21 A
ND2-21850 | PROJ-0951-NDET2-2.8.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - AWO Van Dyke Ave (M53) (1) (8 Mile Rd & E Outer Drive) | 0 | 03-30-21 A | 03-30-21 A
ND2-14410 | PROJ-0951-NDET2-2.9.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Bramford St (8 Mile Rd & Milbank Greenway) | 0 | 03-31-21 A | 03-31-21 A
ND2-15010 | PROJ-0951-NDET2-2.14.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Concord Ave(2) (E Outer Drive & 7 Mile Rd) | 0 | 03-31-21 A | 03-31-21 A
ND2-15490 | PROJ-0951-NDET2-2.18.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Outer Drive (South Side) (Sherwood & Packard ) | 0 | 03-31-21 A | 03-31-21 A
ND2-18640 | PROJ-0951-NDET2-2.40.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - ENO E Outer (Milbank & Milbank Greenway) | 39 | 03-31-21 A | 03-31-21 A
ND2-22700 | PROJ-0951-NDET2-2.17.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Outer Dr (North Side) (Spencer & Stotter) | 0 | 03-31-21 A | 03-31-21 A
ND2-19530 | PROJ-0951-NDET2-2.52.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Helen St (2) (E Outer Drive & 7 Mile Rd) | 0 | 03-31-21 A | 03-31-21 A
ND2-16210 | PROJ-0951-NDET2-2.24.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Monitor St (Conner St & Milbank Greenway) | 0 | 03-31-21 A | 03-31-21 A
ND2-25300 | PROJ-0951-NDET2-2.16.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Packard Ave (2) (E Outer Drive & 7 Mile Rd) | 0 | 03-31-21 A | 03-31-21 A
ND2-16570 | PROJ-0951-NDET2-2.28.2.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Rogge St (1) (8 Mile Rd & E Outer Drive) | 105 | 03-31-21 A | 03-31-21 A
ND2-17530 | PROJ-0951-NDET2-2.35.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Spencer Ave (2) (E Outer Drive & 7 Mile Rd) | 0 | 03-31-21 A | 03-31-21 A
ND2-17650 | PROJ-0951-NDET2-2.36.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Stotter St (1) (8 Mile Rd & E Outer Drive) | 0 | 03-31-21 A | 03-31-21 A
ND2-17770 | PROJ-0951-NDET2-2.37.1.5 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Stotter St (2) (ANO 7 Mile & ASO Outer Drive) | 0 | 03-31-21 A | 03-31-21 A
ND2-24170 | PROJ-0951-NDET2-2.37.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Stotter St (2) (ASO Outer Dr & Outer Dr) | 0 | 03-31-21 A | 03-31-21 A
ND2-24420 | PROJ-0951-NDET2-2.37.2.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Stotter St (2) E Outer Dr Crossing | 0 | 03-31-21 A | 03-31-21 A
ND2-18250 | PROJ-0951-NDET2-2.41.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Veach (8 Mile Rd & Milbank Greenway) | 39 | 03-31-21 A | 03-31-21 A
ND2-18850 | PROJ-0951-NDET2-2.46.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Girardin Ave (Emery St & EOM) | 0 | 04-01-21 A | 04-01-21 A
NWDET-15170 | PROJ-0951-NWDET1CO.32.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Stahelin (2) (Schoolcraft & Davison) | 51 | 04-15-21 A | 05-24-21 A
AA4 20900 | GRP-2021-AA4.37.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Elder Blvd (11' WWPL Crest Ave & Eberwhite Blvd) | 0 | 04-19-21 A | 04-23-21 A
AA4 22218 | GRP-2021-AA4.37.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Elder Blvd (Eberwhite Blvd & EOM 280' EEPL Eberwhite Blvd) | 0 | 04-19-21 A | 04-23-21 A
GP-43660 | PROJ-0951-GP 5 -3.137.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Nottingham 1 (Mack & Kercheval) | 0 | 04-20-21 A | 04-20-21 A
ND2-16690 | PROJ-0951-NDET2-2.28.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Rogge St (2) (E Outer Drive & E Lantz St) | 26 | 04-20-21 A | 04-20-21 A
GP-14720 | PROJ-0951-GP 5 -3.110.1.3 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Westchester 1 (Essex & Fairfax) | 0 | 04-20-21 A | 04-20-21 A
AP 4400 | PROJ-0951-MMOAllen.67.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Promenade (Reeck & Park) | 4 | 04-22-21 A | 05-26-21 A
NWDET-5610 | PROJ-0951-NWDET1CO.29.1.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Artesian (3) (Schoolcraft & SO Glendale) | 12 | 04-22-21 A | 06-01-21 A
RedfMMO1240 | PROJ-0951-MMORedford-1.3.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Seminole (Grand River & 7 Mile) | 0 | 04-22-21 A | 2021-09-23
AA4 20762 | GRP-2021-AA4.19.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Madison Pl (W Madison St & EOM) | 0 | 04-23-21 A | 06-16-21 A
AA4 21898 | GRP-2021-AA4.36.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Eberwhite Blvd West (Lutz & W Madison) | 0 | 04-23-21 A | 05-13-21 A
AA4 24008 | GRP-2021-AA4.40.4.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Lutz Ave (Eberwhite Blvd & S 7th St) | 0 | 04-23-21 A | 05-18-21 A
RedfMMO1720 | PROJ-0951-MMORedford-1.8.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Pembroke (Fox & Gaylord) | 0 | 04-23-21 A | 2021-09-23
AA4 20913 | GRP-2021-AA4.50.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Sunnyside Blvd (EOM & S 7th St) | 0 | 04-23-21 A | 05-18-21 A
AA4 20918 | GRP-2021-AA4.55.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Woodbridge Blvd (Eberwhite Blvd & EOM) | 0 | 04-23-21 A | 05-18-21 A
AA4 23668 | GRP-2021-AA4.40.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Lutz Ave (14' WEPL Soule Blvd & 11' EWPL Crest Ave) | 0 | 04-26-21 A | 05-12-21 A
AA4 23838 | GRP-2021-AA4.40.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Lutz Ave (11' EWPL Crest Ave & Eberwhite Blvd) | 0 | 04-26-21 A | 05-12-21 A
AA4 24178 | GRP-2021-AA4.40.5.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Lutz Ave (EOM 215' WWPL Soule Blvd & 3' WWPL Soule Blvd) | 0 | 04-26-21 A | 05-12-21 A
AA4 20904 | GRP-2021-AA4.41.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Manhattan Dr (Mt Vernon Ave& Mt Pleasant Dr) | 0 | 04-26-21 A | 04-29-21 A
AA4 24508 | GRP-2021-AA4.44.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Mt Vernon Ave (Mt Pleasant Ave & Manhattan Ave) | 0 | 04-26-21 A | 05-03-21 A
GP-14115 | PROJ-0951-GP 5 -3.18.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Beaconsfield 2 (Kercheval & Jefferson) | 0 | 04-27-21 A | 2021-09-29
CDET-2125 | PROJ-0951-CDET1-2.47.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Webb (1) (AWO Linwood & Dexter) | 0 | 04-27-21 A | 05-27-21 A
GP-14710 | PROJ-0951-GP 5 -3.109.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Wayburn 1 (Hampton & Kercheval) | 0 | 04-27-21 A | 04-27-21 A
GP-42300 | PROJ-0951-GP 5 -3.128.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Wayburn 2 (Kercheval & Mack) | 0 | 04-27-21 A | 04-27-21 A
SCDet-3120 | GRP-2021-SCDet1.15.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Hartwell (Joy & Tireman) | 4 | 04-29-21 A | 04-30-21 A
SCDet-8500 | GRP-2021-SCDet1.29.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Wyoming Ave West (Joy & Tireman) | 4 | 04-30-21 A | 2021-09-28
AA4 24988 | GRP-2021-AA4.3.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Potter Ave (4' EWPL Hutchins Ave & 4' WEPL Hutchins Ave) | 0 | 05-03-21 A | 05-21-21 A
AA4 20548 | GRP-2021-AA4.3.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Potter Ave (Hutchins & Presscott Ave) | 0 | 05-03-21 A | 05-21-21 A
AA4 20902 | GRP-2021-AA4.39.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Jefferson Ct (3' EWPL ESO Jefferson Ct & 272' WWPL S 7th St) | 0 | 05-03-21 A | 05-19-21 A
AA4 22298 | GRP-2021-AA4.37.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Elder Blvd (4' WEPL Eberwhite Blvd & 4' EWPL Eberwhite Blvd) | 0 | 05-03-21 A | 05-06-21 A
AA4 22378 | GRP-2021-AA4.37.4.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Elder Blvd (Crest Ave & 11' WEPL Crest Ave) | 0 | 05-03-21 A | 05-06-21 A
AA4 26318 | GRP-2021-AA4.6.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 7th St (Jefferson Ct & W Madison St) | 0 | 05-03-21 A | 05-06-21 A
AA4 28478 | GRP-2021-AA4.6.6.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 7th St (Jefferson & Jefferson Ct) | 0 | 05-03-21 A | 05-06-21 A
CDET-970 | PROJ-0951-CDET1-2.33.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Tyler (1) (Linwood & Dexter) | 0 | 05-03-21 A | 06-16-21 A
GP-14555 | PROJ-0951-GP 5 -3.82.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Maryland 1 (Mack & Kercheval) | 0 | 05-03-21 A | 2021-09-29
GP-44250 | PROJ-0951-GP 5 -3.140.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Maryland 2 (Kercheval & Jefferson) | 0 | 05-03-21 A | 2021-09-29
EDET1 50868 | GRP-2021-ED1.22.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bishop St (2) (Waveney St & Mack Ave) | 0 | 05-04-21 A | 05-26-21 A
EDET1 50872 | GRP-2021-ED1.27.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Grayton St (2) (Waveney St & Mack Ave) | 0 | 05-04-21 A | 2021-09-29
AA4 22708 | GRP-2021-AA4.1.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Hutchins Ave (Princeton Ave & 23' NNPL W Davis Ave) | 0 | 05-04-21 A | 05-27-21 A
GP-43980 | PROJ-0951-GP 5 -3.138.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Lakepointe 1 (Kercheval & Mack) | 0 | 05-04-21 A | 05-04-21 A
AA4 22788 | GRP-2021-AA4.1.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Hutchins Ave (W Davis St & Pauline Blvd) | 0 | 05-04-21 A | 05-27-21 A
GP-14110 | PROJ-0951-GP 5 -3.17.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Beaconsfield 1 (Kercheval & Mack) | 0 | 05-04-21 A | 05-04-21 A
GP-14130 | PROJ-0951-GP 5 -3.21.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Charlevoix (Lakepointe & Wayburn) | 0 | 05-04-21 A | 05-04-21 A
AA4 23108 | GRP-2021-AA4.39.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Jefferson Ct (19' WWPL S 7th & 10' WEPL S 7th St) | 0 | 05-04-21 A | 05-19-21 A
AA4 23188 | GRP-2021-AA4.39.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Jefferson Ct (272' WWPL S 7th St & 16' WWPL S 7th St) | 0 | 05-04-21 A | 05-19-21 A
AA4 28448 | GRP-2021-AA4.7.6.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - ESO Jefferson Ct (Jefferson Ct & EOS) | 0 | 05-04-21 A | 05-19-21 A
AA4 29228 | GRP-2021-AA4.15.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Easement (EOM & S 7th) | 0 | 05-04-21 A | 05-19-21 A
NWDET-5655 | PROJ-0951-NWDET1CO.17.1.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Davison (1) (Auburn & Artesian) | 17 | 05-06-21 A | 05-06-21 A
NWDET-20020 | PROJ-0951-NWDET1CO.53.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Penrod (2) (Schoolcraft & Davison) | 69 | 05-10-21 A | 05-24-21 A
CDET-2035 | PROJ-0951-CDET1-2.45.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Elmhurst (1) (AWO Linwood & Dexter) | 0 | 05-10-21 A | 05-26-21 A
CDET-12915 | PROJ-0951-CDET1-2.64.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Cortland (2) (AWO Linwood & Dexter) | 0 | 05-10-21 A | 05-28-21 A
GP-14750 | PROJ-0951-GP 5 -3.101.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface -Somerset 1 (Mack & Vernor) | 0 | 05-10-21 A | 2021-09-29
EDET1 50873 | GRP-2021-ED1.28.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Harvard Rd (2) (Waveney St & Mack Ave) | 0 | 05-10-21 A | 05-10-21 A
EDET1 507846 | GRP-2021-ED1.6.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Harvard Rd (1) (ASO Warren & Waveney) | 0 | 05-10-21 A | 05-27-21 A
GP-14240 | PROJ-0951-GP 5 -3.38.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Jefferson South (Alter & Balfour) | 0 | 05-10-21 A | 2021-09-29
EDET1 50871 | GRP-2021-ED1.26.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Grayton St (1) (E Warrern Ave & Waveney St) | 0 | 05-10-21 A | 05-27-21 A
CDET-1365 | PROJ-0951-CDET1-2.36.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Sturtevant (1) (Linwood & Dexter) | 0 | 05-10-21 A | 06-02-21 A
AA4 20917 | GRP-2021-AA4.53.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Stadium Blvd (Hutchins Ave & Prescott Ave) | 0 | 05-10-21 A | 05-25-21 A
AA4 22868 | GRP-2021-AA4.1.4.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Hutchins Ave (Pauline Bvd & Potter Ave) | 0 | 05-10-21 A | 05-25-21 A
AA4 22948 | GRP-2021-AA4.1.5.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Hutchins Ave (Potter Ave & W Stadium Blvd) | 0 | 05-10-21 A | 05-25-21 A
AA4 20899 | GRP-2021-AA4.36.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Eberwhite Blvd East (Woodbridge & Elder) | 0 | 05-10-21 A | 05-25-21 A
AA4 20903 | GRP-2021-AA4.40.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Lutz Ave (4' EWPL Soule Blvd & 11' WEPL Soule Blvd) | 0 | 05-10-21 A | 05-25-21 A
AA4 20906 | GRP-2021-AA4.43.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Mt Pleasant Ave (Mt Vernon Ave & Manhattan Dr) | 0 | 05-10-21 A | 05-25-21 A
AA4 20907 | GRP-2021-AA4.44.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Mt Vernon Ave (W Madison St & Mt Vernon Ave) | 0 | 05-10-21 A | 05-25-21 A
AA4 27598 | GRP-2021-AA4.52.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Madison St (6' WEPL Eberwhite Blvd & Madison Pl) | 0 | 05-10-21 A | 05-25-21 A
AA4 20545 | GRP-2021-AA4.4.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Franklin Blvd (S 7th St & Hutchins Ave) | 0 | 05-10-21 A | 05-25-21 A
AA4 21818 | GRP-2021-AA4.36.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Eberwhite Blvd West (W Liberty & Lutz) | 0 | 05-10-21 A | 05-25-21 A
AA4 20914 | GRP-2021-AA4.51.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Virginia St (Bemidji St & W Liberty St) | 0 | 05-10-21 A | 05-18-21 A
AA4 20550 | GRP-2021-AA4.6.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 7th St (12' SNPL W Madison St & 6' NNPL Pauline Blvd) | 0 | 05-10-21 A | 05-28-21 A
CDET-2255 | PROJ-0951-CDET1-2.50.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Collingwood (1) (AWO Linwood & Dexter) | 0 | 05-11-21 A | 05-27-21 A
CDET-13145 | PROJ-0951-CDET1-2.65.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Leslie (2) (Linwood & Dexter) | 0 | 05-11-21 A | 2021-09-29
CDET-10865 | PROJ-0951-CDET1-2.55.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Tuxedo (1) (Dexter & AWO Linwood) | 0 | 05-11-21 A | 05-27-21 A
SCDet-3200 | GRP-2021-SCDet1.16.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Bingham (Littlefield & Tireman) | 4 | 05-13-21 A | 06-16-21 A
SCDet-6690 | GRP-2021-SCDet1.8.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Esper (Mendota & Joy) | 4 | 05-13-21 A | 06-16-21 A
SCDet-9060 | GRP-2021-SCDet1.17.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Cheyenne (Littlefield & Tireman) | 4 | 05-13-21 A | 05-27-21 A
AP 3750 | PROJ-0951-MMOAllen.39.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Kolb 1 (Southway & Goddard) | 4 | 05-13-21 A | 05-13-21 A
CDET-315 | PROJ-0951-CDET1-2.8.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Fleet (1) (Linwood & Oakman) | 0 | 05-13-21 A | 05-13-21 A
AP 3470 | PROJ-0951-MMOAllen.11.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Becker 3 (Wick & Midway) | 4 | 05-13-21 A | 2021-10-19
AP 3760 | PROJ-0951-MMOAllen.40.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Kolb 2 (Midway & Northway) | 4 | 05-13-21 A | 05-13-21 A
AA4 20896 | GRP-2021-AA4.11.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Crest Ave (W Liberty St & Luts Ave) | 0 | 05-14-21 A | 06-01-21 A
AA4 20546 | GRP-2021-AA4.1.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Hutchins Ave (23' NNPL W Davis Ave & 8' SSPL W Davis Ave) | 0 | 05-17-21 A | 05-25-21 A
AA4 20915 | GRP-2021-AA4.52.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Madison St (Soule Blvd & Eberwhite Blvd) | 0 | 05-17-21 A | 05-21-21 A
AA4 27518 | GRP-2021-AA4.52.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Madison St (4' EWPL Soule Blvd & Tie In 35' EEPL Soule Blvd) | 0 | 05-17-21 A | 05-21-21 A
EDET1 50882 | GRP-2021-ED1.37.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Yorkshire Rd (2) (Waveney St & Mack Ave) | 0 | 05-18-21 A | 05-26-21 A
SCDet-4080 | GRP-2021-SCDet1.4.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Freda (Esper & Tireman) | 4 | 05-18-21 A | 06-08-21 A
AP 4350 | PROJ-0951-MMOAllen.66.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Pleasant (Reeck & Park) | 4 | 05-19-21 A | 05-26-21 A
SCDet-4880 | GRP-2021-SCDet1.37.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Greenlawn (Joy & Tireman) | 0 | 05-19-21 A | 05-26-21 A
AP 3880 | PROJ-0951-MMOAllen.52.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Melbourne 3 (Moore & 380' South Of Maylawn Ave) | 4 | 05-19-21 A | 05-19-21 A
SCDet-10950 | GRP-2021-SCDet1.19.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Sorrento (Mackenzie & Tireman) | 4 | 05-20-21 A | 06-02-21 A
CDET-140 | PROJ-0951-CDET1-2.2.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Doris (1) (Linwood & Livernois) | 0 | 05-20-21 A | 05-26-21 A
AP 3600 | PROJ-0951-MMOAllen.24.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Crescent (Reeck & Park) | 4 | 05-20-21 A | 05-20-21 A
AP 5200 | PROJ-0951-MMOAllen.82.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Sterling (Moore & Pennsylvania) | 4 | 05-20-21 A | 06-16-21 A
AA4 24348 | GRP-2021-AA4.43.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Mt Pleasant Ave (Manhattan Dr & Sunnyside Blvd) | 0 | 05-21-21 A | 05-27-21 A
NWDET-17460 | PROJ-0951-NWDET1CO.51.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Greenview (2) (Davison & EOM) | 14 | 05-24-21 A | 05-24-21 A
RedfMMO1560 | PROJ-0951-MMORedford-1.6.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Indian (St. Martins & Grand River) | 0 | 05-24-21 A | 2021-09-23
RedfMMO1880 | PROJ-0951-MMORedford-1.10.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Vassar (Denby & Gaylord) | 0 | 05-24-21 A | 05-27-21 A
ND2-17410 | PROJ-0951-NDET2-2.34.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Spencer Ave (1) (8 Mile Rd & E Outer Drive) | 0 | 05-24-21 A | 2021-09-23
Muni4710 | PROJ-0951-MUN-3.19.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Longfellow (Rosa Parks & Linwood) | 0 | 05-25-21 A | 07-06-21 A
CDET-185 | PROJ-0951-CDET1-2.3.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - W Grand 1 (Dexter & Linwood) | 0 | 05-26-21 A | 2021-09-29
CDET-1145 | PROJ-0951-CDET1-2.4.3.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - W Grand 2 (Dexter & Livernois) | 0 | 05-26-21 A | 2021-09-29
RedfMMO3930 | PROJ-0951-MMORedford-1.32.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface -Grand River (Lexington & Poinciana) | 0 | 05-26-21 A | 2021-09-29
AP 3430 | PROJ-0951-MMOAllen.7.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Balfour 1 (Southway & Goddard) | 4 | 05-26-21 A | 2021-09-30
AP 3440 | PROJ-0951-MMOAllen.8.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Balfour 2 (Midway & Northway) | 4 | 05-26-21 A | 2021-10-06
AP 3580 | PROJ-0951-MMOAllen.22.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Chatham (Wick & 420' South Of Maylawn Ave) | 4 | 05-26-21 A | 05-26-21 A
CDET-270 | PROJ-0951-CDET1-2.7.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Kendall (1) (Linwood & Dexter) | 0 | 05-26-21 A | 05-26-21 A
SCDet-4320 | GRP-2021-SCDet1.30.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Kentucky (Joy & Tireman) | 4 | 05-26-21 A | 05-28-21 A
SCDet-4640 | GRP-2021-SCDet1.34.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Northlawn (Joy & Tireman) | 0 | 05-26-21 A | 05-26-21 A
CDET-360 | PROJ-0951-CDET1-2.9.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Pasadena (1) (Linwood & Dexter) | 0 | 05-26-21 A | 06-14-21 A
CDET-1235 | PROJ-0951-CDET1-2.10.3.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Pasadena (2) (Dexter & Livernois) | 0 | 05-26-21 A | 06-14-21 A
RR1 5473 | GRP-2021-RR1.60.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Elm St (W Jefferson & Genesse St) | 4 | 05-26-21 A | 2021-11-19
AP 4700 | PROJ-0951-MMOAllen.73.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Reeck 3 (Moore & Midway) | 4 | 05-26-21 A | 05-26-21 A
AP 4750 | PROJ-0951-MMOAllen.74.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Rose (Reeck & Park) | 4 | 05-26-21 A | 05-28-21 A
CDET2-4440 | GRP-2021-CDet2.40.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Dexter 1 (Longfellow & Euclid) | 0 | 05-26-21 A | 05-26-21 A
CDET2-9990 | GRP-2021-CDet2.28.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Gladstone (Linwood & Rosa Parks) | 0 | 05-26-21 A | 06-23-21 A
CDET2-6720 | GRP-2021-CDet2.31.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Blaine 2 (La Salle - Rosa Parks) | 0 | 05-26-21 A | 2021-09-28
CDET2-3240 | GRP-2021-CDet2.25.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Hazelwood 1 (Dexter & Linwood) | 0 | 05-26-21 A | 2021-09-29
CDET2-2520 | GRP-2021-CDet2.15.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Edison 2 (Linwood & Rosa Parks) | 0 | 05-26-21 A | 07-21-21 A
CDET2-2760 | GRP-2021-CDet2.18.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Atkinson 2 (Linwood & Rosa Parks) | 0 | 05-26-21 A | 05-26-21 A
SCDet-2480 | GRP-2021-SCDet1.7.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd E 1 (Mackenzie & Tireman) | 4 | 05-26-21 A | 2021-09-28
SCDet-2320 | GRP-2021-SCDet1.5.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd E 3 (Joy & Birwood) | 4 | 05-26-21 A | 05-26-21 A
EDET1 50881 | GRP-2021-ED1.36.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Yorkshire Rd (1) (E Warrern Ave & Waveney St) | 0 | 05-26-21 A | 05-26-21 A
CDET-2080 | PROJ-0951-CDET1-2.48.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Burlingame (1) (Dexter & AWO Linwood) | 0 | 05-26-21 A | 05-26-21 A
EDET1 50867 | GRP-2021-ED1.21.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bishop St (1) (E Warrern Ave & Waveney St) | 0 | 05-26-21 A | 05-26-21 A
CDET-11555 | PROJ-0951-CDET1-2.58.53.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Wildemere (3) (Richton & Monterey) | 0 | 05-26-21 A | 2021-09-29
CDET-230 | PROJ-0951-CDET1-2.5.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Clements (1) (Linwood & Dexter) | 0 | 05-26-21 A | 05-28-21 A
CDET-1190 | PROJ-0951-CDET1-2.6.2.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Clements (2) (Livernois & Dexter) | 0 | 05-26-21 A | 05-26-21 A
SCDet-2080 | GRP-2021-SCDet1.1.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd W 3 (Joy & Birwood) | 4 | 05-27-21 A | 05-27-21 A
SCDet-3600 | GRP-2021-SCDet1.21.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Meyers (Joy & Oakman) | 4 | 05-27-21 A | 05-27-21 A
SCDet-3840 | GRP-2021-SCDet1.25.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Mendota (Esper & Tireman) | 4 | 05-27-21 A | 06-11-21 A
SCDet-4160 | GRP-2021-SCDet1.28.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Normile (Belton & Tireman) | 4 | 05-27-21 A | 05-28-21 A
SCDet-4400 | GRP-2021-SCDet1.31.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Indiana (Joy & Tireman) | 4 | 05-27-21 A | 05-28-21 A
SCDet-4560 | GRP-2021-SCDet1.33.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Ohio (Joy & Tireman) | 4 | 05-27-21 A | 05-27-21 A
CDET2-4120 | GRP-2021-CDet2.36.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Euclid 1 (Dexter & Linwood) | 0 | 05-27-21 A | 2021-09-28
EDET1 50865 | GRP-2021-ED1.19.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Audubon Rd (1) (E Warrern Ave & Waveney St) | 0 | 05-27-21 A | 05-28-21 A
EDET1 501250 | GRP-2021-ED1.72.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Berkshire St (2) (Bremen St & Mack Ave) | 0 | 05-27-21 A | 05-28-21 A
EDET1 501251 | GRP-2021-ED1.73.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Buckingham Ave (1) (E Warrern Ave & Waveney St) | 0 | 05-27-21 A | 2021-09-28
EDET1 501256 | GRP-2021-ED1.78.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Haverhill St (2) (Waveney St& ANO Mack Ave) | 0 | 05-27-21 A | 2021-09-28
SCDet-10360 | GRP-2021-SCDet1.3.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd W 1 (Belton & Tireman) | 4 | 05-27-21 A | 05-27-21 A
RR1 6711 | GRP-2021-RR.16.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Patton (Tireman & Sawyer) | 0 | 05-27-21 A | 05-28-21 A
EDET1 503806 | GRP-2021-ED1.69.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bedford St (1) (E Warren Ave & Waveney St) | 0 | 05-27-21 A | 06-07-21 A
EDET1 506606 | GRP-2021-ED1.76.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Devonshire Rd (2) (Brunswick St & Mack Ave) | 0 | 05-27-21 A | 05-27-21 A
EDET1 506766 | GRP-2021-ED1.76.2.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Devonshire Rd (2) (Bremen St & Brunswick St) | 0 | 05-27-21 A | 05-27-21 A
SCDet-4720 | GRP-2021-SCDet1.35.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Cloverlawn (Joy & Tireman) | 0 | 05-27-21 A | 06-02-21 A
SCDet-4480 | GRP-2021-SCDet1.32.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Wisconsin (Joy & Tireman) | 0 | 05-27-21 A | 07-07-21 A
EDET1 507686 | GRP-2021-ED1.6.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Harvard Rd (1) (Waveney & ANO Warren) | 0 | 05-27-21 A | 2021-09-29
EDET1 50876 | GRP-2021-ED1.31.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Kensington Ave (2) (Waveney St & Mack Ave) | 0 | 05-27-21 A | 05-27-21 A
CDET2-3080 | GRP-2021-CDet2.22.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Taylor 1 (Dexter & Linwood) | 0 | 05-27-21 A | 07-09-21 A
CDET2-3400 | GRP-2021-CDet2.27.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Gladstone 1 (Dexter & Lawton) | 0 | 05-27-21 A | 2021-09-29
RedfMMO4080 | PROJ-0951-MMORedford-1.35.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface -Negaunee (Grand River & 7 Mile Rd) | 0 | 05-27-21 A | 2021-09-29
CDET-405 | PROJ-0951-CDET1-2.11.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Oakman (1) (Fleet & Dexter) | 0 | 05-27-21 A | 07-13-21 A
CDET-450 | PROJ-0951-CDET1-2.15.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Oakman Ct (Linwood & Oakman) | 0 | 05-27-21 A | 05-27-21 A
CDET-1060 | PROJ-0951-CDET1-2.13.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Oakman (3) (Dexter & Linwood) | 0 | 05-27-21 A | 07-13-21 A
CDET-1100 | PROJ-0951-CDET1-2.14.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Oakman (4) (Livernois & Dexter) | 0 | 05-27-21 A | 07-13-21 A
CDET-1410 | PROJ-0951-CDET1-2.37.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Ewald (1) (Dexter & Kendall) | 0 | 05-27-21 A | 05-28-21 A
CDET-1900 | PROJ-0951-CDET1-2.43.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Richton (1) (Dexter & AWO Linwood) | 0 | 05-27-21 A | 05-27-21 A
CDET-1945 | PROJ-0951-CDET1-2.44.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Monterey (1) (Dexter & Linwood) | 0 | 05-27-21 A | 05-27-21 A
CDET-2170 | PROJ-0951-CDET1-2.49.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Lawrence (1) (AWO Linwood & Dexter) | 0 | 05-27-21 A | 05-27-21 A
CDET-2425 | PROJ-0951-CDET1-2.25.2.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Buena Vista (1) (AEO Dexter & Linwood) | 0 | 05-27-21 A | 06-02-21 A
CDET-10415 | PROJ-0951-CDET1-2.53.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Ewald (2) (Livernois & Dexter) | 0 | 05-27-21 A | 05-28-21 A
CDET-10635 | PROJ-0951-CDET1-2.54.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Oakman (5) (Dexter & Livernois) | 0 | 05-27-21 A | 07-13-21 A
CDET-20850 | PROJ-0951-CDET1-2.30.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Leslie South (Dexter & Wildemere St) | 0 | 05-27-21 A | 05-27-21 A
GP-14460 | PROJ-0951-GP 5 -3.67.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Klenk (EOM & Alter) | 0 | 05-27-21 A | 05-27-21 A
GP-44520 | PROJ-0951-GP 5 -3.141.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Hampton 2 (Wayburn & Maryland) | 0 | 05-27-21 A | 2021-09-29
AA4 25148 | GRP-2021-AA4.22.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Princeton Ave (S 7th St & 5th St) | 0 | 05-27-21 A | 06-16-21 A
AP 3780 | PROJ-0951-MMOAllen.42.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Laurence 2 (Moore & Pennsylvania) | 4 | 05-27-21 A | 06-16-21 A
EDET1 507306 | GRP-2021-ED1.5.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Kensington Ave (ASO E Warren & Waveney) | 0 | 05-27-21 A | 05-27-21 A
EDET1 50870 | GRP-2021-ED1.25.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Courville St (2) (Waveney St & Mack Ave) | 0 | 05-27-21 A | 05-27-21 A
AP 3410 | PROJ-0951-MMOAllen.5.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Andrews 2 (Allen & Midway) | 4 | 05-27-21 A | 2021-10-05
EDET1 506306 | GRP-2021-ED1.70.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bedford St (2) (WaveneySt & Mack Ave) | 0 | 05-27-21 A | 05-27-21 A
EDET1 507446 | GRP-2021-ED1.69.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bedford St (1) (E Warren Ave & Waveney St) | 0 | 05-27-21 A | 06-07-21 A
GP-14425 | PROJ-0951-GP 5 -3.62.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Hampton (Alter & Wayburn) | 0 | 05-27-21 A | 2021-09-30
SCDet-3360 | GRP-2021-SCDet1.18.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Ward (Joy & Mackenzie) | 4 | 05-27-21 A | 05-27-21 A
SCDet-7280 | GRP-2021-SCDet1.25.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Mendota (Joy & Oakman) | 4 | 05-27-21 A | 06-11-21 A
EDET1 50866 | GRP-2021-ED1.20.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Audubon Rd (2) (Waveney St & Mack Ave) | 0 | 05-27-21 A | 05-27-21 A
AP 3830 | PROJ-0951-MMOAllen.47.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Manor 2 (Moore & Midway) | 4 | 05-27-21 A | 06-02-21 A
EDET1 501186 | GRP-2021-ED1.56.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Chatsworth St (2) (Bremen St & Mack Ave) | 0 | 05-27-21 A | 06-22-21 A
AP 3520 | PROJ-0951-MMOAllen.16.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Buckingham (Moore & Allen) | 4 | 05-28-21 A | 05-28-21 A
SCDet-4000 | GRP-2021-SCDet1.27.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Morrow (Esper & Tireman) | 4 | 05-28-21 A | 06-07-21 A
SCDet-4240 | GRP-2021-SCDet1.29.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Wyoming Ave East (Joy & Tireman) | 4 | 05-28-21 A | 2021-09-28
EDET1 501249 | GRP-2021-ED1.71.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Berkshire St (1) (ASO E Warrern Ave & Waveney St) | 0 | 05-28-21 A | 2021-09-28
CDET2-2920 | GRP-2021-CDet2.20.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Clairmount 1 (Dexter & Linwood) | 0 | 05-28-21 A | 2021-09-29
EDET1 50869 | GRP-2021-ED1.24.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Courville St (1) (E Warrern Ave & Waveney St) | 0 | 05-28-21 A | 06-07-21 A
NWDET-20740 | PROJ-0951-NWDET1CO.60.6.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Schoolcraft (2) (At Artesian) | 0 | 05-31-21 A | 05-31-21 A
NWDET-20600 | PROJ-0951-NWDET1CO.60.4.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Schoolcraft (2) (At Warwick) | 0 | 05-31-21 A | 05-31-21 A
NWDET-20530 | PROJ-0951-NWDET1CO.60.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Schoolcraft (2) (At Piedmont) | 0 | 05-31-21 A | 05-31-21 A
NWDET-20460 | PROJ-0951-NWDET1CO.60.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Schoolcraft (2) (At Westwood) | 0 | 05-31-21 A | 05-31-21 A
AA4 28768 | GRP-2021-AA4.2.15.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Pauline Blvd (Hutchins & S Main Stt) | 0 | 06-01-21 A | 2021-10-04
NWDET-17690 | PROJ-0951-NWDET1CO.52.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Faust (2) (Schoolcraft & Davison) | 62 | 06-01-21 A | 06-01-21 A
NWDET-17000 | PROJ-0951-NWDET1CO.47.5.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Minock (2) (ASO Schoolcraft & Davison) | 14 | 06-01-21 A | 2021-09-20
NWDET-15260 | PROJ-0951-NWDET1CO.32.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Stahelin (2) (Davison & EOM) | 12 | 06-01-21 A | 06-01-21 A
NWDET-9260 | PROJ-0951-NWDET1CO.56.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Glastonbury (4) (Davison & EOM) | 5 | 06-01-21 A | 06-01-21 A
NWDET-9020 | PROJ-0951-NWDET1CO.56.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Glastonbury (4) (Schoolcraft & Davison) | 58 | 06-01-21 A | 06-01-21 A
NWDET-7400 | PROJ-0951-NWDET1CO.24.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Auburn (1) (Glendale & EOM) | 7 | 06-01-21 A | 06-01-21 A
NWDET-7310 | PROJ-0951-NWDET1CO.24.55.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Auburn (1) (Schoolcraft & Glendale) | 10 | 06-01-21 A | 06-01-21 A
NWDET-15590 | PROJ-0951-NWDET1CO.25.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - ASO Schoolcraft (1) (Artesian & Stahelin) | 1 | 06-01-21 A | 06-01-21 A
RedfMMO2280 | PROJ-0951-MMORedford-1.15.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Poinciana 3 (Curtis & 7 Mile) | 0 | 06-01-21 A | 2021-09-23
Muni1490 | PROJ-0951-MUN-3.27.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Linwood 2 (Oakman & Davison) | 0 | 06-01-21 A | 2021-09-21
CDET-1815 | PROJ-0951-CDET1-2.19.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (3) (Davison & Doris) | 0 | 06-01-21 A | 2021-09-29
CDET-20360 | PROJ-0951-CDET1-2.17.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (1) (Collingwood & Leslie) | 0 | 06-01-21 A | 2021-09-29
CDET-14065 | PROJ-0951-CDET1-2.69.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (9) (Clarimount & Virgina Park) | 0 | 06-01-21 A | 06-01-21 A
CDET-10185 | PROJ-0951-CDET1-2.1.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Kendall (2) (Dexter & Livernois) | 0 | 06-02-21 A | 06-02-21 A
CDET-710 | PROJ-0951-CDET1-2.26.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Livernois (1) (Doris & Davison) | 0 | 06-02-21 A | 2021-09-29
CDET2-7560 | GRP-2021-CDet2.39.38.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Wildemere 2 (W Chicago & Joy) | 0 | 06-02-21 A | 06-02-21 A
SCDet-5760 | GRP-2021-SCDet1.48.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Tireman 2 (Manor & Wisconsin) | 4 | 06-02-21 A | 2021-09-28
SCDet-5680 | GRP-2021-SCDet1.47.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Tireman 1 (Decatur & Appoline) | 4 | 06-02-21 A | 2021-09-28
SCDet-3440 | GRP-2021-SCDet1.19.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Sorrento (Joy & Mackenzie) | 4 | 06-02-21 A | 06-02-21 A
SCDet-11270 | GRP-2021-SCDet1.18.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Ward (Littlefield & Tireman) | 4 | 06-02-21 A | 2021-09-28
WCDET1-1890 | GRP-2021-WCDet1.8.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Dexter E (Davison & Buena Vista) | 0 | 06-02-21 A | 06-02-21 A
WCDET1-14610 | GRP-2021-WCDet1.8.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Dexter West (Buena Vista & Leslie) | 0 | 06-02-21 A | 06-02-21 A
CDET-750 | PROJ-0951-CDET1-2.27.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - AEO Dexter (Leslie & Waverly) | 0 | 06-02-21 A | 2021-09-29
CDET-1770 | PROJ-0951-CDET1-2.18.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (2) (Waverly & Davison) | 0 | 06-02-21 A | 06-02-21 A
CDET-12695 | PROJ-0951-CDET1-2.63.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (4) (Pasadena & Davison) | 0 | 06-02-21 A | 06-02-21 A
CDET-13375 | PROJ-0951-CDET1-2.66.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (6) (Leslie & Glendale) | 0 | 06-02-21 A | 06-02-21 A
ND2-13590 | PROJ-0951-NDET2-2.2.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - 8 Mile Rd (M102) (1) (Veach & Spencer) | 3 | 06-02-21 A | 06-02-21 A
EDET1 501252 | GRP-2021-ED1.74.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Buckingham Ave (2) (Waveney St & Mack Ave) | 0 | 06-02-21 A | 2021-09-28
CDET-1500 | PROJ-0951-CDET1-2.39.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Davison (2) (Dexter & Linwood) | 0 | 06-02-21 A | 06-02-21 A
CDET-1545 | PROJ-0951-CDET1-2.40.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Davison (3) (Linwood & Dexter) | 0 | 06-02-21 A | 06-02-21 A
CDET-1590 | PROJ-0951-CDET1-2.41.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Davison (4) (Dexter & Livernois) | 0 | 06-02-21 A | 2021-09-29
CDET-1455 | PROJ-0951-CDET1-2.38.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Davison (1) (Livernois & Dexter) | 0 | 06-02-21 A | 2021-09-29
EDET1 501246 | GRP-2021-ED1.68.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - 3 Mile Rd (2) (Waveney St & ANO Mack Ave) | 0 | 06-02-21 A | 06-02-21 A
EDET1 502276 | GRP-2021-ED1.67.2.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - 3 Mile Rd (1) (E Warrern Ave & Waveney St) | 0 | 06-02-21 A | 07-08-21 A
RedfMMO3830 | PROJ-0951-MMORedford-1.30.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Denby (Curtis & Vassar) | 0 | 06-02-21 A | 2021-09-29
RedfMMO4030 | PROJ-0951-MMORedford-1.34.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface -Inkster (Margareta & Grand River) | 0 | 06-02-21 A | 2021-09-29
SCDet-2640 | GRP-2021-SCDet1.9.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Littlefield 1 (Joy & Sorrento) | 4 | 06-02-21 A | 06-02-21 A
SCDet-6530 | GRP-2021-SCDet1.8.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Esper (Manor & Mendota) | 4 | 06-02-21 A | 06-02-21 A
SCDet-5280 | GRP-2021-SCDet1.42.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Joy 2 (Manor & Wyoming) | 0 | 06-02-21 A | 2021-09-28
SCDet-9880 | GRP-2021-SCDet1.49.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Mackenzie 1 (Littlefield & Oakman Blvd) | 4 | 06-02-21 A | 06-23-21 A
SCDet-7850 | GRP-2021-SCDet1.28.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Normile (Esper & Belton) | 4 | 06-02-21 A | 06-02-21 A
SCDet-8010 | GRP-2021-SCDet1.28.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Normile (6' NNPL Tireman & Tireman) | 4 | 06-02-21 A | 2021-09-28
SCDet-4800 | GRP-2021-SCDet1.36.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Roselawn (Joy & Tireman) | 0 | 06-02-21 A | 06-08-21 A
WDET-3990 | PROJ-0951-WDET9-4.89.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Westwood 3 (Paul & EOM) | 0 | 06-02-21 A | 2021-09-29
CDET2-2440 | GRP-2021-CDet2.14.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Edison 1 (Dexter & Savery) | 0 | 06-02-21 A | 06-02-21 A
AP 3910 | PROJ-0951-MMOAllen.55.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Moore 2 (Manor & Park) | 4 | 06-02-21 A | 2021-09-29
AP 3890 | PROJ-0951-MMOAllen.53.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Midway (Buckingham & Seavitt) | 4 | 06-02-21 A | 2021-09-28
AA4 20768 | GRP-2021-AA4.26.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Davis Ave (S 7th St & Hutchins) | 0 | 06-04-21 A | 06-17-21 A
AA4 28908 | GRP-2021-AA4.26.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Davis Ave (Hutchins & 5th) | 0 | 06-04-21 A | 06-16-21 A
EDET1 501254 | GRP-2021-ED1.76.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Devonshire Rd (2) (Waveney Ave & Bremen St) | 0 | 06-07-21 A | 06-07-21 A
EDET1 503956 | GRP-2021-ED1.75.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Devonshire Rd (1) (ASO E Warren Ave & Waveney Ave) | 0 | 06-07-21 A | 07-08-21 A
EDET1 501192 | GRP-2021-ED1.62.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Somerset Ave (2) (Waveney St & Mack Ave) | 0 | 06-07-21 A | 07-12-21 A
SCDet-2960 | GRP-2021-SCDet1.13.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Schaefer Hwy E 1 (Joy & Tireman) | 4 | 06-07-21 A | 06-22-21 A
SCDet-3040 | GRP-2021-SCDet1.14.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Schaefer Hwy W 1 (Joy & Tireman) | 4 | 06-07-21 A | 06-22-21 A
AA4 20765 | GRP-2021-AA4.22.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Princeton Ave (9' EWPL S 77th St & 2' WEPL S 77th St) | 0 | 06-08-21 A | 06-16-21 A
CDET2-4200 | GRP-2021-CDet2.37.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Euclid 2 (Linwood & 14th) | 0 | 06-08-21 A | 06-08-21 A
CDET2-10900 | GRP-2021-CDet2.37.3 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Euclid (14th & Rosa Parks) | 0 | 06-08-21 A | 06-08-21 A
CDET2-10170 | GRP-2021-CDet2.8.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Euclid 2 (Linwood & 14th) | 0 | 06-08-21 A | 06-08-21 A
RR1 7611 | GRP-2021-RR.29.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Fielding (McNichols & Grand River) | 0 | 06-08-21 A | 2021-09-28
RR1 7851 | GRP-2021-RR.32.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Lamphere (Fenkell & Eaton) | 0 | 06-08-21 A | 06-11-21 A
AP 3480 | PROJ-0951-MMOAllen.12.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Bellaire (Reeck & 975 Feet East Of Becker) | 4 | 06-09-21 A | 2021-09-28
SCDet-2720 | GRP-2021-SCDet1.10.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Littlefield 2 (Belton & Oakman) | 4 | 06-09-21 A | 06-23-21 A
SCDet-5200 | GRP-2021-SCDet1.41.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Joy 1 (Schaefer & Manor) | 0 | 06-09-21 A | 06-09-21 A
EDET1 50874 | GRP-2021-ED1.29.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Haverhill St (1) (E Warrern Ave & Waveney St) | 0 | 06-10-21 A | 2021-09-28
EDET1 501040 | GRP-2021-ED1.48.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Wayburn Ave (2) (Waveney St & Mack Ave) | 0 | 06-10-21 A | 06-14-21 A
SCDet-7360 | GRP-2021-SCDet1.25.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Mendota (Oakman & Esper) | 4 | 06-10-21 A | 06-11-21 A
SCDet-10040 | GRP-2021-SCDet1.21.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Meyers (Oakman & Civic) | 4 | 06-10-21 A | 06-23-21 A
AP 4500 | PROJ-0951-MMOAllen.69.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Quandt 2 (260' North Moore Ave & Midway Ave) | 4 | 06-14-21 A | 06-14-21 A
AP 4600 | PROJ-0951-MMOAllen.71.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Reeck 1 (Promenade & Goddard) | 4 | 06-16-21 A | 06-16-21 A
CDET-12465 | PROJ-0951-CDET1-2.62.3.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Waverly (2) (AEO Dexter & Lawton) | 0 | 06-16-21 A | 06-16-21 A
NDET3-4215 | GRP-2021-ND3.61.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Sunset St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 06-16-21 A | 2021-09-29
AP 5050 | PROJ-0951-MMOAllen.79.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Ruth 2 (200' South Moore & Midway Ave) | 4 | 06-16-21 A | 06-16-21 A
AP 4950 | PROJ-0951-MMOAllen.78.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Ruth 1 (Englewood & 200' South Moore Ave) | 4 | 06-16-21 A | 06-16-21 A
Muni11070 | PROJ-0951-MUN-2.44.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Southfield Fwy (M-39) (66' EEPL Ashton Ave & 112' WWPL Archdale St) | 0 | 06-16-21 A | 2021-11-10
AP 5150 | PROJ-0951-MMOAllen.81.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Seavitt 2 (Moore & Allen) | 4 | 06-16-21 A | 06-16-21 A
SCDet-6160 | GRP-2021-SCDet1.53.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Westover (Mendota & Middlepointe) | 4 | 06-16-21 A | 06-16-21 A
RR1 8011 | GRP-2021-RR.34.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Appoline (Santa Clara & Mcnichols) | 0 | 06-16-21 A | 06-16-21 A
CDET2-8640 | GRP-2021-CDet2.5.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - W Boston Blvd 1 (Wildemere & EOM) | 0 | 06-17-21 A | 2021-09-28
AP 3550 | PROJ-0951-MMOAllen.19.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Champaign 1 (Pelham & Allen) | 4 | 06-17-21 A | 2021-11-01
NWDET-17770 | PROJ-0951-NWDET1CO.52.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Faust (2) (Davison & EOM) | 18 | 06-21-21 A | 06-21-21 A
CDET2-1560 | GRP-2021-CDet2.2.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Glynn 1 (Dexter & Linwood) | 0 | 06-22-21 A | 07-21-21 A
SCDet-3280 | GRP-2021-SCDet1.17.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Cheyenne (Joy & Littlefield) | 4 | 06-22-21 A | 06-22-21 A
SCDet-8170 | GRP-2021-SCDet1.24.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Pinehurst (Oakman & Esper) | 4 | 06-22-21 A | 06-22-21 A
EDET1 501185 | GRP-2021-ED1.55.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Chatsworth St (1) (E Warrern Ave & Waveney St) | 0 | 06-22-21 A | 07-07-21 A
EDET1 501190 | GRP-2021-ED1.60.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Nottingham Rd (2) (Waveney St & Mack Ave) | 0 | 06-23-21 A | 2021-09-28
NCDET - 22785 | NEWPROJ-6.6.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Hartwell (Puritan & Fenkell) | 86 | 06-23-21 A | 07-15-21 A
SCDet-9720 | GRP-2021-SCDet1.55.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Mackenzie 2 (Oakman Blvd & Morrow Circle) | 4 | 06-23-21 A | 06-23-21 A
GP-14035 | PROJ-0951-GP 5 -3.8.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Alter 3 (Jefferson & Hampton) | 0 | 06-23-21 A | 06-23-21 A
CDET2-3480 | GRP-2021-CDet2.28.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Gladstone 2 (Linwood & Rosa Parks) | 0 | 06-23-21 A | 06-23-21 A
SCDet-9550 | GRP-2021-SCDet1.10.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Littlefield 2 (Oakman & Appoline) | 4 | 06-23-21 A | 06-23-21 A
SCDet-3520 | GRP-2021-SCDet1.20.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Appoline (Joy & Oakman) | 4 | 06-23-21 A | 06-23-21 A
SCDet-8740 | GRP-2021-SCDet1.20.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Appoline (Oakman & Civic) | 4 | 06-23-21 A | 07-06-21 A
SCDet-11350 | GRP-2021-SCDet1.20.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Appoline (Civic & Tireman) | 4 | 06-23-21 A | 06-23-21 A
AP 3540 | PROJ-0951-MMOAllen.18.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Carter 2 (550' North Moore Ave & Midway) | 4 | 06-24-21 A | 07-07-21 A
AA4 20916 | GRP-2021-AA4.54.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Wakefield Ave (Hutchins & Prescott) | 0 | 07-01-21 A | 07-07-21 A
AA4 28968 | GRP-2021-AA4.26.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Davis Ave (5th & Main) | 0 | 07-06-21 A | 07-15-21 A
AA4 20773 | GRP-2021-AA4.31.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Wilder Pl (W Davis Ave & W Hoover Ave) | 0 | 07-06-21 A | 07-15-21 A
RedfMMO2040 | PROJ-0951-MMORedford-1.12.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Inkster 1 (7 Mile & Clarita) | 0 | 07-06-21 A | 07-06-21 A
SCDet-3680 | GRP-2021-SCDet1.22.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Manor (Esper & Tireman) | 4 | 07-06-21 A | 07-06-21 A
SCDet-6850 | GRP-2021-SCDet1.22.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Manor West (Oakman & Civic) | 4 | 07-06-21 A | 07-06-21 A
SCDet-6930 | GRP-2021-SCDet1.22.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Manor East (Oakman & Belton) | 4 | 07-06-21 A | 07-06-21 A
SCDet-7010 | GRP-2021-SCDet1.22.4.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Manor West (Joy & Oakman) | 4 | 07-06-21 A | 07-06-21 A
SCDet-7090 | GRP-2021-SCDet1.22.5.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Manor East (Joy & Oakman) | 4 | 07-06-21 A | 07-06-21 A
SWDET2-6215 | PROJ-0951-SWDET2.58.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lonyo 1 (EOM & Dix) | 4 | 07-06-21 A | 2021-09-28
RR1 8571 | GRP-2021-RR.41.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - 8th (Southfield & W Outer) | 0 | 07-06-21 A | 2021-09-28
CDET2-3320 | GRP-2021-CDet2.26.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Hazelwood 2 (Linwood & La Salle) | 0 | 07-06-21 A | 07-06-21 A
CDET2-6520 | GRP-2021-CDet2.26.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Hazelwood 2 (La Salle & Rosa Parks) | 0 | 07-06-21 A | 07-15-21 A
Muni-1050 | PROJ-0951-MUN-3.38.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Porter 1 (Scotten St & Hubbard Dr) | 0 | 07-07-21 A | 07-07-21 A
CDET2-8220 | GRP-2021-CDet2.49.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Linwood 2 (Joy & Euclid) | 0 | 07-07-21 A | 2021-09-28
SCDet-5040 | GRP-2021-SCDet1.39.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Birwood (Joy & Oakman) | 4 | 07-07-21 A | 07-07-21 A
AP 3720 | PROJ-0951-MMOAllen.36.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Hubert 1 (Englewood & Moore Ave) | 4 | 07-07-21 A | 2021-11-09
AP 3730 | PROJ-0951-MMOAllen.37.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Hubert 2 (Moore & Conrail Rr) | 4 | 07-07-21 A | 07-09-21 A
AP 5300 | PROJ-0951-MMOAllen.84.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Vine 2 (Wick & Moore) | 4 | 07-07-21 A | 07-07-21 A
AP 5350 | PROJ-0951-MMOAllen.85.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Vine 3 (Moore & Conrail Rr) | 4 | 07-07-21 A | 2021-11-12
AP 5250 | PROJ-0951-MMOAllen.83.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Vine 1 (Champaign & Englewood) | 4 | 07-07-21 A | 2021-10-21
AP 3630 | PROJ-0951-MMOAllen.27.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Englewood 2 (Allen & 200' East Of Fox Ave) | 4 | 07-07-21 A | 07-07-21 A
AP 3640 | PROJ-0951-MMOAllen.28.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Englewood 3 (200' East Of Fox Ave & Vine) | 4 | 07-07-21 A | 07-07-21 A
AP 3660 | PROJ-0951-MMOAllen.30.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Fox 2 (Moore & Pennsylvania) | 4 | 07-07-21 A | 2021-11-09
RR1 8091 | GRP-2021-RR.35.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Stoepel (8 Mile & Pembroke) | 0 | 07-07-21 A | 08-05-21 A
RR1 7771 | GRP-2021-RR.31.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Whitney (Grand River & Dexter) | 0 | 07-07-21 A | 07-07-21 A
AP 3950 | PROJ-0951-MMOAllen.59.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Old Goddard (Goddard Rd & Pheasant Run) | 4 | 07-07-21 A | 07-07-21 A
SCDet-5120 | GRP-2021-SCDet1.40.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Griggs (Joy & Oakman) | 4 | 07-07-21 A | 07-07-21 A
RR1 7431 | GRP-2021-RR.27.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Burt (Westfield & Joy) East | 0 | 07-07-21 A | 2021-09-28
RR1 10201 | GRP-2021-RR.27.2.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Burt (Westfield & Joy) West | 0 | 07-07-21 A | 2021-09-28
EDET1 501032 | GRP-2021-ED1.40.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Lakepointe Sr (2) (Waveney St & Mack Ave) | 0 | 07-07-21 A | 07-07-21 A
AA4 22058 | GRP-2021-AA4.17.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Edgewood Pl (W Davis Ave & EOM) | 0 | 07-08-21 A | 07-16-21 A
SWDET2-2855 | PROJ-0951-SWDET2.15.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 3 (Woodmere & Casper) | 4 | 07-08-21 A | 07-08-21 A
SWDET2-8535 | PROJ-0951-SWDET2.2.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 2 (EOM & Lonyo) | 4 | 07-08-21 A | 2021-09-29
SWDET2-8695 | PROJ-0951-SWDET2.16.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 4 (Casper & Central) | 4 | 07-08-21 A | 07-08-21 A
SWDET2-1895 | PROJ-0951-SWDET2.2.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 2 (Lonyo & Woodmere) | 4 | 07-08-21 A | 07-08-21 A
NCDET - 12750 | NEWPROJ-6.21.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Fenkell (3) (Winthrop & Greenfield) | 2 | 07-08-21 A | 2021-09-23
EDET1 506216 | GRP-2021-ED1.49.2.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Balfour Rd (1) (E Warrern Ave & Waveney St) | 0 | 07-08-21 A | 2021-09-28
AP 3930 | PROJ-0951-MMOAllen.57.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Niver 1 (Englewood Ave & 100' North Moore) | 4 | 07-08-21 A | 2021-11-09
WDET-14710 | PROJ-0951-WDET9-4.104.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Rosemont Ave 1 (Sawyer & W Warren) | 0 | 07-08-21 A | 07-08-21 A
AA4 20912 | GRP-2021-AA4.49.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Soule Blvd (4' SSPL W Liberty St & 19' NNPL Lutz Ave) | 0 | 07-09-21 A | 07-21-21 A
AA4 20905 | GRP-2021-AA4.42.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Maxwell Ave (EOM & Soule Blvd) | 0 | 07-09-21 A | 07-21-21 A
SCDet-6000 | GRP-2021-SCDet1.51.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Blowers (Mendota & Middlepointe) | 4 | 07-09-21 A | 2021-09-28
SWDET2-3175 | PROJ-0951-SWDET2.19.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 2 (Richard & EO Oakdale) | 4 | 07-09-21 A | 07-09-21 A
AP 3530 | PROJ-0951-MMOAllen.17.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Carter 1 (Englewood & 550' North Moore) | 4 | 07-09-21 A | 07-12-21 A
EDET1 501036 | GRP-2021-ED1.44.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Maryland St (2) (Waveney St & Mack Ave) | 0 | 07-12-21 A | 07-21-21 A
EDET1 501039 | GRP-2021-ED1.47.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Wayburn Ave (1) (E Warrern Ave & Waveney St) | 0 | 07-12-21 A | 07-21-21 A
EDET1 501191 | GRP-2021-ED1.61.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Somerset Ave (1) (E Warrern Ave & Waveney St) | 0 | 07-12-21 A | 2021-09-28
CDET-3400 | PROJ-0951-CDET1-2.12.4.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Oakman (2) (Linwood & Oakman Ct) | 0 | 07-13-21 A | 07-13-21 A
CDET2-10880 | GRP-2021-CDet2.24.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Taylor 2 (La Salle & Rosa Parks) | 0 | 07-13-21 A | 07-21-21 A
AA4 24648 | GRP-2021-AA4.57.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Myron Ct (W Hoover & EOM) | 0 | 07-15-21 A | 07-16-21 A
SWDET2-17015 | PROJ-0951-SWDET2.78.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Sharon (Woodmere & ANO W Vernor) | 4 | 07-15-21 A | 07-15-21 A
Ypsi 3-10370 | PROJ-0951-YSP3.34.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Olds (Hudson & Desoto) | 5 | 07-15-21 A | 07-15-21 A
Ypsi 3-10620 | PROJ-0951-YSP3.35.2.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Hudson (Ecorse & Olds) | 5 | 07-15-21 A | 2021-10-25
Ypsi 3-2930 | PROJ-0951-YSP3.41.3.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Desoto (Old Ecorse & Dodge) | 5 | 07-15-21 A | 07-15-21 A
Ypsi 3-2470 | PROJ-0951-YSP3.41.2.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Desoto (Tyler & Nash) | 5 | 07-15-21 A | 07-15-21 A
Ypsi 3-10960 | PROJ-0951-YSP3.37.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Nash 1 (Old Ecorse & Desoto) | 5 | 07-15-21 A | 07-15-21 A
Ypsi 3-3040 | PROJ-0951-YSP3.37.2.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Nash 1 (Desoto & Tyler) | 5 | 07-15-21 A | 07-15-21 A
Ypsi 3-10120 | PROJ-0951-YSP3.33.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Dodge (Desoto & Nash) | 5 | 07-15-21 A | 07-15-21 A
CDET2-6360 | GRP-2021-CDet2.24.57.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Taylor 2 (Linwood & La Salle) | 0 | 07-15-21 A | 07-15-21 A
AA4 20760 | GRP-2021-AA4.17.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Edgewood Pl (W Hoover Ave & W Davis Ave) | 0 | 07-16-21 A | 07-29-21 A
AA4 20769 | GRP-2021-AA4.27.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Hoover Ave (5th St & S Main St) | 0 | 07-16-21 A | 07-29-21 A
SWDET2-4055 | PROJ-0951-SWDET2.31.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 3 (Richard & ANO W Vernor) | 4 | 07-21-21 A | 07-21-21 A
CDET2-1070 | GRP-2021-CDet2.4.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Calvert 1 (Dexter & Linwood) | 0 | 07-21-21 A | 07-21-21 A
EDET1 501033 | GRP-2021-ED1.41.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Lakepointe St (1) (E Warrern Ave & Waveney St) | 0 | 07-21-21 A | 07-21-21 A
AP 5450 | PROJ-0951-MMOAllen.86.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Vine 4 (Vine Ave & 146' East Of Vine Ave) | 4 | 07-21-21 A | 2021-11-12
Ypsi 3-5160 | PROJ-0951-YSP3.13.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Gates (94 Service Drive & Tyler) | 5 | 07-21-21 A | 2022-05-02
Ypsi 3-5640 | PROJ-0951-YSP3.15.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Eugene (Tyler & 94 Service Drive) | 5 | 07-21-21 A | 07-21-21 A
Ypsi 3-3660 | PROJ-0951-YSP3.7.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Cayuga (Eugene & Onandaga) | 5 | 07-21-21 A | 07-21-21 A
Ypsi 3-4160 | PROJ-0951-YSP3.9.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Onandaga (Eugene & Old Ecorse) | 5 | 07-21-21 A | 2022-05-13
Ypsi 3-4660 | PROJ-0951-YSP3.11.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Fox (94 Service Drive & Tyler) | 5 | 07-21-21 A | 07-23-21 A
CDET2-3720 | GRP-2021-CDet2.31.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Blaine 2 (Linwood & La Salle) | 0 | 07-22-21 A | 07-23-21 A
CDET2-4840 | GRP-2021-CDet2.45.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Genessee (Chicago & Joy) | 0 | 07-22-21 A | 07-23-21 A
SCDet-7530 | GRP-2021-SCDet1.26.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Middlepointe (Esper & Tireman) | 4 | 07-22-21 A | 07-23-21 A
NDET3-7445 | GRP-2021-ND3.82.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Revere Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 07-23-21 A | 08-13-21 A
EDET1 501035 | GRP-2021-ED1.43.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Maryland St (1) (E Warrern Ave & Waveney St) | 0 | 07-26-21 A | 07-26-21 A
EDET1 501182 | GRP-2021-ED1.52.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Beaconsfield St (2) (Waveney St & Mack Ave) | 0 | 07-26-21 A | 08-13-21 A
NDET3-7350 | GRP-2021-ND3.84.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Wexford (1) (8 Mile Rd & E Outer Dr) | 0 | 07-28-21 A | 08-23-21 A
NDET3-800 | GRP-2021-ND3.86.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Yonka (1) (8 Mile Rd (M102) & E Remington Ave) | 0 | 07-28-21 A | 07-28-21 A
NDET3-3845 | GRP-2021-ND3.55.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Dean Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 07-28-21 A | 2021-09-29
CDET2-3560 | GRP-2021-CDet2.29.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Carter (Dexter & Linwood) | 0 | 07-28-21 A | 2021-09-28
Ypsi 3-7140 | PROJ-0951-YSP3.21.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Eileen (Tyler & Chevrolet) | 5 | 07-28-21 A | 07-28-21 A
Ypsi 3-1300 | PROJ-0951-YSP3.1.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Carol Ann (Eileen & Mary Catherine) | 5 | 07-28-21 A | 07-28-21 A
AP 3620 | PROJ-0951-MMOAllen.26.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Englewood 1 (402' West Of Louise Ave & Louise) | 4 | 07-28-21 A | 07-28-21 A
CDET2-3880 | GRP-2021-CDet2.33.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Pingree 2 (Linwood & La Salle) | 0 | 07-29-21 A | 07-30-21 A
AP 3810 | PROJ-0951-MMOAllen.45.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Lucy (885' West Of Marlborough Ave & Marlborough) | 4 | 07-30-21 A | 07-30-21 A
AP 3790 | PROJ-0951-MMOAllen.43.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Leslie (1361' West Of Allen Road & Allen Rd) | 4 | 07-30-21 A | 07-30-21 A
NCDET - 23085 | NEWPROJ-6.13.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Snowden (Puritan & Fenkell) | 78 | 08-04-21 A | 08-10-21 A
AP 4900 | PROJ-0951-MMOAllen.77.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Rosedale 3 (Moore & Conrail Rr) | 4 | 08-05-21 A | 08-10-21 A
RR1 7111 | GRP-2021-RR.22.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Bloom (7 Mile & Nevada) | 0 | 08-05-21 A | 2021-09-28
SWDET2-5015 | PROJ-0951-SWDET2.43.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mandale (Woodmere & Elsemere) | 4 | 08-10-21 A | 08-10-21 A
SWDET2-19535 | PROJ-0951-SWDET2.42.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Logan 1 (Lawndale & Mullane) | 4 | 08-10-21 A | 08-10-21 A
SWDET2-5495 | PROJ-0951-SWDET2.49.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Green (Dix & W Vernor) | 4 | 08-10-21 A | 08-10-21 A
EDET1 501030 | GRP-2021-ED1.38.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Barham St (1) (E Warrern Ave & Waveney St) | 0 | 08-12-21 A | 08-13-21 A
EDET1 501031 | GRP-2021-ED1.39.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Barham St (2) (Waveney St & Mack Ave) | 0 | 08-12-21 A | 2021-09-28
EDET1 501181 | GRP-2021-ED1.51.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Beaconsfield St (1) (E Warrern Ave & Waveney St) | 0 | 08-12-21 A | 08-13-21 A
RR1 51689 | GRP-2021-RR1.101.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Webster St (Labadie St & EOM @ 158' SSPL Labadie St) | 4 | 08-13-21 A | 2021-09-28
NDET3-7380 | GRP-2021-ND3.40.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Ryan Rd (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 08-13-21 A | 08-13-21 A
NCDET - 24735 | NEWPROJ-6.15.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Sorrento (Puritan & Fenkell) | 97 | 08-13-21 A | 2021-09-29
AP 3690 | PROJ-0951-MMOAllen.33.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Helen (559' West Of Louise Ave & Louise Ave) | 4 | 08-17-21 A | 08-17-21 A
AP 4300 | PROJ-0951-MMOAllen.65.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Pennsylvania (Colwell & Fox) | 4 | 08-17-21 A | 08-17-21 A
Ypsi 3-4910 | PROJ-0951-YSP3.12.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Dorset (Tyler & 94 Service Drive) | 5 | 08-17-21 A | 2022-05-13
CDET2-9350 | GRP-2021-CDet2.1.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - ASO Chicago (Linwood & 14th) | 0 | 08-18-21 A | 08-19-21 A
SWDET2-6375 | PROJ-0951-SWDET2.60.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Rieden 1 (Pitt & W Vernor) | 4 | 08-18-21 A | 08-18-21 A
RR1 51749 | GRP-2021-RR1.11.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Cherrygrove St (W Jefferson Ave & EOM) | 4 | 08-19-21 A | 08-23-21 A
RR1 51686 | GRP-2021-RR1.98.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Josephine St (EOM & W Jefferson) | 4 | 08-19-21 A | 2021-09-28
RR1 51751 | GRP-2021-RR1.102.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Charlotte Ave (W Jefferson Ave & Eliza St) | 4 | 08-19-21 A | 2021-09-28
RR1 51754 | GRP-2021-RR1.105.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Josephine (W Jefferson & EOM) | 4 | 08-19-21 A | 2021-09-28
RR1 57500 | GRP-2021-RR1.83.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - High St 2 (40' SSPL Labadie St & Southfield Rd) | 4 | 08-19-21 A | 08-23-21 A
RR1 8251 | GRP-2021-RR.37.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Varjo (Sherwood & Cliff) | 0 | 08-19-21 A | 2021-09-28
Ypsi 3-2380 | PROJ-0951-YSP3.39.2.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Tyler (EOM & Desoto) | 5 | 08-23-21 A | 2022-05-13
EDET1 50915 | GRP-2021-ED1.1.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Outer Dr (E) (E Warren Ave & Waveney Ave) | 0 | 08-26-21 A | 2021-09-28
SWDET2-4375 | PROJ-0951-SWDET2.35.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lafayette (Woodmere & Lawndale) | 4 | 08-26-21 A | 2021-09-28
SWDET2-7175 | PROJ-0951-SWDET2.71.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Stair (EOM & Vernor) | 4 | 08-26-21 A | 08-26-21 A
SWDET2-16185 | PROJ-0951-SWDET2.71.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Stair (EOM & Vernor) | 4 | 08-26-21 A | 08-26-21 A
SWDET2-21845 | PROJ-0951-SWDET2.76.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Oakdale (Woodmere & ANO W Vernor) | 4 | 08-26-21 A | 08-26-21 A
SWDET2-22005 | PROJ-0951-SWDET2.76.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Oakdale (ASO W Vernor & Mandale) | 4 | 08-26-21 A | 08-26-21 A
RR1 5831 | GRP-2021-RR.5.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Bringard (Reno & Regent) | 0 | 08-26-21 A | 2021-09-28
RR1 7191 | GRP-2021-RR.24.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Spokane (Beechwood & Colfax) | 0 | 08-26-21 A | 2021-09-28
RR1 8331 | GRP-2021-RR.38.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Cliff (Varjo & EOM 181' SSPL Varjo) | 0 | 08-26-21 A | 08-30-21 A
EDET1 504116 | GRP-2021-ED1.1.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Outer Dr (E) (Waveney Ave & Mack Ave) | 0 | 08-26-21 A | 2021-09-28
EDET1 504196 | GRP-2021-ED1.2.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Outer Dr (W) (ASO E Warren Ave & Waveney Ave) | 0 | 08-26-21 A | 2021-09-28
NDET3-7185 | GRP-2021-ND3.50.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Buffalo St (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 08-26-21 A | 08-26-21 A
NDET3-7200 | GRP-2021-ND3.50.4.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Buffalo St (1) (Hamlet St & Amrad St) | 0 | 08-26-21 A | 08-26-21 A
Ypsi 3-7380 | PROJ-0951-YSP3.22.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Mary Catherine (Woodglen & Eileen) | 5 | 08-26-21 A | 2022-05-02
Ypsi 3-6640 | PROJ-0951-YSP3.19.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Lori (Mary Catherine & Tyler) | 5 | 08-26-21 A | 09-07-21 A
Ypsi 3-6890 | PROJ-0951-YSP3.20.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Chevrolet (Tyler & Desoto) | 5 | 08-26-21 A | 09-15-21 A
EDET1 504276 | GRP-2021-ED1.2.4.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Outer Dr (W) (Waveney St & Mack Ave) | 0 | 08-26-21 A | 2021-09-28
NDET3-540 | GRP-2021-ND3.74.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Klinger St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 08-26-21 A | 08-30-21 A
NDET3-7045 | GRP-2021-ND3.51.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Caldwell St (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 08-26-21 A | 2021-09-28
NDET3-7055 | GRP-2021-ND3.51.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Caldwell St (1) (Hamlet St & Amrad St) | 0 | 08-26-21 A | 08-26-21 A
NDET3-525 | GRP-2021-ND3.70.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Gallagher (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 08-26-21 A | 08-26-21 A
NDET3-7050 | GRP-2021-ND3.59.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Keystone St (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 08-27-21 A | 08-27-21 A
NDET3-7060 | GRP-2021-ND3.59.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Keystone St (1) (Hamlet St & E Outer Dr) | 0 | 08-27-21 A | 2021-09-28
SWDET2-7735 | PROJ-0951-SWDET2.76.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Oakdale (NO Woodmere & Woodmere) | 4 | 09-01-21 A | 09-01-21 A
RR1 7931 | GRP-2021-RR.33.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Florence (Hamilton & Woodward) | 0 | 09-01-21 A | 09-07-21 A
NCDET - 13365 | NEWPROJ-6.14.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Steel (Puritan & ANO Fenkell) | 81 | 09-01-21 A | 09-02-21 A
AP 3560 | PROJ-0951-MMOAllen.20.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Champaign 2 (Allen & Fox) | 4 | 09-01-21 A | 09-13-21 A
SWDET2-17335 | PROJ-0951-SWDET2.78.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Sharon (ASO W Vernor & Mandale) | 4 | 09-02-21 A | 09-02-21 A
SWDET2-17175 | PROJ-0951-SWDET2.78.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Sharon (W Vernor & ASO Vernor) | 4 | 09-02-21 A | 2021-11-19
SWDET2-3095 | PROJ-0951-SWDET2.18.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 1 (At Dix) | 4 | 09-07-21 A | 2021-09-29
SWDET2-1975 | PROJ-0951-SWDET2.3.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - EWO Woodmere (At W Vernor) | 4 | 09-07-21 A | 2021-11-30
SWDET2-12685 | PROJ-0951-SWDET2.18.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 1 (Wendall & Pearl) | 4 | 09-07-21 A | 09-07-21 A
SWDET2-12365 | PROJ-0951-SWDET2.18.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 1 (Wendall & WO Cabot) | 4 | 09-07-21 A | 09-07-21 A
SWDET2-12525 | PROJ-0951-SWDET2.18.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 1 (Dix & Pearl) | 4 | 09-07-21 A | 09-07-21 A
NDET3-495 | GRP-2021-ND3.49.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Bloom St (1) (Hamlet St & E Outer Dr) | 0 | 09-07-21 A | 2021-09-28
RR1 10281 | GRP-2021-RR.46.2.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - College (Gunston & Devon) | 0 | 09-07-21 A | 2021-09-28
RR1 8811 | GRP-2021-RR.44.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Kenmoor (Conner & Gunston) | 0 | 09-07-21 A | 09-13-21 A
RR1 59060 | GRP-2021-RR1.92.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Salliotte St (141' WWPL High St & 1' WWPL High St) | 4 | 09-07-21 A | 09-07-21 A
RR1 59140 | GRP-2021-RR1.92.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Salliotte St (5' EEPL High St & W Jefferson Ave) | 4 | 09-07-21 A | 09-07-21 A
RR1 5479 | GRP-2021-RR1.1.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Southfield Rd (207' WWPL Webster & High) | 4 | 09-07-21 A | 09-07-21 A
RedfMMO3450 | PROJ-0951-MMORedford-1.4.2.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Poinciana (Pembroke & 7 Mile) | 0 | 09-13-21 A | 2021-09-23
NCDET - 23475 | NEWPROJ-6.7.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Littlefield (Puritan & Fenkell) | 80 | 09-13-21 A | 09-16-21 A
CDET2-3800 | GRP-2021-CDet2.32.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Pingree 1 (Dexter & Linwood) | 0 | 09-13-21 A | 09-13-21 A
CDET2-7040 | GRP-2021-CDet2.33.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Pingree 2 (La Salle & 14th) | 0 | 09-13-21 A | 09-13-21 A
NDET3-6770 | GRP-2021-ND3.49.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Bloom St (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 09-13-21 A | 09-13-21 A
RR1 51666 | GRP-2021-RR1.77.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Broadway Ave (270' WWPL W Jefferson Ave & 6' WWPL W Jeferson Ave) | 4 | 09-13-21 A | 09-13-21 A
RR1 5911 | GRP-2021-RR.6.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Iowa (Sherwood & School) | 0 | 09-14-21 A | 09-14-21 A
RR1 51681 | GRP-2021-RR1.93.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Sunnyside St (Salliotte Rd & 157' SSPL Salliotte Rd) | 4 | 09-14-21 A | 09-14-21 A
AP 4850 | PROJ-0951-MMOAllen.76.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Rosedale 2 (Englewood & Moore) | 4 | 09-14-21 A | 09-14-21 A
CDET2-6880 | GRP-2021-CDet2.30.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Blaine 1 (Wildemere - Linwood) | 0 | 09-14-21 A | 2021-09-28
CDET2-9660 | GRP-2021-CDet2.31.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Blaine (Dexter & Wildemere) | 0 | 09-14-21 A | 09-14-21 A
CDET2-10290 | GRP-2021-CDet2.30.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Blaine 1 (Wildemere - Linwood) | 0 | 09-14-21 A | 2021-09-23
AP 3650 | PROJ-0951-MMOAllen.29.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Fox 1 (Englewood & Moore) | 4 | 09-15-21 A | 09-15-21 A
CDET2-6040 | GRP-2021-CDet2.11.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Rochester (Wildemere & lawton) | 0 | 09-15-21 A | 09-15-21 A
CDET2-3960 | GRP-2021-CDet2.34.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Philadelphia 1 (Dexter & Linwood) | 0 | 09-15-21 A | 2021-09-28
EDET1 501189 | GRP-2021-ED1.59.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Nottingham Rd (1) (E Warrern Ave & Waveney St) | 0 | 09-16-21 A | 2021-09-28
RR1 8891 | GRP-2021-RR.45.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Engleside (Conner & Gunston) | 0 | 09-16-21 A | 09-16-21 A
NWDET-5630 | PROJ-0951-NWDET1CO.25.4.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - ASO Schoolcraft (1) (EOM & Auburn) | 0 | 2021-09-20 | 2021-09-20
NWDET-21830 | PROJ-0951-NWDET1CO.29.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Artesian (3) (SO Glendale & EEOM Artesian) | 0 | 2021-09-20 | 2021-09-20
CDET2-5080 | GRP-2021-CDet2.48.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Linwood 1 (Collingwood & Longfellow) | 0 | 2021-09-20 | 2021-09-23
EDET1 501248 | GRP-2021-ED1.70.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bishop St (2) (Waveney St & Mack Ave) | 0 | 2021-09-20 | 2021-09-23
AA4 21658 | GRP-2021-AA4.13.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 5th St (W Davis Ave & Pauline Blvd) | 0 | 2021-09-20 | 2021-09-24
NWDET-13760 | PROJ-0951-NWDET1CO.13.4.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Westwood (1) (Glendale & EOM) | 5 | 2021-09-20 | 2021-09-20
NWDET-13670 | PROJ-0951-NWDET1CO.13.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Westwood (1) (Davison & Glendale) | 7 | 2021-09-20 | 2021-09-20
NWDET-13580 | PROJ-0951-NWDET1CO.13.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Westwood (1) (ASO Schoolcraft & Davison) | 9 | 2021-09-20 | 2021-09-20
NWDET-7880 | PROJ-0951-NWDET1CO.17.3.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Davison (1) (Artesian & Glastonbury) | 1 | 2021-09-20 | 2021-09-20
NWDET-7640 | PROJ-0951-NWDET1CO.55.1.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Davison (2) (Glastonbury & Ashton) | 1 | 2021-09-20 | 2021-09-20
NWDET-5715 | PROJ-0951-NWDET1CO.18.1.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Glendale (1) (Auburn & Artesian) | 9 | 2021-09-20 | 2021-09-20
NWDET-18230 | PROJ-0951-NWDET1CO.50.2.2 | 2021 GRP - North West Detroit 1b | Restoration - Soft Surface - Warwick (2) (ASO Schoolcraft & Davison) | 1 | 2021-09-20 | 2021-09-20
RedfMMO1160 | PROJ-0951-MMORedford-1.2.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Grand River (Negaunee & Delaware) | 0 | 2021-09-20 | 2021-09-23
RedfMMO1320 | PROJ-0951-MMORedford-1.4.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Poinciana (Fargo & Pembroke) | 0 | 2021-09-20 | 2021-09-23
RedfMMO1480 | PROJ-0951-MMORedford-1.5.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Negaunee (7 Mile & Cambridge) | 0 | 2021-09-20 | 2021-09-23
RedfMMO1800 | PROJ-0951-MMORedford-1.9.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Denby 2 (Pembroke & Vassar) | 0 | 2021-09-20 | 2021-09-23
RedfMMO1960 | PROJ-0951-MMORedford-1.11.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Inkster 2 (Curtis & Bennett) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2120 | PROJ-0951-MMORedford-1.13.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Seminole 2 (7 Mile & Margareta) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2200 | PROJ-0951-MMORedford-1.14.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Margareta (Seminole & Poinciana) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2360 | PROJ-0951-MMORedford-1.16.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Negaunee 2 (7 Mile & Curtis) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2440 | PROJ-0951-MMORedford-1.17.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - 7 Mile Rd (Inkster & Gaylord) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2520 | PROJ-0951-MMORedford-1.18.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - MMO Redford (Poinciana & Delaware) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2600 | PROJ-0951-MMORedford-1.19.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Delaware (Curtis & 6 Mile) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2760 | PROJ-0951-MMORedford-1.21.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Santa Maria 2 (Denby & Delaware) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2840 | PROJ-0951-MMORedford-1.22.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Gaylord 1 (Santa Maria & Curtis) | 0 | 2021-09-20 | 2021-09-23
RedfMMO2920 | PROJ-0951-MMORedford-1.23.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Fox 2 (Santa Maria & 7 Mile) | 0 | 2021-09-20 | 2021-09-23
RedfMMO3000 | PROJ-0951-MMORedford-1.24.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Denby 3 (7 Mile & Margareta) | 0 | 2021-09-20 | 2021-09-23
RedfMMO3080 | PROJ-0951-MMORedford-1.25.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Indian 2 (7 Mile & Santa Maria) | 0 | 2021-09-20 | 2021-09-23
RedfMMO3160 | PROJ-0951-MMORedford-1.26.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Santa Maria 1 (Indian & Denby) | 0 | 2021-09-20 | 2021-09-23
GP-14435 | PROJ-0951-GP 5 -3.64.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Kercheval (Balfour & Alter) | 0 | 2021-09-20 | 2021-09-23
ND2-15130 | PROJ-0951-NDET2-2.15.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Conner St (Veach & Monitor) | 0 | 2021-09-20 | 2021-09-23
ND2-15610 | PROJ-0951-NDET2-2.19.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Emery St (Girardin St & Van Dyke Ave (M53) | 0 | 2021-09-20 | 2021-09-23
ND2-16090 | PROJ-0951-NDET2-2.23.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Milbank Greenway (Van Dyke & Veach) | 0 | 2021-09-20 | 2021-09-23
ND2-17170 | PROJ-0951-NDET2-2.32.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Sherwood St (1) (8 Mile Rd & E Outer Drive) | 0 | 2021-09-20 | 2021-09-23
ND2-17890 | PROJ-0951-NDET2-2.38.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Terrell Ave (8 Mile Rd & Milbank Greenway) | 0 | 2021-09-20 | 2021-09-23
ND2-18370 | PROJ-0951-NDET2-2.42.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - ANO Outer Drive (Stotter & AWO Van Dyke) | 0 | 2021-09-20 | 2021-09-23
ND2-18490 | PROJ-0951-NDET2-2.43.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - ASO Outer Drive (Stotter & Van Dyke) | 0 | 2021-09-20 | 2021-09-23
ND2-12940 | PROJ-0951-NDET2-2.50.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Carrie Ave (2) (E Outer Drive & 7 Mile Rd) | 0 | 2021-09-20 | 2021-09-23
ND2-14770 | PROJ-0951-NDET2-2.12.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Cliff St (Outer Drive & Lantz) | 0 | 2021-09-20 | 2021-09-23
ND2-14890 | PROJ-0951-NDET2-2.13.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Concord Ave(1) (8 Mile Rd & E Outer Drive) | 0 | 2021-09-20 | 2021-09-23
ND2-15370 | PROJ-0951-NDET2-2.17.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Outer Dr (North Side) (Sherwood & Spencer) | 0 | 2021-09-20 | 2021-09-23
ND2-20370 | PROJ-0951-NDET2-2.12.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Cliff St (Bliss & 7 Mile) | 0 | 2021-09-20 | 2021-09-23
ND2-21010 | PROJ-0951-NDET2-2.32.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Sherwood St (1) (8 Mile Rd & Savage) | 0 | 2021-09-20 | 2021-09-23
ND2-21290 | PROJ-0951-NDET2-2.32.2.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Sherwood St (1) (Outer Drive & Milbank) | 0 | 2021-09-20 | 2021-09-23
ND2-21580 | PROJ-0951-NDET2-2.5.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Carrie Ave (1) (E Outer Drive & 8 Mile Rd) | 0 | 2021-09-20 | 2021-09-23
ND2-22390 | PROJ-0951-NDET2-2.33.4 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Sherwood St (2) (E Outer Drive & 7 Mile Rd) | 0 | 2021-09-20 | 2021-09-23
ND2-22930 | PROJ-0951-NDET2-2.23.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Milbank Greenway (Veach & Monitor ) | 0 | 2021-09-20 | 2021-09-23
ND2-23210 | PROJ-0951-NDET2-2.15.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Conner St (Monitor & State Fair) | 0 | 2021-09-20 | 2021-09-23
ND2-23460 | PROJ-0951-NDET2-2.18.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Outer Drive (South Side) (Packard & Stotter ) | 0 | 2021-09-20 | 2021-09-23
ND2-23710 | PROJ-0951-NDET2-2.8.2.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - AWO Van Dyke Ave (M53) (1) (8 Mile Rd & E Outer Drive) | 0 | 2021-09-20 | 2021-09-23
ND2-16450 | PROJ-0951-NDET2-2.26.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Packard Ave (2) (ANO 7 Mile & 7 Mile) | 0 | 2021-09-20 | 2021-09-23
ND2-23810 | PROJ-0951-NDET2-2.23.2.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Milbank Greenway (Milbank Greenway & 8 Mile ) | 1 | 2021-09-20 | 2021-09-23
ND2-23870 | PROJ-0951-NDET2-2.17.2.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Outer Dr (N) (Van Dyke & EO Van Dyk) | 0 | 2021-09-20 | 2021-09-23
ND2-23920 | PROJ-0951-NDET2-2.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Milbank (Van Dyke & AWO Van Dyke ) | 1 | 2021-09-20 | 2021-09-23
ND2-24520 | PROJ-0951-NDET2-2.15.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Conner St (Terrell & Terrell) | 0 | 2021-09-20 | 2021-09-23
ND2-15730 | PROJ-0951-NDET2-2.20.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Helen St (1) (8 Mile Rd & E Outer Drive) | 0 | 2021-09-20 | 2021-09-23
ND2-16330 | PROJ-0951-NDET2-2.25.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Packard Ave (1) (8 Mile Rd & E Outer Drive) | 0 | 2021-09-20 | 2021-09-23
ND2-19120 | PROJ-0951-NDET2-2.21.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Lantz (Rogge & Cliff) | 39 | 2021-09-20 | 2021-09-23
ND2-25520 | PROJ-0951-NDET2-2.22.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Veach (8 Mile Rd & Milbank Greenway) | 39 | 2021-09-20 | 2021-09-23
ND2-19600 | PROJ-0951-NDET2-2.30.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Bliss Ave (Rogge & Cliff) | 39 | 2021-09-20 | 2021-09-23
ND2-25930 | PROJ-0951-NDET2-2.27.1 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Helen - Dual Main (Outer dr & Lantz) | 0 | 2021-09-20 | 2021-09-23
Euclid 1400 | PROJ-0951-MUN-3.3.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Puritan (Hyden St & Grand River) | 0 | 2021-09-20 | 2021-09-20
NCDET - 25015 | NEWPROJ-6.19.4.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Fenkell (1) (Manor & Pinehurst) | 0 | 2021-09-21 | 2021-09-23
NCDET - 25195 | NEWPROJ-6.19.6.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Fenkell (1) (Mendota & Birwood) | 0 | 2021-09-21 | 2021-09-23
NCDET - 12630 | NEWPROJ-6.43.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - ANO Fenkell 3 (Schaefer & Manor) | 7 | 2021-09-21 | 2021-09-23
NCDET - 12620 | NEWPROJ-6.41.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - ANO Fenkell 1 (Birwood & Washburn) | 3 | 2021-09-21 | 2021-09-23
NCDET - 12625 | NEWPROJ-6.42.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - ANO Fenkell 2 (Pinehurst & Mendota) | 1 | 2021-09-21 | 2021-09-23
NCDET - 12740 | NEWPROJ-6.19.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Fenkell (1) (At Cheyenne) | 0 | 2021-09-21 | 2021-09-23
NCDET - 12745 | NEWPROJ-6.20.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Fenkell (2) (Stansbury & Schaefer) | 2 | 2021-09-21 | 2021-09-23
NCDET - 12760 | NEWPROJ-6.17.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Fenkell 4 (Murray Hill & Winthrop) | 0 | 2021-09-21 | 2021-09-23
NCDET - 12755 | NEWPROJ-6.18.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Fenkell (5) (Southfield & Archdale) | 6 | 2021-09-21 | 2021-09-23
NCDET - 12670 | NEWPROJ-6.45.1.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - ASO Puritan 1 (Schaefer & Mendota) | 0 | 2021-09-21 | 2021-09-23
WDET-19621 | PROJ-0951-WDET9-4.30 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Evergreen Crossing (Evergreen & Warren) | 1 | 2021-09-21 | 2021-09-21
WDET-24530 | PROJ-0951-WDET9-4.30.2.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Piedmont Crossing (Piedmont & Warren) | 1 | 2021-09-21 | 2021-09-21
Muni790 | PROJ-0951-MUN-3.23.3.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Conant (Crossing & Victoria) | 0 | 2021-09-21 | 2021-09-21
Muni1260 | PROJ-0951-MUN-3.26.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Linwood 1(Doris & Oakman) | 0 | 2021-09-21 | 2021-09-21
Muni1720 | PROJ-0951-MUN-3.28.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Linwood 3 (Oakman Crossing) | 0 | 2021-09-21 | 2021-09-21
Muni1950 | PROJ-0951-MUN-3.29.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Linwood 4 (Davison Crossing) | 0 | 2021-09-21 | 2021-09-21
Muni2180 | PROJ-0951-MUN-3.30.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - W Grand Blvd 1 (Linwood & Dexter) | 0 | 2021-09-21 | 2021-09-21
Muni2410 | PROJ-0951-MUN-3.9.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - W Grand Blvd 2(Dexter & Grand River) | 0 | 2021-09-21 | 2021-09-21
Muni2640 | PROJ-0951-MUN-3.10.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - W Grand Blvd 3(Grand River & I-96 SVC Drive) | 0 | 2021-09-21 | 2021-09-21
Muni2870 | PROJ-0951-MUN-3.11.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Grand River 1 (Grand Blvd & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni3100 | PROJ-0951-MUN-3.12.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Grand River 2 (Crossing W Grand Blvd) | 0 | 2021-09-21 | 2021-09-21
Muni3330 | PROJ-0951-MUN-3.13.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Vinewood (Grand Blvd & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni3560 | PROJ-0951-MUN-3.14.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Wildemere (Grand Blvd & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni4020 | PROJ-0951-MUN-3.16.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Linwood 5 (Grand Blvd & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni4250 | PROJ-0951-MUN-3.17.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Linwood 6 (Grand Blvd & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni4480 | PROJ-0951-MUN-3.18.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Rosa Parks 1 (W Philadelphia & Longfellow) | 0 | 2021-09-21 | 2021-09-21
Muni4940 | PROJ-0951-MUN-3.18.3.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Rosa Parks 1 (Longfellow & Lothrop) | 0 | 2021-09-21 | 2021-09-21
Muni5400 | PROJ-0951-MUN-3.21.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Joy (Longfellow & Dexter) | 0 | 2021-09-21 | 2021-09-21
Muni5630 | PROJ-0951-MUN-3.22.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Lawton 2 (Joy & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni7400 | PROJ-0951-MUN-3.31.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Lasalle (Longfellow & EOM)) | 0 | 2021-09-21 | 2021-09-21
Muni7620 | PROJ-0951-MUN-3.32.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Chicago ( Off Linwood) | 0 | 2021-09-21 | 2021-09-21
Muni7830 | PROJ-0951-MUN-3.33.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Dexter (Off Joy) | 0 | 2021-09-21 | 2021-09-21
Muni7860 | PROJ-0951-MUN-3.34.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - linwood (Off Joy) | 0 | 2021-09-21 | 2021-09-21
Muni7920 | PROJ-0951-MUN-3.35.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Virginia Park (Rosa Parks & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni8190 | PROJ-0951-MUN-3.36.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - ASO Davison (Conant & Joseph Campau) | 0 | 2021-09-21 | 2021-09-21
Muni8420 | PROJ-0951-MUN-3.37.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - ASO W Grand Blvd (Linwood & EOM) | 0 | 2021-09-21 | 2021-09-21
Muni8030 | PROJ-0951-MUN-2.12.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Pinehurst (Chicago & Joy) | 0 | 2021-09-21 | 2021-09-21
Muni8430 | PROJ-0951-MUN-2.16.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ASO Michigan (At Vinewood) | 0 | 2021-09-21 | 2021-09-21
Muni8830 | PROJ-0951-MUN-2.21.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Orchard (At Lahser) | 0 | 2021-09-21 | 2021-09-21
Muni8910 | PROJ-0951-MUN-2.13.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Magnolia (Mckinley & Roosevelt) | 0 | 2021-09-21 | 2021-09-21
Muni8990 | PROJ-0951-MUN-2.14.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Michigan (At Vinewood) | 0 | 2021-09-21 | 2021-09-21
Muni9390 | PROJ-0951-MUN-2.19.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Vinewood (Michigan & ASO Michigan) | 0 | 2021-09-21 | 2021-09-21
Muni8620 | PROJ-0951-MUN-3.39.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Rosa Park (Calvert Ave & Gylnn CT) | 0 | 2021-09-22 | 2021-09-22
Muni7230 | PROJ-0951-MUN-2.2.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Chicago 2 (Wyoming & EOM) | 0 | 2021-09-22 | 2021-09-22
Muni7390 | PROJ-0951-MUN-2.4.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO Chicago (Griggs & Wyoming) | 0 | 2021-09-22 | 2021-09-22
Muni7470 | PROJ-0951-MUN-2.5.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Griggs (ANO Chicago & Chicago) | 0 | 2021-09-22 | 2021-09-22
Muni7550 | PROJ-0951-MUN-2.6.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Chicago 1 (Pinehurst & Griggs) | 0 | 2021-09-22 | 2021-09-22
Muni7710 | PROJ-0951-MUN-2.6.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Chicago 1 (Pinehurst & Birwood) | 0 | 2021-09-22 | 2021-09-22
Muni7790 | PROJ-0951-MUN-2.9.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Mendota (Chicago & ASO Chicago) | 0 | 2021-09-22 | 2021-09-22
Muni7870 | PROJ-0951-MUN-2.10.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Birwood (Chicago & ASO Chicago) | 0 | 2021-09-22 | 2021-09-22
Muni7950 | PROJ-0951-MUN-2.11.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ASO Chicago (Pinehurst & Birwood) | 0 | 2021-09-22 | 2021-09-22
Muni8110 | PROJ-0951-MUN-2.7.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Ash (Vinewood & Roosevelt) | 0 | 2021-09-22 | 2021-09-22
Muni8270 | PROJ-0951-MUN-2.14.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Michigan (Hubbard & Vinewood) | 0 | 2021-09-22 | 2021-09-22
Ypsi 3-2810 | PROJ-0951-YSP3.36.3.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Old Ecorse (Nash & Onandaga) | 5 | 2021-09-23 | 2021-09-29
NCDET - 20475 | NEWPROJ-6.2.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Ardmore (Puritan & Fenkell) | 63 | 2021-09-23 | 2021-09-29
NCDET - 23865 | NEWPROJ-6.4.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Cheyenne (Puritan & Fenkell) | 68 | 2021-09-23 | 2021-09-29
NCDET - 24255 | NEWPROJ-6.16.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Ward (Puritan & Fenkell) | 109 | 2021-09-23 | 2021-09-29
GP-14520 | PROJ-0951-GP 5 -3.132.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Mack North 1 (Balfour & Cadieux) | 0 | 2021-09-23 | 2021-09-29
RR1 5478 | GRP-2021-RR1.4.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Coolidge Hwy 1 (332' WWPL Division St & Division St) | 4 | 2021-09-23 | 2021-09-28
RR1 5484 | GRP-2021-RR1.10.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Outer Dr (162' WWPL High St & High St) | 4 | 2021-09-23 | 2021-09-28
SCDet-2160 | GRP-2021-SCDet1.2.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd N 2 (Steel & Birwood) | 4 | 2021-09-23 | 2021-09-28
SCDet-2240 | GRP-2021-SCDet1.3.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd W 1 (Mackenzie & Belton) | 4 | 2021-09-23 | 2021-09-28
SCDet-2400 | GRP-2021-SCDet1.6.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd S 2 (Steel & Birwood) | 4 | 2021-09-23 | 2021-09-28
SCDet-2560 | GRP-2021-SCDet1.8.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Esper (Belton & Mendota) | 4 | 2021-09-23 | 2021-09-28
SCDet-2800 | GRP-2021-SCDet1.11.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Decatur (Belton & EOM) | 4 | 2021-09-23 | 2021-09-28
SCDet-3760 | GRP-2021-SCDet1.24.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Pinehurst (Joy & Oakman) | 4 | 2021-09-23 | 2021-09-28
SCDet-3920 | GRP-2021-SCDet1.26.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Middlepointe (Mendota & Esper) | 4 | 2021-09-23 | 2021-09-28
SCDet-4960 | GRP-2021-SCDet1.38.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Steel (Tireman & Oakman) | 4 | 2021-09-23 | 2021-09-28
SCDet-5440 | GRP-2021-SCDet1.44.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Van Buren (Meadowdale & Schaefer) | 4 | 2021-09-23 | 2021-09-28
SCDet-5520 | GRP-2021-SCDet1.45.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Belton 1 (Decatur & Carlin) | 4 | 2021-09-23 | 2021-09-28
SCDet-5600 | GRP-2021-SCDet1.46.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Belton 2 (Mendota & Middlepointe) | 4 | 2021-09-23 | 2021-09-28
SCDet-5840 | GRP-2021-SCDet1.49.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Mackenzie 1 (Hartwell & Littlefield) | 4 | 2021-09-23 | 2021-09-28
SCDet-5920 | GRP-2021-SCDet1.50.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Civic (Appoline & Manor) | 4 | 2021-09-23 | 2021-09-28
SCDet-6080 | GRP-2021-SCDet1.52.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Maple (Tireman & Morross) | 4 | 2021-09-23 | 2021-09-28
RR1 5434 | GRP-2021-RR1.20.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Emiline St (EOM & Haltiner) | 4 | 2021-09-23 | 2021-09-28
RR1 5437 | GRP-2021-RR1.24.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Furgason (W Pleasant St & Myrtle St) | 4 | 2021-09-23 | 2021-09-28
RR1 5452 | GRP-2021-RR1.39.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Pleasasnt (345' WWPL Dwight St & 246' WWPL Dwight St) | 4 | 2021-09-23 | 2021-09-28
RR1 5453 | GRP-2021-RR1.41.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Harris (4' SSPL E Anchor St & E Cicotte St) | 4 | 2021-09-23 | 2021-09-28
RR1 5472 | GRP-2021-RR1.59.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Great Lakes St (57' WWPL Ironton Ave & Ironton Ave) | 4 | 2021-09-23 | 2021-09-28
CDET2-1720 | GRP-2021-CDet2.5.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - W Boston Blvd 1 (Linwood & Lawton) | 0 | 2021-09-23 | 2021-09-28
CDET2-1880 | GRP-2021-CDet2.7.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Chicago Blvd 1 (Dexter & Wildemere) | 0 | 2021-09-23 | 2021-09-28
CDET2-1960 | GRP-2021-CDet2.7.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Chicago Blvd 1 (Lawton & Linwood) | 0 | 2021-09-23 | 2021-09-28
CDET2-2040 | GRP-2021-CDet2.9.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Chicago Blvd 2 (Wildemere & Genessee) | 0 | 2021-09-23 | 2021-09-28
CDET2-2200 | GRP-2021-CDet2.11.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Rochester (Dexter & Wildemere) | 0 | 2021-09-23 | 2021-09-28
CDET2-2280 | GRP-2021-CDet2.12.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Longfellow 1 (Dexter & Lawton) | 0 | 2021-09-23 | 2021-09-28
CDET2-2600 | GRP-2021-CDet2.16.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Wagner (Dexter & Savery) | 0 | 2021-09-23 | 2021-09-28
CDET2-2680 | GRP-2021-CDet2.17.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Atkinson 1 (Dexter & Savery) | 0 | 2021-09-23 | 2021-09-28
CDET2-2840 | GRP-2021-CDet2.19.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - ANO Joy (Savery & Savery) | 0 | 2021-09-23 | 2021-09-28
CDET2-3000 | GRP-2021-CDet2.21.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Clairmount 2 (Linwood & La Salle) | 0 | 2021-09-23 | 2021-09-28
CDET2-3160 | GRP-2021-CDet2.3.6.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - ANO Chicago (Linwood & La Salle) | 0 | 2021-09-23 | 2021-09-28
CDET2-3640 | GRP-2021-CDet2.30.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Blaine 1 (Dexter & Dexter) | 0 | 2021-09-23 | 2021-09-28
CDET2-4040 | GRP-2021-CDet2.35.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Philadelphia 2 (Linwood & La Salle) | 0 | 2021-09-23 | 2021-09-28
CDET2-4600 | GRP-2021-CDet2.42.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Wildemere 1 (Glynn & W Chicago) | 0 | 2021-09-23 | 2021-09-28
CDET2-4680 | GRP-2021-CDet2.43.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Wildemere 2 (Fullerton & Calvert) | 0 | 2021-09-23 | 2021-09-28
CDET2-4760 | GRP-2021-CDet2.44.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Savery (Chicago & Joy) | 0 | 2021-09-23 | 2021-09-28
CDET2-4920 | GRP-2021-CDet2.46.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Lawton 3 (Gladstone & Carter) | 0 | 2021-09-23 | 2021-09-28
CDET2-5000 | GRP-2021-CDet2.47.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Lawton 2 (Clairmount & Clairmount) | 0 | 2021-09-23 | 2021-09-28
CDET2-5160 | GRP-2021-CDet2.49.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Linwood 2 (Carter & Euclid) | 0 | 2021-09-23 | 2021-09-28
CDET2-5240 | GRP-2021-CDet2.50.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - LaSalle 1 (Clairmount & Gladstone) | 0 | 2021-09-23 | 2021-09-28
CDET2-5560 | GRP-2021-CDet2.38.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Rosa Parks Blvd 1 (ANO W. Chicago & Longfellow) | 0 | 2021-09-23 | 2021-09-28
RR1 51501 | GRP-2021-RR1.65.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Abbott (EOM @ 261' WWPL Genessee St & Genessee St) | 4 | 2021-09-23 | 2021-09-28
RR1 51536 | GRP-2021-RR1.71.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Ironton Ave 1 (E Great Lakes St & Catherine St) | 4 | 2021-09-23 | 2021-09-28
RR1 51502 | GRP-2021-RR1.74.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Stone St (W Jefferson Ave & Genessee St) | 4 | 2021-09-23 | 2021-09-28
RR1 51665 | GRP-2021-RR1.76.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Bell St (High & Visgar) | 4 | 2021-09-23 | 2021-09-28
RR1 51668 | GRP-2021-RR1.79.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Alexis Ave (W Jefferson & Eliza) | 4 | 2021-09-23 | 2021-09-28
RR1 51670 | GRP-2021-RR1.81.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Elton St (High & W Jefferson) | 4 | 2021-09-23 | 2021-09-28
RR1 51672 | GRP-2021-RR1.83.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - High St 2 (7' NSPL W Woodward Ave & 373' SSPL W Outer Dr) | 4 | 2021-09-23 | 2021-09-28
RR1 51673 | GRP-2021-RR1.84.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Knox St (High & W Jefferson) | 4 | 2021-09-23 | 2021-09-28
RR1 51674 | GRP-2021-RR1.85.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Labadie St (55' WWPL Webster St & High St) | 4 | 2021-09-23 | 2021-09-28
RR1 51675 | GRP-2021-RR1.86.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Lafferty Ave (Salliotte & EOM) | 4 | 2021-09-23 | 2021-09-28
RR1 51677 | GRP-2021-RR1.88.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Ridge St (High & W Jefferson) | 4 | 2021-09-23 | 2021-09-28
RR1 51679 | GRP-2021-RR1.91.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Ruth St (High & W Jefferson) | 4 | 2021-09-23 | 2021-09-28
RR1 51680 | GRP-2021-RR1.92.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Salliotte St (351' WWPL Drennan St & 96' WWPL Drennan St) | 4 | 2021-09-23 | 2021-09-28
RR1 51684 | GRP-2021-RR1.96.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Charlotte (14' EEPL High St & 5' WWPL W Jefferson Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 51687 | GRP-2021-RR1.99.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Woodward Ave (EOM & W Jefferson) | 4 | 2021-09-23 | 2021-09-28
RR1 51688 | GRP-2021-RR1.100.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Westfield St (EOM & W Jefferson) | 4 | 2021-09-23 | 2021-09-28
RR1 51756 | GRP-2021-RR1.107.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Joseph St (W Jefferson Ave & Eliza St) | 4 | 2021-09-23 | 2021-09-28
RR1 51757 | GRP-2021-RR1.108.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Ironton Ave 2 (River Rouge City Limits & Rockwood Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 51758 | GRP-2021-RR1.109.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Orchard St (River Rouge City Limits & Ironton Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 51759 | GRP-2021-RR1.110.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Alexis Ave (8' EEPL High St & 9' WWPL W Jefferson Ave) | 4 | 2021-09-23 | 2021-09-28
EDET1 50914 | GRP-2021-ED1.4.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO Mack Ave (1) (Alter Rd & Nottingham Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 50879 | GRP-2021-ED1.34.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (N) (3) (E Outer Dr & Harvard Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 501179 | GRP-2021-ED1.49.1.4 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Balfour Rd (ASOE Warren Ave & Waveney Ave) | 0 | 2021-09-23 | 2021-09-28
EDET1 501183 | GRP-2021-ED1.53.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bremen St (2) (Balfour Rd & Buckingham Ave) | 0 | 2021-09-23 | 2021-09-28
EDET1 501194 | GRP-2021-ED1.64.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (1) (Wayburn Ave & Balfour Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 501195 | GRP-2021-ED1.65.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (2) (Balfour Rd & Courville St) | 0 | 2021-09-23 | 2021-09-28
EDET1 501253 | GRP-2021-ED1.75.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Devonshire Rd (1) (ANO E Warren Ave & ASO E Warren Ave) | 0 | 2021-09-23 | 2021-09-28
SWDET2-2055 | PROJ-0951-SWDET2.5.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Fort (Woodmere & Distel) | 4 | 2021-09-23 | 2021-09-28
SWDET2-3255 | PROJ-0951-SWDET2.20.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - AEO Distel (Olivet & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-3895 | PROJ-0951-SWDET2.29.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Richard (EOM & Woodmere) | 4 | 2021-09-23 | 2021-09-28
SWDET2-4455 | PROJ-0951-SWDET2.36.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Longworth (Woodmere & Lawndale) | 4 | 2021-09-23 | 2021-09-28
SWDET2-5175 | PROJ-0951-SWDET2.45.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mullane (At Cahalan) | 4 | 2021-09-23 | 2021-09-28
SWDET2-5815 | PROJ-0951-SWDET2.53.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pershing (Springwells & Central) | 4 | 2021-09-23 | 2021-09-28
SWDET2-5895 | PROJ-0951-SWDET2.54.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Senator 1 (EOM & Mullane) | 4 | 2021-09-23 | 2021-09-28
SWDET2-6935 | PROJ-0951-SWDET2.67.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Honorah (Dix & W Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-7015 | PROJ-0951-SWDET2.68.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Inglis (ANO W Vernor & W Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-7095 | PROJ-0951-SWDET2.69.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pitt (EOM & Springwells) | 4 | 2021-09-23 | 2021-09-28
SWDET2-7655 | PROJ-0951-SWDET2.75.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Norman (Woodmere & ANO W Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-7815 | PROJ-0951-SWDET2.77.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pearl (Woodmere & Tie-In) | 4 | 2021-09-23 | 2021-09-28
SWDET2-7895 | PROJ-0951-SWDET2.78.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Sharon (NO Woodmere & Woodmere) | 4 | 2021-09-23 | 2021-09-28
RR1 272 | GRP-2021-RR1.5.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - AEO Goodell St (E Great Lakes St & N of Coolidge Hwy) | 4 | 2021-09-23 | 2021-09-28
AA3-5680 | GRP-2021-RR1.8.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Eliza St (35' NNPL E Charlotte Ave & 4' NSPL E Charlotte Ave) | 4 | 2021-09-23 | 2021-09-28
AA3-5750 | GRP-2021-RR1.9.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Florence St 2 (Joseph st & E Charlotte Ave) | 4 | 2021-09-23 | 2021-09-28
SWDET2-9515 | PROJ-0951-SWDET2.12.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor 4 (At Central) | 4 | 2021-09-23 | 2021-09-28
SWDET2-10155 | PROJ-0951-SWDET2.7.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - ANO W Vernor (Norman & Inglis) | 4 | 2021-09-23 | 2021-09-28
SWDET2-10475 | PROJ-0951-SWDET2.9.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Springwells 1 (Rathbone & Chamberlain) | 4 | 2021-09-23 | 2021-09-28
SWDET2-10985 | PROJ-0951-SWDET2.70.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Springwells 2 (Tie-In & W Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-11225 | PROJ-0951-SWDET2.13.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Central 1 E (W Vernor & ASO Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-12845 | PROJ-0951-SWDET2.31.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 3 (ANO W Vernor & W Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-13005 | PROJ-0951-SWDET2.31.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 3 (W Vernor & ASO Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-13165 | PROJ-0951-SWDET2.31.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 3 (ASO Vernor & Elsmere) | 4 | 2021-09-23 | 2021-09-28
SCDet-7690 | GRP-2021-SCDet1.27.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Morrow (Esper & Mackenzie) | 4 | 2021-09-23 | 2021-09-28
SCDet-8330 | GRP-2021-SCDet1.24.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Pinehurst (Esper & Tireman) | 4 | 2021-09-23 | 2021-09-28
SCDet-6320 | GRP-2021-SCDet1.43.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Joy 3 (Ohio & Greenlawn) | 0 | 2021-09-23 | 2021-09-28
SCDet-5360 | GRP-2021-SCDet1.43.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Joy 3 (Wyoming & Ohio) | 0 | 2021-09-23 | 2021-09-28
SCDet-8900 | GRP-2021-SCDet1.54.1.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Belton 3 (Sorrento & Littlefield) | 4 | 2021-09-23 | 2021-09-28
EDET1 501416 | GRP-2021-ED1.65.83.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (Warren & Waveney)20049 | 0 | 2021-09-23 | 2021-09-28
SCDet-9220 | GRP-2021-SCDet1.11.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Decatur (Belton & 309' NNPL Tireman) | 4 | 2021-09-23 | 2021-09-28
SCDet-9380 | GRP-2021-SCDet1.11.2.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Decatur (309' NNPL Tireman & Tireman) | 4 | 2021-09-23 | 2021-09-28
EDET1 501896 | GRP-2021-ED1.34.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (N) (3) (Harvard & Harvard) | 0 | 2021-09-23 | 2021-09-28
SCDet-10200 | GRP-2021-SCDet1.3.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd W 1 (10' SNPL Mackenzie & 13' NSPL Mackenzie) | 4 | 2021-09-23 | 2021-09-28
CDET2-5880 | GRP-2021-CDet2.5.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - W Boston Blvd 1 (Wildemere & Wildemere) | 0 | 2021-09-23 | 2021-09-28
SCDet-11110 | GRP-2021-SCDet1.18.3.2 | 2021 GRP - South Central Detroit 1 | Restoration - Soft Surface - Ward (Mackenzie & Littlefield) | 4 | 2021-09-23 | 2021-09-28
CDET2-6200 | GRP-2021-CDet2.21.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Clairmount 2 (La Salle & Rosa Parks) | 0 | 2021-09-23 | 2021-09-28
CDET2-7200 | GRP-2021-CDet2.35.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Philadelphia 2 (La Salle & 14th) | 0 | 2021-09-23 | 2021-09-28
CDET2-7360 | GRP-2021-CDet2.35.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Philadelphia 2 (14th & EOM) | 0 | 2021-09-23 | 2021-09-28
CDET2-7740 | GRP-2021-CDet2.48.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Linwood 1 (ANO Chicago & Llongfellow) | 0 | 2021-09-23 | 2021-09-28
CDET2-7900 | GRP-2021-CDet2.48.2.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Linwood 1 (Longfellow & Atkinson) | 0 | 2021-09-23 | 2021-09-28
CDET2-8060 | GRP-2021-CDet2.49.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Linwood 2 (Gladstone & Carter) | 0 | 2021-09-23 | 2021-09-28
CDET2-8380 | GRP-2021-CDet2.49.4.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Linwood 2 (Atkinson & Gladstone) | 0 | 2021-09-23 | 2021-09-28
CDET2-8560 | GRP-2021-CDet2.50.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - LaSalle 1 (Gladstone & W Euclid) | 0 | 2021-09-23 | 2021-09-28
CDET2-8800 | GRP-2021-CDet2.1.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - ASO Chicago (14th & Rosa Parks) | 0 | 2021-09-23 | 2021-09-28
CDET2-8950 | GRP-2021-CDet2.3.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - ANO Chicago (Linwood & Linwood) | 0 | 2021-09-23 | 2021-09-28
CDET2-9190 | GRP-2021-CDet2.1.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - ASO Chicago (Rosa Parks & Rosa Parks) | 0 | 2021-09-23 | 2021-09-28
WCDET1-8710 | GRP-2021-WCDet1.26.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Monica West 1 (Oakman & Buena Vista) | 0 | 2021-09-23 | 2021-09-28
WCDET1-10550 | GRP-2021-WCDet1.17.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 4 (Davison & EOM) | 0 | 2021-09-23 | 2021-09-28
WCDET1-10710 | GRP-2021-WCDet1.17.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 4 (Buena Vista & Buena Vista) | 0 | 2021-09-23 | 2021-09-28
WCDET1-10870 | GRP-2021-WCDet1.48.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 2 (Livernois & EOM) | 0 | 2021-09-23 | 2021-09-28
RR1 54220 | GRP-2021-RR1.15.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Cora (4' EWPL Haltiner St & 5' WEPL Haltiner St) | 4 | 2021-09-23 | 2021-09-28
RR1 55740 | GRP-2021-RR1.53.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E James South (4' EWPL Burke St & 3' WEPL Burke St) 3" | 4 | 2021-09-23 | 2021-09-28
AA3-5820 | GRP-2021-RR1.8.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Eliza St (Joseph St & E Charlotte Ave) | 4 | 2021-09-23 | 2021-09-28
AA3-5890 | GRP-2021-RR1.8.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Eliza St (E Charlotte Ave & EOM @ 108' SSPL E Alexis Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 57260 | GRP-2021-RR1.41.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Harris (E Cicotte St & 18' NNPL E James St) | 4 | 2021-09-23 | 2021-09-28
RR1 57340 | GRP-2021-RR1.41.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Harris (18' NNPL E James St & 18' NNPL E Pleasant St) | 4 | 2021-09-23 | 2021-09-28
RR1 57670 | GRP-2021-RR1.71.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Ironton Ave 1 (Catherine St & Orchard St) | 4 | 2021-09-23 | 2021-09-28
RR1 57830 | GRP-2021-RR1.108.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Ironton Ave 2 (Rockwood Ave & E Glenwood Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 58000 | GRP-2021-RR1.85.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Labadie St (190' WWPL Webster St & 55' WWPL Webster St) | 4 | 2021-09-23 | 2021-09-28
RR1 58980 | GRP-2021-RR1.92.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Salliotte St (96' WWPL Drennan St & High St) | 4 | 2021-09-23 | 2021-09-28
AP 3450 | PROJ-0951-MMOAllen.9.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Becker 1 (Bellaire & Goddard) | 4 | 2021-09-23 | 2021-09-28
RR1 59430 | GRP-2021-RR1.80.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Visgar Rd (EOM & W Jefferson Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 59560 | GRP-2021-RR1.112.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Auburn Ave (High St & W Jefferson Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 61070 | GRP-2021-RR1.2.15.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (W Great Lakes St & Neiman St) | 4 | 2021-09-23 | 2021-09-28
RR1 61310 | GRP-2021-RR1.2.18.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (0' WEPL W Jefferson Ave & 22' WEPL W Jefferson Ave) | 4 | 2021-09-23 | 2021-09-28
AA3-6170 | GRP-2021-RR1.7.5.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (2) (5' NSPL Salliotte Rd & 12' SNPL Salliotte Rd) | 4 | 2021-09-23 | 2021-09-28
AA3-6240 | GRP-2021-RR1.7.6.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (2) (11' WEPL W Jefferson Ave & 6' EWPL W Jefferson Ave) | 4 | 2021-09-23 | 2021-09-28
RR1 61830 | GRP-2021-RR1.39.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Pleasasnt (246' WWPL Dwight St & 130' WWPL Dwight St) | 4 | 2021-09-23 | 2021-09-28
SWDET2-13635 | PROJ-0951-SWDET2.80.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - ASO W Vernor 2 (Central & Beard) | 4 | 2021-09-23 | 2021-09-28
SWDET2-13795 | PROJ-0951-SWDET2.30.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Witt (Lawndale & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-14115 | PROJ-0951-SWDET2.30.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Witt (At Lawndale) | 4 | 2021-09-23 | 2021-09-28
SWDET2-14435 | PROJ-0951-SWDET2.55.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Whitaker 1 (Lawndale & Mullane) | 4 | 2021-09-23 | 2021-09-28
SWDET2-14675 | PROJ-0951-SWDET2.72.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cabot (ANO Vernor & W Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-15535 | PROJ-0951-SWDET2.65.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Carson (Tie-In & W Vernor) | 4 | 2021-09-23 | 2021-09-28
SWDET2-15445 | PROJ-0951-SWDET2.79.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Wendell (ANO W Vernor & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-15935 | PROJ-0951-SWDET2.13.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Central 1 E W (ASO Vernor & Logan) | 4 | 2021-09-23 | 2021-09-28
SWDET2-16345 | PROJ-0951-SWDET2.25.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Elsmere 2 (Lafayette & Olivet) | 4 | 2021-09-23 | 2021-09-28
SWDET2-16855 | PROJ-0951-SWDET2.73.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Ferris (ANO Vernor & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-19695 | PROJ-0951-SWDET2.51.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Logan 2 (EOM & Central) | 4 | 2021-09-23 | 2021-09-28
SWDET2-19855 | PROJ-0951-SWDET2.36.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Longworth (Tie-in & Lawndale) | 4 | 2021-09-23 | 2021-09-28
SWDET2-20015 | PROJ-0951-SWDET2.36.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Longworth (Tie-in & Tie-in) | 4 | 2021-09-23 | 2021-09-28
SWDET2-20175 | PROJ-0951-SWDET2.36.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Longworth (Tie-in & Springwells) | 4 | 2021-09-23 | 2021-09-28
SWDET2-20535 | PROJ-0951-SWDET2.43.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mandale (Elsemere & Lawndale) | 4 | 2021-09-23 | 2021-09-28
SWDET2-20705 | PROJ-0951-SWDET2.45.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mullane (Logan & Longworth) | 4 | 2021-09-23 | 2021-09-28
SWDET2-20865 | PROJ-0951-SWDET2.45.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mullane (Longworth & Homer) | 4 | 2021-09-23 | 2021-09-28
SWDET2-20935 | PROJ-0951-SWDET2.45.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mullane (At Homer) | 4 | 2021-09-23 | 2021-09-28
SWDET2-22725 | PROJ-0951-SWDET2.69.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pitt (Springwells & Casper) | 4 | 2021-09-23 | 2021-09-28
SWDET2-22885 | PROJ-0951-SWDET2.69.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pitt (Casper & Central) | 4 | 2021-09-23 | 2021-09-28
SWDET2-23045 | PROJ-0951-SWDET2.69.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pitt (Honorah & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-23125 | PROJ-0951-SWDET2.69.5.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pitt (Honorah & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-23205 | PROJ-0951-SWDET2.69.6.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pitt (Honorah & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-23285 | PROJ-0951-SWDET2.69.7.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pitt (Honorah & EOM) | 4 | 2021-09-23 | 2021-09-28
SWDET2-23355 | PROJ-0951-SWDET2.45.5.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mullane (At Whittaker) | 4 | 2021-09-23 | 2021-09-28
SWDET2-23435 | PROJ-0951-SWDET2.45.6.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mullane (At Lane) | 4 | 2021-09-23 | 2021-09-28
SWDET2-24005 | PROJ-0951-SWDET2.82.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 1W (W Vernor & ASO Vernor) | 0 | 2021-09-23 | 2021-09-28
SWDET2-24165 | PROJ-0951-SWDET2.82.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 1W (At Witt) | 0 | 2021-09-23 | 2021-09-28
SWDET2-24245 | PROJ-0951-SWDET2.82.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 1W (Chamberlain & Witt) | 0 | 2021-09-23 | 2021-09-28
SWDET2-24335 | PROJ-0951-SWDET2.74.5.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 2 (Woodmere & W Vernor) | 0 | 2021-09-23 | 2021-09-28
RR1 6071 | GRP-2021-RR.8.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Westphalia (7 Mile & Greiner) | 0 | 2021-09-23 | 2021-09-28
RR1 6791 | GRP-2021-RR.18.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - St Marys (Chicago & Plymouth) | 0 | 2021-09-23 | 2021-09-28
RR1 7271 | GRP-2021-RR.25.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Irvington (State Fair & 7 Mile) | 0 | 2021-09-23 | 2021-09-28
RR1 8651 | GRP-2021-RR.42.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Coram (Gratiot & Hayes) | 0 | 2021-09-23 | 2021-09-28
RR1 8971 | GRP-2021-RR.46.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - College (Conner & Gunston) | 0 | 2021-09-23 | 2021-09-28
RR1 9131 | GRP-2021-RR.48.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Gunston (Nashville & Gunston) | 0 | 2021-09-23 | 2021-09-28
RR1 10741 | GRP-2021-RR.37.2.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Varjo (Cliff & Van Dyke) | 0 | 2021-09-23 | 2021-09-28
EDET1 502916 | GRP-2021-ED1.4.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO Mack Ave (1) (Somerset Ave & Balfour Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 502996 | GRP-2021-ED1.4.4.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO Mack Ave (1) (Crossing At Balfour Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 503476 | GRP-2021-ED1.11.4.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (3) (Harvard Rd & Cadieux Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 503716 | GRP-2021-ED1.11.7.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (3) (E Warren Ave & ASO E Warren Ave) | 0 | 2021-09-23 | 2021-09-28
EDET1 504516 | GRP-2021-ED1.16.4.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (1) (Balfour Rd & Balfour Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 504606 | GRP-2021-ED1.18.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Cadieux Rd) | 0 | 2021-09-23 | 2021-09-28
EDET1 505166 | GRP-2021-ED1.18.10.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) N (ANO E Warren Ave & ASO E Warren Ave @ Neff Ave) | 0 | 2021-09-23 | 2021-09-28
EDET1 505246 | GRP-2021-ED1.18.11.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) S (Bishop St & Grayton St) | 0 | 2021-09-23 | 2021-09-28
EDET1 505326 | GRP-2021-ED1.26.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Grayton St (1) (E Warrern Ave & Waveney St) | 0 | 2021-09-23 | 2021-09-28
EDET1 505826 | GRP-2021-ED1.3.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Mack Ave (ASO Mack Ave & ANO Mack Avee) | 0 | 2021-09-23 | 2021-09-28
EDET1 505876 | GRP-2021-ED1.3.2.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Mack Ave (Nottingham Rd & Somerset Ave) | 0 | 2021-09-23 | 2021-09-28
EDET1 506136 | GRP-2021-ED1.49.3.1 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Balfour Rd (E Warren Ave & ASOE Warren Ave) | 0 | 2021-09-23 | 2021-09-28
EDET1 506386 | GRP-2021-ED1.70.4.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bedford St (2) (Bedford & Bedford) crossing | 0 | 2021-09-23 | 2021-09-28
EDET1 506966 | GRP-2021-ED1.65.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (2) (Courville St & E Outer Dr) | 0 | 2021-09-23 | 2021-09-28
WCDET1-15300 | GRP-2021-WCDet1.59.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Bourke (East) (Burnette & EOM Burnette) | 0 | 2021-09-23 | 2021-09-28
SWDET2-1062 | GRP-2021-WCDet1.61.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Bourke (North) (Livernois & Quincy) | 0 | 2021-09-23 | 2021-09-28
WCDET1-15700 | GRP-2021-WCDet1.27.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Stoepel 1 (Ewald & Oakman) | 0 | 2021-09-23 | 2021-09-28
RR1 10971 | GRP-2021-RR.61.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Carpenter (McDougall & Charest) | 0 | 2021-09-23 | 2021-09-28
NDET3-5805 | GRP-2021-ND3.13.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Dwyer St (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 2021-09-23 | 2021-09-28
NDET3-6575 | GRP-2021-ND3.46.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Albany Ave (1) (Hamlet & Amrad St) | 0 | 2021-09-23 | 2021-09-28
NDET3-7225 | GRP-2021-ND3.52.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Conley Ave (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 2021-09-23 | 2021-09-28
NDET3-7000 | GRP-2021-ND3.60.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Moenart St (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 2021-09-23 | 2021-09-28
NDET3-470 | GRP-2021-ND3.62.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Syracuse Ave (1) (8 Mile Rd (M102) & Hamlet St) | 0 | 2021-09-23 | 2021-09-28
NDET3-485 | GRP-2021-ND3.76.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Sherwood St Abandonment (E Outer Dr & District Regulator 10742) | 0 | 2021-09-23 | 2021-09-28
NDET3-6255 | GRP-2021-ND3.5.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mound Rd (east) - (Mound Rd & Mound Rd | 0 | 2021-09-23 | 2021-09-28
NDET3-6585 | GRP-2021-ND3.46.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Albany Ave (1) (Hamlet St & EOM) | 0 | 2021-09-23 | 2021-09-28
NDET3-7235 | GRP-2021-ND3.52.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Conley Ave (1) (Hamlet St & E Outer Dr) | 0 | 2021-09-23 | 2021-09-28
NDET3-7010 | GRP-2021-ND3.60.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Moenart St (1) (Hamlet St & E Outer Dr) | 0 | 2021-09-23 | 2021-09-28
NDET3-4535 | GRP-2021-ND3.4.4.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - E Outer Dr (North) - (Mt Elliot St & Mt Elliot St) | 0 | 2021-09-23 | 2021-09-28
NDET3-505 | GRP-2021-ND3.97.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - E Lantz Ave (1) (E Lantz Ave & E Lantz Ave) | 0 | 2021-09-23 | 2021-09-28
NDET3-6755 | GRP-2021-ND3.62.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Syracuse Ave (1) (Hamlet St & Amrad St) | 0 | 2021-09-23 | 2021-09-28
NDET3-830 | GRP-2021-ND3.3.8.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Crossing At Bloom St) | 0 | 2021-09-23 | 2021-09-28
NDET3-835 | GRP-2021-ND3.3.9.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Crossing At Mt Elliot St) | 0 | 2021-09-23 | 2021-09-28
NDET3-510 | GRP-2021-ND3.28.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Dwyer St (ANO 7 Mile Rd & 7 Mile Rd) | 0 | 2021-09-23 | 2021-09-28
RR1 9771 | GRP-2021-FR.56.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - 24th (Fort & Jefferson) | 0 | 2021-09-23 | 2021-09-28
RR1 9611 | GRP-2021-FR.54.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - 16th (65' NNPL Lafayette & Lafayette) | 0 | 2021-09-23 | 2021-09-28
RR1 9451 | GRP-2021-FR.52.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Lafayette (16th & St Anne) | 0 | 2021-09-23 | 2021-09-28
RR1 6631 | GRP-2021-RR.50.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Rademacher (Lafayette & 157' SSPL Lafayette) | 0 | 2021-09-23 | 2021-09-28
RR1 6551 | GRP-2021-RR.49.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Livernois (EOM & W Lafayette) | 0 | 2021-09-23 | 2021-09-28
RR1 6471 | GRP-2021-RR.15.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Crawford (56' NNPL Lafayette & 124' SSPL Lafayette) | 0 | 2021-09-23 | 2021-09-28
RR1 6391 | GRP-2021-RR.14.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Casgrain (40' NNPL Lafayette & 131' NNPL Lafayette) | 0 | 2021-09-23 | 2021-09-28
RR1 6311 | GRP-2021-RR.13.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Lafayette (Rademacher & Campbell) | 0 | 2021-09-23 | 2021-09-28
EDET1 508006 | GRP-2021-ED1.6.2.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Harvard Rd (1) (ASO Warren & Warren) | 0 | 2021-09-23 | 2021-09-29
EDET1 508196 | GRP-2021-ED1.7.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO Mack Ave 2 (Courville & Courville) | 0 | 2021-09-23 | 2021-09-28
EDET1 508516 | GRP-2021-ED1.8.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO Mack Ave (3) (Yorkshire & Yorkshire) | 0 | 2021-09-23 | 2021-09-28
CDET2-10360 | GRP-2021-CDet2.6.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Collingwood (AWO Linwood & Linwood) | 0 | 2021-09-23 | 2021-09-28
CDET2-10510 | GRP-2021-CDet2.13.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Lawton 1 (Gladstone & Carter) | 0 | 2021-09-23 | 2021-09-29
CDET2-10650 | GRP-2021-CDet2.41.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Lawton 2 (Clairmount & Clairmount ) | 0 | 2021-09-23 | 2021-09-29
CDET2-10800 | GRP-2021-CDet2.10.3.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Blaine 2 (14TH - Rosa Parks) | 0 | 2021-09-23 | 2021-09-28
NDET3-7840 | GRP-2021-ND3.8.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - E Remington St (Norwood & Yonka) | 0 | 2021-09-23 | 2021-09-28
RedfMMO1070 | PROJ-0951-MMORedford-1.1.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - 7 Mile Rd (Inkster & Gaylord) | 0 | 2021-09-23 | 2021-09-29
RedfMMO1640 | PROJ-0951-MMORedford-1.7.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Denby (Grand River & Pembroke) | 0 | 2021-09-23 | 2021-09-29
RedfMMO2680 | PROJ-0951-MMORedford-1.20.1.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Gaylord 2 (Delaware & Santa Maria) | 3 | 2021-09-23 | 2021-09-29
RedfMMO3690 | PROJ-0951-MMORedford-1.23.3.2 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Fox (Grand River & Pembroke) | 0 | 2021-09-23 | 2021-09-29
RedfMMO3880 | PROJ-0951-MMORedford-1.31.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface - Fox (Pembroke & Grand River) | 0 | 2021-09-23 | 2021-09-29
RedfMMO3980 | PROJ-0951-MMORedford-1.33.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface -Indiana (7 Mile Rd & St Martins ave) | 0 | 2021-09-23 | 2021-09-29
RedfMMO4130 | PROJ-0951-MMORedford-1.36.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface -Poinciana (Grand River & Fargo) | 0 | 2021-09-23 | 2021-09-29
RedfMMO4180 | PROJ-0951-MMORedford-1.37.1 | 2020 GRP - Carry Over - MMO 6382 Redford | Restoration - Soft Surface -Poinnciana (7 Mile & Vassar) | 0 | 2021-09-23 | 2021-09-29
CDET-575 | PROJ-0951-CDET1-2.20.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Linwood (1) (Dexter & Cortland) | 0 | 2021-09-23 | 2021-09-29
CDET-790 | PROJ-0951-CDET1-2.28.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - AWO Linwood (1) (Cortland & Collingwood) | 0 | 2021-09-23 | 2021-09-29
CDET-1280 | PROJ-0951-CDET1-2.34.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Leslie (1) (Dexter & AEO Dexter) | 0 | 2021-09-23 | 2021-09-29
CDET-1680 | PROJ-0951-CDET1-2.21.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Linwood (2) (Monterey & Elmhurst) | 0 | 2021-09-23 | 2021-09-29
CDET-1855 | PROJ-0951-CDET1-2.42.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Cortland (1) (Linwood & AWO Linwood) | 0 | 2021-09-23 | 2021-09-29
CDET-1990 | PROJ-0951-CDET1-2.46.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Tuxedo Stub (AWO Linwood & Linwood) | 0 | 2021-09-23 | 2021-09-29
CDET-2215 | PROJ-0951-CDET1-2.51.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Wildemere (1) (Davison & ANO Davison) | 0 | 2021-09-23 | 2021-09-29
CDET-2300 | PROJ-0951-CDET1-2.52.53.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Wildemere (2) (Webb & Tuxedo) | 0 | 2021-09-23 | 2021-09-29
CDET-3620 | PROJ-0951-CDET1-2.24.3.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Waverly (1) (AEO Dexter & Dexter) | 0 | 2021-09-23 | 2021-09-29
CDET-11095 | PROJ-0951-CDET1-2.56.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Linwood (3) (Monterey & Richton) | 0 | 2021-09-23 | 2021-09-29
CDET-11325 | PROJ-0951-CDET1-2.57.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Monterey (2) (Linwood & Dexter) | 0 | 2021-09-23 | 2021-09-29
CDET-11785 | PROJ-0951-CDET1-2.59.53.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Wildemere (5) (Buena Vista & Glendale) | 0 | 2021-09-23 | 2021-09-29
CDET-12015 | PROJ-0951-CDET1-2.60.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (5) (Tyler & Buena Vista) | 0 | 2021-09-23 | 2021-09-29
CDET-12245 | PROJ-0951-CDET1-2.61.53.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Wildemere (4) (Tyler & Waverly) | 0 | 2021-09-23 | 2021-09-29
CDET-13605 | PROJ-0951-CDET1-2.67.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (7) (Clairmount & Collingwood) | 0 | 2021-09-23 | 2021-09-29
CDET-13835 | PROJ-0951-CDET1-2.68.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Dexter (8) (Collingwood & Clarimount) | 0 | 2021-09-23 | 2021-09-29
CDET-21060 | PROJ-0951-CDET1-2.32.1.2 | 2020 GRP - Carry Over - Central Detroit 1 | Restoration - Soft Surface - Ewald N (1) (Petoskey & Petoskey ) | 0 | 2021-09-23 | 2021-09-29
GP-14225 | PROJ-0951-GP 5 -3.35.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Jefferson North (Balfour & Ashland) | 0 | 2021-09-23 | 2021-09-29
GP-14265 | PROJ-0951-GP 5 -3.41.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - E Vernor Hwy 2 (Chalmers & City Limit) | 0 | 2021-09-23 | 2021-09-29
GP-14270 | PROJ-0951-GP 5 -3.42.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Vernor 2 (Maryland & EOM) | 0 | 2021-09-23 | 2021-09-29
GP-14420 | PROJ-0951-GP 5 -3.61.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Halley (Nottingham & Lakepointe) | 0 | 2021-09-23 | 2021-09-29
GP-14470 | PROJ-0951-GP 5 -3.69.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Lakepointe 2 (Kercheval & Jefferson) | 0 | 2021-09-23 | 2021-09-29
GP-14765 | PROJ-0951-GP 5 -3.104.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface -St Paul (Somerset & Beaconsfield) | 0 | 2021-09-23 | 2021-09-29
GP-45050 | PROJ-0951-GP 5 -3.3.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Beaconsfield 4 (Kercheval & ANO Kercheval) | 0 | 2021-09-23 | 2021-09-29
GP-46470 | PROJ-0951-GP 5 -3.10.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Notre Dame 1 GP4 (Kercheval & ANO Kercheval) | 0 | 2021-09-23 | 2021-09-29
GP-46690 | PROJ-0951-GP 5 -3.11.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - St. Clair 1 GP4 (ASO Kercheval & Kerchval) | 0 | 2021-09-23 | 2021-09-29
GP-46910 | PROJ-0951-GP 5 -3.7.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Alter (Klenk & Detroit City Limit) | 0 | 2021-09-23 | 2021-09-29
GP-47170 | PROJ-0951-GP 5 -3.114.3.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - ASO Kercheval (Lakepoint & Lakepointe ) | 0 | 2021-09-23 | 2021-09-29
WDET-195 | PROJ-0951-WDET9-4.15.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Alter Rd (Evergreen Rd & Artesian St) | 0 | 2021-09-23 | 2021-09-29
WDET-315 | PROJ-0951-WDET9-4.9.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Artesian (ASO W Warren & Warren) | 0 | 2021-09-23 | 2021-09-29
WDET-765 | PROJ-0951-WDET9-4.16.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Brace 3 (Paul & Ford) | 78 | 2021-09-23 | 2021-09-29
WDET-855 | PROJ-0951-WDET9-4.18.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Brooklawn Dr (Whitlock Ave & Whitlock Ave) | 0 | 2021-09-23 | 2021-09-29
WDET-900 | PROJ-0951-WDET9-4.19.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Brookwood (Forest & Williamsburg)) | 0 | 2021-09-23 | 2021-09-29
WDET-945 | PROJ-0951-WDET9-4.20.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Country Lane (Garling Dr & Garling Dr)) | 0 | 2021-09-23 | 2021-09-29
WDET-990 | PROJ-0951-WDET9-4.21.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Crestmont Lane (Whitlock Ave & Brooklawn Dr)) | 0 | 2021-09-23 | 2021-09-29
WDET-1215 | PROJ-0951-WDET9-4.26.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Fairview (Whitlock Ave & Whitlock Ave) | 0 | 2021-09-23 | 2021-09-29
WDET-1260 | PROJ-0951-WDET9-4.27.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Faust (Kirkwood & Paul) | 0 | 2021-09-23 | 2021-09-29
WDET-1440 | PROJ-0951-WDET9-4.31.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Forrest Hills (Ann Arbor Trail & Brookwood) | 0 | 2021-09-23 | 2021-09-29
WDET-1485 | PROJ-0951-WDET9-4.32.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Foxcraft (Brooklawn & Ann Arbor Trail) | 0 | 2021-09-23 | 2021-09-29
WDET-1530 | PROJ-0951-WDET9-4.33.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Garling (Ann Arbor Trail & Whitlock) | 0 | 2021-09-23 | 2021-09-29
WDET-1665 | PROJ-0951-WDET9-4.39.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Greenview 3 (Paul & Ford) | 3 | 2021-09-23 | 2021-09-29
WDET-1800 | PROJ-0951-WDET9-4.36.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Grandville 3 (Paul & Kirkwood) | 0 | 2021-09-23 | 2021-09-29
WDET-1845 | PROJ-0951-WDET9-4.40.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Heritage Ct (River Oaks & EOM) | 0 | 2021-09-23 | 2021-09-29
WDET-1935 | PROJ-0951-WDET9-4.42.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Heyden 2 (W Warren & Ann Arbor) | 0 | 2021-09-23 | 2021-09-29
WDET-1975 | PROJ-0951-WDET9-4.43.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Kirkwood 1 (Penrod & Rosemont) | 0 | 2021-09-23 | 2021-09-29
WDET-2020 | PROJ-0951-WDET9-4.44.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Kirkwood 2 (Piedmont & Southfield) | 0 | 2021-09-23 | 2021-09-29
WDET-2155 | PROJ-0951-WDET9-4.47.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Minock 3 (Paul & EOM) | 67 | 2021-09-23 | 2021-09-29
WDET-2200 | PROJ-0951-WDET9-4.48.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Old Colony Blvd (River Oaks & Evergreen) | 0 | 2021-09-23 | 2021-09-29
WDET-2370 | PROJ-0951-WDET9-4.7.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ann Arbor Trail North (Evergreen & Heyden) | 0 | 2021-09-23 | 2021-09-29
WDET-2640 | PROJ-0951-WDET9-4.58.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Piedmont 3 (Paul & Kirkwood) | 0 | 2021-09-23 | 2021-09-29
WDET-2730 | PROJ-0951-WDET9-4.61.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Plainview Ave 3 (Paul & Kirkwood) | 0 | 2021-09-23 | 2021-09-29
WDET-2775 | PROJ-0951-WDET9-4.62.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - River Oaks Dr (Williamsburg & Old Colony Blvd) | 3 | 2021-09-23 | 2021-09-29
WDET-2955 | PROJ-0951-WDET9-4.66.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Rosemont Ave 3 (Paul & Kirkwood) | 3 | 2021-09-23 | 2021-09-29
WDET-3000 | PROJ-0951-WDET9-4.67.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Rouge Ct (River Oaks Dr & EOM) | 0 | 2021-09-23 | 2021-09-29
WDET-3225 | PROJ-0951-WDET9-4.72.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Stahelin Ave 3 (Paul & Ford) | 0 | 2021-09-23 | 2021-09-29
WDET-3405 | PROJ-0951-WDET9-4.76.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Town Lane (Garling Dr & Garling Dr) | 54 | 2021-09-23 | 2021-09-29
WDET-3495 | PROJ-0951-WDET9-4.78.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Vaughan 2 (W Warren & Ann Arbor Trail) | 0 | 2021-09-23 | 2021-09-29
WDET-3855 | PROJ-0951-WDET9-4.86.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Warwick 3 (Paul & EOM) | 0 | 2021-09-23 | 2021-09-29
WDET-4035 | PROJ-0951-WDET9-4.90.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - whitlock (Fairview Dr & Heyden) - Dearborn Heights | 0 | 2021-09-23 | 2021-09-29
WDET-4125 | PROJ-0951-WDET9-4.92.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Williamsburg (River Oaks & EOM) | 0 | 2021-09-23 | 2021-09-29
WDET-4245 | PROJ-0951-WDET9-4.95.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - ASO Warren Ave 1 (Rosemont & Artesian) | 0 | 2021-09-23 | 2021-09-29
WDET-4315 | PROJ-0951-WDET9-4.95.2.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - ASO Warren Ave 2 (Warwick & Evergreen) | 0 | 2021-09-23 | 2021-09-29
WDET-4360 | PROJ-0951-WDET9-4.97.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Paul Ave - South (Evergreen & Artesian) | 0 | 2021-09-23 | 2021-09-29
WDET-4450 | PROJ-0951-WDET9-4.48.2.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Old Colony Blvd (River Oaks & Brookwood) | 0 | 2021-09-23 | 2021-09-29
WDET-4520 | PROJ-0951-WDET9-4.4.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ann Arbor Trail - South (Forrest Hills & EOM)- Detroit | 0 | 2021-09-23 | 2021-09-29
WDET-5060 | PROJ-0951-WDET9-4.39.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Greenview 3 (Paul & Ford) | 0 | 2021-09-23 | 2021-09-29
WDET-5310 | PROJ-0951-WDET9-4.66.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Crossroad Center (Ford & EOM) | 0 | 2021-09-23 | 2021-09-29
WDET-5400 | PROJ-0951-WDET9-4.72.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Stahelin 3 (Paul & Ford) | 0 | 2021-09-23 | 2021-09-29
WDET-14035 | PROJ-0951-WDET9-4.5.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Westwood 2 (ASO W Warren & Paul) | 0 | 2021-09-23 | 2021-09-29
WDET-1710 | PROJ-0951-WDET9-4.38.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Greenview 2 (W Warren & Paul ) | 0 | 2021-09-23 | 2021-09-29
WDET-2110 | PROJ-0951-WDET9-4.46.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Minock 2 (W Warren & Paul ) | 0 | 2021-09-23 | 2021-09-29
WDET-2330 | PROJ-0951-WDET9-4.51.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Paul Ave North (Ashton & Evergreen) | 0 | 2021-09-23 | 2021-09-29
WDET-4275 | PROJ-0951-WDET9-4.96.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ford (Greenview & Artesian) | 7 | 2021-09-23 | 2021-09-29
WDET-5280 | PROJ-0951-WDET9-4.60.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Plainview Rd (W Warren & Paul ) | 0 | 2021-09-23 | 2021-09-29
WDET-1305 | PROJ-0951-WDET9-4.28.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Faust (W Warren & Paul ) | 0 | 2021-09-23 | 2021-09-29
WDET-2910 | PROJ-0951-WDET9-4.57.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Grandville 2 (W Warren & Paul ) | 3 | 2021-09-23 | 2021-09-29
WDET-2460 | PROJ-0951-WDET9-4.54.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Penrod 2 (W Warren & Paul ) | 0 | 2021-09-23 | 2021-09-29
WDET-3915 | PROJ-0951-WDET9-4.65.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Piedmont (W Warren & Paul ) | 0 | 2021-09-23 | 2021-09-29
WDET-3930 | PROJ-0951-WDET9-4.71.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Stahelin Ave 2 (W Warren & Paul ) | 0 | 2021-09-23 | 2021-09-29
WDET-6360 | PROJ-0951-WDET9-4.71.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Stahelin 2 (W Warren & Paul) | 0 | 2021-09-23 | 2021-09-29
WDET-14230 | PROJ-0951-WDET9-4.14.65.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - W Warren (Ashton & Evergreen) | 3 | 2021-09-23 | 2021-09-29
WDET-14470 | PROJ-0951-WDET9-4.103.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Sawyer St 2 (Ashton & Rosemont) | 0 | 2021-09-23 | 2021-09-29
WDET-14950 | PROJ-0951-WDET9-4.105.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Rosemont Ave 1 (ASO Warren & Paul) | 0 | 2021-09-23 | 2021-09-29
WDET-15190 | PROJ-0951-WDET9-4.106.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Warwick 2 (Paul & W Warren) | 94 | 2021-09-23 | 2021-09-29
WDET-15250 | PROJ-0951-WDET9-4.106.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Warwick 1 (Tireman & W Warren) | 0 | 2021-09-23 | 2021-09-29
WDET-585 | PROJ-0951-WDET9-4.12.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Auburn 2 (Paul & EOM) | 0 | 2021-09-23 | 2021-09-29
WDET-4790 | PROJ-0951-WDET9-4.12.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Auburn 2 (W Warren & Paul) | 87 | 2021-09-23 | 2021-09-29
WDET-16440 | PROJ-0951-WDET9-4.7.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ann Arbor Trail North (Heyden & EOM) | 33 | 2021-09-23 | 2021-09-29
WDET-16960 | PROJ-0951-WDET9-4.11.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Williamsburg (Old Colony & Brookwood) | 0 | 2021-09-23 | 2021-09-29
WDET-17600 | PROJ-0951-WDET9-4.6.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Penrod 2 (Dayton & Paul) | 0 | 2021-09-23 | 2021-09-29
WDET-18010 | PROJ-0951-WDET9-4.14.13.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - W Warren (Artesian & Warwick) | 3 | 2021-09-23 | 2021-09-29
WDET-18140 | PROJ-0951-WDET9-4.4.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Ann Arbor Trail - South (Forest Hills & Evergreen)- Detroit | 0 | 2021-09-23 | 2021-09-29
WDET-18620 | PROJ-0951-WDET9-4.23.2.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Evergreen 2 (ASO W Warren & Paul) | 0 | 2021-09-23 | 2021-09-29
WDET-18860 | PROJ-0951-WDET9-4.97.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Paul Ave - South (Crossing at Grandville) | 0 | 2021-09-23 | 2021-09-29
WDET-18940 | PROJ-0951-WDET9-4.97.2.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Paul Ave - South (Crossing at Rosemont) | 0 | 2021-09-23 | 2021-09-29
WDET-19010 | PROJ-0951-WDET9-4.14.1.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - W Warren (Heyden & EOM) | 3 | 2021-09-23 | 2021-09-29
WDET-19080 | PROJ-0951-WDET9-4.14.2.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - W Warren (W Warren & Pierson) | 3 | 2021-09-23 | 2021-09-29
WDET-19310 | PROJ-0951-WDET9-4.95.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - ASO Warren Ave 2 (Evergreen & Heyden) | 0 | 2021-09-23 | 2021-09-29
WDET-19580 | PROJ-0951-WDET9-4.17.2.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Artesian (ASO W Warren & Warren) | 0 | 2021-09-23 | 2021-09-29
WDET-19670 | PROJ-0951-WDET9-4.86.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Warwick (Paul & EOM) | 0 | 2021-09-23 | 2021-09-29
WDET-19760 | PROJ-0951-WDET9-4.42.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Heyden 2 (W Warren & Ann Arbor) | 0 | 2021-09-23 | 2021-09-29
WDET-19830 | PROJ-0951-WDET9-4.14.3.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - W Warren (W Warren & Garling) | 3 | 2021-09-23 | 2021-09-29
WDET-19920 | PROJ-0951-WDET9-4.15.3.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Alter Rd (Evergreen & Altar) | 0 | 2021-09-23 | 2021-09-29
WDET-20200 | PROJ-0951-WDET9-4.17.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Artesian (Whitlock & Paul) | 0 | 2021-09-23 | 2021-09-29
WDET-20260 | PROJ-0951-WDET9-4.17.1.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Artesian (Whitlock & W Warren) | 0 | 2021-09-23 | 2021-09-29
WDET-20500 | PROJ-0951-WDET9-4.33.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Garling (Whitlock & Town Lane) | 0 | 2021-09-23 | 2021-09-29
WDET-20580 | PROJ-0951-WDET9-4.33.2.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Garling (Town Lane & W Warren) | 0 | 2021-09-23 | 2021-09-29
WDET-20860 | PROJ-0951-WDET9-4.19.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Brookwood (Old Colony & Forest Hills)) | 0 | 2021-09-23 | 2021-09-29
WDET-21110 | PROJ-0951-WDET9-4.13.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - River Oaks Shopping CTR (River Oaks & Brookwood) | 3 | 2021-09-23 | 2021-09-29
WDET-22490 | PROJ-0951-WDET9-4.22.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Kirkwood 2 (Evergreen & Grandville) | 0 | 2021-09-23 | 2021-09-29
WDET-22870 | PROJ-0951-WDET9-4.97.4.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Paul Ave - South (Artesian & Ashton) | 0 | 2021-09-23 | 2021-09-29
WDET-22970 | PROJ-0951-WDET9-4.16.2.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Brace (Paul & W Warren) | 98 | 2021-09-23 | 2021-09-29
WDET-23190 | PROJ-0951-WDET9-4.27.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Faust (Kirkwood & Greenview) | 58 | 2021-09-23 | 2021-09-29
WDET-23440 | PROJ-0951-WDET9-4.6.3.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Penrod 2 (Dayton & Kirkwood) | 3 | 2021-09-23 | 2021-09-29
WDET-23530 | PROJ-0951-WDET9-4.24.1.1 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Cross Center Dr (Faust & EOM) | 1 | 2021-09-23 | 2021-09-29
WDET-23920 | PROJ-0951-WDET9-4.25.1.2 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Kirkwood 1 (Penrod & Faust) | 0 | 2021-09-23 | 2021-09-29
WDET-24230 | PROJ-0951-WDET9-4.17.4.3 | 2020 GRP - Carry Over - West Detroit 9 | Restoration - Soft Surface - Artesian (Ford & Paul) | 0 | 2021-09-23 | 2021-09-29
ND2-22120 | PROJ-0951-NDET2-2.10.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Outer Drive Insert (Van Dyke & EOM) | 0 | 2021-09-23 | 2021-09-29
ND2-24450 | PROJ-0951-NDET2-2.33.6.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Sherwood St (2) (Outer Drive & Outer Drive) | 0 | 2021-09-23 | 2021-09-29
ND2-24870 | PROJ-0951-NDET2-2.6.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Outer Dr (Abandonment) (Conner & 7 Mile )t | 3 | 2021-09-23 | 2021-09-29
ND2-25090 | PROJ-0951-NDET2-2.6.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - E Outer Dr (Abandonment) (Regulator Station to Outer Dr | 0 | 2021-09-23 | 2021-09-29
ND2-16810 | PROJ-0951-NDET2-2.28.3.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Rogge St (3) (Bliss Ave & 7 Mile Rd | 0 | 2021-09-23 | 2021-09-29
ND2-18880 | PROJ-0951-NDET2-2.31.1.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Sherwood (Savage & E Outer Dr) | 39 | 2021-09-23 | 2021-09-29
ND2-25870 | PROJ-0951-NDET2-2.28.4.2 | 2020 GRP - Carry Over - North Detroit 2 | Restoration - Soft Surface - Rogge St (3) (Bliss Ave & 7 Mile Rd | 0 | 2021-09-23 | 2021-09-29
Euclid 1720 | PROJ-0951-MUN-3.7.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - ASO Vernor (Clark Ave & McKinstry St) | 0 | 2021-09-23 | 2021-09-28
NDET3-8150 | GRP-2021-ND3.9.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (3) (Filer & Conrail RR) | 0 | 2021-09-23 | 2021-09-28
CDET2-11000 | GRP-2021-CDet2.37.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Euclid 2 (Rosa Parks & Rosa Parks | 0 | 2021-09-23 | 2021-09-28
NDET3-8480 | GRP-2021-ND3.88.2.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Gallagher St & Gallagher St) | 0 | 2021-09-23 | 2021-09-28
NDET3-8550 | GRP-2021-ND3.88.4.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Revere St & Revere St) | 0 | 2021-09-23 | 2021-09-28
NDET3-8620 | GRP-2021-ND3.88.5.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Norwood St & Norwood St) | 0 | 2021-09-23 | 2021-09-28
NDET3-8690 | GRP-2021-ND3.12.6.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Sunset St & Shields St) | 0 | 2021-09-23 | 2021-09-28
NDET3-8760 | GRP-2021-ND3.12.7.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Justine Ave & Eureka St) | 0 | 2021-09-23 | 2021-09-28
NDET3-8830 | GRP-2021-ND3.12.8.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Healy St & Lamont Ave) | 0 | 2021-09-23 | 2021-09-28
NDET3-8900 | GRP-2021-ND3.12.9.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Lamont Ave & Fenelon Ave) | 0 | 2021-09-23 | 2021-09-28
NDET3-8970 | GRP-2021-ND3.12.10.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Conley Ave & Keys&ne Ave) | 0 | 2021-09-23 | 2021-09-28
NDET3-9040 | GRP-2021-ND3.12.11.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Keystone Ave) | 0 | 2021-09-23 | 2021-09-28
NDET3-9110 | GRP-2021-ND3.9.12.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Dwyer St & Dwyer St) | 0 | 2021-09-23 | 2021-09-28
NDET3-9320 | GRP-2021-ND3.9.15.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (At Albany Ave) | 0 | 2021-09-23 | 2021-09-28
CDET2-11180 | GRP-2021-CDet2.51.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Wildemere 3 (Pingree & Pingree) | 0 | 2021-09-23 | 2021-09-28
CDET2-11330 | GRP-2021-CDet2.53.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - AEO Linwood (Clairmount & Clairmount) | 0 | 2021-09-23 | 2021-09-28
Muni7310 | PROJ-0951-MUN-2.3.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Wyoming (ANO Chicago & Chicago) | 0 | 2021-09-23 | 2021-09-23
Muni12030 | PROJ-0951-MUN-2.32.3.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ASO W Warren Ave (1) (24' EWPL Archdale St & 4' WEPL Archdale St) | 0 | 2021-09-23 | 2021-09-23
CDET2-11370 | GRP-2021-CDet2.47.3 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - Lawton 1 (W Boston & W Chicago) | 0 | 2021-09-23 | 2021-09-28
EDET1 508666 | GRP-2021-ED1.11.8.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (3) (E Warren & ASO Warren) | 0 | 2021-09-23 | 2021-09-28
NCDET - 25585 | NEWPROJ-6.3.2.2 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Birwood (ANO Fenkell & Fenkell) | 54 | 2021-09-23 | 2021-09-29
EDET1 508776 | GRP-2021-ED1.13.1 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bremen (1) (Barham st & Beaconsfield st) | 0 | 2021-09-23 | 2021-09-28
EDET1 508866 | GRP-2021-ED1.18.12.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Kensigton | 0 | 2021-09-23 | 2021-09-28
RR1 5436 | GRP-2021-RR1.22.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Florence St (W Jefferson & Haltiner) | 4 | 2021-09-24 | 2021-09-29
RR1 5440 | GRP-2021-RR1.27.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Le Blanc (Haltiner & W Jefferson) | 4 | 2021-09-24 | 2021-09-29
RR1 5448 | GRP-2021-RR1.35.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Cicotte St (Dwight & W Jefferson) | 4 | 2021-09-24 | 2021-09-29
RR1 5451 | GRP-2021-RR1.38.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Oak St (EOM & W Jefferson) | 4 | 2021-09-24 | 2021-09-29
WCDET1-5010 | GRP-2021-WCDet1.48.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 2 (Bourke & Doris) | 0 | 2021-09-24 | 2021-09-29
CDET2-5400 | GRP-2021-CDet2.52.1.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - 14th 1 (Pingree & W Euclid) | 0 | 2021-09-24 | 2021-09-29
RR1 5475 | GRP-2021-RR1.62.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Oak St (W Jefferson & 4' EWPL Burke St) | 4 | 2021-09-24 | 2021-09-29
RR1 51533 | GRP-2021-RR1.68.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Forest St (W Jefferson Ave & Genessee St) | 4 | 2021-09-24 | 2021-09-29
RR1 51671 | GRP-2021-RR1.82.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - High St 1 (River Rouge City Limits & W Josephine St) | 4 | 2021-09-24 | 2021-09-29
RR1 51682 | GRP-2021-RR1.94.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Union St (High & W Jefferson) | 4 | 2021-09-24 | 2021-09-29
RR1 51685 | GRP-2021-RR1.97.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Glenwood Ave (420' WWPL W Jefferson Ave & 12' WWPL W Jefferson Ave) | 4 | 2021-09-24 | 2021-09-29
SWDET2-2295 | PROJ-0951-SWDET2.8.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - ASO W Vernor 1 (Woodmere & Lawndale) | 4 | 2021-09-24 | 2021-09-29
SWDET2-2775 | PROJ-0951-SWDET2.14.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Central 2 (NO Dix & Dix) | 4 | 2021-09-24 | 2021-09-29
SWDET2-7415 | PROJ-0951-SWDET2.72.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cabot (NO Woodmere & Woodmere) | 4 | 2021-09-24 | 2021-09-29
RR1 271 | GRP-2021-RR1.3.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Francis Riopelle Ave (Richter St & EOM) | 4 | 2021-09-24 | 2021-09-29
SWDET2-9005 | PROJ-0951-SWDET2.5.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Fort (EO Distal & Elsmere) | 4 | 2021-09-24 | 2021-09-29
SWDET2-11545 | PROJ-0951-SWDET2.17.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 1E (Chamberlain & Witt) | 4 | 2021-09-24 | 2021-09-29
EDET1 501576 | GRP-2021-ED1.21.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Bishop St (1) (ASO E Warrern Ave & Waveney St) | 0 | 2021-09-24 | 2021-09-29
WCDET1-11030 | GRP-2021-WCDet1.48.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 2 (Intervale & Ewald) | 0 | 2021-09-24 | 2021-09-29
RR1 53020 | GRP-2021-RR1.50.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Burke 1 (4' SNPL Coolidge Hwy & 2' NSPL Coolidge Hwy) | 4 | 2021-09-24 | 2021-09-29
WCDET1-12080 | GRP-2021-WCDet1.30.4.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Buena Vista 1 (Stoepel & Livernois) | 0 | 2021-09-24 | 2021-09-29
RR1 56060 | GRP-2021-RR1.62.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Oak St (4' EWPL Burke St & 2' WEPL Burke St) | 4 | 2021-09-24 | 2021-09-29
RR1 57100 | GRP-2021-RR1.69.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Genenssee St 2 (5' SNPL Forest St & 4' NSPL Forest St) | 4 | 2021-09-24 | 2021-09-29
AP 3670 | PROJ-0951-MMOAllen.31.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Goddard (Allen & 500' East Of Becker) | 4 | 2021-09-24 | 2021-09-29
AP 3860 | PROJ-0951-MMOAllen.50.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Melbourne 1 (Southway & Goddard) | 4 | 2021-09-24 | 2021-09-29
RR1 60350 | GRP-2021-RR1.2.6.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (3' WEPL W Jefferson Ave & 0' WWPL W Jefferson Ave) | 4 | 2021-09-24 | 2021-09-29
RR1 60670 | GRP-2021-RR1.2.10.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (2' WEPL Burke St & 3' NSPL Maple St) | 4 | 2021-09-24 | 2021-09-29
RR1 60910 | GRP-2021-RR1.2.13.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (E Great Lakes St & 5' NSPL W Great Lakes St) | 4 | 2021-09-24 | 2021-09-29
RR1 60990 | GRP-2021-RR1.2.14.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (5' EWPL W Jefferson Ave & 4' WEPL W Jefferson Ave) | 4 | 2021-09-24 | 2021-09-29
RR1 61150 | GRP-2021-RR1.2.16.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (Neiman St & 118' NNPL Cora St) | 4 | 2021-09-24 | 2021-09-29
RR1 61230 | GRP-2021-RR1.2.17.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (Stoner St & Forest St) | 4 | 2021-09-24 | 2021-09-29
RR1 61390 | GRP-2021-RR1.2.19.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (Forest St & River Rouge City Limits) | 4 | 2021-09-24 | 2021-09-29
AA3-5960 | GRP-2021-RR1.7.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (2) (133' SSPL Rockwood & W Glenwood) | 4 | 2021-09-24 | 2021-09-29
AA3-6030 | GRP-2021-RR1.7.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (2) (82' NNPL Ridge & 265' NNPL W Charlotte) | 4 | 2021-09-24 | 2021-09-29
RR1 61650 | GRP-2021-RR1.10.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Outer Dr (High St & 252' EEPL High St) | 4 | 2021-09-24 | 2021-09-29
SWDET2-16505 | PROJ-0951-SWDET2.25.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Elsmere 2 (Olivet & Witt) | 4 | 2021-09-24 | 2021-09-29
SWDET2-16665 | PROJ-0951-SWDET2.25.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Elsmere 2 (Witt & Fort) | 4 | 2021-09-24 | 2021-09-29
RR1 7691 | GRP-2021-RR.30.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Grand River (61' NNPL Whitney & Whitney) | 0 | 2021-09-24 | 2021-09-29
EDET1 502836 | GRP-2021-ED1.80.2.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO E Warren Ave (2) (Neff Ave & Hereford St) | 0 | 2021-09-24 | 2021-09-29
EDET1 503396 | GRP-2021-ED1.11.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (3) (Grayton St & Harvard Rd) | 0 | 2021-09-24 | 2021-09-29
EDET1 503636 | GRP-2021-ED1.11.6.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (3) (Neff Ave & Hereford St) | 0 | 2021-09-24 | 2021-09-29
EDET1 504686 | GRP-2021-ED1.18.4.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) (Cadieux Rd & ANO E Warren Ave) | 0 | 2021-09-24 | 2021-09-29
EDET1 504766 | GRP-2021-ED1.18.5.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) (Cadieux Dr & ASO E Warren Ave) | 0 | 2021-09-24 | 2021-09-29
EDET1 504846 | GRP-2021-ED1.18.6.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) (ANO E Warren Ave & E Warren Ave @ Woodhall St) | 0 | 2021-09-24 | 2021-09-29
EDET1 504926 | GRP-2021-ED1.18.7.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) (E Warren Ave & ASO E Warren Ave @ Woodhall St (West Side)) | 0 | 2021-09-24 | 2021-09-29
EDET1 505006 | GRP-2021-ED1.18.8.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) (Caduiex St & Neff Ave) | 0 | 2021-09-24 | 2021-09-29
EDET1 505086 | GRP-2021-ED1.18.9.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) S (Woodhall St & Neff Ave) | 0 | 2021-09-24 | 2021-09-29
EDET1 505776 | GRP-2021-ED1.3.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Mack Ave (Alter Rd & Alter Rd) | 0 | 2021-09-24 | 2021-09-29
RR1 11051 | GRP-2021-RR.62.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Nevada (WO Moenart & Bloom) | 0 | 2021-09-24 | 2021-09-29
NDET3-7465 | GRP-2021-ND3.1.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 8 Mile Rd (M102) (1) (Harned St & Sunset St) | 0 | 2021-09-24 | 2021-09-29
NDET3-6560 | GRP-2021-ND3.11.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - ANO 7 Mile Rd (3) (Bloom & Mound Rd)) | 0 | 2021-09-24 | 2021-09-29
NDET3-6845 | GRP-2021-ND3.17.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Filer Ave (1) (E Outer Dr & EOM) | 0 | 2021-09-24 | 2021-09-29
NDET3-5120 | GRP-2021-ND3.22.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - St Louis Ave (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-09-24 | 2021-09-29
NDET3-5460 | GRP-2021-ND3.56.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Fenelon Ave (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 2021-09-24 | 2021-09-29
NDET3-5675 | GRP-2021-ND3.58.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Hamlet St (2) (Fenelon Ave & Mound Rd) | 0 | 2021-09-24 | 2021-09-29
NDET3-7525 | GRP-2021-ND3.63.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Binder St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 2021-09-24 | 2021-09-29
NDET3-880 | GRP-2021-ND3.65.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Charest St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 2021-09-24 | 2021-09-29
NDET3-545 | GRP-2021-ND3.78.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mitchell St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 2021-09-24 | 2021-09-29
NDET3-7500 | GRP-2021-ND3.80.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Norwood St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 2021-09-24 | 2021-09-29
NDET3-7490 | GRP-2021-ND3.81.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Norwood St (2) (E Outer Dr & 7 Mile Rd) | 0 | 2021-09-24 | 2021-09-29
NDET3-4390 | GRP-2021-ND3.88.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (1) (Harned St & Mitchell St) | 0 | 2021-09-24 | 2021-09-29
NDET3-515 | GRP-2021-ND3.97.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - E Lantz Ave (1) (Keystone & Bloom) | 0 | 2021-09-24 | 2021-09-29
NDET3-6230 | GRP-2021-ND3.102.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Emery St (Buffalo St & Caldwell St) | 0 | 2021-09-24 | 2021-09-29
NDET3-6200 | GRP-2021-ND3.45.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 8 Mile Rd (2) (Mound Rd & Dwyer St) | 0 | 2021-09-24 | 2021-09-29
NDET3-5680 | GRP-2021-ND3.58.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Hamlet St (2) (Mound Rd & Dwyer St) | 0 | 2021-09-24 | 2021-09-29
NDET3-6070 | GRP-2021-ND3.20.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mt Elliote St (1) (Mt Elliot & Mt Elliot) | 0 | 2021-09-24 | 2021-09-29
NDET3-6045 | GRP-2021-ND3.20.2.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mt Elliote St (1) (8 Mile Rd (M102) & 8 Mile Rd (M102) 2) | 0 | 2021-09-24 | 2021-09-29
NDET3-4715 | GRP-2021-ND3.20.4.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mt Elliote St (1) (E Outer Dr & E Outer Dr) | 0 | 2021-09-24 | 2021-09-29
NDET3-805 | GRP-2021-ND3.3.2.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Crossing At Harned St) | 0 | 2021-09-24 | 2021-09-29
NDET3-810 | GRP-2021-ND3.3.4.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Crossing At Mitchell St) | 0 | 2021-09-24 | 2021-09-29
NDET3-815 | GRP-2021-ND3.3.5.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Crossing At Norwood St) | 0 | 2021-09-24 | 2021-09-29
NDET3-820 | GRP-2021-ND3.3.6.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Crossing At Sunset St) | 0 | 2021-09-24 | 2021-09-29
NDET3-825 | GRP-2021-ND3.3.7.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Crossing At Fenelon Ave) | 0 | 2021-09-24 | 2021-09-29
NDET3-840 | GRP-2021-ND3.3.10.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (From Mt Elliot St & Filer Ave) | 0 | 2021-09-24 | 2021-09-29
NDET3-845 | GRP-2021-ND3.3.11.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Filer Ave & EOM) | 0 | 2021-09-24 | 2021-09-29
NDET3-6525 | GRP-2021-ND3.11.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - ANO 7 Mile Rd (3) (Mound Rd & Mt Elliott) | 0 | 2021-09-24 | 2021-09-29
NDET3-6465 | GRP-2021-ND3.11.2.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - ANO 7 Mile Rd (3) (Mt Elliott & Filer Ave) | 0 | 2021-09-24 | 2021-09-29
RR1 11411 | GRP-2021-FR.65.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Rohns (Mack & Goethe) | 0 | 2021-09-24 | 2021-09-29
RR1 10891 | GRP-2021-FR.59.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Mack (Crane & McClellan) | 0 | 2021-09-24 | 2021-09-29
GP-45290 | PROJ-0951-GP 5 -3.67.3.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Klenk (Balfour & Cadieux) | 0 | 2021-09-24 | 2021-09-30
Muni5170 | PROJ-0951-MUN-3.20.1.2 | 2020 GRP - Carry Over - Municipality | Restoration - Soft Surface - Linwood 7 (Longfellow & Joy) | 3 | 2021-09-24 | 2021-09-28
NDET3-8000 | GRP-2021-ND3.9.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 7 Mile Rd (3) (Sherwood & Conrail RR) | 0 | 2021-09-24 | 2021-09-29
WCDET1-8290 | GRP-2021-WCDet1.10.4.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd West (Stoepel & Stoepel) | 0 | 2021-09-24 | 2021-09-30
WCDET1-11760 | GRP-2021-WCDet1.30.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Buena Vista 1 (Turner & Ewald) | 0 | 2021-09-24 | 2021-09-30
WCDET1-11920 | GRP-2021-WCDet1.30.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Buena Vista 1 (Ewald & Stoepel) | 0 | 2021-09-24 | 2021-09-30
RR1 5429 | GRP-2021-RR1.15.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Cora (5' WEPL Haltiner St & 11' EWPL W Jefferson Ave) | 4 | 2021-09-27 | 2021-09-30
RR1 5444 | GRP-2021-RR1.31.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Nieman (Haltiner & W Jefferson) | 4 | 2021-09-27 | 2021-09-30
RR1 5471 | GRP-2021-RR1.58.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Coolidge Hwy 2 (W Jefferson & Burke St) | 4 | 2021-09-27 | 2021-09-30
RR1 51753 | GRP-2021-RR1.104.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Rockwood Ave (W Jefferson Ave & Ironton Ave) | 4 | 2021-09-27 | 2021-09-30
EDET1 50707 | GRP-2021-ED1.9.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (1) (Alter Rd& Chatsworth St) | 0 | 2021-09-27 | 2021-09-30
EDET1 50709 | GRP-2021-ED1.11.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (3) (E Outer Dr & Bishop St) | 0 | 2021-09-27 | 2021-09-30
EDET1 50716 | GRP-2021-ED1.18.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren Ave (3) S (Bishop St & Grayton St) | 0 | 2021-09-27 | 2021-09-30
SWDET2-2215 | PROJ-0951-SWDET2.7.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - ANO W Vernor (Woodmere & Norman) | 4 | 2021-09-27 | 2021-09-30
SWDET2-2455 | PROJ-0951-SWDET2.10.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor 2 (Dearborn City Limit & Woodmere) | 4 | 2021-09-27 | 2021-09-30
SWDET2-3495 | PROJ-0951-SWDET2.24.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Elsmere 1 (Woodmere & Avis) | 4 | 2021-09-27 | 2021-09-30
SWDET2-3975 | PROJ-0951-SWDET2.30.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Witt (EOM & Elsmere) | 4 | 2021-09-27 | 2021-09-30
SWDET2-4135 | PROJ-0951-SWDET2.32.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 4 (Mandale & Avis) | 4 | 2021-09-27 | 2021-09-30
SWDET2-7575 | PROJ-0951-SWDET2.74.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 2 (NO Woodmere & Woodmere) | 4 | 2021-09-27 | 2021-09-30
AA3-5610 | GRP-2021-RR1.7.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (2) (River Rouge City Limits & E Glenwood) | 4 | 2021-09-27 | 2021-09-30
SWDET2-9085 | PROJ-0951-SWDET2.5.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Fort (Elsmere & EOM) | 4 | 2021-09-27 | 2021-09-30
RR1 52700 | GRP-2021-RR1.50.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Burke 1 (4' SNPL E Pleasant St & 3' SNPL Delisle St) | 4 | 2021-09-27 | 2021-09-30
RR1 53180 | GRP-2021-RR1.50.5.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Burke 1 (2' NSPL Coolidge Hwy & 2' NSPL W Oak St) | 4 | 2021-09-27 | 2021-09-30
RR1 53340 | GRP-2021-RR1.50.6.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Burke 1 (2' NSPL W Oak St & 3' NSPL Maple St) | 4 | 2021-09-27 | 2021-09-30
RR1 53500 | GRP-2021-RR1.67.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Cattherine St (38' WWPL Ironton St & Ironton St) | 4 | 2021-09-27 | 2021-09-30
RR1 55020 | GRP-2021-RR1.59.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Great Lakes St (4' WEPL Richter St & 4' WEPL AWO Goodell St) | 4 | 2021-09-27 | 2021-09-30
RR1 60270 | GRP-2021-RR1.2.5.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (Myrtle St & 12' SSPL Myrtle St) | 4 | 2021-09-27 | 2021-09-30
RR1 60510 | GRP-2021-RR1.2.8.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (Coolidge Hwy & Oak St) | 4 | 2021-09-27 | 2021-09-30
RR1 60750 | GRP-2021-RR1.2.11.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (Maple St & E Great Lakes St) | 4 | 2021-09-27 | 2021-09-30
RR1 60830 | GRP-2021-RR1.2.12.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (4' NSPL Burke St & W Great Lakes St) | 4 | 2021-09-27 | 2021-09-30
SWDET2-22405 | PROJ-0951-SWDET2.77.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pearl (ANO W Vernor & EOM) | 4 | 2021-09-27 | 2021-09-30
SWDET2-23625 | PROJ-0951-SWDET2.81.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 3 (Witt & Fort) | 4 | 2021-09-27 | 2021-09-30
RR1 8411 | GRP-2021-RR.39.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Fairport (E McNichols & Gratiot) | 0 | 2021-09-27 | 2021-09-30
EDET1 502706 | GRP-2021-ED1.80.3.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO E Warren Ave (2) (E Warren Ave & Woodshall St) | 0 | 2021-09-27 | 2021-09-30
NDET3-6595 | GRP-2021-ND3.10.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - ANO 7 Mile Rd (2) (Ryan Rd & Bloom St) | 0 | 2021-09-27 | 2021-09-30
NDET3-6130 | GRP-2021-ND3.20.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mt Elliote St (1) (8 Mile Rd (M102) & 8 Mile Rd (M102)) | 0 | 2021-09-27 | 2021-09-30
NDET3-7180 | GRP-2021-ND3.41.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Ryan Rd (2) (E Outer Dr & Emery St) | 0 | 2021-09-27 | 2021-09-30
NDET3-4210 | GRP-2021-ND3.57.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Hamlet St (1) (Ryan Rd & Sunset St) | 0 | 2021-09-27 | 2021-09-30
NDET3-6695 | GRP-2021-ND3.91.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - ANO 7 Mile Rd (1) (Mitchell St & Ryan St) | 0 | 2021-09-27 | 2021-09-30
NDET3-7205 | GRP-2021-ND3.41.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Ryan Rd (2) (Ryan Rd & Ryan Rd) | 0 | 2021-09-27 | 2021-09-30
NDET3-7210 | GRP-2021-ND3.41.2.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Ryan Rd (2) (Emery St & ANO 7 Mile Rd) | 0 | 2021-09-27 | 2021-09-30
RR1 11481 | GRP-2021-FR.66.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Holcomb (Mack & 74' SSPL Mack) | 0 | 2021-09-27 | 2021-09-30
WCDET1-3570 | GRP-2021-WCDet1.30.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Buena Vista 1 (Turner & Turner) | 0 | 2021-09-27 | 2021-10-01
WCDET1-8210 | GRP-2021-WCDet1.10.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd South 1 (Stoepel & EOM) | 0 | 2021-09-27 | 2021-10-01
SWDET2-10232 | GRP-2021-WCDet1.56.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Quincy 1 (EOM & John C Lodge Services Dr) | 0 | 2021-09-27 | 2021-10-01
Ypsi 3-5390 | PROJ-0951-YSP3.14.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - 94 Service Drive (Eugene & Gates) | 5 | 2021-09-28 | 2021-10-04
Ypsi 3-2270 | PROJ-0951-YSP3.42.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - State (McCartney & Desoto) | 5 | 2021-09-28 | 2021-10-04
GP-14525 | PROJ-0951-GP 5 -3.131.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Mack North 2 (Balfour & Cadieux) | 0 | 2021-09-28 | 2021-10-01
WCDET1-1810 | GRP-2021-WCDet1.7.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Broadstreet (Waverly & Buena Vista) | 0 | 2021-09-28 | 2021-10-01
WCDET1-3170 | GRP-2021-WCDet1.25.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd North 1(Prairie & Stoepel) | 0 | 2021-09-28 | 2021-10-01
RR1 51531 | GRP-2021-RR1.66.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Alexander 1 (139' SSPL E Great Lakes St & Abbott St) | 4 | 2021-09-28 | 2021-10-01
AA4 20770 | GRP-2021-AA4.28.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Jefferson St North (12' EWPL 5Th St & S 1St St) | 0 | 2021-09-28 | 2021-10-04
EDET1 50708 | GRP-2021-ED1.10.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (2) (Chatsworth St & E Outer Dr) | 0 | 2021-09-28 | 2021-10-01
SWDET2-3415 | PROJ-0951-SWDET2.22.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Distel (Olivet & Fort) | 4 | 2021-09-28 | 2021-10-01
SWDET2-3655 | PROJ-0951-SWDET2.26.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Fulton (EOM & Elsmere) | 4 | 2021-09-28 | 2021-10-01
SWDET2-4855 | PROJ-0951-SWDET2.41.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lane 1 (Woodmere & Elsmere) | 4 | 2021-09-28 | 2021-10-01
SWDET2-13485 | PROJ-0951-SWDET2.26.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Fulton (Elsmere & EOM) | 4 | 2021-09-28 | 2021-10-01
RR1 52860 | GRP-2021-RR1.50.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Burke 1 (3' SNPL Delisle St & 4' SNPL Coolidge Hwy) | 4 | 2021-09-28 | 2021-10-01
WCDET1-12400 | GRP-2021-WCDet1.40.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Buena Vista 2 (Livernois & Broadstreet) | 0 | 2021-09-28 | 2021-10-01
RR1 55900 | GRP-2021-RR1.53.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E James South (3' WEPL Burke St & 8' EWPL Harris St) 2" | 4 | 2021-09-28 | 2021-10-01
RR1 58820 | GRP-2021-RR1.56.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Richter (Lorey St & Maple St) | 4 | 2021-09-28 | 2021-10-01
Ypsi 3-11700 | PROJ-0951-YSP3.3.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - S Outerlane Dr (8' SSPL State St & EOM) | 5 | 2021-09-28 | 2021-10-04
SWDET2-13955 | PROJ-0951-SWDET2.30.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Witt (Elsmere & Lawndale) | 4 | 2021-09-28 | 2021-10-01
SWDET2-22245 | PROJ-0951-SWDET2.28.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Olivet (Lawndale & EOM) | 4 | 2021-09-28 | 2021-10-01
RR1 6951 | GRP-2021-RR.20.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - ANO E Grand (John R & Melrose) | 0 | 2021-09-28 | 2021-10-01
RR1 7031 | GRP-2021-RR.21.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Dwyer (Charles & Casemere) | 0 | 2021-09-28 | 2021-10-01
EDET1 502446 | GRP-2021-ED1.35.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO E Warren Ave (1) (Devonshire Rd & E Outer Dr) | 0 | 2021-09-28 | 2021-10-01
EDET1 502576 | GRP-2021-ED1.80.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ANO E Warren Ave (2) (E Outer Dr & Cadiuex Rd) | 0 | 2021-09-28 | 2021-10-01
EDET1 503556 | GRP-2021-ED1.11.5.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - ASO E Warren Ave (3) (E Warren Ave & Woodshall St) | 0 | 2021-09-28 | 2021-10-01
AP 5100 | PROJ-0951-MMOAllen.80.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Seavitt 1 (Highland & Seavitt) | 4 | 2021-09-28 | 2021-10-01
NDET3-6290 | GRP-2021-ND3.5.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mound Rd (east) - (8 Mile Rd & Hamlet St | 0 | 2021-09-28 | 2021-10-01
NDET3-6295 | GRP-2021-ND3.6.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mound Rd (west) - (8 Mile Rd & Hamlet St | 0 | 2021-09-28 | 2021-10-01
NDET3-6805 | GRP-2021-ND3.18.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Filer Ave (2) (Emery St & ANO 7 Mile Rd) | 0 | 2021-09-28 | 2021-10-01
NDET3-6815 | GRP-2021-ND3.18.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Filer Ave (2) (ANO 7 Mile Rd & 7 Mile Rd) | 0 | 2021-09-28 | 2021-10-01
NDET3-6570 | GRP-2021-ND3.27.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Caldwell St (2) (Emery St & ANO 7 Mile Rd) | 0 | 2021-09-28 | 2021-10-01
NDET3-6315 | GRP-2021-ND3.31.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mound Rd (west) - (8 Mile Rd & Hamlet St | 0 | 2021-09-28 | 2021-10-01
NDET3-6320 | GRP-2021-ND3.31.2.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mound Rd (west) - (8 Mile Rd & Hamlet St | 0 | 2021-09-28 | 2021-10-01
NDET3-4085 | GRP-2021-ND3.2.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Girardin Ave (Tie-in at 7 Mile Rd) | 0 | 2021-09-28 | 2021-10-01
AA4 28688 | GRP-2021-AA4.2.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Pauline Blvd (S 7th St & Hutchinst) | 0 | 2021-09-28 | 2021-10-04
WCDET1-1556145 | GRP-2021-WCDet1.28.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 5 (Fullerton & Elmhurst) | 0 | 2021-09-28 | 2021-10-04
RR1 5443 | GRP-2021-RR1.30.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Myrtle (Division & W Jefferson) | 4 | 2021-09-29 | 2021-10-04
WCDET1-3090 | GRP-2021-WCDet1.13.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald Cr North 1 (Schoolcraft & Livernois) | 0 | 2021-09-29 | 2021-10-04
RR1 51538 | GRP-2021-RR1.73.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Perrin St (E Great Lakes & Abbott) | 4 | 2021-09-29 | 2021-10-04
SWDET2-5095 | PROJ-0951-SWDET2.44.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mason (Woodmere & Elsemere) | 4 | 2021-09-29 | 2021-10-04
SWDET2-6055 | PROJ-0951-SWDET2.56.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Beard (W Vernor & Cahalan) | 4 | 2021-09-29 | 2021-10-04
SWDET2-6855 | PROJ-0951-SWDET2.66.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Casper (Dix & Tie-In) | 4 | 2021-09-29 | 2021-10-04
SWDET2-10315 | PROJ-0951-SWDET2.8.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - ASO W Vernor 1 (Lawndale & Central) | 4 | 2021-09-29 | 2021-10-04
AA4 25638 | GRP-2021-AA4.5.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 1st St (12' NNPL W Davis Ave & 4' NSPL W Davis Ave) | 0 | 2021-09-29 | 2021-10-05
RR1 55820 | GRP-2021-RR1.53.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E James North (3' WEPL Burke St & 8' EWPL Harris St) 3" | 4 | 2021-09-29 | 2021-10-04
RR1 56940 | GRP-2021-RR1.42.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Genessee 1 (Coolidge Hwy & E Great Lakes St) | 4 | 2021-09-29 | 2021-10-04
AP 3400 | PROJ-0951-MMOAllen.4.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Andrews 1 (Southway & Goddard) | 4 | 2021-09-29 | 2021-10-04
AP 3850 | PROJ-0951-MMOAllen.49.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Maylawn (Reeck & Becker) | 4 | 2021-09-29 | 2021-10-04
RR1 60430 | GRP-2021-RR1.2.7.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (56' NNPL Coolidge Hwy & 4' SNPL Coolidge Hwy) | 4 | 2021-09-29 | 2021-10-04
AA3-6100 | GRP-2021-RR1.7.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (2) (32' SSPL Knox & 8' SSPL W Alexis) | 4 | 2021-09-29 | 2021-10-04
SWDET2-13875 | PROJ-0951-SWDET2.38.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Avis (Elsmere & Lawndale) | 4 | 2021-09-29 | 2021-10-04
SWDET2-14595 | PROJ-0951-SWDET2.72.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cabot (Woodmere & ANO W Vernor) | 4 | 2021-09-29 | 2021-10-04
RR1 5751 | GRP-2021-RR.4.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Manistique (E Jefferson & Essex) | 0 | 2021-09-29 | 2021-10-04
RR1 7351 | GRP-2021-RR.26.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Alger (Woodward & Beaubien) | 0 | 2021-09-29 | 2021-10-04
RR1 8171 | GRP-2021-RR.36.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Canton (EOM 100' NNPL Farnsworth & Gration) | 0 | 2021-09-29 | 2021-10-04
RR1 8491 | GRP-2021-RR.40.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Glenwood (Gratiot & Chalmers) | 0 | 2021-09-29 | 2021-10-04
AP 4250 | PROJ-0951-MMOAllen.64.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Pelham 2 (450' South Conrail Rr & Goddard) | 4 | 2021-09-29 | 2021-10-04
GP-42550 | PROJ-0951-GP 5 -3.133.1.2 | 2020 GRP - Carry Over - GP 5 | Restoration - Soft Surface - Mack South (Alter & Balfour) | 0 | 2021-09-29 | 2021-10-04
EDET1 508596 | GRP-2021-ED1.17.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - E Warren (2) (Chatsworth & E Outer Dr) | 0 | 2021-09-29 | 2021-10-04
SWDET2-9852 | GRP-2021-WCDet1.33.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Utica (Bryden & American) | 0 | 2021-09-29 | 2021-10-05
RR1 5439 | GRP-2021-RR1.26.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Haltiner St (108' NNPL Louis St & 50' NNPL Cora St) | 4 | 2021-09-30 | 2021-10-05
WCDET1-4290 | GRP-2021-WCDet1.39.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Bryden (Utica & Elmhurst) | 0 | 2021-09-30 | 2021-10-05
RR1 51532 | GRP-2021-RR1.67.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Cattherine St (Alexander St & 179' WWPL Ironton St) | 4 | 2021-09-30 | 2021-10-05
RR1 51534 | GRP-2021-RR1.69.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Genenssee St 2 (12' NSPL E Great Lakes St & 5' SNPL Forest St) | 4 | 2021-09-30 | 2021-10-05
RR1 51535 | GRP-2021-RR1.70.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Hill St (Genessee St & 27' WWPL Alexander St) | 4 | 2021-09-30 | 2021-10-05
RR1 51537 | GRP-2021-RR1.72.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Orcahard St (W Jefferson & Ecorse City Limit) | 4 | 2021-09-30 | 2021-10-05
SWDET2-2535 | PROJ-0951-SWDET2.11.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor 3 (Woodmere & Central) | 4 | 2021-09-30 | 2021-10-05
SWDET2-2695 | PROJ-0951-SWDET2.13.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Central 1 W W (ASO Vernor & Logan) | 4 | 2021-09-30 | 2021-10-05
SWDET2-2935 | PROJ-0951-SWDET2.16.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 4 (Central & W Vernor) | 4 | 2021-09-30 | 2021-10-05
SWDET2-4615 | PROJ-0951-SWDET2.38.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Avis (Woodmere & Elsmere) | 4 | 2021-09-30 | 2021-10-05
SWDET2-5975 | PROJ-0951-SWDET2.55.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Whitaker 1 (Mullane & Springwells) | 4 | 2021-09-30 | 2021-10-05
SWDET2-11145 | PROJ-0951-SWDET2.13.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Central 1 W (Logan & Pershing) | 4 | 2021-09-30 | 2021-10-05
RR1 54380 | GRP-2021-RR1.16.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Division (W Cicotte St & 10' NSPL W Pleasant St) | 4 | 2021-09-30 | 2021-10-05
WCDET1-13220 | GRP-2021-WCDet1.31.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Elmhurst (Bryden & Livernois) | 0 | 2021-09-30 | 2021-10-05
WCDET1-13380 | GRP-2021-WCDet1.31.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Elmhurst (American & AWO Livernois) | 0 | 2021-09-30 | 2021-10-05
AP 3380 | PROJ-0951-MMOAllen.2.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Allen 1 (Pelham & 150' North Of Moore) | 4 | 2021-09-30 | 2021-10-05
AP 3920 | PROJ-0951-MMOAllen.56.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Moore 3 (Fox & Allen Park Corporate Limits) | 4 | 2021-09-30 | 2021-10-05
RR1 60590 | GRP-2021-RR1.2.9.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (4' WEPL W Jefferson Ave & 0' WWPL W Jefferson Ave) | 4 | 2021-09-30 | 2021-10-05
SWDET2-14755 | PROJ-0951-SWDET2.72.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cabot (ASO Vernor & Mandale) | 4 | 2021-09-30 | 2021-10-05
SWDET2-15085 | PROJ-0951-SWDET2.64.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Whitaker 2 (Green & Beard) | 4 | 2021-09-30 | 2021-10-05
SWDET2-18885 | PROJ-0951-SWDET2.35.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lafayette (Lawndale & EOM) | 4 | 2021-09-30 | 2021-10-05
RR1 5511 | GRP-2021-RR.1.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Corbett 2 (Coplin & Chalmers) | 0 | 2021-09-30 | 2021-10-05
RR1 6871 | GRP-2021-RR.19.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - McDougall (Davison & Carpenter) | 0 | 2021-09-30 | 2021-10-05
RR1 11551 | GRP-2021-FR.67.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Belvidere (Mack & Charlevoix) | 0 | 2021-09-30 | 2021-10-05
RR1 11621 | GRP-2021-FR.68.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Charlevoix (Belvidere & McClellan) | 0 | 2021-09-30 | 2021-10-05
WCDET1-1556225 | GRP-2021-WCDet1.28.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 5 (Elmhurst & Burlingame) | 0 | 2021-09-30 | 2021-10-05
Muni12190 | PROJ-0951-MUN-2.52.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Longacre St (2) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-09-30 | 2021-09-30
RR1 5461 | GRP-2021-RR1.48.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Delisle (W Jefferson & Burke) | 4 | 2021-10-01 | 2021-10-06
WCDET1-3650 | GRP-2021-WCDet1.31.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Elmhurst (Bryden & American) | 0 | 2021-10-01 | 2021-10-06
RR1 51750 | GRP-2021-RR1.90.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Auburn Ave (W Jefferson Ave & Ironton Ave) | 4 | 2021-10-01 | 2021-10-06
RR1 51752 | GRP-2021-RR1.103.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Glenwood Ave (W Jefferson Ave & Ironton Ave) | 4 | 2021-10-01 | 2021-10-06
AA4 20552 | GRP-2021-AA4.8.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Liberty St (54' EEPL Crest Ave & 21' WWPL S 7Th St) | 35 | 2021-10-01 | 2021-10-18
AA4 20895 | GRP-2021-AA4.32.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 8th St (W Liberty St & EOM) | 0 | 2021-10-01 | 2021-10-18
SWDET2-3815 | PROJ-0951-SWDET2.28.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Olivet (Woodmere & Lawndale) | 4 | 2021-10-01 | 2021-10-06
WCDET1-7730 | GRP-2021-WCDet1.15.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd 3 (American & American) | 0 | 2021-10-01 | 2021-10-06
AA4 26798 | GRP-2021-AA4.49.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Soule Blvd (102' SSPL Wakefield Ave & 373' SSPL Lutz Ave) | 0 | 2021-10-01 | 2021-10-18
AA4 27118 | GRP-2021-AA4.8.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Liberty St (Soule Blvd & Crest Ave) | 0 | 2021-10-01 | 2021-10-18
AP 3900 | PROJ-0951-MMOAllen.54.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Moore 1 (107' West Of Buckingham Ave & Marlborough) | 4 | 2021-10-01 | 2021-10-06
SWDET2-14925 | PROJ-0951-SWDET2.64.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Whitaker 2 (Central & Green) | 4 | 2021-10-01 | 2021-10-06
SWDET2-15695 | PROJ-0951-SWDET2.66.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Casper (Tie-In & W Vernor) | 4 | 2021-10-01 | 2021-10-06
SWDET2-17725 | PROJ-0951-SWDET2.61.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Senator 2 (Springwells & Central) | 4 | 2021-10-01 | 2021-10-06
NDET3-5715 | GRP-2021-ND3.24.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Albany Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-01 | 2021-10-06
RR1 11341 | GRP-2021-FR.64.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Rolfs (571' NNPL Mack & Mack) | 0 | 2021-10-01 | 2021-10-06
Ypsi 3-12510 | PROJ-0951-YSP3.10.3.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Calder (94 Service Drive) | 5 | 2021-10-01 | 2021-10-07
WCDET1-4130 | GRP-2021-WCDet1.37.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Stoepel 2 (Buena Vista & Fullerton) | 0 | 2021-10-01 | 2021-10-07
WCDET1-1650 | GRP-2021-WCDet1.5.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Waverly (Broadstreet & Dexter) | 0 | 2021-10-04 | 2021-10-07
RR1 5469 | GRP-2021-RR1.56.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Richter (E Pleasant St & Leroy St) | 4 | 2021-10-04 | 2021-10-07
SWDET2-3015 | PROJ-0951-SWDET2.17.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 1E (ASO Vernor & Chamberlain) | 4 | 2021-10-04 | 2021-10-07
SWDET2-6695 | PROJ-0951-SWDET2.64.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Whitaker 2 (Springwells & Central) | 4 | 2021-10-04 | 2021-10-07
SWDET2-8215 | PROJ-0951-SWDET2.1.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 1 (Railroad & W Vernor) | 4 | 2021-10-04 | 2021-10-07
SWDET2-8855 | PROJ-0951-SWDET2.16.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 4 (At Central) | 4 | 2021-10-04 | 2021-10-07
SWDET2-13325 | PROJ-0951-SWDET2.32.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Woodmere 4 (Avis & Fort) | 4 | 2021-10-04 | 2021-10-07
AA4 27198 | GRP-2021-AA4.8.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Liberty St (26' NNPL W Liberty St & 8' NSPL W Liberty St) | 0 | 2021-10-04 | 2021-10-19
WCDET1-12240 | GRP-2021-WCDet1.40.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Buena Vista 2 (Broadstreet & Petoskey) | 0 | 2021-10-04 | 2021-10-07
RR1 56460 | GRP-2021-RR1.44.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Pleasasnt North (4' EWPL Burke St & 8' WEPL Genessee St) | 4 | 2021-10-04 | 2021-10-07
Ypsi 3-11910 | PROJ-0951-YSP3.40.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - S Pasadena Ave (Coolidge & State) | 5 | 2021-10-04 | 2021-10-11
SWDET2-16105 | PROJ-0951-SWDET2.33.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Chamberlain (Lawndale & Springwells) | 4 | 2021-10-04 | 2021-10-07
SWDET2-17655 | PROJ-0951-SWDET2.61.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Senator 2 (Green & Beard) | 4 | 2021-10-04 | 2021-10-07
SWDET2-18135 | PROJ-0951-SWDET2.49.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Green (W Vernor & EOM) | 4 | 2021-10-04 | 2021-10-07
SWDET2-24075 | PROJ-0951-SWDET2.82.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 1W (ASO Vernor & Chamberlain) | 0 | 2021-10-04 | 2021-10-07
NDET3-7415 | GRP-2021-ND3.39.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Moenart St (2) (EOM & E Lantz Ave) | 0 | 2021-10-04 | 2021-10-07
NDET3-7420 | GRP-2021-ND3.39.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Moenart St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-04 | 2021-10-07
WCDET1-7250 | GRP-2021-WCDet1.35.3.4 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd East 2 (Prairie & Davison) | 0 | 2021-10-04 | 2021-10-08
WCDET1-7490 | GRP-2021-WCDet1.45.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd West 2 (Prairie & Davison) | 0 | 2021-10-04 | 2021-10-08
Ypsi 3-2580 | PROJ-0951-YSP3.36.2.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Old Ecorse (73' NSPL Ecorse Rd & 3' NSPL Ecorse Rd) | 5 | 2021-10-05 | 2021-10-12
RR1 5445 | GRP-2021-RR1.32.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Summit St (2' NSPL Nieman St & 4' SNPL Cora St) | 4 | 2021-10-05 | 2021-10-08
SWDET2-6455 | PROJ-0951-SWDET2.61.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Senator 2 (Central & Green) | 4 | 2021-10-05 | 2021-10-08
SWDET2-6535 | PROJ-0951-SWDET2.62.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Stratton 1 (Beard & Waterman) | 4 | 2021-10-05 | 2021-10-08
SWDET2-7975 | PROJ-0951-SWDET2.79.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Wendell (Woodmere & W Vernor) | 4 | 2021-10-05 | 2021-10-08
RR1 51920 | GRP-2021-RR1.65.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Abbott (Genessee St & Ironton Ave) | 4 | 2021-10-05 | 2021-10-08
RR1 59300 | GRP-2021-RR1.74.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Stone St (Genessee St & Ironton Ave) | 4 | 2021-10-05 | 2021-10-08
SWDET2-19055 | PROJ-0951-SWDET2.41.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lane 1 (Elsmere & Lawndale) | 4 | 2021-10-05 | 2021-10-08
SWDET2-20375 | PROJ-0951-SWDET2.44.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mason (Elsemere & Lawndale) | 4 | 2021-10-05 | 2021-10-08
RR1 6151 | GRP-2021-RR.9.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Spring Garden 1 (Chalmers & Hayes) | 0 | 2021-10-05 | 2021-10-08
Muni8350 | PROJ-0951-MUN-2.15.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - West Grand Blvd (1) (West Grand Blvd & EOM) | 0 | 2021-10-05 | 2021-10-05
Muni8590 | PROJ-0951-MUN-2.18.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Mckinley (NO Magnolia & Magnolia) | 0 | 2021-10-05 | 2021-10-05
Muni8670 | PROJ-0951-MUN-2.19.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Vinewood (Magnolia & Michigan) | 0 | 2021-10-05 | 2021-10-05
Muni10270 | PROJ-0951-MUN-2.34.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Clayburn St (2) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-10-05 | 2021-10-05
Muni10670 | PROJ-0951-MUN-2.39.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Memorial St (1) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-10-05 | 2021-10-05
Muni10750 | PROJ-0951-MUN-2.40.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Memorial St (2) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-10-05 | 2021-10-05
Muni12110 | PROJ-0951-MUN-2.51.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Clayburn St (1) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-10-05 | 2021-10-05
NCDET - 12650 | NEWPROJ-6.1.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Appoline (Puritan & Fenkell) | 0 | 2021-10-06 | 2021-10-12
RR1 5430 | GRP-2021-RR1.16.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Division (Victoria St & W Cicotte St) | 4 | 2021-10-06 | 2021-10-11
RR1 5435 | GRP-2021-RR1.21.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Fairmont (Nieman & Cora) | 4 | 2021-10-06 | 2021-10-11
WCDET1-4370 | GRP-2021-WCDet1.40.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Buena Vista 2 (Livernois & Dexter) | 0 | 2021-10-06 | 2021-10-11
RR1 5474 | GRP-2021-RR1.61.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Maple St (W Jefferson & Goodell) | 4 | 2021-10-06 | 2021-10-11
AA4 20547 | GRP-2021-AA4.2.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Pauline Blvd (Redeemer & S 7th Stt) | 0 | 2021-10-06 | 2021-10-14
SWDET2-11385 | PROJ-0951-SWDET2.14.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Central 2 (Dix & W Vernor) | 4 | 2021-10-06 | 2021-10-11
RR1 54460 | GRP-2021-RR1.16.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Division (10' NSPL W Pleasant St & Linden St) | 4 | 2021-10-06 | 2021-10-11
SWDET2-18725 | PROJ-0951-SWDET2.37.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Rathbone (Lawndale & Springwells) | 4 | 2021-10-06 | 2021-10-11
SWDET2-19215 | PROJ-0951-SWDET2.41.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lane 1 (Lawndale & Springwells) | 4 | 2021-10-06 | 2021-10-11
NDET3-6075 | GRP-2021-ND3.27.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Caldwell St (2) (E Outer Dr & Emery St) | 0 | 2021-10-06 | 2021-10-11
NDET3-5955 | GRP-2021-ND3.44.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Syracuse Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-06 | 2021-10-11
Muni8190 | PROJ-0951-MUN-2.13.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Magnolia (Vinewood & Mckinley) | 0 | 2021-10-06 | 2021-10-06
Muni8510 | PROJ-0951-MUN-2.17.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Hubbard (West Grand Blvd & Michigan) | 0 | 2021-10-06 | 2021-10-06
Muni8750 | PROJ-0951-MUN-2.20.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Lahser (Santa Clara & Mcnichols) | 0 | 2021-10-06 | 2021-10-06
Muni9070 | PROJ-0951-MUN-2.15.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - West Grand Blvd (1) (West Grand Blvd & Vinewood) | 0 | 2021-10-06 | 2021-10-06
Muni9150 | PROJ-0951-MUN-2.15.3.2 | 2021 GRP - Municipality | Restoration - Soft Surface - West Grand Blvd (1) (EOM & Mckinley) | 0 | 2021-10-06 | 2021-10-06
Muni9230 | PROJ-0951-MUN-2.22.4.2 | 2021 GRP - Municipality | Restoration - Soft Surface - West Grand Blvd (2) (Mckinley & Ash) | 0 | 2021-10-06 | 2021-10-06
Muni9310 | PROJ-0951-MUN-2.18.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Mckinley (Magnolia & West Grand Blvd) | 0 | 2021-10-06 | 2021-10-06
Ypsi 3-12770 | PROJ-0951-YSP3.39.3.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Tyler (Nevada & Desoto) | 0 | 2021-10-06 | 2021-10-14
WCDET1-1556485 | GRP-2021-WCDet1.29.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - American (Tuxedo & Burlingame) | 0 | 2021-10-06 | 2021-10-12
NCDET - 12695 | NEWPROJ-6.3.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Birwood (Pilgrim & Fenkell) | 54 | 2021-10-07 | 2021-10-14
AA4 20755 | GRP-2021-AA4.12.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 4th St (W Jefferson St & W Madison St) | 0 | 2021-10-07 | 2021-10-15
SWDET2-4535 | PROJ-0951-SWDET2.37.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Rathbone (Woodmere & Lawndale) | 4 | 2021-10-07 | 2021-10-12
SWDET2-7495 | PROJ-0951-SWDET2.73.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Ferris (Woodmere & ANO W Vernor) | 4 | 2021-10-07 | 2021-10-12
WCDET1-8130 | GRP-2021-WCDet1.10.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd South 1 (Santa Rosa & Stoepel) | 0 | 2021-10-07 | 2021-10-12
RR1 52540 | GRP-2021-RR1.25.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Burke 2 (Louis St & Nieman St) | 4 | 2021-10-07 | 2021-10-12
RR1 56780 | GRP-2021-RR1.68.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Forest St (Genessee St & Ironton Ave) | 4 | 2021-10-07 | 2021-10-12
RR1 58160 | GRP-2021-RR1.54.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Leroy (Genessee St & Richter St) | 4 | 2021-10-07 | 2021-10-12
NDET3-5900 | GRP-2021-ND3.32.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Eureka St (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-07 | 2021-10-12
NDET3-5130 | GRP-2021-ND3.33.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Fenelon Ave (2) (E Outer Dr & 7 Mile Rd) | 0 | 2021-10-07 | 2021-10-12
NDET3-5690 | GRP-2021-ND3.34.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Hasse Ave (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-07 | 2021-10-12
Ypsi 3-12210 | PROJ-0951-YSP3.44.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Beverly St (Coolidge & State) | 5 | 2021-10-07 | 2021-10-15
Muni12270 | PROJ-0951-MUN-2.47.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (201' WWPL Longacre St & 13' EEPL Clayburn St) | 0 | 2021-10-07 | 2021-10-07
RR1 5463 | GRP-2021-RR1.51.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Brownlee (E Anchor St & E Cicotte St) | 4 | 2021-10-08 | 2021-10-13
SWDET2-1735 | PROJ-0951-SWDET2.4.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - ENO Pitt (Central & EOM) | 4 | 2021-10-08 | 2021-10-13
SWDET2-2375 | PROJ-0951-SWDET2.9.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Springwells 1 (ASO Vernor & Rathbone) | 4 | 2021-10-08 | 2021-10-13
SWDET2-3335 | PROJ-0951-SWDET2.21.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Bank (Springwells & EOM) | 4 | 2021-10-08 | 2021-10-13
SWDET2-4295 | PROJ-0951-SWDET2.34.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Homer (Woodmere & Lawndale) | 4 | 2021-10-08 | 2021-10-13
SWDET2-4775 | PROJ-0951-SWDET2.40.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Falcon (Woodmere & Lawndale) | 4 | 2021-10-08 | 2021-10-13
WCDET1-9350 | GRP-2021-WCDet1.46.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Santa Rosa 1 (Davison & Davison) | 0 | 2021-10-08 | 2021-10-13
RR1 54540 | GRP-2021-RR1.16.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Division (Linden St & Coolidge Hwy) | 4 | 2021-10-08 | 2021-10-13
RR1 58660 | GRP-2021-RR1.56.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Richter (Maple St & E Great Lakes St) | 4 | 2021-10-08 | 2021-10-13
RR1 5671 | GRP-2021-RR.3.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Wayburn (Berkshire & Evanston) | 0 | 2021-10-08 | 2021-10-13
RR1 7531 | GRP-2021-RR.28.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Calvert (Hamilton & Woodward) | 0 | 2021-10-08 | 2021-10-13
AP 4150 | PROJ-0951-MMOAllen.62.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Park 3 (Moore & Midway) | 4 | 2021-10-08 | 2021-10-13
NDET3-5090 | GRP-2021-ND3.3.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -E Outer Dr (South) - (Anglin St & Mt Elliott St) | 0 | 2021-10-08 | 2021-10-13
NDET3-5310 | GRP-2021-ND3.38.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Lamont Ave (E Outer Dr & 7 Mile Rd) | 0 | 2021-10-08 | 2021-10-13
NDET3-7505 | GRP-2021-ND3.66.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Charest St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-08 | 2021-10-13
AA4 20756 | GRP-2021-AA4.13.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 5th St (W Jefferson St & W Madison St) | 0 | 2021-10-11 | 2021-10-18
SWDET2-3735 | PROJ-0951-SWDET2.27.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Mint (Springwells & EOM) | 4 | 2021-10-11 | 2021-10-14
SWDET2-4215 | PROJ-0951-SWDET2.33.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Chamberlain (Woodmere & Lawndale) | 4 | 2021-10-11 | 2021-10-14
AA4 21488 | GRP-2021-AA4.13.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 5th St (W Madison St & Davis Ave) | 0 | 2021-10-11 | 2021-10-18
WCDET1-7970 | GRP-2021-WCDet1.10.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd South 1 (Monica & Santa Rosa) | 0 | 2021-10-11 | 2021-10-14
RR1 54860 | GRP-2021-RR1.46.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Cicotte (Burke St & Harris St) | 4 | 2021-10-11 | 2021-10-14
WCDET1-13570 | GRP-2021-WCDet1.41.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Tuxedo (American & EOM) | 0 | 2021-10-11 | 2021-10-14
RR1 58330 | GRP-2021-RR1.28.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Linden (4' EWPL Division St & 5' WEPL Division St) | 4 | 2021-10-11 | 2021-10-14
NDET3-5155 | GRP-2021-ND3.14.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Dwyer St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-11 | 2021-10-14
NDET3-5335 | GRP-2021-ND3.19.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Gable Ave (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-11 | 2021-10-14
NDET3-6635 | GRP-2021-ND3.29.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Dean Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-11 | 2021-10-14
NDET3-5520 | GRP-2021-ND3.35.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Healy St (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-11 | 2021-10-14
NDET3-6055 | GRP-2021-ND3.36.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Justine Ave (E Outer Dr & 7 Mile Rd) | 0 | 2021-10-11 | 2021-10-14
NDET3-7330 | GRP-2021-ND3.37.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Keystone St (2) (E Lantz St & ANO 7 Mile Rd) | 0 | 2021-10-11 | 2021-10-14
NDET3-490 | GRP-2021-ND3.77.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Klinger St (2) (E Outer Dr& 7 Mile Rd) | 0 | 2021-10-11 | 2021-10-14
Ypsi 3-12680 | PROJ-0951-YSP3.42.3.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - State (McCartney & Beverly) | 5 | 2021-10-11 | 2021-10-18
WCDET1-9910 | GRP-2021-WCDet1.27.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Stoepel 1 (Oakman & Buena Vista)) | 0 | 2021-10-11 | 2021-10-15
RR1 5446 | GRP-2021-RR1.33.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Victoria St (Division & W Jefferson) | 4 | 2021-10-12 | 2021-10-15
WCDET1-1730 | GRP-2021-WCDet1.6.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Tyler (Broadstreet & Dexter) | 0 | 2021-10-12 | 2021-10-15
SWDET2-6615 | PROJ-0951-SWDET2.63.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Waterman 1 (W Vernor & EOM) | 4 | 2021-10-12 | 2021-10-15
WCDET1-8540 | GRP-2021-WCDet1.45.4.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd West 2 (Davison & Davison) | 0 | 2021-10-12 | 2021-10-15
SWDET2-18455 | PROJ-0951-SWDET2.67.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Honorah (EOM & Dix) | 4 | 2021-10-12 | 2021-10-15
RR1 9051 | GRP-2021-RR.47.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Minden (Conner & Gunston) | 0 | 2021-10-12 | 2021-10-15
AA4 28048 | GRP-2021-AA4.13.4.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 5th St (W Jefferson St & Tie-in) | 0 | 2021-10-12 | 2021-10-19
NDET3-6510 | GRP-2021-ND3.26.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Buffalo St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-12 | 2021-10-15
NDET3-6475 | GRP-2021-ND3.42.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Shields St (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-12 | 2021-10-15
NDET3-530 | GRP-2021-ND3.72.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Harned St (1) (8 Mile Rd (M102) & E Outer Dr) | 0 | 2021-10-12 | 2021-10-15
NDET3-535 | GRP-2021-ND3.73.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Harned St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-12 | 2021-10-15
NDET3-5285 | GRP-2021-ND3.4.2.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - E Outer Dr (North) - (Mt Elliot St & Conrail) | 0 | 2021-10-12 | 2021-10-15
Muni12350 | PROJ-0951-MUN-2.47.3.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (150' WWPL Longacre St & 215' Longacre St) | 0 | 2021-10-12 | 2021-10-12
WCDET1-1970 | GRP-2021-WCDet1.9.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - AWO Livernois (Fullerton & Elmhurst) | 0 | 2021-10-12 | 2021-10-18
SWDET2-2135 | PROJ-0951-SWDET2.6.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor (Dix & Detroit City Limit) | 4 | 2021-10-13 | 2021-10-18
WCDET1-10070 | GRP-2021-WCDet1.37.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Stoepel 2 (Fullerton & Elmhurst) | 0 | 2021-10-13 | 2021-10-18
SWDET2-22565 | PROJ-0951-SWDET2.77.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Pearl (Tie-In & ANO Vernor) | 4 | 2021-10-13 | 2021-10-18
NDET3-7260 | GRP-2021-ND3.43.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Sunset St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-13 | 2021-10-18
WCDET1-1555285 | GRP-2021-WCDet1.54.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald East 2 (Oakman & Buena Vista) | 0 | 2021-10-13 | 2021-10-18
Ypsi 3-6390 | PROJ-0951-YSP3.18.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Zephyr (Tyler & Chevrolet) | 5 | 2021-10-14 | 2021-10-20
Ypsi 3-10720 | PROJ-0951-YSP3.36.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Old Ecorse (Nash & Hudson) | 5 | 2021-10-14 | 2021-10-20
RR1 5462 | GRP-2021-RR1.49.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Byron (E Pleasant St & Leroy St) | 4 | 2021-10-14 | 2021-10-19
A1110 | PROJ-0951-YSP3.41.5.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Desoto (Desoto & Dodge) | 5 | 2021-10-14 | 2021-10-20
RR1 9211 | GRP-2021-FR.49.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - St Anne (Lafayette & Jefferson) | 0 | 2021-10-14 | 2021-10-19
Muni10590 | PROJ-0951-MUN-2.38.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Longacre St (3) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-10-14 | 2021-10-14
Muni11550 | PROJ-0951-MUN-2.26.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO W Warren Ave (1) (Archdale St & Clayburn St) | 0 | 2021-10-14 | 2021-10-14
Ypsi 3-3410 | PROJ-0951-YSP3.6.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Coolidge (McCartney & Pasadena) | 5 | 2021-10-15 | 2021-10-21
Ypsi 3-5890 | PROJ-0951-YSP3.16.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Buick (Tyler & Chevrolet) | 5 | 2021-10-15 | 2021-10-21
NCDET - 13075 | NEWPROJ-6.10.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Meyers (Puritan & Keeler) | 0 | 2021-10-15 | 2021-10-20
RR1 5449 | GRP-2021-RR1.36.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Great Lakes (Burke & W Jefferson) | 4 | 2021-10-15 | 2021-10-20
RR1 5454 | GRP-2021-RR1.42.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Genessee 1 (E Pleasant St & Coolidge Hwy) | 4 | 2021-10-15 | 2021-10-20
WCDET1-2770 | GRP-2021-WCDet1.19.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Davison North 1 (Turner & Ewald) | 0 | 2021-10-15 | 2021-10-20
NDET3-5125 | GRP-2021-ND3.28.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Conley Ave (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-15 | 2021-10-20
NDET3-7230 | GRP-2021-ND3.83.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Revere Ave (2) (E Outer Dr & 7 Mile Rd) | 0 | 2021-10-15 | 2021-10-20
RR1 9291 | GRP-2021-FR.50.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Church (Woodward & John) | 0 | 2021-10-15 | 2021-10-20
WCDET1-1075 | GRP-2021-WCDet1.4.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Turner (Schoolcraft & Davison) | 0 | 2021-10-15 | 2021-10-21
WCDET1-3490 | GRP-2021-WCDet1.29.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - American (Burlingame & ANO Grand River) | 0 | 2021-10-15 | 2021-10-21
RR1 5441 | GRP-2021-RR1.28.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Linden (4' WEPL Division St & 43' WWPL W Jefferson Ave) | 4 | 2021-10-18 | 2021-10-21
WCDET1-9510 | GRP-2021-WCDet1.16.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Santa Rosa 2 (Buena Vista & Elmhurst) | 0 | 2021-10-18 | 2021-10-21
RR1 61990 | GRP-2021-RR1.39.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Pleasasnt (120' WWPL Division St & Division St) | 4 | 2021-10-18 | 2021-10-21
AP 5600 | PROJ-0951-MMOAllen.89.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Yost 1 (Vine & Joseph) | 4 | 2021-10-18 | 2021-10-21
Muni10910 | PROJ-0951-MUN-2.42.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Rutland St (1) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-10-18 | 2021-10-18
WCDET1-11250 | GRP-2021-WCDet1.29.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - American (Oakman & Tuxedo) | 0 | 2021-10-18 | 2021-10-22
SWDET2-96511 | GRP-2021-WCDet1.34.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - ANO Grand River (American & Prairie) | 0 | 2021-10-18 | 2021-10-22
Ypsi 3-3910 | PROJ-0951-YSP3.8.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Oswego (Onandaga & Eugene) | 5 | 2021-10-19 | 2021-10-25
NCDET - 13070 | NEWPROJ-6.10.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Meyers (Keeler & Fenkell) | 0 | 2021-10-19 | 2021-10-22
RR1 5442 | GRP-2021-RR1.29.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Louis (Burke St & W Jefferson Ave) | 4 | 2021-10-19 | 2021-10-22
WCDET1-5090 | GRP-2021-WCDet1.49.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Schoolcraft (Turner & Ewald) | 0 | 2021-10-19 | 2021-10-22
RR1 5470 | GRP-2021-RR1.57.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Chestnut St (W Jefferson & 489' WWPL Genessee St) | 4 | 2021-10-19 | 2021-10-22
SWDET2-5255 | PROJ-0951-SWDET2.46.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cahalan 2 (EOM & Central) | 4 | 2021-10-19 | 2021-10-22
RR1 273 | GRP-2021-RR1.6.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - AWO Goodell St (Maple St & Coolidge Hwy) | 4 | 2021-10-19 | 2021-10-22
SWDET2-10825 | PROJ-0951-SWDET2.70.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Springwells 2 (At Dix) | 4 | 2021-10-19 | 2021-10-22
AA4 25308 | GRP-2021-AA4.45.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Redeemer Ave (Pauline Blvd & Hewett Rd) | 0 | 2021-10-19 | 2021-10-25
RR1 52220 | GRP-2021-RR1.6.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - AWO Goodell St (Maple St & E Great Lakes) | 4 | 2021-10-19 | 2021-10-22
RR1 54700 | GRP-2021-RR1.47.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Anchor (Burke St & Brownlee St) | 4 | 2021-10-19 | 2021-10-22
AP 3590 | PROJ-0951-MMOAllen.23.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Cowell (Moore & Pennsylvania Ave) | 4 | 2021-10-19 | 2021-10-22
AP 3940 | PROJ-0951-MMOAllen.58.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Niver 2 (100' North Moore Ave & Midway) | 4 | 2021-10-19 | 2021-10-22
SWDET2-18295 | PROJ-0951-SWDET2.34.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Homer (Lawndale & Springwells) | 4 | 2021-10-19 | 2021-10-22
RR1 5447 | GRP-2021-RR1.34.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Anchor St (Division St & 7' WWPL W Jefferson Ave) | 4 | 2021-10-20 | 2021-10-25
RR1 5467 | GRP-2021-RR1.54.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Leroy (W Jefferson Ave & Burke St) | 4 | 2021-10-20 | 2021-10-25
AA4 20554 | GRP-2021-AA4.10.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 2nd St (W Jefferson St & W Madison St) | 0 | 2021-10-20 | 2021-10-26
AA4 20771 | GRP-2021-AA4.29.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Madison St 2 (S 7Th St & S 1St St) | 0 | 2021-10-20 | 2021-10-25
AA4 26638 | GRP-2021-AA4.9.4.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S Main (62' NNPL E Hoover Ave & E Hoover Ave) | 0 | 2021-10-20 | 2021-10-26
WCDET1-9190 | GRP-2021-WCDet1.46.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Santa Rosa 1 (Oakman & Davison) | 0 | 2021-10-20 | 2021-10-25
NDET3-480 | GRP-2021-ND3.71.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Gallagher St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-20 | 2021-10-25
Muni12430 | PROJ-0951-MUN-2.47.4.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (4' WEPL Ruthland St & 158' EEPL Ruthland St) | 0 | 2021-10-20 | 2021-10-20
RR1 55180 | GRP-2021-RR1.45.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Henry (Burke St & 85' WWPL Byron St) | 4 | 2021-10-21 | 2021-10-26
RR1 61910 | GRP-2021-RR1.39.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Pleasasnt (107' WWPL Dwight St & 1' WWPL Charles St) | 4 | 2021-10-21 | 2021-10-26
NDET3-4360 | GRP-2021-ND3.79.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mitchell St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-10-21 | 2021-10-26
NDET3-4370 | GRP-2021-ND3.79.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface -Mitchell St (2) (ANO 7 Mile Rd & 7 Mile Rd) | 0 | 2021-10-21 | 2021-10-26
Ypsi 3-7630 | PROJ-0951-YSP3.23.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Jeff (Desoto & Mary Catherine) | 5 | 2021-10-22 | 2021-10-29
SWDET2-19375 | PROJ-0951-SWDET2.42.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Logan 1 (At Lawndale) | 4 | 2021-10-22 | 2021-10-27
Ypsi 3-12270 | PROJ-0951-YSP3.45.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - US-12 (Gill & Gates) | 5 | 2021-10-22 | 2021-10-29
Muni9470 | PROJ-0951-MUN-2.24.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Abington Ave (1) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-10-22 | 2021-10-22
Muni10990 | PROJ-0951-MUN-2.43.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Rutland St (2) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-10-22 | 2021-10-22
Muni11630 | PROJ-0951-MUN-2.26.3.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO W Warren Ave (1) (Clayburn St & Woodmont Ave) | 0 | 2021-10-22 | 2021-10-22
WCDET1-4530 | GRP-2021-WCDet1.42.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Davison South 1 (Stoepel & Livernois) | 0 | 2021-10-22 | 2021-10-28
WCDET1-2290 | GRP-2021-WCDet1.53.54.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald Cr West 2 (Schoolcraft & Davison) | 0 | 2021-10-25 | 2021-10-28
AA4 20757 | GRP-2021-AA4.14.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 6th St (W Jefferson St & W Madison St) | 0 | 2021-10-25 | 2022-05-02
AA4 20767 | GRP-2021-AA4.25.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Tuner Park Ct (W Madison St & EOM) | 0 | 2021-10-25 | 2022-05-02
AA4 26558 | GRP-2021-AA4.9.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S Main (4' EWPL S Main St & 3' WEPL S Main St) | 0 | 2021-10-25 | 2022-05-02
WCDET1-13030 | GRP-2021-WCDet1.19.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Davison North 1 (Stoepel & Livernois) | 0 | 2021-10-25 | 2021-10-28
RR1 54060 | GRP-2021-RR1.58.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Coolidge Hwy 2 (Goodell St & AEO Goodell St) | 4 | 2021-10-25 | 2021-10-28
AP 3570 | PROJ-0951-MMOAllen.21.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Champaign 3 (Fox & Vine) | 4 | 2021-10-25 | 2021-10-28
AP 3740 | PROJ-0951-MMOAllen.38.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Joseph (N Yost Ave & S Yost Ave) | 4 | 2021-10-25 | 2021-10-28
Ypsi 3-4410 | PROJ-0951-YSP3.10.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Calder (Tyler & 94 Service Drive) | 5 | 2021-10-26 | 2022-05-03
RR1 5465 | GRP-2021-RR1.40.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W James (EOM @ 40' EEPL Dwight St & 4' EWPL Division St) | 4 | 2021-10-26 | 2021-10-29
SWDET2-2615 | PROJ-0951-SWDET2.12.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor 4 (Central & EOM) | 4 | 2021-10-26 | 2021-10-29
WCDET1-6930 | GRP-2021-WCDet1.14.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Prairie 1 (Ewald & Prairie) | 0 | 2021-10-26 | 2021-10-29
AA4 26958 | GRP-2021-AA4.28.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Jefferson St South (1' WEPL S 7Th St & S 1St St) | 0 | 2021-10-26 | 2022-05-03
WCDET1-13780 | GRP-2021-WCDet1.51.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Webb (American & EOM) | 0 | 2021-10-26 | 2021-10-29
WCDET1-14290 | GRP-2021-WCDet1.58.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Grand River Ave N (Monica & Monica) | 0 | 2021-10-26 | 2021-10-29
WCDET1-14450 | GRP-2021-WCDet1.58.59.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Grand River Ave N (Stoepel & EOM) | 0 | 2021-10-26 | 2021-10-29
RR1 5991 | GRP-2021-RR.7.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Mayfield (Chalmers & Kelly) | 0 | 2021-10-26 | 2021-10-29
RR1 11131 | GRP-2021-RR.11.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Novara (Crusade & Kelly) | 0 | 2021-10-26 | 2021-10-29
Muni12510 | PROJ-0951-MUN-2.47.5.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (189' WWPL Abington Ave & Abington Ave) | 0 | 2021-10-26 | 2021-10-26
AA4 25978 | GRP-2021-AA4.5.5.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 1st St (Nob Hill Pl & 12' NNPL W Davis Ave) | 0 | 2021-10-26 | 2022-05-04
WCDET1-1555125 | GRP-2021-WCDet1.54.55.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald East 2 (Schoolcraft & EOM) | 0 | 2021-10-26 | 2021-11-01
WCDET1-3250 | GRP-2021-WCDet1.26.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Monica West 1 (Ewald & Ewald) | 0 | 2021-10-27 | 2021-11-01
WCDET1-3330 | GRP-2021-WCDet1.27.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Stoepel 1 (Ewald & Ewald) | 0 | 2021-10-27 | 2021-11-01
WCDET1-13970 | GRP-2021-WCDet1.58.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Grand River Ave N (Prairie & Monica) | 0 | 2021-10-27 | 2021-11-01
AP 5500 | PROJ-0951-MMOAllen.87.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Wick 1 (Pelham & Becker) | 4 | 2021-10-27 | 2021-11-01
NDET3-7690 | GRP-2021-ND3.7.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Yonka (2) (7 Mile Rd & E Outer Dr) | 0 | 2021-10-27 | 2021-11-01
WCDET1-4850 | GRP-2021-WCDet1.46.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Santa Rosa 1 (Ewald & Ewald) | 0 | 2021-10-27 | 2021-11-02
WCDET1-14130 | GRP-2021-WCDet1.58.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Grand River Ave N (Monica & Stoepel) | 0 | 2021-10-27 | 2021-11-02
WCDET1-1555375 | GRP-2021-WCDet1.55.10.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald Cr South 1 (Schoolcraft & Prairie) | 0 | 2021-10-27 | 2021-11-02
RR1 5431 | GRP-2021-RR1.17.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Dwight (Linden & W Pleasant) | 4 | 2021-10-28 | 2021-11-02
WCDET1-1570 | GRP-2021-WCDet1.3.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Burnette (Grand River & I-96 Service Rd) | 0 | 2021-10-28 | 2021-11-02
WCDET1-2610 | GRP-2021-WCDet1.17.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 4 (Davison & Davison) | 0 | 2021-10-28 | 2021-11-02
WCDET1-4450 | GRP-2021-WCDet1.41.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Tuxedo (American & AWO Livernois) | 0 | 2021-10-28 | 2021-11-02
WCDET1-4610 | GRP-2021-WCDet1.43.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - San Juan (Ewald & Ewald) | 0 | 2021-10-28 | 2021-11-02
WCDET1-6770 | GRP-2021-WCDet1.14.4.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Prairie 1 (Ewald & Ewald) | 0 | 2021-10-28 | 2021-11-02
SWDET2-1072 | GRP-2021-WCDet1.52.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Quincy 2 (Bourke & EOM) | 0 | 2021-10-28 | 2021-11-02
SWDET2-15295 | PROJ-0951-SWDET2.46.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cahalan 2 (Central & Green) | 4 | 2021-10-28 | 2021-11-02
SWDET2-1082 | GRP-2021-WCDet1.56.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Quincy 1 (Huges & John C Lodge Service) | 0 | 2021-10-28 | 2021-11-02
RR1 9531 | GRP-2021-FR.53.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - 15th (Fort & Jefferson) | 0 | 2021-10-28 | 2021-11-02
Muni12590 | PROJ-0951-MUN-2.47.6.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (114' WWPL Abington Ave & 160' EEPL Abington Ave) | 0 | 2021-10-28 | 2021-10-28
WCDET1-2130 | GRP-2021-WCDet1.11.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Burlingame (American & Livernois) | 0 | 2021-10-28 | 2021-11-03
WCDET1-3730 | GRP-2021-WCDet1.32.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Georgeland (Stoepel & Livernois) | 0 | 2021-10-28 | 2021-11-03
SWDET2-9999 | GRP-2021-WCDet1.44.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Stearns (Livernois & LIvernois) | 0 | 2021-10-28 | 2021-11-03
WCDET1-1555455 | GRP-2021-WCDet1.55.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald Cr South 1 (Prairie & Ewald) | 0 | 2021-10-28 | 2021-11-03
WCDET1-2690 | GRP-2021-WCDet1.18.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois 6 (Burlingame & Grand River) | 0 | 2021-10-29 | 2021-11-03
WCDET1-2930 | GRP-2021-WCDet1.21.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Annland (Stoepel & Livernois) | 0 | 2021-10-29 | 2021-11-03
AA4 20901 | GRP-2021-AA4.38.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Hewett Rd (Russett Rd & Russell Rd) | 0 | 2021-10-29 | 2022-05-05
AA4 21078 | GRP-2021-AA4.10.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 2nd St (W Madison St & W Mosely St) | 0 | 2021-10-29 | 2022-05-04
SWDET2-10182 | GRP-2021-WCDet1.52.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Quincy 2 ((ANO Fenkell& Bourke) | 0 | 2021-10-29 | 2021-11-03
RR1 59860 | GRP-2021-RR1.40.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W James (4' EWPL Division St & 0' WEPL W Jefferson Ave) | 4 | 2021-10-29 | 2021-11-03
WCDET1-1555945 | GRP-2021-WCDet1.63.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - ASO Grand River Ave (Burnette & Jeffries) | 0 | 2021-10-29 | 2021-11-03
Muni11710 | PROJ-0951-MUN-2.26.4.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO W Warren Ave (1) (Asbury Park & St Marys St) | 0 | 2021-10-29 | 2021-10-29
WCDET1-7810 | GRP-2021-WCDet1.15.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd 3 (American & Prairie) | 0 | 2021-10-29 | 2021-11-04
WCDET1-1555545 | GRP-2021-WCDet1.38.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Livernois - EAS (Livernois & EOM) | 0 | 2021-10-29 | 2021-11-04
WCDET1-3010 | GRP-2021-WCDet1.22.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Tuller (Schoolcraft & Schoolcratf) | 0 | 2021-11-01 | 2021-11-04
RR1 5477 | GRP-2021-RR1.64.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Walnut St (W Jefferson Ave & Genessee St) | 4 | 2021-11-01 | 2021-11-04
AP 3770 | PROJ-0951-MMOAllen.41.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Laurence 1 (Englewood & Moore) | 4 | 2021-11-01 | 2021-11-04
RR1 62150 | GRP-2021-RR1.39.6.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Pleasasnt (11' SNPL W Pleasant St & 4' NSPL W Pleasant St) | 4 | 2021-11-01 | 2021-11-04
SWDET2-15375 | PROJ-0951-SWDET2.46.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cahalan 2 (Green & Beard) | 4 | 2021-11-01 | 2021-11-04
WCDET1-15070 | GRP-2021-WCDet1.57.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Burlingame (Grand River & Jeffries Fawy) | 0 | 2021-11-01 | 2021-11-04
WCDET1-1556045 | GRP-2021-WCDet1.63.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - ASO Grand River Ave (Burnette & Burnette) | 0 | 2021-11-01 | 2021-11-04
Muni9550 | PROJ-0951-MUN-2.25.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Abington Ave (2) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-11-01 | 2021-11-01
Muni10350 | PROJ-0951-MUN-2.35.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Grandmont Ave (1) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-11-01 | 2021-11-01
WCDET1-1555785 | GRP-2021-WCDet1.62.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - The Lodge (Quincy & Livernois) | 0 | 2021-11-01 | 2021-11-05
SWDET2-11715 | PROJ-0951-SWDET2.74.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 2 (Woodmere & Tie-in) | 4 | 2021-11-02 | 2021-11-05
WCDET1-9030 | GRP-2021-WCDet1.12.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Monica East 3 (Grand River & EOM) | 0 | 2021-11-02 | 2021-11-05
WCDET1-13730 | GRP-2021-WCDet1.51.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Webb (American & AWO Livernois) | 0 | 2021-11-02 | 2021-11-05
RR1 62070 | GRP-2021-RR1.39.5.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Pleasasnt (Division St & 117' WWPL W Jefferson Ave) | 4 | 2021-11-02 | 2021-11-05
NDET3-550 | GRP-2021-ND3.85.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Wexford (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-11-02 | 2021-11-05
WCDET1-1410 | GRP-2021-WCDet1.1.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Barr (Stoepel & Livernois) | 0 | 2021-11-02 | 2021-11-08
WCDET1-15460 | GRP-2021-WCDet1.60.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Bourke (West) (Burnette & EOM Burnette) | 0 | 2021-11-02 | 2021-11-08
WCDET1-2450 | GRP-2021-WCDet1.15.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd 3 (Jeffries & American) | 0 | 2021-11-03 | 2021-11-08
SWDET2-9835 | PROJ-0951-SWDET2.12.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor 4 (Tee to Tee at Waterman) | 4 | 2021-11-03 | 2021-11-08
SWDET2-9995 | PROJ-0951-SWDET2.12.5.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor 4 (Tie-in & Dix) | 4 | 2021-11-03 | 2021-11-08
RR1 62230 | GRP-2021-RR1.39.7.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Pleasasnt (117' WWPL W Jefferson Ave & W Jefferson Ave) | 4 | 2021-11-03 | 2021-11-08
SWDET2-10192 | GRP-2021-WCDet1.56.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Quincy 1 (Hughes & Fenkell) | 0 | 2021-11-03 | 2021-11-08
RR1 11271 | GRP-2021-FR.63.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Easement (Church & Candler) | 0 | 2021-11-03 | 2021-11-08
Muni12670 | PROJ-0951-MUN-2.47.7.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (Grandmont Ave & 149' EEPL Grandmont Ave) | 0 | 2021-11-03 | 2021-11-03
RR1 270 | GRP-2021-RR1.2.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (70' NNPL E Anchor St & 40' NNPL E James St) | 4 | 2021-11-04 | 2021-11-09
WCDET1-11600 | GRP-2021-WCDet1.24.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Davison 2 (Dexter & EOM) | 0 | 2021-11-04 | 2021-11-09
WCDET1-14770 | GRP-2021-WCDet1.8.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Dexter West (Pasadena & Pasadena) | 0 | 2021-11-04 | 2021-11-09
AP 3710 | PROJ-0951-MMOAllen.35.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Herrick 2 (1080 West Of Cortland Ave & Cortland Ave) | 4 | 2021-11-04 | 2021-11-09
AP 3870 | PROJ-0951-MMOAllen.51.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Melbourne 2 (Chatham & Moore) | 4 | 2021-11-04 | 2021-11-09
SWDET2-24415 | PROJ-0951-SWDET2.74.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 2 (Tie-In & W Vernor) | 0 | 2021-11-04 | 2021-11-09
WCDET1-4050 | GRP-2021-WCDet1.36.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Monica West 2 (Buena Vista & Elmhurst) | 0 | 2021-11-05 | 2021-11-10
SWDET2-5575 | PROJ-0951-SWDET2.50.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lane 2 (Evans & Central) | 4 | 2021-11-05 | 2021-11-10
SWDET2-8375 | PROJ-0951-SWDET2.1.5.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 1 (At Ferney) | 4 | 2021-11-05 | 2021-11-10
SWDET2-9675 | PROJ-0951-SWDET2.12.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - W Vernor 4 (Central & Waterman) | 4 | 2021-11-05 | 2021-11-10
SWDET2-10635 | PROJ-0951-SWDET2.9.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Springwells 1 (W Vernor & ASO Vernor) | 4 | 2021-11-05 | 2021-11-10
WCDET1-7570 | GRP-2021-WCDet1.45.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd West 2 (Davison & Buena Vista) | 0 | 2021-11-05 | 2021-11-10
NDET3-7435 | GRP-2021-ND3.64.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Binder St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-11-05 | 2021-11-10
Muni10430 | PROJ-0951-MUN-2.36.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Grandmont Ave (2) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-11-05 | 2021-11-05
WCDET1-2370 | GRP-2021-WCDet1.14.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Prairie 3 (Burlingame & Grand River) | 0 | 2021-11-05 | 2021-11-11
WCDET1-2530 | GRP-2021-WCDet1.46.24.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Santa Rosa 1 (Davison & Buena Vista) | 0 | 2021-11-08 | 2021-11-11
SWDET2-5735 | PROJ-0951-SWDET2.52.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Navy 1 (Lawndale & Springwells) | 4 | 2021-11-08 | 2021-11-11
SWDET2-6295 | PROJ-0951-SWDET2.59.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Navy 2 (Springwells & Central) | 4 | 2021-11-08 | 2021-11-11
RR1 56620 | GRP-2021-RR1.44.5.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Pleasasnt South (Harris St & Richter St) | 4 | 2021-11-08 | 2021-11-11
WCDET1-1555205 | GRP-2021-WCDet1.54.12.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald East 2 (Davison & Buena Vista) | 0 | 2021-11-08 | 2021-11-11
RR1 5457 | GRP-2021-RR1.47.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Anchor (W Jefferson Ave & Burke St) | 4 | 2021-11-09 | 2021-11-12
RR1 5460 | GRP-2021-RR1.44.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Pleasasnt North (W Jefferson Ave & 4' EWPL Burke St) | 4 | 2021-11-09 | 2021-11-12
RR1 56380 | GRP-2021-RR1.44.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Pleasasnt South (W Jefferson Ave & Burke St) | 4 | 2021-11-09 | 2021-11-12
RR1 61480 | GRP-2021-RR1.2.20.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (0' SSPL Linden St & 4' NSPL W Henry St) | 4 | 2021-11-09 | 2021-11-12
SWDET2-14835 | PROJ-0951-SWDET2.72.5.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cabot (W Vernor & ASO Vernor) | 4 | 2021-11-09 | 2021-11-12
SWDET2-15775 | PROJ-0951-SWDET2.66.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Casper (Belle & Pitt) | 4 | 2021-11-09 | 2021-11-12
SWDET2-17885 | PROJ-0951-SWDET2.57.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Gartner 2 (Central & Green) | 4 | 2021-11-09 | 2021-11-12
AP 5650 | PROJ-0951-MMOAllen.90.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Yost 2 (Vine & Joseph) | 4 | 2021-11-09 | 2021-11-12
Muni12750 | PROJ-0951-MUN-2.47.8.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (213' WWPL Woodmont Ave & 4' EWPL Woodmont Ave) | 0 | 2021-11-09 | 2021-11-09
WCDET1-6370 | GRP-2021-WCDet1.53.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald Cr West 2 (Ewald & Buena Vista) | 0 | 2021-11-10 | 2021-11-15
WCDET1-5410 | GRP-2021-WCDet1.22.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Tuller (Buena Vista & Buena Vista) | 0 | 2021-11-10 | 2021-11-16
RR1 5476 | GRP-2021-RR1.63.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Pine St (Burke St & Genessee St) | 4 | 2021-11-11 | 2021-11-16
SWDET2-5335 | PROJ-0951-SWDET2.47.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Evans (Gartner & Pershing) | 4 | 2021-11-11 | 2021-11-16
RR1 5431 | GRP-2021-RR.17.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Corbett 1 (Annsbury & Coplin) | 0 | 2021-11-11 | 2021-11-16
Muni12910 | PROJ-0951-MUN-2.47.10.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (4' WEPL Asbury Park & 95' EEPL Asbury Park) | 0 | 2021-11-11 | 2021-11-11
WDET31070 | PROJ-0951-MUN-2.1.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Southfield Fwy (M-39) (66' EEPL Ashton Ave & 112' WWPL Archdale St) | 0 | 2021-11-11 | 2021-11-11
WCDET1-2210 | GRP-2021-WCDet1.4.10.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Turner (Buena Vista & EOM)) | 0 | 2021-11-11 | 2021-11-17
WCDET1-3810 | GRP-2021-WCDet1.22.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Tuller (Schoolcraft & Davision) | 0 | 2021-11-11 | 2021-11-17
WCDET1-7090 | GRP-2021-WCDet1.14.5.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Prairie 2 (Oakman & Elmhurst) | 0 | 2021-11-11 | 2021-11-17
RR1 5426 | GRP-2021-RR1.12.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - AWO W Jefferson (W Henry & EOM) | 4 | 2021-11-12 | 2021-11-17
RR1 5450 | GRP-2021-RR1.37.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Henry (Division St & 4' WWPL W Jefferson Ave) | 4 | 2021-11-12 | 2021-11-17
WCDET1-12880 | GRP-2021-WCDet1.50.4.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Fullerton (AWO Livernois & Livernois)) | 0 | 2021-11-12 | 2021-11-17
RR1 55500 | GRP-2021-RR1.45.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Henry (110' WWPL Richter St & Richter St) | 4 | 2021-11-12 | 2021-11-17
RR1 58500 | GRP-2021-RR1.63.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Pine St (Genessee St & Richter St) | 4 | 2021-11-12 | 2021-11-17
AP 3460 | PROJ-0951-MMOAllen.10.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Becker 2 (Englewood & Wick) | 4 | 2021-11-12 | 2021-11-17
SWDET2-21365 | PROJ-0951-SWDET2.75.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Norman (ANO Vernor & W Vernor) | 4 | 2021-11-12 | 2021-11-17
SWDET2-21525 | PROJ-0951-SWDET2.75.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Norman (Tie-In & ANO Vernor) | 4 | 2021-11-12 | 2021-11-17
SWDET2-21685 | PROJ-0951-SWDET2.75.4.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Norman (ANO Vernor & ANO Vernor) | 4 | 2021-11-12 | 2021-11-17
AP 4050 | PROJ-0951-MMOAllen.61.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Park 2 (Englewood & Moore) | 4 | 2021-11-12 | 2021-11-17
NCET4-95 | Proj-NCDET43-1 PA.40.1 | NCDET4 Pull Ahead | Restoration - Soft Surface - Prest (McNichols & Puritan) | 0 | 2021-11-12 | 2021-11-18
RFordMMO150 | Proj-Redford PA.12.1.1 | Redford - Pull Ahead | Restoration - Soft Surface - Centralia St (6 Mile Rd & Curtis St) | 0 | 2021-11-12 | 2021-11-18
WCDET1-8460 | GRP-2021-WCDet1.25.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd W (Davison & Davison) | 0 | 2021-11-15 | 2021-11-18
RR1 56540 | GRP-2021-RR1.44.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Pleasasnt North (8' WEPL Genesse St & Harris St) | 4 | 2021-11-15 | 2021-11-18
SWDET2-21125 | PROJ-0951-SWDET2.59.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Navy 2 (Central & Green) | 4 | 2021-11-15 | 2021-11-18
NDET3-5880 | GRP-2021-ND3.45.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - 8 Mile Rd (Dwyer St & Elliot St) | 0 | 2021-11-15 | 2021-11-18
RR1 9371 | GRP-2021-FR.51.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Fort (15th & 21st) | 0 | 2021-11-15 | 2021-12-06
Muni11870 | PROJ-0951-MUN-2.27.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO W Warren Ave (4) (EOM Penrod St & Rosemont Ave) | 0 | 2021-11-15 | 2021-11-15
Muni12990 | PROJ-0951-MUN-2.47.11.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (108' WWPL Asbury Park & Asbury Park) | 0 | 2021-11-15 | 2021-11-15
WDET30190 | PROJ-0951-MUN-2.51.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Clayburn St (1) (23' NNPL ANO W Warren Ave & 5' NSPL ANO W Warren Ave) | 0 | 2021-11-15 | 2021-11-15
RR1 5459 | GRP-2021-RR1.50.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Burke 1 (E James St & E Pleasant St) | 4 | 2021-11-16 | 2021-11-19
RR1 5466 | GRP-2021-RR1.53.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E James North (W Jefferson & 3' WEPL Burke St) 3" | 4 | 2021-11-16 | 2021-11-19
RR1 55660 | GRP-2021-RR1.53.80.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E James South (W Jefferson & 4' EWPL Burke St) 2" | 4 | 2021-11-16 | 2021-11-19
SWDET2-24585 | PROJ-0951-SWDET2.50.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lane 2 (Central & Green) | 4 | 2021-11-16 | 2021-11-19
WCDET1-5570 | GRP-2021-WCDet1.22.4.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Tuller (Buena Vista & Fullerton) | 0 | 2021-11-16 | 2021-11-22
WCDET1-8870 | GRP-2021-WCDet1.12.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Monica East 3 (Burlingame & Grand River) | 0 | 2021-11-16 | 2021-11-22
NCET4-215 | Proj-NCDET43-1 PA.21.2 | NCDET4 Pull Ahead | Restoration - Soft Surface - ASO McNichols (4) (Snowden & Steel) | 0 | 2021-11-16 | 2021-11-22
RR1 5455 | GRP-2021-RR1.43.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Goodell (Francis Riopelle Ave & 31' NNPL Coolidge Hwy) | 4 | 2021-11-17 | 2021-11-22
RR1 5456 | GRP-2021-RR1.46.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Cicotte (W Jefferson Ave & Burke St) | 4 | 2021-11-17 | 2021-11-22
WCDET1-1490 | GRP-2021-WCDet1.2.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Grand River Ave South (Priarie & Livernois) | 0 | 2021-11-17 | 2021-11-22
WCDET1-4930 | GRP-2021-WCDet1.47.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Stoepel (Burlingame & Grand River) | 0 | 2021-11-17 | 2021-11-22
WCDET1-5170 | GRP-2021-WCDet1.50.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Fullerton (Tuller & Ewald) | 0 | 2021-11-17 | 2021-11-22
WCDET1-12560 | GRP-2021-WCDet1.50.3.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Fullerton (Ewald & Oakman) | 0 | 2021-11-17 | 2021-11-22
WCDET1-12720 | GRP-2021-WCDet1.50.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Fullerton (Stoepel & AWO Livernois) | 0 | 2021-11-17 | 2021-11-22
RR1 55340 | GRP-2021-RR1.45.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Henry (33' EEPL Genessee St & 110' WWPL Richter St) | 4 | 2021-11-17 | 2021-11-22
SWDET2-21205 | PROJ-0951-SWDET2.59.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Navy 2 (Green & Beard) | 4 | 2021-11-17 | 2021-11-22
Muni11790 | PROJ-0951-MUN-2.26.5.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO W Warren Ave (1) (Southfield Rd & 18' WWPL Archdale St) | 0 | 2021-11-17 | 2021-11-17
Muni13070 | PROJ-0951-MUN-2.47.12.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (Asbury Park & 209' EEPL Asbury Park) | 0 | 2021-11-17 | 2021-11-17
RR1 5458 | GRP-2021-RR1.45.80.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Henry (W Jefferson Ave & Burke St) | 4 | 2021-11-18 | 2021-11-23
EDET1 501038 | GRP-2021-ED1.46.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (N) (1) (Wayburn & Balfour) | 0 | 2021-11-18 | 2021-11-23
SWDET2-3575 | PROJ-0951-SWDET2.25.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Elsmere 2 (At Rathbone) | 4 | 2021-11-18 | 2021-11-23
AP 4650 | PROJ-0951-MMOAllen.72.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Reeck 2 (Allen & Moore) | 4 | 2021-11-18 | 2021-11-23
RR1 10631 | GRP-2021-FR.58.2.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Jefferson (21St & 15Th) | 0 | 2021-11-18 | 2021-11-23
RR1 9851 | GRP-2021-FR.57.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - Jefferson (24Th & 95' EEPL 23Rd) | 0 | 2021-11-18 | 2021-11-23
Muni10030 | PROJ-0951-MUN-2.31.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Asbury Park (3) (W Waren Ave & ASO W Warren Ave) | 0 | 2021-11-18 | 2021-11-18
Muni10830 | PROJ-0951-MUN-2.41.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Mettetal St (3) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-11-18 | 2021-11-18
Muni13150 | PROJ-0951-MUN-2.47.13.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (Mettetal St & 266' EEPL Mettetal St) | 0 | 2021-11-18 | 2021-11-18
WDET31390 | PROJ-0951-MUN-2.50.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Woodmont Ave (1) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-11-18 | 2021-11-18
SWDET2-4935 | PROJ-0951-SWDET2.42.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Logan 1 (Mullane & Springwells) | 4 | 2021-11-19 | 2021-11-24
SWDET2-11875 | PROJ-0951-SWDET2.74.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Lawndale 2 (ANO W Vernor & W Vernor) | 0 | 2021-11-19 | 2021-11-24
RR1 53660 | GRP-2021-RR1.4.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Coolidge Hwy 1 (Division St & W Jefferson Ave) | 4 | 2021-11-19 | 2021-11-24
RR1 53740 | GRP-2021-RR1.4.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Coolidge Hwy 1 (Division St & 400' EEPL Division St) | 4 | 2021-11-19 | 2021-11-24
RR1 55420 | GRP-2021-RR1.45.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Henry (4' NSPL E Henry St & 4' SNPL E Henry St) | 4 | 2021-11-19 | 2021-11-24
RR1 56140 | GRP-2021-RR1.62.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Oak St (25' EEPL Byron St & Genessee St) | 4 | 2021-11-19 | 2021-11-24
AP 5550 | PROJ-0951-MMOAllen.88.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Wick 2 (Pelham & Vine) | 4 | 2021-11-19 | 2021-11-24
Muni9630 | PROJ-0951-MUN-2.26.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO W Warren Ave (1) (26' WWPL Archdale St & Archdale St) | 0 | 2021-11-19 | 2021-11-19
Muni11950 | PROJ-0951-MUN-2.32.2.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ASO W Warren Ave (1) (Archdale St & St Marys St) | 0 | 2021-11-19 | 2021-11-19
SWDET2-8135 | PROJ-0951-SWDET2.1.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 1 (At Railroad) | 4 | 2021-11-22 | 2021-11-26
Muni9710 | PROJ-0951-MUN-2.27.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ANO W Warren Ave (4) (Rosemont Ave & 25' EEPL Ashton Ave) | 0 | 2021-11-22 | 2021-11-22
NCET4-170 | Proj-NCDET43-1 PA.37.1 | NCDET4 Pull Ahead | Restoration - Soft Surface - Whitcomb (McNichols & Puritan) | 0 | 2021-11-22 | 2021-11-29
RR1 53980 | GRP-2021-RR1.58.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Coolidge Hwy 2 (Richter St & Goodell St) | 4 | 2021-11-23 | 2021-11-29
NDET3-4685 | GRP-2021-ND3.21.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Mt Elliote St (2) (E Outer Dr & ANO 7 Mile Rd) | 0 | 2021-11-23 | 2021-11-29
Muni10110 | PROJ-0951-MUN-2.32.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - ASO W Warren Ave (1) (Southfield Rd & Archdale St) | 0 | 2021-11-23 | 2021-11-23
RFordMMO155 | Proj-Redford PA.19.1.1 | Redford - Pull Ahead | Restoration - Soft Surface - Norborne St (Curtis St & Bennett St) | 0 | 2021-11-23 | 2021-11-29
SWDET2-5655 | PROJ-0951-SWDET2.51.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Logan 2 (Central & EOM) | 4 | 2021-11-24 | 2021-11-30
AP 3800 | PROJ-0951-MMOAllen.44.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Louise (Englewood & Leslie) | 4 | 2021-11-24 | 2021-11-30
SWDET2-18645 | PROJ-0951-SWDET2.68.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Inglis (Woodmere & W Vernor) | 4 | 2021-11-24 | 2021-11-30
Muni9790 | PROJ-0951-MUN-2.28.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Archdale St (2) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-11-24 | 2021-11-24
Muni11470 | PROJ-0951-MUN-2.49.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Woodmont Ave (2) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-11-24 | 2021-11-24
Muni12830 | PROJ-0951-MUN-2.47.9.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (4' EWPL Woodmont Ave & 4' WEPL Asbury Park) | 0 | 2021-11-24 | 2021-11-24
EDET1 501193 | GRP-2021-ED1.63.1.2 | 2021 GRP - East Detroit 1 | Restoration - Soft Surface - Waveney Ave (3) (E Outer Dr & Harvard Rd) | 0 | 2021-11-26 | 2021-12-01
RR1 53900 | GRP-2021-RR1.58.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Coolidge Hwy 2 (Burke St & Richter St) | 4 | 2021-11-26 | 2021-12-01
RR1 56220 | GRP-2021-RR1.62.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - E Oak St (4' WEPL Genessee St & Richer St) | 4 | 2021-11-26 | 2021-12-01
Muni11310 | PROJ-0951-MUN-2.47.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (0' SNPL W Warren Ave & 0' NSPL W Warren Ave) | 0 | 2021-11-26 | 2021-11-26
WCDET1-5890 | GRP-2021-WCDet1.53.2.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Ewald Cr West 2 (Buena Vista & Cortland) | 0 | 2021-11-26 | 2021-12-02
RR1 5464 | GRP-2021-RR1.52.1.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Batavia (Burke St & Genessee St) | 4 | 2021-11-29 | 2021-12-02
RR1 52380 | GRP-2021-RR1.52.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - Batavia (Genessee St & Richer St) | 4 | 2021-11-29 | 2021-12-02
AP 3490 | PROJ-0951-MMOAllen.13.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Bert (535 Feet West Of Louise & Louise) | 4 | 2021-11-29 | 2021-12-02
RR1 60110 | GRP-2021-RR1.2.2.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (4' NNPL Leroy St & Coolidge Hwy) | 4 | 2021-11-29 | 2021-12-02
Muni9950 | PROJ-0951-MUN-2.30.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Asbury Park (2) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-11-29 | 2021-11-29
WDET30510 | PROJ-0951-MUN-2.52.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Longacre St (2) (EOM & ANO W Warren Ave) | 0 | 2021-11-29 | 2021-11-29
SWDET2-6775 | PROJ-0951-SWDET2.65.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Carson (Dix & W Vernor) | 4 | 2021-11-30 | 2021-12-03
SWDET2-7255 | PROJ-0951-SWDET2.70.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Springwells 2 (Dix & W Vernor) | 4 | 2021-11-30 | 2021-12-03
SWDET2-15135 | PROJ-0951-SWDET2.39.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cahalan 1 (Lawndale & Mullane) | 4 | 2021-11-30 | 2021-12-03
NDET3-7110 | GRP-2021-ND3.25.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Bloom St (2) (E Outer Dr & E Lantz Ave) | 0 | 2021-11-30 | 2021-12-03
NDET3-7120 | GRP-2021-ND3.25.3.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - Bloom St (2) (E Lantz Ave & ANO 7Mile Rd) | 0 | 2021-11-30 | 2021-12-03
Muni9870 | PROJ-0951-MUN-2.29.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - Archdale St (3) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-11-30 | 2021-11-30
SWDET2-14275 | PROJ-0951-SWDET2.55.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Whitaker 1 (At Lawndale) | 4 | 2021-12-01 | 2021-12-06
RR1 6231 | GRP-2021-RR.10.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Spring Garden 2 (Hayes & Kelly) | 0 | 2021-12-01 | 2021-12-06
RR1 8731 | GRP-2021-RR.43.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Outer (Eaton & Kendall) | 0 | 2021-12-01 | 2021-12-06
WDET31150 | PROJ-0951-MUN-2.23.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - St Marys St (2) (ANO W Warren Ave & W Warren Ave) | 0 | 2021-12-01 | 2021-12-01
WCDET1-4770 | GRP-2021-WCDet1.45.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd West 2 (Buena Vista & Cortland) | 0 | 2021-12-01 | 2021-12-07
SWDET2-4695 | PROJ-0951-SWDET2.39.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Cahalan 1 (Mullane & Springwells) | 4 | 2021-12-02 | 2021-12-07
RR1 60030 | GRP-2021-RR1.2.3.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (12' NSPL E Pleasant St & Delisle St) | 4 | 2021-12-02 | 2021-12-07
RR1 60190 | GRP-2021-RR1.2.4.2 | 2021 GRP - River Rouge | Restoration - Soft Surface - W Jefferson Ave (1) (42' NNPL Myrtle St & Myrtle St) | 4 | 2021-12-02 | 2021-12-07
SWDET2-17495 | PROJ-0951-SWDET2.54.3.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Senator 1 (Mullane & Springwells) | 4 | 2021-12-02 | 2021-12-07
Muni13230 | PROJ-0951-MUN-2.47.14.2 | 2021 GRP - Municipality | Restoration - Soft Surface - W Warren Ave (1) (0' SNPL W Warren Ave & 0' Sspl W Warren Ave) | 0 | 2021-12-02 | 2021-12-02
WDET31230 | PROJ-0951-MUN-2.8.1.2 | 2021 GRP - Municipality | Restoration - Soft Surface - St Marys St (3) (W Warren Ave & ASO W Warren Ave) | 0 | 2021-12-02 | 2021-12-02
SWDET2-1815 | PROJ-0951-SWDET2.1.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Dix 1 (Miller & Railroad) | 4 | 2021-12-06 | 2021-12-09
WCDET1-3970 | GRP-2021-WCDet1.35.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd East 2 (Buena Vista & Cortland) | 0 | 2021-12-06 | 2021-12-10
WCDET1-7330 | GRP-2021-WCDet1.35.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Oakman Blvd East 2 (Davison & Buena Vista) | 0 | 2021-12-06 | 2021-12-10
AP 3510 | PROJ-0951-MMOAllen.15.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Brody 2 (1368 Feet West Of Allen Road & Allen) | 4 | 2021-12-07 | 2021-12-10
SWDET2-6135 | PROJ-0951-SWDET2.57.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Gartner 2 (Springwells & Central) | 4 | 2021-12-08 | 2021-12-13
CDET2-9030 | GRP-2021-CDet2.3.57.2 | 2021 GRP - Central Detroit 2 | Restoration - Soft Surface - ANO Chicago (La Salle & Rosa Parks) | 0 | 2021-12-08 | 2021-12-13
AP 3420 | PROJ-0951-MMOAllen.6.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Aster (Allen & Rosedale) | 4 | 2021-12-08 | 2021-12-13
AP 4800 | PROJ-0951-MMOAllen.75.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Rosedale 1 (Belmont & Englewood) | 4 | 2021-12-08 | 2021-12-13
SWDET2-5415 | PROJ-0951-SWDET2.48.1.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Gartner 1 (Lawndale & Springwells) | 4 | 2021-12-09 | 2021-12-14
RFordMMO160 | Proj-Redford PA.16.1.1 | Redford - Pull Ahead | Restoration - Soft Surface - Kinloch St (Curtis St & Santa Maria Ave) | 0 | 2021-12-09 | 2021-12-14
NCET4-180 | Proj-NCDET43-1 PA.36.1 | NCDET4 Pull Ahead | Restoration - Soft Surface - sussex (McNichols & Puritan) | 0 | 2021-12-09 | 2021-12-15
RFordMMO165 | Proj-Redford PA.7.1.1 | Redford - Pull Ahead | Restoration - Soft Surface - Bennett St (1) (MacArthur & Kinloch St) | 0 | 2021-12-09 | 2021-12-15
AP 3960 | PROJ-0951-MMOAllen.60.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Park 1 (Champaign & Englewood) | 4 | 2021-12-10 | 2021-12-15
RR1 9691 | GRP-2021-FR.55.1.2 | 2021 GRP - Field Recommendation | Restoration - Soft Surface - 18th (Lafayette & Fort) | 0 | 2021-12-10 | 2021-12-15
AP 3680 | PROJ-0951-MMOAllen.32.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Grey (1018' West Of Marlborough & Marlborough Ave) | 4 | 2021-12-14 | 2021-12-17
WD3PH-5690 | Proj-WDET3PLH.1.1.2 | West Detroit 3 - Pull Ahead 2021 | Restoration - Soft Surface - Paul (Archdale & Abington) | 0 | 2021-12-17 | 2021-12-22
WD3PH-5770 | Proj-WDET3PLH.2.1.2 | West Detroit 3 - Pull Ahead 2021 | Restoration - Soft Surface - Longacre (ASO Warren & Paul) | 0 | 2021-12-17 | 2021-12-22
WD3PH-5850 | Proj-WDET3PLH.5.1.2 | West Detroit 3 - Pull Ahead 2021 | Restoration - Soft Surface - Rutland (ASO Warren & Paul) | 0 | 2021-12-17 | 2021-12-22
WD3PH-5930 | Proj-WDET3PLH.6.1.2 | West Detroit 3 - Pull Ahead 2021 | Restoration - Soft Surface - Abgington (ASO Warren & Paul) | 0 | 2021-12-17 | 2021-12-22
AP 3700 | PROJ-0951-MMOAllen.34.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Herrick 1 (745' East Of Pelham & Pelham Ave ) | 4 | 2021-12-20 | 2021-12-23
SWDET2-17965 | PROJ-0951-SWDET2.57.2.2 | 2021 GRP - South West Detroit 2 | Restoration - Soft Surface - Gartner 2 (Green & Beard) | 4 | 2021-12-20 | 2021-12-23
NCET4-185 | Proj-NCDET43-1 PA.35.1 | NCDET4 Pull Ahead | Restoration - Soft Surface - Robson (McNichols & Puritan) | 0 | 2021-12-20 | 2021-12-23
RR1 5591 | GRP-2021-RR.2.1.2 | 2021 GRP - Risk Rank | Restoration - Soft Surface - Fairview (E Warren & E Canfield) | 0 | 2021-12-21 | 2021-12-28
RFordMMO170 | Proj-Redford PA.18.1.1 | Redford - Pull Ahead | Restoration - Soft Surface - MacArthur (6 Mile Rd & 6 Mile Rd) | 0 | 2021-12-21 | 2021-12-29
AP 4450 | PROJ-0951-MMOAllen.68.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Quandt 1 (Englewood & 260' North Moore Ave) | 4 | 2021-12-22 | 2021-12-29
NDET3-5265 | GRP-2021-ND3.4.1.2 | 2021 GRP - North Detroit 3 | Restoration - Soft Surface - E Outer Dr (North) - (Anglin St & Mt Elliot St) | 0 | 2021-12-22 | 2021-12-29
SWDET2-962 | GRP-2021-WCDet1.20.1.2 | 2021 GRP - West Central Detroit 1 | Restoration - Soft Surface - Jefferies (Burlingame & Burlingame) | 4 | 2021-12-28 | 2022-01-04
AP 3820 | PROJ-0951-MMOAllen.46.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Manor 1 (Allen & Moore) | 4 | 2022-01-05 | 2022-01-10
AA5-106 | Proj-AA5-PLH.1.1 | Ann Arbor 5 - Pull Ahead 2021 | Restoration - Soft Surface - Street (Cross St 1 & Cross St 2) | 0 | 2022-01-07 | 2022-01-12
WD3PH-5610 | Proj-WDET3PLH.4.1.2 | West Detroit 3 - Pull Ahead 2021 | Restoration - Soft Surface - Archdale (Warren & Paul) | 0 | 2022-01-07 | 2022-01-12
AP 3390 | PROJ-0951-MMOAllen.3.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Allen 2 (150' North Of Moore & Champaign) | 4 | 2022-01-21 | 2022-01-26
AP 4550 | PROJ-0951-MMOAllen.70.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Ray (826' West Of Louise Ave & Louise Ave) | 4 | 2022-01-27 | 2022-02-01
AP 3840 | PROJ-0951-MMOAllen.48.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Marlborough (Wick & Moore) | 4 | 2022-02-03 | 2022-02-08
AP 3610 | PROJ-0951-MMOAllen.25.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Dale (756' West Of Marlborough & Marlborough) | 4 | 2022-02-09 | 2022-02-14
AP 3500 | PROJ-0951-MMOAllen.14.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Brody 1 (Pelham & 949 Feet East Of Pelham Road) | 4 | 2022-02-15 | 2022-02-18
AP 4200 | PROJ-0951-MMOAllen.63.1.2 | 2021 GRP - Allen Park MMO | Restoration - Soft Surface - Pelham 1 (250' North Of Champaign & 450' South Conrail Rr) | 4 | 2022-02-16 | 2022-02-21
Ypsi 3-6140 | PROJ-0951-YSP3.17.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Studebaker (Chevrolet & Tyler) | 5 | 2022-05-02 | 2022-05-06
Ypsi 3-2020 | PROJ-0951-YSP3.2.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Desoto (State & Tyler) | 5 | 2022-05-02 | 2022-05-06
AA4 20553 | GRP-2021-AA4.9.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S Main (Hill St & W Hoover St) | 0 | 2022-05-02 | 2022-05-06
AA4 26478 | GRP-2021-AA4.9.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S Main (S Main St & 58' EEPL S Main St) | 0 | 2022-05-02 | 2022-05-06
AA4 20764 | GRP-2021-AA4.21.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Nob Hill Pl (S 1st St & Nob Hill Ct) | 0 | 2022-05-02 | 2022-05-09
Ypsi 3-1080 | PROJ-0951-YSP3.5.4.1 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - McCartney 1 (Tyler & EOM) | 5 | 2022-05-03 | 2022-05-09
AA4 27358 | GRP-2021-AA4.29.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Madison St 2 (S 1St St & 88' EEPL S Main St) | 0 | 2022-05-03 | 2022-05-09
Ypsi 3-7880 | PROJ-0951-YSP3.24.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Ponderosa (Woodglen & EOM) | 5 | 2022-05-04 | 2022-05-10
NCDET - 12995 | NEWPROJ-6.8.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Manor (Puritan & Fenkell) | 0 | 2022-05-04 | 2022-05-09
AA4 20775 | GRP-2021-AA4.34.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 3rd St (W Jefferson St & W Madison St) | 0 | 2022-05-04 | 2022-05-10
Ypsi 3-11430 | PROJ-0951-YSP3.38.2.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface -McCartney (McCartney & EOM) | 5 | 2022-05-04 | 2022-05-10
Ypsi 3-9370 | PROJ-0951-YSP3.30.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Sunnyglen (Glengrove & Nash) | 5 | 2022-05-05 | 2022-05-11
NCDET - 13035 | NEWPROJ-6.9.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Mendota (ASO Puritan & Pilgrim) | 12 | 2022-05-05 | 2022-05-10
NCDET - 13045 | NEWPROJ-6.9.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Mendota (Pilgrim & ANO Fenkell) | 39 | 2022-05-05 | 2022-05-10
NCDET - 13115 | NEWPROJ-6.11.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Monte Vista (Puritan & Fenkell) | 97 | 2022-05-05 | 2022-05-10
NCDET - 13220 | NEWPROJ-6.12.1.1 | 2020 GRP - Carry Over - North Central Detroit 3 | Restoration - Soft Surface - Pinehurst (Puritan & ANO Fenkell) | 82 | 2022-05-05 | 2022-05-10
AA4 22538 | GRP-2021-AA4.56.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - EWO Main St (170' WWPL S Main St & S Main St) | 0 | 2022-05-05 | 2022-05-11
AA4 21248 | GRP-2021-AA4.34.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 3rd St (W Madison St & W Mosley St) | 0 | 2022-05-06 | 2022-05-12
Ypsi 3-8130 | PROJ-0951-YSP3.25.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Pineridge (Woodglen & EOM) | 5 | 2022-05-09 | 2022-05-13
Ypsi 3-8370 | PROJ-0951-YSP3.26.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Briardale (Woodglen & EOM) | 5 | 2022-05-09 | 2022-05-13
Ypsi 3-8870 | PROJ-0951-YSP3.28.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Cedarcliff (Woodglen & EOM) | 5 | 2022-05-09 | 2022-05-13
Ypsi 3-9120 | PROJ-0951-YSP3.29.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Woodglen (Tyler & Cedarcliff) | 5 | 2022-05-09 | 2022-05-13
Ypsi 3-9620 | PROJ-0951-YSP3.31.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Glengrove (State & Sunnyglen) | 5 | 2022-05-09 | 2022-05-13
Ypsi 3-9870 | PROJ-0951-YSP3.32.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Ravinewood (Nash & Glengrove) | 5 | 2022-05-09 | 2022-05-13
Ypsi 3-1530 | PROJ-0951-YSP3.38.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface -McCartney (State & I-94) | 5 | 2022-05-09 | 2022-05-13
Ypsi 3-3160 | PROJ-0951-YSP3.4.3.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Nash 2 (Tyler & State) | 5 | 2022-05-09 | 2022-05-13
AA4 20549 | GRP-2021-AA4.5.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 1st St (2' NSPL W Madison St & W Mosley St) | 0 | 2022-05-09 | 2022-05-13
AA4 20761 | GRP-2021-AA4.18.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Koch Ave (3rd St & 50' EEPL 3rd St) | 0 | 2022-05-09 | 2022-05-13
AA4 20763 | GRP-2021-AA4.20.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Nob Hill Ct (Nob Hill Pl & Nob Hill Pl) | 0 | 2022-05-09 | 2022-05-13
AA4 20772 | GRP-2021-AA4.30.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Mosley St (3rd St & S Ashley St) | 0 | 2022-05-09 | 2022-05-13
AA4 20908 | GRP-2021-AA4.45.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Redeemer Ave (Rusell Rd & Hewett Rd) | 0 | 2022-05-09 | 2022-05-13
AA4 20909 | GRP-2021-AA4.46.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Russell Rd (Russett Rd & Hewett Dr) | 0 | 2022-05-09 | 2022-05-13
AA4 20910 | GRP-2021-AA4.47.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Russett Rd (Russell Rd & Hewett Dr) | 0 | 2022-05-09 | 2022-05-13
AA4 21328 | GRP-2021-AA4.34.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - 3rd St (W Mosley St & W Davis Ave) | 0 | 2022-05-09 | 2022-05-13
Ypsi 3-11200 | PROJ-0951-YSP3.38.3.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - McCartney (Coolidge & William) | 5 | 2022-05-09 | 2022-05-13
AA4 23348 | GRP-2021-AA4.18.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Koch Ave (96' WWPL S 1st St & 49' EEPL S 1st St) | 0 | 2022-05-09 | 2022-05-13
AA4 23428 | GRP-2021-AA4.18.2.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Koch Ave (50' EEPL 3rd St & 96' WWPL S 1st St) | 0 | 2022-05-09 | 2022-05-13
AA4 23508 | GRP-2021-AA4.18.4.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Koch Ave (49' EEPL S 1st St & S Main St) | 0 | 2022-05-09 | 2022-05-13
AA4 24818 | GRP-2021-AA4.58.1.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - Nob Hill Apts (EOM & S Main St) | 0 | 2022-05-09 | 2022-05-13
AA4 25468 | GRP-2021-AA4.5.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 1st St (W Mosely St & 114' NNPL Nob Hill Pl) | 0 | 2022-05-09 | 2022-05-13
AA4 25808 | GRP-2021-AA4.5.4.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 1st St (114' NNPL Nob Hill Pl & Nob Hill Pl) | 0 | 2022-05-09 | 2022-05-13
AA4 26148 | GRP-2021-AA4.5.6.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S 1st St (48' NNPL W Jefferson St & W Madison St) | 0 | 2022-05-09 | 2022-05-13
AA4 27758 | GRP-2021-AA4.30.3.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - W Mosley St (S Ashley St & S Main St) | 0 | 2022-05-09 | 2022-05-13
A1200 | PROJ-0951-YSP3.39.4.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Desoto (Tyler & Tyler) | 5 | 2022-05-09 | 2022-05-13
AA4 27828 | GRP-2021-AA4.9.5.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S Main (Hill & Tie-in) | 0 | 2022-05-09 | 2022-05-13
AA4 27888 | GRP-2021-AA4.9.6.2 | 2021 GRP - Ann Arbor 4 | Restoration - Soft Surface - S Main (Moseley & Tie-in) | 0 | 2022-05-09 | 2022-05-13
Ypsi 3-8620 | PROJ-0951-YSP3.27.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Brooktree (Woodglen & EOM) | 5 | 2022-05-16 | 2022-05-20
Ypsi 3-1770 | PROJ-0951-YSP3.39.1.2 | 2021 GRP - Ypsilanti 3 | Restoration - Soft Surface - Tyler (Desoto & McCartney) | 5 | 2022-05-16 | 2022-05-20