## Dist. 1, 2, 7 All
DWSD Utility Status Update for 2021 Speed Hump Installation Project - PW 7035B, 8/3/21
OBJECTID | STREET | FROM | TO | Selected_Blocks | COUNT | speed hump installation status | DistrictNu |  | DWSD Coordination | DWSD utility conflict status update, 8/3/21 | Id
13149 | Westmoreland Rd | Florence St | Verne St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | No utility work scheduled.
13333 | Westmoreland Rd | Florence St | Verne St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | No utility work scheduled.
6596 | Fielding St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.12 |  | Cambridge | [5 empty] | District 1 |  |  | 491.6651 | 104963.2692 | 279 | 2021 | Cambridge from Fielding to Burt | Class C | SMD Survey | Pending Utility Review | Fielding | Burt | 1
6822 | Pierson St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.12 |  | Cambridge | [5 empty] | District 1 |  |  | 491.6651 | 104963.2692 | 279 | 2021 | Cambridge from Fielding to Burt | Class C | SMD Survey | Pending Utility Review | Fielding | Burt | 1
6604 | Patton St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.12 |  | Cambridge | [5 empty] | District 1 |  |  | 491.6651 | 104963.2692 | 279 | 2021 | Cambridge from Fielding to Burt | Class C | SMD Survey | Pending Utility Review | Fielding | Burt | 1
3822 | Ashton Ave | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.342 |  | Fargo | [5 empty] | District 1 |  |  | 915.2833 | 104963.2692 | 283 | 2021 | Fargo from Southfield to Stahelin | Class C | SMD Survey | Pending Utility Review | Southfield | Stahelin | 6
5444 | Fielding St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.371 |  | St. Martins | [5 empty] | District 1 |  |  | 949.0589 | 104963.2692 | 297 | 2021 | St. Martins from Pierson to Evergreen | Class C | SMD Survey | Pending Utility Review | Pierson | Evergreen | 1
5457 | Patton St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.371 |  | St. Martins | [5 empty] | District 1 |  |  | 949.0589 | 104963.2692 | 297 | 2021 | St. Martins from Pierson to Evergreen | Class C | SMD Survey | Pending Utility Review | Pierson | Evergreen | 1
3167 | Ashton Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.097 |  | Trojan | [5 empty] | District 1 |  |  | 253.8372 | 104963.2692 | 299 | 2021 | Trojan from Rosemont to Southfield | Class C | SMD Survey | Pending Utility Review | Rosemont | Southfield | 2
6017 | Fielding St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.477 |  | Vassar | [5 empty] | District 1 |  |  | 1194.3345 | 104963.2692 | 301 | 2021 | Vassar from Pierson to Westmoreland | Class C | SMD Survey | Pending Utility Review | Pierson | Westmoreland | 1
5960 | Westmoreland Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.477 |  | Vassar | [5 empty] | District 1 |  |  | 1194.3345 | 104963.2692 | 301 | 2021 | Vassar from Pierson to Westmoreland | Class C | SMD Survey | Pending Utility Review | Pierson | Westmoreland | 1
5967 | Plainview Ave | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.477 |  | Vassar | [5 empty] | District 1 |  |  | 1194.3345 | 104963.2692 | 301 | 2021 | Vassar from Pierson to Westmoreland | Class C | SMD Survey | Pending Utility Review | Pierson | Westmoreland | 1
6028 | Patton St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.477 |  | Vassar | [5 empty] | District 1 |  |  | 1194.3345 | 104963.2692 | 301 | 2021 | Vassar from Pierson to Westmoreland | Class C | SMD Survey | Pending Utility Review | Pierson | Westmoreland | 1
6047 | Pierson St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.477 |  | Vassar | [5 empty] | District 1 |  |  | 1194.3345 | 104963.2692 | 301 | 2021 | Vassar from Pierson to Westmoreland | Class C | SMD Survey | Pending Utility Review | Pierson | Westmoreland | 1
3900 | Pembroke Ave | Stahelin Ave | Avon Ave | Yes | 1 | Will be Installed 2021 | 1 | [8 empty] | 0.925101165 |  | Avon | [5 empty] | District 1 |  |  | 2013.3713 | 104963.2692 | 69 | 2021 | Avon from 8 Mile to 7 Mile | Class A | 2020 Alternates |  | 8 Mile | 7 Mile | 1 | No Conflicts | 42
12088 | Fielding St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | Coordinate with DTE GRP | Coordinate with DWSD - Sewer |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  | 2021 Risk Rank | Fielding | Grand River | McNichols | 6/11/2020 | NAD 1983 | Detroit | Fielding (Grand River-McNichols) |  | 66966.4348 | 1426.558 | 104963.2692 | [12 empty] | DWS903_190 | Design | Miller Grove | 0 | Design | DWS-903 | Sewer | Within Neighborhood |  |  | 2020 | 2022 | 2019-11-01
12124 | Pierson St | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | No utility work scheduled.
12026 | Vaughan St | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | No utility work scheduled.
12051 | Kentfield St | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | No utility work scheduled.
13044 | Rosemont Ave | Florence St | Verne St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | No utility work scheduled.
14000 | Avon Rd | Scarsdale St | Avon Ave & Puritan St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | No utility work scheduled.
13927 | Bretton Dr | Shaftsbury Ave | Warwick | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12432 | Verne St | Rosemont Ave | Ashton Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13873 | Bretton Dr | Shaftsbury Ave | Puritan St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13422 | Bretton Dr | Huntington Rd | W Outer Dr | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12421 | Ashton Ave | Verne St | Grove St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13089 | Florence St | Stahelin Ave | Avon Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13094 | Sunderland Rd | Florence St | Verne St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12463 | Greenview Ave | Verne St | Grove St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13465 | Bretton Dr | Edinborough Rd | Huntington Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13103 | Florence St | Warwick St | Sunderland Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12521 | Verne St | Shaftsbury Ave | Warwick St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
13835 | Bretton Dr | Westmoreland Rd | Westmoreland Rd & Lancashire St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12490 | Sunderland Rd | Verne St | Grove St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
11972 | Grove St | Edinborough Rd | Huntington Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13607 | Puritan St | Rosemont Ave | Ashton Ave & Ashton Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13590 | Bretton Dr | Lancashire St | Edinborough Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
12003 | Grove St | Plainview Ave | Westmoreland Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12559 | Verne St | Plainview Ave | Westmoreland Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12462 | Verne St | Greenview Ave | Glastonbury Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13608 | Rosemont Ave | Puritan St | Florence St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
13597 | Ashton Ave | Puritan St & Ashton Rd | Florence St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
11855 | Grove St | Rosemont Ave | Ashton Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12548 | Verne St | Edinborough Rd | Huntington Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
13636 | Greenview Ave | Puritan St | Florence St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13558 | Bretton Dr | W Outer Dr | Shaftsbury Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
12482 | Verne St | Stahelin Ave | Avon Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13603 | Bretton Dr | W Outer Dr | Shaftsbury Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
13464 | Bretton Dr | Huntington Rd | W Outer Dr | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13834 | Bretton Dr | Westmoreland Rd | Lancashire St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13031 | Ashton Ave | Florence St | Verne St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
11893 | Grove St | Greenview Ave | Glastonbury Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13066 | Greenview Ave | Florence St | Verne St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13434 | Bretton Dr | Edinborough Rd | Huntington Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13122 | Florence St | W Outer Dr | Shaftsbury Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
13680 | Sunderland Rd | Puritan St | Florence St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
11923 | Sunderland Rd | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
13567 | Bretton Dr | Westmoreland Rd & Lancashire St | Edinborough Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14334 | Ashton Rd | Pilgrim St | Puritan St & Ashton Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
14345 | Avon Rd | Bretton Dr | Scarsdale St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
15356 | Ashton Rd | Keeler St | Midland St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
15453 | Bretton Dr | Kentford St | Keeler St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14860 | Ashton Rd | Midland St | Pilgrim St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14866 | Gainsborough Rd | Avon Rd | Glastonbury Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14346 | Bretton Dr | Warwick St | Avon Rd | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14973 | Bretton Dr | Glastonbury Ave | Rosemont Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14499 | Gainsborough Rd | Warwick St | Avon Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Utility work completed, paving not completed yet, scheduled for OCT 2021
15678 | Bretton Dr | Lancashire St | Bretton Dr | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14546 | Bretton Dr | Avon Rd | Glastonbury Ave | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
15389 | Bretton Dr | Kentford St | Keeler St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
15131 | Bretton Dr | Rosemont Ave | Kentford St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14378 | Bretton Dr | Warwick St | Avon Rd | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14952 | Bretton Dr | Glastonbury/Bretton Cutoff | Rosemont Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14332 | Gainsborough Rd | W Outer Dr | Warwick St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
15677 | Bretton Dr | Keeler St | Bretton Dr | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
15160 | Bretton Dr | Rosemont Ave | Kentford St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14983 | Grandville Ave | Midland St | Grand River Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14574 | Bretton Dr | Avon Rd | Glastonbury Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | NO Utility work scheduled
14458 | Auburn St | Pilgrim St | Grand River Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
13473 | Florence St | Blackstone St | Trinity St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
13053 | W Parkway St | Verne St | S Riverdale Dr | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
13408 | Florence St | Patton St | Fielding St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
17909 | Stahelin Rd | Lyndon St | Eaton St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16522 | Faust Ave | Chalfonte St | Fenkell St |  | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
17366 | Glastonbury Ave | Eaton St | Chalfonte St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16014 | Grandville Ave | Fenkell St | Keeler St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16505 | Chalfonte St | Rosemont Ave | Ashton Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
17902 | Glastonbury Ave | Lyndon St | Eaton St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16521 | Chalfonte St | Faust Ave | Penrod St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
17349 | Faust Ave | Eaton St | Chalfonte St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16575 | Chalfonte St | Artesian St | Stahelin Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
12896 | Trinity St | Verne St | Grand River Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
12458 | Beaverland St | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
12417 | Rockdale St | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
12965 | Greydale Ave | Verne St | W McNichols Rd | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
13403 | Fielding St | Florence St | Grand River Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
12953 | Burgess St | Verne St | W McNichols Rd | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
12908 | Blackstone St | Verne St | Grand River Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
14522 | Fielding St | Pilgrim St | Puritan St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
14501 | Heyden St | Pilgrim St | Puritan St |  | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
14514 | Stout St | Pilgrim St | Puritan St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
14872 | Lamphere St | Pilgrim St | Puritan St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16618 | Chalfonte St | Westwood St | Grandville Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16498 | Ashton Rd | Chalfonte St | Bretton Dr & Grand River Ave & Fenkell St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Sewer | Not in North Rosedale Park
16894 | Eaton St | Sussex St | Coyle St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
18463 | Coyle St | Grand River Ave | Lyndon St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
19457 | Prevost St | Schoolcraft St | Kendall St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
19442 | Montrose St | Schoolcraft St | Kendall St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
19434 | Winthrop St | Schoolcraft St | Kendall St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
12895 | Verne St | Trinity St | Burt Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
12916 | Verne St | Westbrook St | Blackstone St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
13498 | Florence St | Bentler St | Westbrook St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
13526 | Florence St | Burgess St | Chapel St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
13442 | Florence St | Pierson St | Braile St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
13527 | Burgess St | Florence St | Verne St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
12964 | Verne St | Greydale Ave | Burgess St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
12993 | Rockdale St | Verne St | Grove St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8090 | Avon Ave | Margareta St | Pickford St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
9021 | Curtis St | Huntington Rd | Grandville Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8062 | Faust Ave | Pickford St | Margareta St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7547 | Margareta St | Grandville Ave | Shaftsbury Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7512 | Margareta St | Sunderland Rd | Stahelin Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8938 | Avon Ave | Pickford St | Curtis St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8921 | Faust Ave | Curtis St | Pickford St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
9066 | Curtis St | Plainview Ave | Westmoreland Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7428 | Plainview Ave | Clarita St | W 7 Mile Rd | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8079 | Greenview Ave | Pickford St | Margareta St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7548 | Grandville Ave | Margareta St | W 7 Mile Rd | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8990 | Curtis St | Shaftsbury Ave | Warwick St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8032 | Pickford St | Rosemont Ave | Ashton Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7457 | Margareta St | Faust Ave | Glastonbury Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8974 | Warwick St | Curtis St | Pickford St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8061 | Pickford St | Faust Ave | Glastonbury Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8120 | Pickford St | Sunderland Rd | Stahelin Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
9044 | Curtis St | Annchester Rd | Edinborough Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7499 | Stahelin Ave | Margareta St | W 7 Mile Rd | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8389 | Plainview Ave | Pickford St | Clarita St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7427 | Clarita St | Plainview Ave | Westmoreland Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8957 | Curtis St | Sunderland Rd | Stahelin Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7473 | Greenview Ave | Margareta St | W 7 Mile Rd | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8937 | Curtis St | Avon Ave | Greenview Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8887 | Curtis St | Rosemont Ave | Ashton Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8144 | Pickford St | Shaftsbury Ave | Warwick St | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7488 | Margareta St | Avon Ave | Greenview Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8359 | Annchester Rd | Pickford St | Clarita St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8089 | Pickford St | Avon Ave | Greenview Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
8920 | Curtis St | Faust Ave | Glastonbury Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7401 | Clarita St | Annchester Rd | Edinborough Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7362 | Huntington Rd | Clarita St & Margareta St | W 7 Mile Rd | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
7008 | Ashton Ave | Clarita St | W 7 Mile Rd | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11134 | Stahelin Ave | W McNichols Rd | W Outer Dr | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11433 | Plainview Ave | W McNichols Rd | Santa Maria St | Yes | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10352 | Shaftsbury Ave | W Outer Dr | Curtis St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10081 | Westmoreland Rd | Santa Clara Ave | Curtis St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10100 | Sunderland Rd | W Outer Dr | Curtis St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10076 | Avon Ave | Curtis St | W Outer Dr | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10096 | Plainview Ave | Santa Clara Ave | Curtis St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10637 | Santa Maria St | Plainview Ave | Westmoreland Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10071 | Greenview Ave | W Outer Dr | Curtis St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11330 | Sunderland Rd | W McNichols Rd | W Outer Dr | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11872 | Glastonbury Rd | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10630 | Westmoreland Rd | Santa Maria St | Santa Clara Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10091 | Stahelin Ave | W Outer Dr | Curtis St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11840 | Ashton Ave | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11001 | Faust Ave | Greenview Ave | W Outer Dr | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11993 | Westmoreland Rd | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11856 | Rosemont Ave | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10611 | Santa Maria St | Edinborough Rd | Huntington Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10638 | Plainview Ave | Santa Maria St | Santa Clara Ave | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
11894 | Greenview Ave | Grove St | W McNichols Rd | Yes | 1 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10038 | Huntington Rd | Santa Clara Ave | Curtis St |  | 2 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
10059 | Faust Ave | W Outer Dr | Curtis St | Yes | 3 | Speed Hump Installation in progress | 1 |  | Coordinate with DWSD - Water | Not in North Rosedale Park
12851 | Fielding St | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  | 2021 Risk Rank | Fielding | Grand River | McNichols | 6/11/2020 | NAD 1983 | Detroit | Fielding (Grand River-McNichols) |  | 66966.4348 | 1426.558 | 104963.2692
17417 | Grandville Ave | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09 |  |  | Rosedale Park
18516 | Acacia St | Piedmont St | Warwick St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16597 | Chalfonte St | Piedmont St | Warwick St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09 |  |  | Rosedale Park
16838 | Plainview Ave | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16651 | Auburn St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
2027 | Hessel Ave | Ashton Ave | Rosemont Ave | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_179 | Procurement | Rosemont Fargo to Hessel | 0.25537 | Repair | CS-1909A | Water | Rosemont | Fargo | Hessel | 2020 | 2022 | 2019-05-13 | 8 | 1 | O'Hair Park
12906 | Woodbine St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_19 | Procurement | South of Six | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
20978 | Glendale St | Woodmont Ave | Asbury Park | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_199 | Procurement | Woodmont Fullerton to Schoolcraft | 0.48375 | Repair | CS-1909A | Water | Woodmont | Fullerton | Schoolcraft | 2020 | 2022 | 2019-05-13 | 8 | 1 | Schoolcraft-I96
20343 | W Davison St | Woodmont Ave | Asbury Park | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_199 | Procurement | Woodmont Fullerton to Schoolcraft | 0.48375 | Repair | CS-1909A | Water | Woodmont | Fullerton | Schoolcraft | 2020 | 2022 | 2019-05-13 | 8 | 1 | Schoolcraft-I96
18882 | Kendall St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_200 | Procurement | Montrose Schoolcraft to Grand River | 0.44364 | Repair | CS-1909A | Water | Montrose | Schoolcraft | Grand River | 2020 | 2022 | 2019-05-13 | 8 | 1 | Greenfield-Grand River
18119 | Acacia St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_200 | Procurement | Montrose Schoolcraft to Grand River | 0.44364 | Repair | CS-1909A | Water | Montrose | Schoolcraft | Grand River | 2020 | 2022 | 2019-05-13 | 8 | 1 | Greenfield-Grand River
19040 | Kendall St | Piedmont St | Warwick St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_22 | Procurement | Grandmont #1 | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
18988 | Rosemont Ave | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_22 | Procurement | Grandmont #1 | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
19009 | Greenview Rd | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_22 | Procurement | Grandmont #1 | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
18654 | Whitcomb St | Kendall St | Grand River Ave | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_39 | Procurement | Cadillac Comunity | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
20434 | Prest St | Tyler St | Schoolcraft St | Yes | 3 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_39 | Procurement | Cadillac Comunity | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood | Greenfield | Grand River | 2020 | 2021 | 2020-01-10 | 8 | 1
15027 | Midland St | Plainview Ave | Auburn St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_5584 | Procurement | Auburn Fenkell to Midland | 0.26321 | Repair | CS-1909A | Water | Auburn | Fenkell | Midland | 2020 | 2022 | 2019-05-13 | 8 | 1 | Minock Park
11489 | Prevost St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
15625 | Mansfield St | Fenkell St | Keeler St |  | 1 | 2020 Carryover | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16022 | Mettetal St | Ellsworth St | Fenkell St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16153 | Winthrop St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
15612 | Rutherford St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16008 | Saint Marys St | Ellsworth St | Fenkell | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
15636 | Saint Marys St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11402 | Robson St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11327 | Freeland St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11429 | Whitcomb St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11387 | Lauder St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11435 | Prest St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11374 | Marlowe St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11413 | Coyle St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [11 empty] | District 1 |  |  |  | 104963.2692 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3070 | Trojan St | Blackstone St | Trinity St & Griffin Drain | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3367 | Stahelin Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4066 | Grandview St | Fargo St | Norfolk St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2082 | Hessel Ave | Avon Ave | Stahelin Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3191 | Norfolk St | Cherokee St | Berg Rd | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2415 | Vaughan St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2930 | Plainview Ave | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4546 | Saint Martins Ave | Sunderland Rd | Stahelin Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3532 | Stout St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4532 | Stahelin Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2897 | Huntington Rd | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4429 | Pembroke Ave | Greydale Ave | Burgess St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3521 | Norfolk St | Fenton St | Woodbine St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3320 | Faust Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4590 | Grandville Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3847 | Greydale Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4450 | Ashton Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3862 | Pembroke Ave | Faust Ave | Glastonbury Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2028 | Rosemont Ave | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3890 | Northrop St | Fargo St | Chippewa St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3183 | Rosemont Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2987 | Kentfield St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4402 | Woodbine St | Leewin St | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2997 | Stout St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4077 | Kentfield St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2474 | Hessel Ave | Braile St & Griffin Drain | Patton St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3512 | Kentfield St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3019 | Trojan St | Braile St | Patton St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2494 | Hessel Ave | Burt Rd | Pierson St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3487 | Norfolk St | Salem St | Grandview St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4430 | Greydale Ave | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3872 | Cooley St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2996 | Trojan St | Stout St | Kentfield St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3901 | Stahelin Ave | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2830 | Stahelin Ave | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3163 | Trojan St | Greydale Ave | Burgess St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2058 | Hessel Ave | Faust Ave | Greenview Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2566 | Hessel Ave | Chapel St | Bentler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3131 | Trojan St | Chapel St | Bentler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2083 | Stahelin Ave | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2352 | Hessel Ave | Annchester Rd | Huntington Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3460 | Norfolk St | Winston St | Fenton St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4481 | Northrop St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2425 | Hessel Ave | Heyden St | Vaughan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4573 | Shaftsbury Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2594 | Hessel Ave | Greydale Ave | Burgess St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4045 | Fargo St | Fenton St | Woodbine St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3838 | Pembroke Ave | Rosemont Ave | Ashton Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3499 | Vaughan St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4078 | McIntyre St | Leewin St | Chippewa St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3473 | Grandview St | Norfolk St | Shiawassee Dr | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4093 | Stout St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4494 | McIntyre St | Pembroke Ave | Leewin St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3841 | Woodbine St | Chippewa St | Norfolk St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2515 | Hessel Ave | Blackstone Ct & Blackstone St | Trinity St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2972 | Trojan St | Heyden St | Vaughan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2377 | Hessel Ave | Plainview Ave | Westmoreland Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4667 | Vaughan St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4357 | Pembroke Ave | Blackstone St | Trinity St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2955 | Vaughan St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4048 | Vaughan St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3044 | Trojan St | Burt Rd | Pierson St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
3176 | Greydale Ave | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
2452 | Hessel Ave | Stout St | Kentfield St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4567 | Saint Martins Ave | Shaftsbury Ave | Warwick St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4469 | Houghton St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5319 | Shaftsbury Ave | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7520 | Fielding St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5357 | Annchester Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5511 | Trinity St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7364 | Glenhurst St | Kress/Glenhurst Cutoff & Grayfield St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7969 | Woodbine St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4828 | Grandview St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8421 | Pickford St | Heyden St | Vaughan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5366 | Westmoreland Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6947 | Beaverland St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5489 | Pierson St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5953 | Annchester Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5919 | Huntington Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6071 | Trinity St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7465 | Shiawassee Dr | Kress St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7462 | Vaughan St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5171 | Sunderland Rd | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6095 | Riverview St | Vassar Ave | Verdun St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7531 | Patton St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6533 | Plainview Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7610 | Glenhurst St | Clarita St | Kress St & Glenhurst/Grayfield Cutoff | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5074 | Frisbee St | Lenore Ave | Woodbine St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5588 | Greydale Ave | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6927 | Cooley St | W 7 Mile Rd | Vassar Ave | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5559 | Chapel St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8447 | Woodbine St | Grand River Ave | Clarita St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5856 | Sunderland Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6933 | Houghton St | W 7 Mile Rd | Vassar Ave | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5865 | Warwick St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5089 | Cooley St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5349 | Edinborough Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6388 | Greenview Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
9087 | Pickford St | Fenton St | Lenore Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8448 | Pickford St | Stout St | Kentfield St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
9510 | Cooley St | Curtis St | Karl St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8896 | Cooley St | Pickford St | Roxford St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5328 | Vassar Ave | Grandville Ave | Shaftsbury Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5180 | Warwick St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5935 | Edinborough Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6850 | Trinity St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6471 | Huntington Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
9074 | Lenore Ave | Margareta St | Pickford St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6489 | Edinborough Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5339 | Huntington Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5567 | Verdun St | Riverview St | Appleton St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6997 | Shiawassee Dr | W 7 Mile Rd | Verdun St | Yes | 4 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5546 | Bentler St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7346 | Grandview St | W 7 Mile Rd | Frisbee St | Yes | 5 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6418 | Sunderland Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8436 | Kentfield St | Pickford St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8440 | Glenhurst St | Grayfield St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5540 | Shiawassee Dr | Verdun St | Frisbee St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6451 | Chapel St | Cambridge Ave | Vassar Ave | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5179 | Vassar Ave | Warwick St | Sunderland Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7570 | Burt Rd | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8458 | Fielding St | Pickford St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7873 | Chapel St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5119 | Frisbee St | Winston St | Lenore Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
4972 | Blackstone St | Pembroke Ave | St Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5329 | Grandville Ave | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7022 | Riverview St | Vassar Ave | 7 Mile Rd W | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5054 | Greydale Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7492 | Kentfield St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7559 | Pierson St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6084 | Blackstone St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5568 | Riverview St | Verdun St | Frisbee St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8414 | Vaughan St | Pickford St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5020 | Chapel St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5004 | Bentler St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7325 | Winston St | W 7 Mile Rd | Frisbee St | Yes | 5 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6069 | Appleton St | Verdun St | Appleton St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5099 | Houghton St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5142 | Grandview St | Frisbee St | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7866 | Bentler St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6107 | Dale St | Vassar Ave | Verdun St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6885 | Bentler St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6111 | Bentler St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6403 | Stahelin Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
8482 | Shiawassee Dr | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
7624 | Shiawassee Dr | Clarita St | Kress St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
9416 | Bentler St | Curtis St | Karl St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6430 | Riverview St | Vassar Ave | 7 Mile Rd W | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6938 | McIntyre St | W 7 Mile Rd | Vassar Ave | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
6517 | Westmoreland Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5599 | Verdun St | Telegraph Rd | Dale St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
5903 | Grandville Ave | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11997 | Wormer St | W McNichols Rd | Santa Maria St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13475 | Ferguson St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12465 | Prest St | Florence St | Grove St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14015 | Mansfield St | Pilgrim St | Puritan St |  | 1 | 2020 Carryover | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14044 | Asbury Park | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12429 | Florence St | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13882 | Florence St | Salem St | Winston St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
9827 | Lenore Ave | Pickford St | Curtis St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12407 | Florence St | Robson St | Lauder St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12344 | Florence St | Strathmoor St | Mark Twain St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13519 | Vaughan St | Grand River Ave | Verne St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12109 | Mansfield St | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12464 | Florence St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13654 | Florence St | Wormer St | Woodbine St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10030 | Fielding St | Marian Pl | Glenco St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12369 | Florence St | Marlowe St | Hubbell St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13135 | Fenton St | Grove St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10382 | Santa Clara Ave | Patton St | Fielding St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13040 | Forrer St | Hemlock St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10383 | Patton St | Santa Clara Ave | Marian Pl | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13423 | Heyden St | Grand River Ave | Verne St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12423 | Coyle St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
9903 | Bentler St | Thatcher Ave | Glenco St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13061 | Mark Twain St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10452 | Bentler St | Santa Clara Ave | Bennett St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13935 | Prest St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10371 | Fielding St | Santa Clara Ave | Marian Pl | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13343 | Whitcomb St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12449 | Whitcomb St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14116 | Burgess St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12408 | Robson St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13894 | Coyle St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12900 | Asbury Park | Florence St | Verne St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13056 | Prevost St | Hemlock St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13655 | Wormer St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13837 | Florence St | Fenton St | Lenore Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14064 | Biltmore St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11537 | Murray Hill St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14083 | Lindsay St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13360 | Prest St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14053 | Ferguson St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13514 | Lindsay St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12524 | Pierson St | Grand River Ave | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12132 | Florence St | Freeland St | Ardmore St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11504 | Rutherford St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10881 | Patton St | Santa Maria St | Santa Clara Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10836 | Vaughan St | Santa Maria St | Santa Clara Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10494 | Wormer St | Bennett St | Curtis St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12583 | Braile St | Grand River Ave | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13535 | Harlow St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13136 | Coyle St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13916 | Whitcomb St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13561 | Fenmore St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11508 | Mansfield St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12329 | Asbury Park | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10050 | Patton St | Marian Pl | Glenco St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13488 | Biltmore St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10875 | Fielding St | Santa Maria St | Santa Clara Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12065 | Forrer St | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13084 | Saint Marys St | Hemlock St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13071 | Strathmoor St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12430 | Sussex St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12944 | Verne St | Chapel St | Bentler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11585 | Bentler St | W McNichols Rd | Orchard St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12567 | Vaughan St | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11422 | Sussex St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12370 | Marlowe St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11867 | Beaverland St | W McNichols Rd | Santa Maria St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13051 | Freeland St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11522 | Saint Marys St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13000 | Fenmore St | Florence St | Verne St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13046 | Beaverland St | Verne St | S Riverdale Dr | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
11441 | Vaughan St | W McNichols Rd | Santa Maria St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13838 | Fenton St | Grove St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
13528 | Oakfield St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
12397 | Lauder St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18944 | Kendall St | Grandmont Ave | Woodmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16087 | Chalfonte St | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18136 | Acacia St | Prevost St | Forrer St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18987 | Kendall St | Rosemont Ave | Ashton Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17596 | Mettetal St | Lyndon St | Grand River Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18378 | Strathmoor St | Intervale St | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15396 | Lamphere St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17383 | Rutland St | Monnier Rd | Grand River Ave | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15578 | Winthrop St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17648 | Rutland St | Lyndon St | Monnier Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17024 | Mettetal St | Grand River Ave | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18347 | Acacia St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16909 | Whitcomb St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16004 | Chalfonte St | Freeland St | Ardmore St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17443 | Strathmoor St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15604 | Fielding St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14544 | Mansfield St | Midland St | Pilgrim St |  | 1 | 2020 Carryover | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17081 | Saint Marys St | Grand River | Chalfonte St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16025 | Chalfonte St | Strathmoor St | Mark Twain St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18418 | Archdale St | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17451 | Vaughan St | Eaton St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17858 | Ashton Rd | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17647 | Lyndon St | Rutland St | Abington Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16082 | Stout St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16386 | Chalfonte St | Saint Marys St | Prevost St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17841 | Archdale St | Lyndon St | Monnier Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18901 | Mansfield St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17545 | Prevost St | Grand River Ave | Eaton St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18363 | Lyndon St | Bramell St | Chatham St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18120 | Montrose St | Acacia St | Grand River Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15588 | Kentfield St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19001 | Kendall St | Faust Ave | Penrod St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16876 | Kentfield St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19046 | Mark Twain St | Grand River Ave | Intervale St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16638 | Archdale St | Tournier St | Grand River Ave | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18622 | Pierson St | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18518 | Robson St | Grand River Ave | Lyndon St | Yes | 4 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18443 | Rosemont Ave | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17432 | Mark Twain St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15057 | Heyden St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18971 | Archdale St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18958 | Kendall St | Rutland St | Abington Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15060 | Winthrop St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16874 | Eaton St | Robson St | Terry St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18883 | Montrose St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16860 | Vaughan St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16625 | Longacre St | Tournier St | Grand River Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15021 | Whitcomb St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15031 | Prest St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14447 | Whitcomb St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18364 | Bramell St | Lyndon St | Wanamaker Pl | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18912 | Saint Marys St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14437 | Winthrop St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18458 | Acacia St | Faust Ave | Penrod St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17404 | Archdale St | Monnier Rd | Tournier St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15063 | Kentfield St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17881 | Winthrop St | Grand River Ave | Eaton St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17631 | Beaverland St | Eaton St | Chalfonte St & Grayfield St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18561 | Plainview Ave | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19025 | Kendall St | Artesian St | Stahelin Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17501 | Robson St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18088 | Whitcomb St | Grand River Ave | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18921 | Kendall St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16394 | Chalfonte St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16918 | Eaton St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16053 | Chalfonte St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16124 | Chalfonte St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16072 | Kentfield St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18417 | Acacia St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18345 | Acacia St | Mansfield St | Rutherford St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16091 | Fielding St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15514 | Grandville Ave | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17540 | Prest St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17087 | Ashton Rd | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16854 | Eaton St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16980 | Rutherford St | Eaton St | Hackett St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17531 | Whitcomb St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14478 | Fenton St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18410 | Lauder St | Intervale St | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15545 | Prest St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17589 | Lyndon St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18374 | Acacia St | Grandmont Ave | Woodmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15597 | Stout St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16063 | Heyden St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18471 | Greenview Rd | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17885 | Faust Ave | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14448 | Wormer St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18352 | Ashton Rd | Dead End or Start | Lyndon St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16583 | Ferguson St | Grand River Ave | Chalfonte St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19016 | Kendall St | Glastonbury Ave | Greenview Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18442 | Acacia St | Rosemont Ave | Southfield Service Drive | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18874 | Winthrop St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17840 | Lyndon St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17608 | Lyndon St | Asbury Park | Mettetal St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15074 | Stout St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15679 | Gilchrist St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18870 | Bramell St | Ray St | Malta St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14466 | Prest St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16609 | Grandville Ave | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16125 | Prest St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16336 | Chalfonte St | Forrer St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15535 | Whitcomb St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16555 | Chalfonte St | Glastonbury Ave | Greenview Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16919 | Prest St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16062 | Chalfonte St | Robson St | Terry St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15110 | Mansfield St | Keeler St | Midland St |  | 1 | 2020 Carryover | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18393 | Acacia St | Rutland St | Abington Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16106 | Whitcomb St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14412 | Lauder St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18899 | Kendall St | Prevost St | Forrer St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16986 | Mansfield St | Eaton St | Hackett St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16950 | Winthrop St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18481 | Acacia St | Glastonbury Ave | Greenview Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17393 | Longacre St | Monnier Rd | Tournier St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18399 | Marlowe St | Intervale St | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18970 | Kendall St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18386 | Sussex St | Grand River Ave | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18919 | Kendall St | Mansfield St | Rutherford St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
17628 | Lyndon St | Grandmont Ave | Woodmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
15673 | Biltmore St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
18498 | Acacia St | Artesian St | Stahelin Rd | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
16870 | Heyden St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
14390 | Strathmoor St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19852 | Artesian St | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19998 | W Davison St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21929 | Glendale St | W Parkway St | Beaverland St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19351 | Fielding St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20993 | Glendale St | Abington Ave | Grandmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21853 | Abington Ave | Fullerton St | Glendale St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19560 | Archdale St | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21866 | Memorial St | Fullerton St | Glendale St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19595 | Greenview Rd | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20408 | Archdale St | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21014 | Rutland St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20357 | Grandmont Ave | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20046 | W Davison St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21036 | Archdale St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20961 | Glendale St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19086 | Plainview Ave | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20994 | Abington Ave | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21848 | Grandmont Ave | Fullerton St | Glendale St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20368 | Abington Ave | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21941 | Dale St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20066 | Bramell St | Schoolcraft St | Kendall St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20986 | Grandmont Ave | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19847 | Stahelin Rd | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21001 | Memorial St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21013 | Glendale St | Rutland St | Memorial St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21051 | Dale St | W Davison St | Schoolcraft St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19907 | Plainview Ave | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19409 | Whitcomb St | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20388 | W Davison St | Rutland St | Memorial St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19405 | Bramell St | S Kane St | Ray St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20407 | W Davison St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21035 | Glendale St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20018 | W Davison St | Rutherford St | Forrer St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
21960 | Glendale St | Bramell St | Chatham St | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
20367 | W Davison St | Abington Ave | Grandmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
19985 | Winthrop St | Schoolcraft St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [16 empty] | District 1 |  |  |  | 104963.2692
10525 | Snowden St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 |  | Coordinate with DWSD - Water |  |  | DWSD |  |  |  | 0.095 |  | Santa Maria | [5 empty] | District 2 |  |  | 265.3319 | 119775.9774 | 296 | 2021 | Santa Maria from Schaefer to Snowden | Class C | SMD Survey | Pending Utility Review | Schaefer | Snowden | 1 |  |  |  | WS-706_45 | Construction | McNichols Schaefer to James Couzens | 0.36324 | Repair | WS-706 | Water | McNichols | Schaefer | James Couzens | 2018 | 2020 | 2019-05-13 | 8 | 2
15667 | Chalfonte St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 |  |  | Coordinate with DPW Residential Resurfacing | [5 empty] | 0.500681244 |  | Birwood | [5 empty] | District 2 |  |  | 1088.9717 | 119775.9774 | 72 | 2021 | Birwood from Fenkell to Lyndon | Class A | 2020 Alternates | DTE Coordination Needed | Fenkell | Lyndon | 2 | 2020 NCDet3 Carryover, at Fenkell Only | 33 | Speed hump to be installed
10519 | Littlefield St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | WS-706_45 | Construction | McNichols Schaefer to James Couzens | 0.36324 | Repair | WS-706 | Water | McNichols | Schaefer | James Couzens | 2018 | 2020 | 2019-05-13 | 8 | 2
4012 | Whitcomb St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | WS-707_32 | Construction | Pembroke James Couzens to Biltmore | 0.89824 | Repair | WS-707 | Water | Pembroke | James Couzens | Biltmore | 2019 | 2020 | 2019-05-13 | 8 | 2
3464 | Winthrop St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 2 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | WS-707_32 | Construction | Pembroke James Couzens to Biltmore | 0.89824 | Repair | WS-707 | Water | Pembroke | James Couzens | Biltmore | 2019 | 2020 | 2019-05-13 | 8 | 2
3555 | Murray Hill St | Pembroke Ave | Trojan St | Yes | 3 | Will be Installed 2021 | 2 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | WS-707_32 | Construction | Pembroke James Couzens to Biltmore | 0.89824 | Repair | WS-707 | Water | Pembroke | James Couzens | Biltmore | 2019 | 2020 | 2019-05-13 | 8 | 2
3537 | Saint Marys St | Pembroke Ave | Trojan St | Yes | 3 | Will be Installed 2021 | 2 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | WS-707_32 | Construction | Pembroke James Couzens to Biltmore | 0.89824 | Repair | WS-707 | Water | Pembroke | James Couzens | Biltmore | 2019 | 2020 | 2019-05-13 | 8 | 2
4026 | Prest St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | WS-707_32 | Construction | Pembroke James Couzens to Biltmore | 0.89824 | Repair | WS-707 | Water | Pembroke | James Couzens | Biltmore | 2019 | 2020 | 2019-05-13 | 8 | 2
1910 | Chippewa St | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  | 2021 Risk Rank | Stoepel | 8 Mile | Pembroke | 6/11/2020 | NAD 1983 | Detroit | Stoepel (8 Mile-Pembroke) |  | 90202.9323 | 2296.9196 | 119775.9774
18045 | Wildemere St | Waverly | W Davison St | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1944 | Ferguson St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1932 | Asbury Park | Hessel Ave | 8 Mile | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6867 | Lindsay St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6022 | Saint Marys St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
5973 | Winthrop St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6042 | Asbury Park | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6112 | Harlow St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6833 | Ferguson St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3837 | Prairie St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3849 | San Juan Dr | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1456 | Mendota St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1487 | Norfolk St | Appoline St | Meyers Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1324 | Monica St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3935 | Roselawn St | W Outer Dr | S Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3912 | Woodingham Dr | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1462 | Pinehurst St | Norfolk St | 8 Mile Rd |  | 2 | 2020 Carryover | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3825 | Monica St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1430 | Washburn St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
4819 | Birwood St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3611 | Hartwell St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_20 | Procurement | Greenwich | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3026 | Ward St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_20 | Procurement | Greenwich | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6044 | Sorrento St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_20 | Procurement | Greenwich | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
2564 | Canterbury Rd | Pembroke Ave & Warrington Dr | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_21 | Procurement | Sherwood Forest | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
4071 | Pinehurst St | W Outer Dr | Saint Martins Ave |  | 1 | 2020 Carryover | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
4046 | Birwood St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
4654 | Ilene St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
5480 | Sorrento St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
6077 | Snowden St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11008 | Birwood St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11090 | Sorrento St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10986 | Ilene St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11102 | Ward St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10999 | Griggs St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11051 | Manor St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10991 | Littlefield St | Verne St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10976 | Washburn St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11027 | Pinehurst St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
6114 | Tracey St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_31 | Procurement | Tri-Point | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10939 | Mansfield St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
10935 | Rutherford St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
5908 | Coyle St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
8055 | Curtis St | Tracey St | Schaefer Hwy | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
5946 | Whitcomb St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
7109 | Margareta St | Winthrop St | Greenfield Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11082 | Tracey St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [11 empty] | District 2 |  |  |  | 119775.9774 | [12 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1925 | Chippewa St | Prairie St | Monica St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4530 | Danbury St | W 7 Mile Rd | Penrose St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2970 | W Lantz St | Havana St | Charleston St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1083 | Norfolk St | Gardendale St | Picadilly Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1881 | Hessel Ave | Forrer St | Winthrop St & James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2491 | Biltmore St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1436 | Norfolk St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2992 | Bauman St | W Lantz St | Fernhill St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3096 | Pembroke Ave | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1931 | Hessel Ave | Asbury Park | Murray Hill St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1914 | Hessel Ave | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4130 | Ward St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2539 | Archdale St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2384 | Tracey St | Chippewa St | Norfolk St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4337 | Snowden St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3040 | Ferguson St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1517 | Ward St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2529 | Marlowe St | Chippewa St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4651 | Prest St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1832 | Renfrew Rd | Bloomfield Rd | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2462 | Murray Hill St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2419 | Chippewa St | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3092 | Oakfield St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4558 | Havana St | W 7 Mile Rd | Penrose St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1862 | Audrey St | Norfolk St | 8 Mile Service Drive | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2320 | Monte Vista St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3346 | Santa Barbara Dr | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2398 | Chippewa St | Littlefield St | Cheyenne St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4646 | Washburn St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2087 | Chippewa St | Shrewsbury Rd | Roslyn Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4634 | Cambridge Ave | Kentucky St | Indiana St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3566 | Ward St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4478 | Cambridge Ave | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3843 | Danbury St | Penrose St | Exeter St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2455 | Saint Marys St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3075 | Lindsay St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
898 | Woodstock Dr | Renfrew Rd | Briarcliff Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4399 | Lesure St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1988 | Archdale St | Hessel Ave | Circle Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2085 | Trojan St | Marlowe St | Hubbell St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2965 | Pinehurst St | Pembroke Ave | Chippewa St |  | 2 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2005 | Chippewa St | Cherrylawn St | Northlawn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2619 | Monica St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1810 | Lauder St | Norfolk St | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2483 | Bauman St | Adeline St | W State Fair St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2361 | Chippewa St | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1934 | Chippewa St | Warrington Dr | Canterbury Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1838 | Norfolk St | Basil St | Carol St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4418 | Stansbury St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2314 | Chippewa St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4040 | Winthrop St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3432 | Whitcomb St | Pembroke Ave | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3189 | Monica St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3481 | Canterbury Rd | Chesterfield Rd | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4635 | Kentucky St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2035 | Kentucky St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2090 | Chippewa St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2001 | Fenmore St | Hessel Ave | Circle Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4508 | Cambridge Ave | Prairie St | Monica St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2501 | Gilchrist St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2034 | Chippewa St | Kentucky St | Indiana St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3055 | Biltmore St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2382 | Ward St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3646 | Lesure St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1953 | Chippewa St | Santa Barbara Dr | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2064 | Chippewa St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2554 | Fenmore St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3332 | Pennington Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1504 | Norfolk St | Sorrento St | Steel St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4640 | Whitcomb St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2877 | Mendota St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4553 | Carman St | W 7 Mile Rd | Penrose St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2472 | Asbury Park | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2424 | Prevost St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3875 | Carman St | Penrose St | Annin St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1461 | Norfolk St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4534 | Cambridge Ave | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2401 | Winthrop St | Trojan St | James Couzens Fwy & Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1449 | Norfolk St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4580 | Cambridge Ave | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1340 | San Juan Dr | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3177 | Saint Martins Ave | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4083 | Prevost St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2339 | Chippewa St | Meyers Rd | Manor St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2381 | Chippewa St | Ward St | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4382 | Tracey St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1472 | Norfolk St | Manor St | Monte Vista St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
909 | Stratford Rd | Woodstock Dr | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1861 | Norfolk St | Audrey St | Oxley St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2413 | Stansbury St | Chippewa St | Norfolk St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
859 | Woodstock Dr | Queenston St | E M 1 Service Drive | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4499 | Strathmoor St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3081 | Tracey St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3387 | Roselawn St | Saint Martins Ave | N Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1567 | Tracey St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4613 | Vassar Ave | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4650 | Vassar Ave | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3477 | Pinehurst St | Saint Martins Ave | Pembroke Ave |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3894 | Havana St | Penrose St | Annin St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2055 | Washburn St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2945 | Winthrop St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1806 | Lichfield Rd | Bloomfield Rd | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1915 | Saint Marys St | Hessel Ave | 8 Mile Service Drive | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2835 | Griggs St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1809 | Norfolk St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1095 | Norfolk St | Warrington Dr | Sheffield Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1889 | Prevost St | Hessel Ave | Motor Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3065 | Gilchrist St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3097 | Lesure St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
875 | Woodstock Dr | Durham St | Queenston St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3621 | Bauman St | Wildwood St | Bryson St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2018 | Chippewa St | Wisconsin St | Ohio St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2859 | Ilene St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3027 | Asbury Park | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1895 | Hessel Ave | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1952 | Biltmore St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4348 | Hartwell St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1865 | Wakefield St | Canterbury Rd | Warrington Dr | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4564 | Cambridge Ave | Woodingham Dr | Santa Barbara Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2912 | Kentucky St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3120 | Canterbury Rd | Saint Martins Ave | Pembroke Ave & Warrington Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4476 | Mark Twain St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1923 | Murray Hill St | Hessel Ave | 8 Mile Rd & 8 Mile Service Drive | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2514 | Lindsay St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4611 | Cambridge Ave | Wisconsin St | Ohio St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1972 | Lindsay St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1030 | Lichfield Rd | Norfolk St | Woodstock Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1469 | Monte Vista St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2466 | Havana St | Adeline St | W State Fair St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2308 | Mendota St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3130 | Annin St | Carman St | Blake St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4598 | Cherrylawn St | Cambridge Ave | N Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1438 | Picadilly Rd | Canterbury Rd | Norfolk St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2527 | Oakfield St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4125 | Saint Marys St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3644 | Fenmore St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4436 | Ardmore St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4467 | Bauman St | Larchwood St | Balmoral Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1980 | Oakfield St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4102 | Saint Martins Ave | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3063 | Pembroke Ave | Schaefer Hwy | Hartwell St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2846 | Washburn St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2975 | Monte Vista St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2960 | Forrer St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
888 | Woodstock Dr | Lichfield Rd | Durham St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2315 | Pinehurst St | Chippewa St | Norfolk St |  | 2 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3856 | Charleston St | Penrose St | Annin St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1964 | Gilchrist St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3631 | Tracey St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4509 | Prairie St | Cambridge Ave | W Outer Dr |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4103 | Rutherford St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2858 | Pembroke Ave | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3141 | Ardmore St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
1984 | Chippewa St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4584 | Vassar Ave | Robson St | Lauder St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
3122 | Fenmore St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2971 | Havana St | W Lantz St | Fernhill St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
2481 | Ferguson St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6394 | Strathmoor St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5894 | Northlawn St | Clarita St | Wendel V Hall Blvd & W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8912 | Santa Clara St | Prairie St | Monica St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6444 | Margareta St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6091 | Lindsay St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5368 | Whitcomb St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7931 | San Juan Dr | London Ave | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5820 | Prairie St | Clarita St | W 7 Mile Rd |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8629 | Covington Dr | Manderson Rd | 3rd St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7366 | Saint Marys St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9026 | Coyle St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7823 | Wisconsin St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7081 | Prest St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6843 | Margareta St | Littlefield St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7871 | Ilene St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8610 | Manderson Rd | Whitmore Rd | Covington Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8424 | Coyle St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7630 | Ohio St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6613 | Steel St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5184 | Woodingham Dr | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7320 | Pinehurst St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7507 | Margareta St | Fenmore St | Archdale St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8116 | Ardmore St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6969 | Strathmoor St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6607 | Saint Marys St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8434 | Kentucky St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6443 | Lauder St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8348 | Santa Barbara Dr | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8847 | Fenmore St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5388 | Winthrop St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8494 | Birwood St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7844 | Kentucky St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6575 | Monte Vista St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9366 | Sorrento St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7616 | Lauder St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5939 | Kentucky St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5164 | Pennington Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6539 | Ilene St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6895 | Harlow St | Clarita St | W 7 Mile Rd |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7875 | Prest St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4920 | Sorrento St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8523 | Pinehurst St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8621 | Ferguson St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4842 | Pinehurst St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9340 | Mansfield St | Thatcher St | Curtis St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4846 | Prevost St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8074 | Lesure St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7417 | Margareta St | Biltmore St | Ferguson St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6468 | Cherrylawn St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6467 | Margareta St | Cherrylawn St | Northlawn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9351 | Steel St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7532 | Curtis St | Livernois Ave | Warrington Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9487 | Quincy St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6856 | Gilchrist St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7031 | Ohio St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5358 | Kentucky St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8493 | Thatcher St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7617 | Northlawn St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8456 | Washburn St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7859 | Whitcomb St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9076 | Prest St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8609 | Asbury Park | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7483 | Margareta St | Harlow St | Oakfield St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8096 | Stansbury St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8387 | Lauder St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8522 | Thatcher St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9433 | Lesure St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7860 | Washburn St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8634 | Littlefield St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7846 | Sussex St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8410 | Ohio St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8842 | Lesure St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7331 | Monte Vista St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6932 | Stoepel St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7554 | Freeland St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6360 | Stoepel St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6558 | Birwood St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8596 | Murray Hill St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6880 | Pickford St | Warrington Dr | Oak Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8942 | Santa Clara St | Woodingham Dr | Santa Barbara Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9061 | Covington Dr | 2nd Blvd | Woodward Ave | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6904 | Clarita St | Archdale St | Harlow St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6525 | Washburn St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7975 | Sorrento St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6483 | Margareta St | Wisconsin St | Ohio St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8600 | Sorrento St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7622 | Cherrylawn St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5372 | Washburn St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6424 | Margareta St | Woodingham Dr | Santa Barbara Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6618 | Murray Hill St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7956 | Mansfield St | Pickford St | Margareta St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9097 | Santa Clara St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8843 | Covington Dr | 3rd St | 2nd Blvd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4941 | Cambridge Ave | W Outer Dr | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9471 | Oak Dr | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5985 | Mendota St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8608 | Curtis St | Asbury Park | Murray Hill St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8931 | Pennington Ave | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7355 | Mansfield St | Margareta St | Clarita St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7629 | Robson St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6975 | Fenmore St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4831 | Cambridge Ave | Mendota St | Birwood St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7384 | Sorrento St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8408 | Robson St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6974 | Clarita St | Fenmore St | Archdale St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9122 | Pinehurst St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8095 | Curtis St | Stansbury St | Lesure St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7587 | Strathmoor St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7898 | Mendota St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6338 | Clarita St | Stansbury St | Lesure St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9072 | Santa Clara St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8930 | Santa Clara St | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6940 | Freeland St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8560 | Curtis St | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6514 | Whitcomb St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6048 | Ferguson St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6905 | Archdale St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7449 | Margareta St | Lindsay St | Gilchrist St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8615 | Thatcher St | W Outer Dr | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6598 | Mansfield St | Clarita St | W 7 Mile Rd |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5337 | Cherrylawn St | W 7 Mile Rd | S Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7929 | Manor St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9121 | Santa Clara St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7522 | Stansbury St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6537 | Prest St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4860 | Rutherford St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8465 | Thatcher St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9353 | Murray Hill St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7886 | Birwood St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6100 | Oakfield St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7952 | Appoline St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6564 | Mendota St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8525 | Curtis St | Forrer St | Winthrop St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8971 | W Parkhurst Pl | Woodward Ave | John R St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8117 | Thatcher St | Stoepel St | Livernois Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8017 | Fenmore St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6853 | Snowden St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8585 | Curtis St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7891 | W Montana St | Woodward Ave | John R St | Yes | 4 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8646 | Cedarhurst Pl | Woodward Ave & Merrill Plaisance St | W Longwood Pl | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6821 | Asbury Park | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5576 | Fenmore St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8135 | Curtis St | Freeland St | Ardmore St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8010 | Snowden St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5376 | Ilene St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8358 | Woodingham Dr | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7825 | Coyle St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8893 | Santa Clara St | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9519 | Stoepel St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5993 | Pinehurst St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6600 | Appoline St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8960 | Santa Clara St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7484 | Harlow St | Margareta St | Clarita St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5621 | Stoepel St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7845 | Pickford St | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5332 | Cambridge Ave | Robson St | Lauder St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6499 | Margareta St | Kentucky St | Indiana St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6322 | Clarita St | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7024 | Cherrylawn St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8052 | Harlow St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6818 | Sorrento St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7335 | Margareta St | Prevost St | Forrer St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8067 | Archdale St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7919 | Monte Vista St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9034 | Kentucky St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8936 | Santa Barbara Dr | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7075 | Pickford St | Washburn St | Wyoming St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5956 | Washburn St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7396 | Pickford St | W Outer Dr | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5155 | San Juan Dr | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6342 | Margareta St | Warrington Dr | Oak Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8943 | Woodingham Dr | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8325 | Mark Twain St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6397 | Margareta St | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8345 | Curtis St | Strathmoor St | Mark Twain St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7076 | Washburn St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6382 | Mark Twain St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8590 | Thatcher St | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6860 | Birchcrest Dr | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8082 | Worcester Pl | Woodward Ave | John R St | Yes | 4 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9137 | Edgevale St | John R St | Brush St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8573 | Mansfield St | Curtis St | Pickford St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7108 | Mendota St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7508 | Fenmore St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8591 | Steel St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
4908 | Cambridge Ave | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6449 | Northlawn St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7575 | Mark Twain St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7909 | Pinehurst St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6864 | Margareta St | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5066 | Stansbury St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8346 | Strathmoor St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9144 | Santa Clara St | Manor St | Pinehurst St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
5822 | W Golden Gate Ave | Woodward Ave | Charleston St | Yes | 4 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7963 | Steel St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7060 | Kentucky St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7359 | Appoline St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7424 | Snowden St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6335 | Fenmore St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6844 | Littlefield St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6954 | Mark Twain St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6326 | W Grixdale Ave | Woodward Ave | Charleston St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7874 | Pickford St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
6500 | Kentucky St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
7543 | Stoepel St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
8684 | Santa Clara St | Quincy St | Oak Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12001 | Florence St | Cheyenne St | Ward St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9588 | Coyle St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10094 | Santa Barbara Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10896 | Monica St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10388 | Prest St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12984 | Lesure St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10024 | Quincy St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10378 | Kentucky St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9908 | Asbury Park | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12395 | Mendota St | James Couzens Fwy | Florence St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12556 | Washburn St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14071 | Littlefield St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14026 | Appoline St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13468 | Princeton St | Midland St | Puritan St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9558 | Santa Maria St | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13987 | Pinehurst St | Pilgrim St | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11026 | Grove St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12010 | Littlefield St | Florence St | Grove St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13145 | Ohio St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13594 | Midland St | Petoskey Ave | Quincy St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13020 | Cruse St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9994 | Fairfield St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11953 | Appoline St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10427 | Birwood St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11007 | Grove St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10884 | Stoepel St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11849 | Kentucky St | Marygrove Dr | Florence St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10879 | Whitcomb St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14030 | Midland St | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9632 | Kentucky St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11890 | Florence St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9901 | Manor St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11869 | Washburn St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13470 | Ward St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12870 | Appoline St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14031 | Steel St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10560 | Inverness St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11930 | Florence St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13467 | Midland St | Princeton St | Linwood St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10410 | Ilene St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11865 | Pinehurst St | Pinehurst St | Grove St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11921 | Mendota St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11961 | Steel St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11073 | Appoline St | Grove St | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10453 | Santa Maria St | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12428 | Stoepel St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12507 | Roselawn St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11531 | Stoepel St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11910 | Florence St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10933 | Prevost St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10449 | Pinehurst St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12525 | Ohio St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10897 | Prest St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11376 | La Salle Ave | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13938 | Fairfield St | Hughes St | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10102 | Woodingham Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9909 | Santa Maria St | Meyers Rd | Manor St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11901 | Griggs St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12511 | Northlawn St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12880 | Steel St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9976 | Hartwell St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12089 | Baylis St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13833 | Normandy St | Hughes St | Pilgrim St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9638 | Prest St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9882 | Pinehurst St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13931 | Washburn St | James Couzens Fwy & Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12913 | Cheyenne St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12114 | Normandy St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11353 | Littlefield St | Grove St | Verne St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11891 | Ilene St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10077 | San Juan Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10122 | Steel St | James Couzens Fwy | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10838 | Fairfield St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13489 | Midland St | Alden St | Lawton St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11050 | Grove St | Manor St | Monte Vista St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11911 | Birwood St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10018 | Oak Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10985 | Grove St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13624 | Midland St | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10446 | Prevost St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12103 | Florence St | Cruse St | Stansbury St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13562 | Midland St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9959 | Santa Maria St | Littlefield St | Ward St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11084 | Steel St | Grove St | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11977 | Sorrento St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13595 | Petoskey Ave | Puritan St | Midland St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12077 | Florence St | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9900 | Santa Maria St | Manor St | Pinehurst St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9975 | Santa Maria St | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10377 | Whitcomb St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9546 | San Juan Dr | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9568 | Woodingham Dr | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10086 | Pennington Ave | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13450 | Steel St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9996 | Belden St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9559 | Pennington Ave | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13579 | Quincy St | Midland St | Puritan St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10010 | Birchcrest Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10396 | Washburn St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11360 | Florence St | Inverness St | Baylis St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12547 | Kentucky St | Florence St | Puritan St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11463 | Florence St | Muirland St | Fairfield St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10574 | La Salle Ave | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10565 | Baylis St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9651 | Washburn St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13015 | Normandy St | Pilgrim St | Puritan St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13007 | Stansbury St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9851 | Birwood St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9858 | Prevost St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12904 | Ward St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13354 | Washburn St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14048 | Ward St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12971 | Tracey St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9883 | Mansfield St | W Outer Dr | Thatcher St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
9970 | Snowden St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12461 | San Juan Dr | Puritan St | W McNichols Rd |  | 6 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12891 | Sorrento St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10432 | Santa Maria St | Forrer St | Winthrop St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
13440 | Appoline St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10463 | Santa Maria St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10433 | Forrer St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
10057 | Stoepel St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
11446 | Florence St | Parkside St | Wildemere St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
12059 | Tracey St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15836 | Monte Vista St | Fenkell St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15392 | Desoto St | Greenlawn St | Tuller St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14468 | Ilene St | Keeler Ave | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15984 | Chalfonte St | Cruse St | Stansbury St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16423 | Birwood St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15150 | Ward St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16155 | Roselawn St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14568 | Keeler Ave | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17080 | Clements St | Linwood St | La Salle Blvd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14868 | Keeler Ave | Cruse St | Stansbury St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15180 | Snowden St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15565 | Chalfonte St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16496 | Clements St | 14th St | Rosa Parks Blvd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
18454 | Waverly | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15156 | Ellsworth St | Wyoming St | Cherrylawn St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15122 | Appoline St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15949 | Tracey St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14610 | Littlefield St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14569 | Steel St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16161 | Steel St | Hillview St | Chalfonte St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16896 | Clements St | La Salle Blvd | 14th St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15081 | Pinehurst St | Keeler Ave | Fenkell St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15428 | Desoto St | Cherrylawn St | Greenlawn St |  | 3 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17958 | Pasadena St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14609 | Keeler Ave | Littlefield St | Cheyenne St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
18461 | Wildemere St | W Buena Vista St | Tyler St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14592 | Ward St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16452 | La Belle St | Linwood St | La Salle Blvd | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15334 | Hartwell St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17011 | Kentucky St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14633 | Hartwell St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17594 | Kendall St | Livernois Ave | Holmur St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
18062 | W Grand St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15630 | Washburn St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17051 | Birwood St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16560 | Hartwell St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
18460 | W Buena Vista St | Wildemere St | Lawton St |  | 1 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14558 | Appoline St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
18083 | Pasadena St | Petoskey Ave | Holmur St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15959 | Chalfonte St | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14591 | Keeler Ave | Ward St | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15125 | Ellsworth St | Cherrylawn St | Greenlawn St | Yes | 3 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15022 | Washburn St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17354 | W Grand St | Lawton St | Linwood St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17644 | Clements St | Wildemere St | Lawton St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15459 | Desoto St | Wyoming St | Cherrylawn St |  | 3 | 2020 Carryover | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15682 | Pinehurst St | Fenkell St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15431 | Holmur St | Chalfonte St | Fenkell St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15092 | Ellsworth St | Greenlawn St | Tuller St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15897 | Cheyenne St | Chalfonte St | Fenkell St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14632 | Keeler Ave | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15924 | Hartwell St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
17472 | Clements St | Lawton St | Linwood St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
14518 | Pinehurst St | Midland St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16574 | Tracey St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
16972 | Roselawn St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 2 | [16 empty] | District 2 |  |  |  | 119775.9774
15519 | Chalfonte St | Monica St | Santa Rosa Dr | Yes | 1 | Will be Installed 2021 | 7 |  |  | Coordinate with DPW Class C Resurfacing | [5 empty] | 0.121 |  | Monica | [5 empty] | District 7 |  |  | 342.7145 | 144454.0173 | 291 | 2021 | Monica from Fenkell to Chalfonte | Class C | SMD Survey | Pending Utility Review | Fenkell | Chalfonte | 6
15049 | Ellsworth St | Monica St | Livernois Ave | Yes | 2 | Will be Installed 2021 | 7 |  |  | Coordinate with DPW Class C Resurfacing | [5 empty] | 0.121 |  | Monica | [5 empty] | District 7 |  |  | 342.7145 | 144454.0173 | 291 | 2021 | Monica from Fenkell to Chalfonte | Class C | SMD Survey | Pending Utility Review | Fenkell | Chalfonte | 6
15343 | Desoto St | Monica St | Livernois Ave |  | 2 | 2020 Carryover | 7 |  |  | Coordinate with DPW Class C Resurfacing | [5 empty] | 0.121 |  | Monica | [5 empty] | District 7 |  |  | 342.7145 | 144454.0173 | 291 | 2021 | Monica from Fenkell to Chalfonte | Class C | SMD Survey | Pending Utility Review | Fenkell | Chalfonte | 6
15364 | Desoto St | Tuller St | Monica St |  | 1 | 2020 Carryover | 7 |  |  | Coordinate with DPW Class C Resurfacing | [5 empty] | 0.128 |  | Tuller | [5 empty] | District 7 |  |  | 339.4378 | 144454.0173 | 300 | 2021 | Tuller from Fenkell to Chalfonte | Class C | SMD Survey | Pending Utility Review | Fenkell | Chalfonte | 1
15069 | Ellsworth St | Tuller St | Monica St | Yes | 2 | Will be Installed 2021 | 7 |  |  | Coordinate with DPW Class C Resurfacing | [5 empty] | 0.128 |  | Tuller | [5 empty] | District 7 |  |  | 339.4378 | 144454.0173 | 300 | 2021 | Tuller from Fenkell to Chalfonte | Class C | SMD Survey | Pending Utility Review | Fenkell | Chalfonte | 1
28466 | Asbury Park | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 |  |  | Coordinate with DPW Residential Resurfacing | [5 empty] | 0.16 |  | Asbury Park | [5 empty] | District 7 |  |  | 360.477 | 144454.0173 | 36 | 2021 | Asbury Park from Joy to Ellis | Class A | 2020 Carryover |  | Joy | Ellis | 7 | No Conflicts | 16
18634 | Ohio St | Schoolcraft St | Intervale St | Yes | 3 | Will be Installed 2021 | 7 |  |  | Coordinate with DPW Residential Resurfacing | [5 empty] | 0.52 |  | Intervale | [5 empty] | District 7 |  |  | 805.1318 | 144454.0173 | 49 | 2021 | Intervale from Wyoming to Cloverlawn | Class A | 2020 Carryover |  | Wyoming | Cloverlawn | 7 | No Conflicts | 29 | Existing Speed Cushion
18644 | Wisconsin St | Schoolcraft St | Intervale St | Yes | 3 | Will be Installed 2021 | 7 |  |  | Coordinate with DPW Residential Resurfacing | [5 empty] | 0.52 |  | Intervale | [5 empty] | District 7 |  |  | 805.1318 | 144454.0173 | 49 | 2021 | Intervale from Wyoming to Cloverlawn | Class A | 2020 Carryover |  | Wyoming | Cloverlawn | 7 | No Conflicts | 29 | Existing Speed Cushion
28377 | Sussex | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 |  |  | Coordinate with DPW Residential Resurfacing | [5 empty] | 0.32 |  | Sussex | [5 empty] | District 7 |  |  | 1087.6933 | 144454.0173 | 61 | 2021 | Sussex from Chicago to Joy | Class A | 2020 Carryover |  | Chicago | Joy | 7 | No Conflicts | 12 | Speed hump to be installed
30374 | Coyle St | Payne Ave & Tireman Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS-706_40 | Construction | Tireman Greenfield to Hubbell | 0.49836 | Repair | WS-706 | Water | Tireman | Greenfield | Hubbell | 2018 | 2020 | 2019-05-13 | 8 | 7
30394 | Whitcomb St | Tireman Ave & Coleman Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS-706_40 | Construction | Tireman Greenfield to Hubbell | 0.49836 | Repair | WS-706 | Water | Tireman | Greenfield | Hubbell | 2018 | 2020 | 2019-05-13 | 8 | 7
30371 | Robson St | Tireman Ave & Mead Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS-706_40 | Construction | Tireman Greenfield to Hubbell | 0.49836 | Repair | WS-706 | Water | Tireman | Greenfield | Hubbell | 2018 | 2020 | 2019-05-13 | 8 | 7
30405 | Prest St | Tireman Ave & Yinger Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS-706_40 | Construction | Tireman Greenfield to Hubbell | 0.49836 | Repair | WS-706 | Water | Tireman | Greenfield | Hubbell | 2018 | 2020 | 2019-05-13 | 8 | 7
19944 | Petoskey Ave | Fullerton St | Leslie St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS-707_38 | Construction | Fullerton Petoskey to Dexter | 0.24785 | Repair | WS-707 | Water | Fullerton | Petoskey | Dexter | 2019 | 2020 | 2019-05-13 | 8 | 7
31581 | Parkland St | Sawyer St | Rockdale St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood | Sawyer | Parkland ST | 2020 | 2022 | 2020-01-16 | 8 | 7
30884 | Parkland St | Dacosta | Lamphere St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31047 | Lamphere St | Tireman St | Parkland St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16 |  |  | PC-808 Far West Detroit
31894 | Lamphere St | Sawyer St | Tireman St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31909 | Beaverland St | Sawyer St | Tireman St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16 |  |  | PC-808 Far West Detroit
31904 | Sawyer St | Bramell St | Chatham St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29976 | Beaverland St | Constance Ave | Parkland St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16 |  |  | PC-808 Far West Detroit
32428 | Beaverland St | Majestic Ave | Sawyer St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31875 | Dolphin St | Sawyer St | Tireman St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16 |  |  | PC-808 Far West Detroit
32898 | Rockdale St | Rockdale Ave & W Warren Rd | Majestic Ave | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31373 | Parkland St | Rockdale St | Tireman St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31090 | Tireman St | City/Twp Line | Beaverland St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood | Tireman | Sawyer | 2020 | 2022 | 2020-01-16 | 8 | 7 | Far West Detroit
31019 | Parkland St | Tireman St | Dacosta | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30486 | Parkland St | Lamphere St | Belton Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31046 | Tireman St | Lamphere St | Dacosta | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31062 | Chatham St | Tireman St | Belton Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16 |  |  | PC-808 Far West Detroit
32886 | Parkland St | W Warren Rd | Majestic Ave | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood | Parkland | Heyden | 2020 | 2022 | 2020-01-16 | 8 | 7 | PC-808 Far West Detroit
31868 | Rockdale St | Sawyer St | Parkland St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31069 | Tireman St | Bramell St | Chatham St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_1 | Design | Far West Detroit | 0 | Construction | WS-720 | Water | Within Neighborhood | Tireman | Constance | 2020 | 2022 | 2020-01-16 | 8 | 7 | Far West Detroit
28564 | Artesian St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
28549 | Greenview Ave | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
28567 | Warwick St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31506 | Heyden St | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33047 | Greenview Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
32454 | Heyden St | W Warren Rd & W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33041 | Faust Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
29625 | Grandville Ave | Constance Ave | Van Buren Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31452 | Piedmont St | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33029 | Ashton Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
32471 | Patton St | W Warren Rd | Braile St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Parkland | Heyden | 2020 | 2022 | 2020-01-16 | 8 | 7
31409 | Penrod St | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31430 | Stahelin Ave | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31423 | Sawyer St | Brace St | Greenview Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32410 | Artesian St | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31405 | Rosemont Ave | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30614 | Plainview Ave | Tireman St | Belton Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33078 | Warwick St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
29382 | Vaughan St | Van Buren Ave | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32399 | Brace St | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31512 | Stout St | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33032 | Rosemont Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
32446 | Auburn St | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30903 | Braile St | Tireman St | Belton Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30373 | Vaughan St | Belton Ave | Constance Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Belton | Constance | 2020 | 2022 | 2020-01-16 | 8 | 7 | Warrendale
32415 | Warwick St | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30073 | Grandville Ave | Belton Ave | Constance Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32426 | Grandville Ave | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30061 | Warwick St | Belton St | Constance St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32420 | Piedmont St | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29152 | Plainview Ave | Van Buren Ave | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
28868 | Plainview Ave | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32371 | Ashton Ave | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30390 | Stout St | Belton Ave | Constance Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29868 | Vaughan St | Constance Ave | Van Buren Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32367 | Patton St | Braile St | Sawyer St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31488 | Sawyer St | Plainview Ave | Auburn St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29100 | Piedmont St | Van Buren Ave & Van Buren St | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29142 | Auburn St | Van Buren Ave | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30446 | Trinity St | Belton Ave | Constance Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29092 | Warwick St | Van Buren St | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31520 | Sawyer St | Fielding St | Stout St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32395 | Greenview Ave | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29441 | Burt Rd | Van Buren Ave | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31417 | Faust Ave | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30102 | Plainview Ave | Belton Ave | Constance Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33055 | Brace St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
32387 | Faust Ave | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32380 | Penrod St | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
28882 | Vaughan St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31484 | Auburn St | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30000 | Ashton Ave | Belton St | Constance St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31457 | Grandville Ave | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31534 | Sawyer St | Braile St | Patton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31434 | Sawyer St | Artesian St | Stahelin Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31460 | Sawyer St | Westwood | Grandville Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32407 | Stahelin Ave | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32456 | Stout St | W Warren Rd | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Parkland | Heyden | 2020 | 2022 | 2020-01-16 | 8 | 7
28608 | Auburn St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30914 | Trinity St | Tireman St | Belton Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31441 | Warwick St | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31489 | Plainview Ave | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32368 | Braile St | Patton St | Sawyer St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31498 | Vaughan St | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31420 | Greenview Ave | Sawyer St | Tireman St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33063 | Stahelin Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
31451 | Sawyer St | Piedmont St | Warwick St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29655 | Plainview Ave | Constance Ave | Van Buren Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
31505 | Sawyer St | Heyden St | Vaughan St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
30883 | Stout St | Tireman St | Belton Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
32450 | Vaughan St | W Warren Ave | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34920 | Kirkwood St | Rosemont Ave | Ashton Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34925 | Piedmont St | Kirkwood St | Dayton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34372 | Vaughan St | Ann Arbor Trl | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33401 | Plainview Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
34475 | Piedmont St | Dayton St | Paul Dr | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34450 | Faust Ave | Dayton St | Paul Dr | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34006 | Faust Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34943 | Stahelin Ave | Kirkwood St | Dayton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33382 | Westwood | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
34398 | Stahelin Ave | Paul St | Dayton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34942 | Kirkwood St | Stahelin Ave | Brace St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33388 | Minock St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
34061 | Plainview Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33395 | Auburn St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
34472 | Warwick St | Dayton St | Paul Dr | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33370 | Piedmont St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Heyden | Evergreen | 2020 | 2022 | 2020-01-16 | 8 | 7
34002 | Penrod St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34048 | Westwood | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34038 | Piedmont St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
33996 | Rosemont Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34921 | Rosemont Ave | Kirkwood St | Dayton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34437 | Rosemont Ave | Dayton St | Paul Dr | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34932 | Faust Ave | Kirkwood St | Dayton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34953 | Warwick St | Kirkwood St | Dayton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34026 | Stahelin Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34444 | Penrod St | Dayton St | Paul Dr | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34933 | Kirkwood St | Greenview Ave | Faust Ave | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood | Kirkwood | Dayton | 2020 | 2022 | 2020-01-16 | 8 | 7 | Warrendale
33990 | Ashton Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
35417 | Faust Ave | Unknown | Kirkwood St | Yes | 2 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
35469 | Stahelin Ave | Ford Rd | Kirkwood St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34019 | Brace St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34968 | Auburn St | Kirkwood St | Dayton St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34035 | Warwick St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34952 | Kirkwood St | Warwick St | Artesian St | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
34493 | Auburn St | Dayton St | Paul Dr | Yes | 1 | Will be Installed 2021 | 7 |  | Coordinate with DWSD - Water |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | WS720_2 | Design | Warrendale | 0 | Construction | WS-720 | Water | Within Neighborhood |  |  | 2020 | 2022 | 2020-01-16
29409 | Belton St | Appoline Ave | Meyers Rd | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173 | [12 empty] | CS-1909A_201 | Procurement | Appoline Joy to Tireman | 0.50836 | Repair | CS-1909A | Water | Appoline | Joy | Tireman | 2020 | 2022 | 2019-05-13 | 8 | 7 | Aviation Sub
29385 | Belton St | Manor | Pinehurst St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173 | [12 empty] | CS-1909A_203 | Procurement | Pinehurst Joy to Tireman | 0.5046 | Repair | CS-1909A | Water | Pinehurst | Joy | Tireman | 2020 | 2022 | 2019-05-13 | 8 | 7 | Aviation Sub
27893 | Ohio St | Joy Rd | Stawell St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173 | [12 empty] | CS-1909A_215 | Procurement | Joy Road Wyoming to Livernois | 1.0003 | Repair | CS-1909A | Water | Joy Road | Wyoming | Livernois | 2020 | 2022 | 2019-05-13 | 8 | 6 | Barton-McFarland
28550 | Littlefield St | Mackenzie St | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173 | [12 empty] | CS-1909A_25 | Procurement | Barton-McFarland | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
28497 | Mackenzie St | Normile St | Wyoming St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173 | [12 empty] | CS-1909A_25 | Procurement | Barton-McFarland | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
29864 | Northlawn St | Tireman Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173 | [12 empty] | CS-1909A_25 | Procurement | Barton-McFarland | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
19015 | Petoskey Ave | Tyler St | Waverly | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 144454.0173
19898 | Monica St | W Buena Vista St | W Davison St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 144454.0173
23054 | Monica St | Webb St | Tuxedo St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 144454.0173
19472 | Petoskey Ave | Glendale St | W Buena Vista St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 144454.0173
24406 | Stoepel St | Barr St | Georgeland St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 144454.0173
23906 | Stoepel St | Annland St | Stearns St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 144454.0173
27973 | Burt Rd | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  | 2021 Risk Rank | Burt | Joy | Westfield | 6/11/2020 | NAD 1983 | Detroit | Burt (Joy-Westfield) |  | 64370.9106 | 1646.6544 | 144454.0173
28513 | Mackenzie St | Esper St | Freda St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
27884 | Northlawn St | Joy Rd | Stawell St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
24483 | Monica St | Grand River Ave | Burlingame St | Yes | 3 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021WCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 6/29/2020 | NAD 1983 | Detroit | West-Central Detroit 1 (WCDet1) | WCDet1 | 3398649.8427 | 17062.7053 | 144454.0173
28498 | Normile St | Mackenzie St | Esper St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
28438 | Roselawn St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
28569 | Sorrento St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
28435 | Burt Rd | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  | 2021 Risk Rank | Burt | Joy | Westfield | 6/11/2020 | NAD 1983 | Detroit | Burt (Joy-Westfield) |  | 64370.9106 | 1646.6544 | 144454.0173
28485 | Kentucky St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
26451 | Saint Marys St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  | 2021 Risk Rank | St Marys | Chicago | Plymouth | 6/11/2020 | NAD 1983 | Detroit | St. Marys (Chicago-Plymouth) |  | 126041.898 | 2377.5019 | 144454.0173
29899 | Normile St | Normile Ave & Tireman Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29140 | Middlepoint St | Belton St | Esper St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29364 | Belton St | Mendota St | Middlepoint St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
30032 | Carlin St | Neckel Ave & Tireman Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29445 | Belton St | Cheyenne St | Ward St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29105 | Normile St | Belton St | Mackenzie St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29461 | Hartwell St | Belton St | Mackenzie St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
30014 | Hartwell St | Tireman Ave & Calhoun Ave | Belton St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29071 | Indiana St | Belton St | Mackenzie St | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
28863 | Hartwell St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29119 | Belton St | Freda St | Normile St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
28937 | Burt Rd | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal |  |  | 2021 Risk Rank | Burt | Joy | Westfield | 6/11/2020 | NAD 1983 | Detroit | Burt (Joy-Westfield) |  | 64370.9106 | 1646.6544 | 144454.0173
29129 | E Morrow Cir | Belton St | E Morrow Cir | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29460 | Belton St | Hartwell St | Bingham Ave | Yes | 1 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
29478 | Carlin St | Belton St | Van Buren St | Yes | 3 | Will be Installed 2021 | 7 | Coordinate with DTE GRP |  |  | 0 | DTE Gas - GRP | Design - Planning | Gas Main Renewal | SEGRID2021SCDet1 |  | 2021 MGA Grid | Multiple | Multiple | Multiple | 2/3/2020 | NAD 1983 | Detroit (Possbly a bit in Dearborn) | South-Central Detroit 1 (SCDet1) | SCDet1 | 4079245.6847 | 9802.5269 | 144454.0173
20545 | Elmhurst St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
19565 | Sturtevant St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
21069 | Webb St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
21587 | Lawrence St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
19901 | Cortland St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
20941 | Tuxedo St | Dexter | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
20011 | Richton St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
27427 | Heyden St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_158 | Procurement | W. Chicago Stout to Evergreen | 0.19281 | Repair | CS-1909A | Water | W. Chicago | Stout | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27414 | Vaughan St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_158 | Procurement | W. Chicago Stout to Evergreen | 0.19281 | Repair | CS-1909A | Water | W. Chicago | Stout | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27575 | Ashton Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_160 | Procurement | Cathedral Grandville to Southfield Freeway | 0.25597 | Repair | CS-1909A | Water | Cathedral | Grandville | Southfield Freeway | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27103 | Westfield St | Faust Ave | Penrod St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_164 | Procurement | Faust W. Chicago to Cathedral | 0.23763 | Repair | CS-1909A | Water | Faust | W. Chicago | Cathedral | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26100 | Pierson St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26049 | Vaughan St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26870 | Westwood | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26088 | Braile St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26081 | Patton St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27877 | Cloverlawn St | Joy Rd | Stawell St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_215 | Procurement | Joy Road Wyoming to Livernois | 1.0003 | Repair | CS-1909A | Water | Joy Road | Wyoming | Livernois | 2020 | 2022 | 2019-05-13 | 8 | 6 | Barton-McFarland
27868 | Roselawn St | Joy Rd | Stawell St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_215 | Procurement | Joy Road Wyoming to Livernois | 1.0003 | Repair | CS-1909A | Water | Joy Road | Wyoming | Livernois | 2020 | 2022 | 2019-05-13 | 8 | 6 | Barton-McFarland
25438 | Braile St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_216 | Procurement | Plymouth Redford City Limit to Evergreen | 1.5501 | Repair | CS-1909A | Water | Plymouth | Redford City Limit | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | West Outer Drive
24935 | W Parkway St | Plymouth Rd | Wadsworth St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_216 | Procurement | Plymouth Redford City Limit to Evergreen | 1.5501 | Repair | CS-1909A | Water | Plymouth | Redford City Limit | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | West Outer Drive
24906 | Chatham St | Plymouth Rd | Wadsworth St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_216 | Procurement | Plymouth Redford City Limit to Evergreen | 1.5501 | Repair | CS-1909A | Water | Plymouth | Redford City Limit | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | West Outer Drive
23610 | Hartwell St | Plymouth Rd | Wadsworth St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_217 | Procurement | Plymouth Schaefer to Wyoming | 1.0046 | Repair | CS-1909A | Water | Plymouth | Schaefer | Wyoming | 2020 | 2022 | 2019-05-13 | 8 | 7 | Pride Area Community
28037 | Hartwell St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_25 | Procurement | Barton-McFarland | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
24471 | Hartwell St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_25 | Procurement | Barton-McFarland | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
27096 | W Parkway St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_32 | Procurement | West Outer Drive | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood | Tireman | Plymouth | 2020 | 2021 | 2020-01-10 | 8 | 7 | West Outer Drive
28995 | Prest St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_33 | Procurement | Fiskhorn | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
28988 | Whitcomb St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_33 | Procurement | Fiskhorn | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
29918 | Trinity St | Constance Ave | Van Buren Ave | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_38 | Procurement | Rouge Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
28946 | Trinity St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_38 | Procurement | Rouge Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
32477 | Pierson St | W Warren Rd | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [11 empty] | District 7 |  |  |  | 144454.0173 | [12 empty] | CS-1909A_38 | Procurement | Rouge Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood | Parkland | Heyden | 2020 | 2021 | 2020-01-10 | 8 | 7
18514 | Clements St | Petoskey Ave | Holmur St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
18379 | Clements St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
18978 | Glendale St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
15532 | Chalfonte St | San Juan Dr | Prairie St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
15504 | Chalfonte St | Stoepel St | Livernois Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
15548 | Chalfonte St | Cloverdale St | Turner St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
18033 | Clements St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
18934 | Clements St | Livernois Ave | Petoskey Ave | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
18596 | Roselawn St | Schoolcraft St | Intervale St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
22408 | Hartwell St | Capitol St | Foley St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23644 | Cedarlawn St | Mendota St | Griggs St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23609 | Stahelin Ave | Wadsworth St | Dead End or Start | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
22855 | Capitol St | Rutherford St | Forrer St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23129 | Wadsworth St | Hubbell St | Strathmoor St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20480 | Petoskey Ave | Cortland St | Sturtevant St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20563 | Fullerton St | Old Mill Pl | Broadstreet Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
19408 | Indiana St | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23406 | Wadsworth St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23430 | Montrose St | Wadsworth St | Capitol St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23045 | Wadsworth St | Shirley Ave | Schaefer Hwy | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
22911 | Castleton St | Shirley Ave | Schaefer Hwy | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23368 | Petoskey Ave | W Boston Blvd | Collingwood St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23422 | Winthrop St | Wadsworth St | Capitol St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23046 | Shirley Ave | Wadsworth St | Castleton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20049 | Leslie St | Broadstreet Ave | Petoskey Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20466 | Fullerton St | Broadstreet Ave | Petoskey Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20906 | Fullerton St | Livernois | Old Mill Pl | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23065 | Collingwood St | Broadstreet Ave | N Martindale St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
19426 | Fullerton St | Dexter | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
21505 | Northlawn St | Cortland St | Fullerton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23407 | Prest St | Wadsworth St | Castleton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
21545 | Kentucky St | Cortland St | Fullerton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
22369 | Washburn St | Grand River Ave | Fullerton St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23121 | Strathmoor St | Wadsworth St | Capitol St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20992 | Indiana St | Fullerton St | W Buena Vista St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23453 | Wadsworth St | Rutherford St | Forrer St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23351 | Wadsworth St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
19943 | Fullerton St | Petoskey Ave | Holmur St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23387 | Sussex | Wadsworth St | Castleton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23020 | Hartwell St | Wadsworth St | Capitol St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20072 | W Buena Vista St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23536 | W Boston Blvd | N Martindale St | Otsego St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23429 | Wadsworth St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23361 | Wadsworth St | Robson St | Terry St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
21539 | Indiana St | Cortland St | Fullerton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23386 | Wadsworth St | Sussex | Coyle St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
20453 | Leslie St | Old Mill Pl | Broadstreet Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23001 | Collingwood St | N Martindale St | Petoskey Ave | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24415 | Steel St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26624 | Piedmont St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25645 | Abington Ave | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27080 | Ashton Ave | Westfield St | Fitzpatrick St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23956 | Sussex | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27904 | Vaughan St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26921 | Vaughan St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24497 | Auburn St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26465 | Mettetal St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26617 | Warwick St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27399 | Plainview Ave | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27614 | Stahelin Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25136 | Westwood | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26039 | Decatur St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27673 | Grandville Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27361 | Grandville Ave | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23990 | Winthrop St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25976 | Cheyenne St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25384 | Vaughan St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25010 | Archdale St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26917 | Robson St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26859 | Grandville Ave | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27940 | Patton St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27507 | Trinity St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27535 | Dawes St | Wyoming St | Stawell St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27627 | Artesian St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25131 | Grandville Ave | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28069 | Dover St | Greenview Ave | Faust Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24569 | Lauder St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27113 | Stahelin Ave | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26514 | Rutland St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24459 | Littlefield St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25098 | Warwick St | Elmira St | Fitzpatrick St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26613 | Hartwell St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25990 | Littlefield St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25359 | Decatur St | Orangelawn St | Keal St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25867 | Rutland St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27518 | Hartwell St | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28442 | Trinity St | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26006 | Hartwell St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28079 | Stahelin Ave | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28363 | Plainview Ave | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24994 | Rutland St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26116 | N Martindale St | Grand River Ave | Joy Rd | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27867 | Rutherford St | Ellis St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25551 | Morley | Griggs St | Wyoming St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28070 | Greenview Ave | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28364 | Robson St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25127 | Hartwell St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27374 | Westwood | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25939 | Appoline | W Chicago St | Elmira St | Yes | 4 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28372 | Vaughan St | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25463 | Lauder St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25033 | Elmira St | Rosemont Ave | Ashton Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27922 | Esper St | Joy Rd | Otto St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27977 | Trinity St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25073 | Sorrento St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27612 | Sussex | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27860 | Westwood | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27087 | Westfield St | Rosemont Ave | Ashton Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25023 | Elmira St | Ashton Ave | Southfield Service Drive | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26969 | Winthrop St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26861 | Carlin St | Westfield St | W Chicago St & Carlin Ave | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26956 | Patton St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26528 | Longacre St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28032 | Littlefield St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24877 | Winthrop St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28082 | Artesian St | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24425 | Sorrento St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23885 | Strathmoor St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25378 | Elmira St | Plainview Ave | Auburn St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28368 | Coyle St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26948 | Prest St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25034 | Rosemont Ave | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25537 | Winthrop St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27407 | Northlawn St | Stawell St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24562 | Marlowe St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24532 | Fielding St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26519 | Archdale St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27883 | Plainview Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26895 | Ohio St | Dawes St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25142 | Carlin Ave | Orangelawn St | Keal St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27613 | Cathedral St | Stahelin Ave | Brace St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25994 | Westwood | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27404 | Robson St | Cathedral St | Unknown & Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27129 | Warwick St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27587 | W Parkway St | Hazelton Ave | Meadow Park | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26026 | Carlin Ave | W Chicago St & Carlin St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27593 | Robson St | Ellis St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28024 | Cheyenne St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26572 | Sorrento St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25887 | Archdale St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27663 | Winthrop St | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26119 | Lauder St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26142 | Coyle St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27637 | Prest St | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23949 | Coyle St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25104 | Littlefield St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26478 | Asbury Park | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26395 | Winthrop St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24449 | Cheyenne St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28468 | W Parkway St | Dover Ave | Meadow Park St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25094 | Cheyenne St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25456 | Marlowe St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25118 | Piedmont St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28058 | Dover St | Penrod St | Rosemont Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27586 | Esper St | Otto St | Stawell St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26110 | Marlowe St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
27395 | Cloverlawn St | Stawell St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26542 | Manor | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25985 | Grandville Ave | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26373 | Prest St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
23984 | Prest St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
26905 | Lauder St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
24593 | Ohio St | Orangelawn St | Beechdale St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25973 | Piedmont St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
25507 | Whitcomb St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32047 | Grandmont Ave | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32939 | Montrose St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32963 | Saint Marys St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32974 | Whitlock St | Asbury Park | Mettetal St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
30978 | Forrer St | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32046 | Woodmont Ave | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31525 | Woodmont Ave | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
28905 | Patton St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32052 | Abington Ave | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32975 | Asbury Park | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31009 | Woodmont Ave | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
29928 | Saint Marys St | Belton St | Constance St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32955 | Mansfield St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
29587 | Whitcomb St | Belton St | Mackenzie St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31531 | Grandmont Ave | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
30452 | Saint Marys St | Tireman St | Belton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33021 | Archdale St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32025 | Mansfield St | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31542 | Memorial St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32942 | Forrer St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33000 | Memorial St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31022 | Abington Ave | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31039 | Rutland St | Diversey | Rutland Ave & Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
29449 | Trinity St | Van Buren Ave | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31030 | Memorial St | Diversey | Tireman St & Memorial Ave | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
29038 | W Parkway St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31491 | Rutherford St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32984 | Grandmont Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31540 | Pierson St | Sawyer St | Dead End or Start | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31538 | Abington Ave | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32935 | Winthrop St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
30467 | Asbury Park | Tireman St | Belton Ave & Belton St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31014 | Grandmont Ave | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32056 | Memorial St | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31508 | Mettetal St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
30481 | Abington Ave | Tireman St | Belton Ave | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
30999 | Mettetal St | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
30988 | Mansfield St | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33016 | Longacre St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
29594 | Prest St | Belton St | Mackenzie St | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31496 | Mansfield St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
31560 | Rutland St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
32954 | Whitlock St | Mansfield St | Rutherford St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33961 | Rutland St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33931 | Asbury Park | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33915 | Mansfield St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33436 | Winthrop St | Radcliffe St | Whitlock St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33894 | Winthrop St | Paul Dr | Radcliffe St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33948 | Abington Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33962 | Longacre St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33942 | Grandmont Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33975 | Archdale St | City/Twp Line | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33920 | Saint Marys St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33899 | Montrose St | Paul Dr | Radcliffe St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173
33439 | Montrose St | Radcliffe St | Whitlock St | Yes | 1 | Will be Installed 2021 | 7 | [16 empty] | District 7 |  |  |  | 144454.0173

## Dist 1, 2, 7 Clear
Speed Hump Program | [7 empty] | Utility Coordination |  |  | DTE GRP Projects | [18 empty] | DPW Resurfacing Coordination | [12 empty] | DWSD Coordination
Sami Kaffarani | [7 empty] | Sam Krassenstein |  |  | Brandon Francis | [18 empty] | Pam Lemme, Steve Bannasch | [12 empty] | Rodney Burlett, Pei Boayue, Mohamad Jaber
OBJECTID | RDNAME | FROMDESC | TODESC | Selected_Blocks | COUNT | site_status | DistrictNu | DTE Coordination | DWSD Coordination | DPW Coordination | Id | Agency | Phase | Activity | Project_ID | Length | Contract | Proj_Type | Street | From_ | To | Last_Updat | Datum | Municipali | Name | Name_1 | Shape__Area | Shape__Length | Shape_Leng | GIS_ID | Target_Year | Project_Name | Road_Type | Project_Notes | Utility_Status | From | To | District_Number | DTE_Review | DWSD_Review | Pave Order | Speed_Hump | Unique_ID | ProjectPHA | ProjNamLOC | Length_MI | ActTYP | ContNMBR | ProjectTYP | StreetCRRD | StreetFROM | StreetTo | EstCstBDAT | EstCstNDAT | LsUPATE | Diameter | District | Neighborhood
17417 | Grandville Ave | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09 |  |  | Rosedale Park
18516 | Acacia St | Piedmont St | Warwick St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16597 | Chalfonte St | Piedmont St | Warwick St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09 |  |  | Rosedale Park
16838 | Plainview Ave | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16651 | Auburn St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_15 | Procurement | Westwood Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
2027 | Hessel Ave | Ashton Ave | Rosemont Ave | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_179 | Procurement | Rosemont Fargo to Hessel | 0.25537 | Repair | CS-1909A | Water | Rosemont | Fargo | Hessel | 2020 | 2022 | 2019-05-13 | 8 | 1 | O'Hair Park
12906 | Woodbine St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_19 | Procurement | South of Six | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
20978 | Glendale St | Woodmont Ave | Asbury Park | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_199 | Procurement | Woodmont Fullerton to Schoolcraft | 0.48375 | Repair | CS-1909A | Water | Woodmont | Fullerton | Schoolcraft | 2020 | 2022 | 2019-05-13 | 8 | 1 | Schoolcraft-I96
20343 | W Davison St | Woodmont Ave | Asbury Park | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_199 | Procurement | Woodmont Fullerton to Schoolcraft | 0.48375 | Repair | CS-1909A | Water | Woodmont | Fullerton | Schoolcraft | 2020 | 2022 | 2019-05-13 | 8 | 1 | Schoolcraft-I96
18882 | Kendall St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_200 | Procurement | Montrose Schoolcraft to Grand River | 0.44364 | Repair | CS-1909A | Water | Montrose | Schoolcraft | Grand River | 2020 | 2022 | 2019-05-13 | 8 | 1 | Greenfield-Grand River
18119 | Acacia St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_200 | Procurement | Montrose Schoolcraft to Grand River | 0.44364 | Repair | CS-1909A | Water | Montrose | Schoolcraft | Grand River | 2020 | 2022 | 2019-05-13 | 8 | 1 | Greenfield-Grand River
19040 | Kendall St | Piedmont St | Warwick St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_22 | Procurement | Grandmont #1 | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
18988 | Rosemont Ave | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_22 | Procurement | Grandmont #1 | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
19009 | Greenview Rd | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_22 | Procurement | Grandmont #1 | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
18654 | Whitcomb St | Kendall St | Grand River Ave | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_39 | Procurement | Cadillac Comunity | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
20434 | Prest St | Tyler St | Schoolcraft St | Yes | 3 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_39 | Procurement | Cadillac Comunity | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood | Greenfield | Grand River | 2020 | 2021 | 2020-01-10 | 8 | 1
15027 | Midland St | Plainview Ave | Auburn St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_5584 | Procurement | Auburn Fenkell to Midland | 0.26321 | Repair | CS-1909A | Water | Auburn | Fenkell | Midland | 2020 | 2022 | 2019-05-13 | 8 | 1 | Minock Park
11489 | Prevost St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
15625 | Mansfield St | Fenkell St | Keeler St |  | 1 | 2020 Carryover | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16022 | Mettetal St | Ellsworth St | Fenkell St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16153 | Winthrop St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
15612 | Rutherford St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
16008 | Saint Marys St | Ellsworth St | Fenkell | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
15636 | Saint Marys St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11402 | Robson St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11327 | Freeland St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11429 | Whitcomb St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11387 | Lauder St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11435 | Prest St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11374 | Marlowe St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11413 | Coyle St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 |  |  |  |  | DWSD | [12 empty] | District 1 |  |  |  | 104963.2692 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3070 | Trojan St | Blackstone St | Trinity St & Griffin Drain | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3367 | Stahelin Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4066 | Grandview St | Fargo St | Norfolk St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2082 | Hessel Ave | Avon Ave | Stahelin Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3191 | Norfolk St | Cherokee St | Berg Rd | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2415 | Vaughan St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2930 | Plainview Ave | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4546 | Saint Martins Ave | Sunderland Rd | Stahelin Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3532 | Stout St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4532 | Stahelin Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2897 | Huntington Rd | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4429 | Pembroke Ave | Greydale Ave | Burgess St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3521 | Norfolk St | Fenton St | Woodbine St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3320 | Faust Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4590 | Grandville Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3847 | Greydale Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4450 | Ashton Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3862 | Pembroke Ave | Faust Ave | Glastonbury Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2028 | Rosemont Ave | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3890 | Northrop St | Fargo St | Chippewa St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3183 | Rosemont Ave | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2987 | Kentfield St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4402 | Woodbine St | Leewin St | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2997 | Stout St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4077 | Kentfield St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2474 | Hessel Ave | Braile St & Griffin Drain | Patton St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3512 | Kentfield St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3019 | Trojan St | Braile St | Patton St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2494 | Hessel Ave | Burt Rd | Pierson St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3487 | Norfolk St | Salem St | Grandview St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4430 | Greydale Ave | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3872 | Cooley St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2996 | Trojan St | Stout St | Kentfield St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3901 | Stahelin Ave | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2830 | Stahelin Ave | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3163 | Trojan St | Greydale Ave | Burgess St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2058 | Hessel Ave | Faust Ave | Greenview Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2566 | Hessel Ave | Chapel St | Bentler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3131 | Trojan St | Chapel St | Bentler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2083 | Stahelin Ave | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2352 | Hessel Ave | Annchester Rd | Huntington Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3460 | Norfolk St | Winston St | Fenton St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4481 | Northrop St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2425 | Hessel Ave | Heyden St | Vaughan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4573 | Shaftsbury Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2594 | Hessel Ave | Greydale Ave | Burgess St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4045 | Fargo St | Fenton St | Woodbine St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3838 | Pembroke Ave | Rosemont Ave | Ashton Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3499 | Vaughan St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4078 | McIntyre St | Leewin St | Chippewa St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3473 | Grandview St | Norfolk St | Shiawassee Dr | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4093 | Stout St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4494 | McIntyre St | Pembroke Ave | Leewin St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3841 | Woodbine St | Chippewa St | Norfolk St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2515 | Hessel Ave | Blackstone Ct & Blackstone St | Trinity St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2972 | Trojan St | Heyden St | Vaughan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2377 | Hessel Ave | Plainview Ave | Westmoreland Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4667 | Vaughan St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4357 | Pembroke Ave | Blackstone St | Trinity St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2955 | Vaughan St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4048 | Vaughan St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3044 | Trojan St | Burt Rd | Pierson St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
3176 | Greydale Ave | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
2452 | Hessel Ave | Stout St | Kentfield St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4567 | Saint Martins Ave | Shaftsbury Ave | Warwick St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4469 | Houghton St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5319 | Shaftsbury Ave | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7520 | Fielding St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5357 | Annchester Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5511 | Trinity St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7364 | Glenhurst St | Kress/Glenhurst Cutoff & Grayfield St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7969 | Woodbine St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4828 | Grandview St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8421 | Pickford St | Heyden St | Vaughan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5366 | Westmoreland Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6947 | Beaverland St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5489 | Pierson St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5953 | Annchester Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5919 | Huntington Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6071 | Trinity St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7465 | Shiawassee Dr | Kress St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7462 | Vaughan St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5171 | Sunderland Rd | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6095 | Riverview St | Vassar Ave | Verdun St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7531 | Patton St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6533 | Plainview Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7610 | Glenhurst St | Clarita St | Kress St & Glenhurst/Grayfield Cutoff | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5074 | Frisbee St | Lenore Ave | Woodbine St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5588 | Greydale Ave | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6927 | Cooley St | W 7 Mile Rd | Vassar Ave | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5559 | Chapel St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8447 | Woodbine St | Grand River Ave | Clarita St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5856 | Sunderland Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6933 | Houghton St | W 7 Mile Rd | Vassar Ave | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5865 | Warwick St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5089 | Cooley St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5349 | Edinborough Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6388 | Greenview Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
9087 | Pickford St | Fenton St | Lenore Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8448 | Pickford St | Stout St | Kentfield St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
9510 | Cooley St | Curtis St | Karl St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8896 | Cooley St | Pickford St | Roxford St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5328 | Vassar Ave | Grandville Ave | Shaftsbury Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5180 | Warwick St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5935 | Edinborough Rd | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6850 | Trinity St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6471 | Huntington Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
9074 | Lenore Ave | Margareta St | Pickford St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6489 | Edinborough Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5339 | Huntington Rd | Vassar Ave | Pembroke Ave | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5567 | Verdun St | Riverview St | Appleton St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6997 | Shiawassee Dr | W 7 Mile Rd | Verdun St | Yes | 4 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5546 | Bentler St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7346 | Grandview St | W 7 Mile Rd | Frisbee St | Yes | 5 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6418 | Sunderland Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8436 | Kentfield St | Pickford St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8440 | Glenhurst St | Grayfield St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5540 | Shiawassee Dr | Verdun St | Frisbee St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6451 | Chapel St | Cambridge Ave | Vassar Ave | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5179 | Vassar Ave | Warwick St | Sunderland Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7570 | Burt Rd | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8458 | Fielding St | Pickford St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7873 | Chapel St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5119 | Frisbee St | Winston St | Lenore Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
4972 | Blackstone St | Pembroke Ave | St Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5329 | Grandville Ave | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7022 | Riverview St | Vassar Ave | 7 Mile Rd W | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5054 | Greydale Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7492 | Kentfield St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7559 | Pierson St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6084 | Blackstone St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5568 | Riverview St | Verdun St | Frisbee St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8414 | Vaughan St | Pickford St | Clarita St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5020 | Chapel St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5004 | Bentler St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7325 | Winston St | W 7 Mile Rd | Frisbee St | Yes | 5 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6069 | Appleton St | Verdun St | Appleton St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5099 | Houghton St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5142 | Grandview St | Frisbee St | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7866 | Bentler St | Clarita St | W 7 Mile Rd | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6107 | Dale St | Vassar Ave | Verdun St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6885 | Bentler St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6111 | Bentler St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6403 | Stahelin Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
8482 | Shiawassee Dr | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
7624 | Shiawassee Dr | Clarita St | Kress St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
9416 | Bentler St | Curtis St | Karl St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6430 | Riverview St | Vassar Ave | 7 Mile Rd W | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6938 | McIntyre St | W 7 Mile Rd | Vassar Ave | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
6517 | Westmoreland Rd | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5599 | Verdun St | Telegraph Rd | Dale St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
5903 | Grandville Ave | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11997 | Wormer St | W McNichols Rd | Santa Maria St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13475 | Ferguson St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12465 | Prest St | Florence St | Grove St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14015 | Mansfield St | Pilgrim St | Puritan St |  | 1 | 2020 Carryover | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14044 | Asbury Park | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12429 | Florence St | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13882 | Florence St | Salem St | Winston St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
9827 | Lenore Ave | Pickford St | Curtis St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12407 | Florence St | Robson St | Lauder St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12344 | Florence St | Strathmoor St | Mark Twain St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13519 | Vaughan St | Grand River Ave | Verne St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12109 | Mansfield St | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12464 | Florence St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13654 | Florence St | Wormer St | Woodbine St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10030 | Fielding St | Marian Pl | Glenco St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12369 | Florence St | Marlowe St | Hubbell St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13135 | Fenton St | Grove St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10382 | Santa Clara Ave | Patton St | Fielding St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13040 | Forrer St | Hemlock St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10383 | Patton St | Santa Clara Ave | Marian Pl | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13423 | Heyden St | Grand River Ave | Verne St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12423 | Coyle St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
9903 | Bentler St | Thatcher Ave | Glenco St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13061 | Mark Twain St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10452 | Bentler St | Santa Clara Ave | Bennett St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13935 | Prest St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10371 | Fielding St | Santa Clara Ave | Marian Pl | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13343 | Whitcomb St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12449 | Whitcomb St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14116 | Burgess St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12408 | Robson St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13894 | Coyle St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12900 | Asbury Park | Florence St | Verne St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13056 | Prevost St | Hemlock St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13655 | Wormer St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13837 | Florence St | Fenton St | Lenore Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14064 | Biltmore St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11537 | Murray Hill St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14083 | Lindsay St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13360 | Prest St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14053 | Ferguson St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13514 | Lindsay St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12524 | Pierson St | Grand River Ave | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12132 | Florence St | Freeland St | Ardmore St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11504 | Rutherford St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10881 | Patton St | Santa Maria St | Santa Clara Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10836 | Vaughan St | Santa Maria St | Santa Clara Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10494 | Wormer St | Bennett St | Curtis St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12583 | Braile St | Grand River Ave | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13535 | Harlow St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13136 | Coyle St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13916 | Whitcomb St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13561 | Fenmore St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11508 | Mansfield St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12329 | Asbury Park | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10050 | Patton St | Marian Pl | Glenco St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13488 | Biltmore St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
10875 | Fielding St | Santa Maria St | Santa Clara Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12065 | Forrer St | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13084 | Saint Marys St | Hemlock St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13071 | Strathmoor St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12430 | Sussex St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12944 | Verne St | Chapel St | Bentler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11585 | Bentler St | W McNichols Rd | Orchard St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12567 | Vaughan St | Verne St | Grove St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11422 | Sussex St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12370 | Marlowe St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11867 | Beaverland St | W McNichols Rd | Santa Maria St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13051 | Freeland St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11522 | Saint Marys St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13000 | Fenmore St | Florence St | Verne St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13046 | Beaverland St | Verne St | S Riverdale Dr | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
11441 | Vaughan St | W McNichols Rd | Santa Maria St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13838 | Fenton St | Grove St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
13528 | Oakfield St | Puritan St | Florence St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
12397 | Lauder St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18944 | Kendall St | Grandmont Ave | Woodmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16087 | Chalfonte St | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18136 | Acacia St | Prevost St | Forrer St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18987 | Kendall St | Rosemont Ave | Ashton Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17596 | Mettetal St | Lyndon St | Grand River Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18378 | Strathmoor St | Intervale St | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15396 | Lamphere St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17383 | Rutland St | Monnier Rd | Grand River Ave | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15578 | Winthrop St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17648 | Rutland St | Lyndon St | Monnier Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17024 | Mettetal St | Grand River Ave | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18347 | Acacia St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16909 | Whitcomb St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16004 | Chalfonte St | Freeland St | Ardmore St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17443 | Strathmoor St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15604 | Fielding St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14544 | Mansfield St | Midland St | Pilgrim St |  | 1 | 2020 Carryover | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17081 | Saint Marys St | Grand River | Chalfonte St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16025 | Chalfonte St | Strathmoor St | Mark Twain St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18418 | Archdale St | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17451 | Vaughan St | Eaton St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17858 | Ashton Rd | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17647 | Lyndon St | Rutland St | Abington Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16082 | Stout St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16386 | Chalfonte St | Saint Marys St | Prevost St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17841 | Archdale St | Lyndon St | Monnier Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18901 | Mansfield St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17545 | Prevost St | Grand River Ave | Eaton St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18363 | Lyndon St | Bramell St | Chatham St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18120 | Montrose St | Acacia St | Grand River Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15588 | Kentfield St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19001 | Kendall St | Faust Ave | Penrod St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16876 | Kentfield St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19046 | Mark Twain St | Grand River Ave | Intervale St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16638 | Archdale St | Tournier St | Grand River Ave | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18622 | Pierson St | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18518 | Robson St | Grand River Ave | Lyndon St | Yes | 4 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18443 | Rosemont Ave | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17432 | Mark Twain St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15057 | Heyden St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18971 | Archdale St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18958 | Kendall St | Rutland St | Abington Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15060 | Winthrop St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16874 | Eaton St | Robson St | Terry St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18883 | Montrose St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16860 | Vaughan St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16625 | Longacre St | Tournier St | Grand River Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15021 | Whitcomb St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15031 | Prest St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14447 | Whitcomb St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18364 | Bramell St | Lyndon St | Wanamaker Pl | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18912 | Saint Marys St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14437 | Winthrop St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18458 | Acacia St | Faust Ave | Penrod St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17404 | Archdale St | Monnier Rd | Tournier St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15063 | Kentfield St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17881 | Winthrop St | Grand River Ave | Eaton St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17631 | Beaverland St | Eaton St | Chalfonte St & Grayfield St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18561 | Plainview Ave | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19025 | Kendall St | Artesian St | Stahelin Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17501 | Robson St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18088 | Whitcomb St | Grand River Ave | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18921 | Kendall St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16394 | Chalfonte St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16918 | Eaton St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16053 | Chalfonte St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16124 | Chalfonte St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16072 | Kentfield St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18417 | Acacia St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18345 | Acacia St | Mansfield St | Rutherford St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16091 | Fielding St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15514 | Grandville Ave | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17540 | Prest St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17087 | Ashton Rd | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16854 | Eaton St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16980 | Rutherford St | Eaton St | Hackett St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17531 | Whitcomb St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14478 | Fenton St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18410 | Lauder St | Intervale St | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15545 | Prest St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17589 | Lyndon St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18374 | Acacia St | Grandmont Ave | Woodmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15597 | Stout St | Keeler St | Midland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16063 | Heyden St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18471 | Greenview Rd | Acacia St | Lyndon St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17885 | Faust Ave | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14448 | Wormer St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18352 | Ashton Rd | Dead End or Start | Lyndon St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16583 | Ferguson St | Grand River Ave | Chalfonte St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19016 | Kendall St | Glastonbury Ave | Greenview Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18442 | Acacia St | Rosemont Ave | Southfield Service Drive | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18874 | Winthrop St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17840 | Lyndon St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17608 | Lyndon St | Asbury Park | Mettetal St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15074 | Stout St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15679 | Gilchrist St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18870 | Bramell St | Ray St | Malta St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14466 | Prest St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16609 | Grandville Ave | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16125 | Prest St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16336 | Chalfonte St | Forrer St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15535 | Whitcomb St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16555 | Chalfonte St | Glastonbury Ave | Greenview Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16919 | Prest St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16062 | Chalfonte St | Robson St | Terry St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15110 | Mansfield St | Keeler St | Midland St |  | 1 | 2020 Carryover | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18393 | Acacia St | Rutland St | Abington Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16106 | Whitcomb St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14412 | Lauder St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18899 | Kendall St | Prevost St | Forrer St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16986 | Mansfield St | Eaton St | Hackett St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16950 | Winthrop St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18481 | Acacia St | Glastonbury Ave | Greenview Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17393 | Longacre St | Monnier Rd | Tournier St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18399 | Marlowe St | Intervale St | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18970 | Kendall St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18386 | Sussex St | Grand River Ave | Lyndon St | Yes | 3 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18919 | Kendall St | Mansfield St | Rutherford St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
17628 | Lyndon St | Grandmont Ave | Woodmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
15673 | Biltmore St | Fenkell St | Keeler St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18498 | Acacia St | Artesian St | Stahelin Rd | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
16870 | Heyden St | W Outer Dr | Fenkell St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
14390 | Strathmoor St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19852 | Artesian St | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19998 | W Davison St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21929 | Glendale St | W Parkway St | Beaverland St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19351 | Fielding St | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20993 | Glendale St | Abington Ave | Grandmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21853 | Abington Ave | Fullerton St | Glendale St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19560 | Archdale St | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21866 | Memorial St | Fullerton St | Glendale St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19595 | Greenview Rd | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20408 | Archdale St | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21014 | Rutland St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20357 | Grandmont Ave | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20046 | W Davison St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21036 | Archdale St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20961 | Glendale St | Mettetal St | Saint Marys St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19086 | Plainview Ave | Kendall St | Acacia St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20994 | Abington Ave | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21848 | Grandmont Ave | Fullerton St | Glendale St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20368 | Abington Ave | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21941 | Dale St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20066 | Bramell St | Schoolcraft St | Kendall St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20986 | Grandmont Ave | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19847 | Stahelin Rd | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21001 | Memorial St | Glendale St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21013 | Glendale St | Rutland St | Memorial St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21051 | Dale St | W Davison St | Schoolcraft St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19907 | Plainview Ave | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19409 | Whitcomb St | Schoolcraft St | Kendall St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20388 | W Davison St | Rutland St | Memorial St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19405 | Bramell St | S Kane St | Ray St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20407 | W Davison St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21035 | Glendale St | Archdale St | Longacre St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20018 | W Davison St | Rutherford St | Forrer St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
21960 | Glendale St | Bramell St | Chatham St | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
20367 | W Davison St | Abington Ave | Grandmont Ave | Yes | 1 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
19985 | Winthrop St | Schoolcraft St | W Davison St | Yes | 2 | Will be Installed 2021 | 1 | [17 empty] | District 1 |  |  |  | 104963.2692
18045 | Wildemere St | Waverly | W Davison St | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1944 | Ferguson St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1932 | Asbury Park | Hessel Ave | 8 Mile | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6867 | Lindsay St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6022 | Saint Marys St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
5973 | Winthrop St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6042 | Asbury Park | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6112 | Harlow St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6833 | Ferguson St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _5 | Procurement | Greenfield | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3837 | Prairie St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3849 | San Juan Dr | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1456 | Mendota St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1487 | Norfolk St | Appoline St | Meyers Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1324 | Monica St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3935 | Roselawn St | W Outer Dr | S Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3912 | Woodingham Dr | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1462 | Pinehurst St | Norfolk St | 8 Mile Rd |  | 2 | 2020 Carryover | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3825 | Monica St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1430 | Washburn St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
4819 | Birwood St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A _7 | Procurement | Pembroke | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3611 | Hartwell St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_20 | Procurement | Greenwich | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
3026 | Ward St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_20 | Procurement | Greenwich | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
6044 | Sorrento St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_20 | Procurement | Greenwich | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
2564 | Canterbury Rd | Pembroke Ave & Warrington Dr | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_21 | Procurement | Sherwood Forest | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
4071 | Pinehurst St | W Outer Dr | Saint Martins Ave |  | 1 | 2020 Carryover | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
4046 | Birwood St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
4654 | Ilene St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
5480 | Sorrento St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
6077 | Snowden St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11008 | Birwood St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11090 | Sorrento St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10986 | Ilene St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11102 | Ward St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10999 | Griggs St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11051 | Manor St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10991 | Littlefield St | Verne St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10976 | Washburn St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
11027 | Pinehurst St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_30 | Procurement | Schulze | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
6114 | Tracey St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_31 | Procurement | Tri-Point | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
10939 | Mansfield St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
10935 | Rutherford St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_8 | Procurement | Crary/St Marys | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
5908 | Coyle St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
8055 | Curtis St | Tracey St | Schaefer Hwy | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
5946 | Whitcomb St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
7109 | Margareta St | Winthrop St | Greenfield Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
11082 | Tracey St | Grove St | W McNichols Rd | Yes | 1 | Will be Installed 2021 | 2 |  |  |  |  | DWSD | [12 empty] | District 2 |  |  |  | 119775.9774 | [13 empty] | CS-1909A_9 | Procurement | Winship | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
1925 | Chippewa St | Prairie St | Monica St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4530 | Danbury St | W 7 Mile Rd | Penrose St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2970 | W Lantz St | Havana St | Charleston St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1083 | Norfolk St | Gardendale St | Picadilly Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1881 | Hessel Ave | Forrer St | Winthrop St & James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2491 | Biltmore St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1436 | Norfolk St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2992 | Bauman St | W Lantz St | Fernhill St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3096 | Pembroke Ave | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1931 | Hessel Ave | Asbury Park | Murray Hill St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1914 | Hessel Ave | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4130 | Ward St | W Outer Dr | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2539 | Archdale St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2384 | Tracey St | Chippewa St | Norfolk St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4337 | Snowden St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3040 | Ferguson St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1517 | Ward St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2529 | Marlowe St | Chippewa St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4651 | Prest St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1832 | Renfrew Rd | Bloomfield Rd | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2462 | Murray Hill St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2419 | Chippewa St | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3092 | Oakfield St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4558 | Havana St | W 7 Mile Rd | Penrose St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1862 | Audrey St | Norfolk St | 8 Mile Service Drive | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2320 | Monte Vista St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3346 | Santa Barbara Dr | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2398 | Chippewa St | Littlefield St | Cheyenne St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4646 | Washburn St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2087 | Chippewa St | Shrewsbury Rd | Roslyn Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4634 | Cambridge Ave | Kentucky St | Indiana St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3566 | Ward St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4478 | Cambridge Ave | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3843 | Danbury St | Penrose St | Exeter St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2455 | Saint Marys St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3075 | Lindsay St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
898 | Woodstock Dr | Renfrew Rd | Briarcliff Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4399 | Lesure St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1988 | Archdale St | Hessel Ave | Circle Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2085 | Trojan St | Marlowe St | Hubbell St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2965 | Pinehurst St | Pembroke Ave | Chippewa St |  | 2 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2005 | Chippewa St | Cherrylawn St | Northlawn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2619 | Monica St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1810 | Lauder St | Norfolk St | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2483 | Bauman St | Adeline St | W State Fair St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2361 | Chippewa St | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1934 | Chippewa St | Warrington Dr | Canterbury Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1838 | Norfolk St | Basil St | Carol St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4418 | Stansbury St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2314 | Chippewa St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4040 | Winthrop St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3432 | Whitcomb St | Pembroke Ave | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3189 | Monica St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3481 | Canterbury Rd | Chesterfield Rd | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4635 | Kentucky St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2035 | Kentucky St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2090 | Chippewa St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2001 | Fenmore St | Hessel Ave | Circle Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4508 | Cambridge Ave | Prairie St | Monica St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2501 | Gilchrist St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2034 | Chippewa St | Kentucky St | Indiana St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3055 | Biltmore St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2382 | Ward St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3646 | Lesure St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1953 | Chippewa St | Santa Barbara Dr | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2064 | Chippewa St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2554 | Fenmore St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3332 | Pennington Ave | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1504 | Norfolk St | Sorrento St | Steel St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4640 | Whitcomb St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2877 | Mendota St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4553 | Carman St | W 7 Mile Rd | Penrose St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2472 | Asbury Park | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2424 | Prevost St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3875 | Carman St | Penrose St | Annin St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1461 | Norfolk St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4534 | Cambridge Ave | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2401 | Winthrop St | Trojan St | James Couzens Fwy & Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1449 | Norfolk St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4580 | Cambridge Ave | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1340 | San Juan Dr | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3177 | Saint Martins Ave | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4083 | Prevost St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2339 | Chippewa St | Meyers Rd | Manor St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2381 | Chippewa St | Ward St | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4382 | Tracey St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1472 | Norfolk St | Manor St | Monte Vista St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
909 | Stratford Rd | Woodstock Dr | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1861 | Norfolk St | Audrey St | Oxley St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2413 | Stansbury St | Chippewa St | Norfolk St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
859 | Woodstock Dr | Queenston St | E M 1 Service Drive | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4499 | Strathmoor St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3081 | Tracey St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3387 | Roselawn St | Saint Martins Ave | N Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1567 | Tracey St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4613 | Vassar Ave | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4650 | Vassar Ave | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3477 | Pinehurst St | Saint Martins Ave | Pembroke Ave |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3894 | Havana St | Penrose St | Annin St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2055 | Washburn St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2945 | Winthrop St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1806 | Lichfield Rd | Bloomfield Rd | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1915 | Saint Marys St | Hessel Ave | 8 Mile Service Drive | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2835 | Griggs St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1809 | Norfolk St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1095 | Norfolk St | Warrington Dr | Sheffield Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1889 | Prevost St | Hessel Ave | Motor Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3065 | Gilchrist St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3097 | Lesure St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
875 | Woodstock Dr | Durham St | Queenston St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3621 | Bauman St | Wildwood St | Bryson St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2018 | Chippewa St | Wisconsin St | Ohio St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2859 | Ilene St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3027 | Asbury Park | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1895 | Hessel Ave | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1952 | Biltmore St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4348 | Hartwell St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1865 | Wakefield St | Canterbury Rd | Warrington Dr | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4564 | Cambridge Ave | Woodingham Dr | Santa Barbara Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2912 | Kentucky St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3120 | Canterbury Rd | Saint Martins Ave | Pembroke Ave & Warrington Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4476 | Mark Twain St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1923 | Murray Hill St | Hessel Ave | 8 Mile Rd & 8 Mile Service Drive | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2514 | Lindsay St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4611 | Cambridge Ave | Wisconsin St | Ohio St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1972 | Lindsay St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1030 | Lichfield Rd | Norfolk St | Woodstock Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1469 | Monte Vista St | Norfolk St | 8 Mile Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2466 | Havana St | Adeline St | W State Fair St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2308 | Mendota St | Chippewa St | Norfolk St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3130 | Annin St | Carman St | Blake St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4598 | Cherrylawn St | Cambridge Ave | N Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1438 | Picadilly Rd | Canterbury Rd | Norfolk St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2527 | Oakfield St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4125 | Saint Marys St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3644 | Fenmore St | Pembroke Ave | Fargo St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4436 | Ardmore St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4467 | Bauman St | Larchwood St | Balmoral Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1980 | Oakfield St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4102 | Saint Martins Ave | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3063 | Pembroke Ave | Schaefer Hwy | Hartwell St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2846 | Washburn St | Pembroke Ave | Chippewa St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2975 | Monte Vista St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2960 | Forrer St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
888 | Woodstock Dr | Lichfield Rd | Durham St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2315 | Pinehurst St | Chippewa St | Norfolk St |  | 2 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3856 | Charleston St | Penrose St | Annin St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1964 | Gilchrist St | Hessel Ave | 8 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3631 | Tracey St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4509 | Prairie St | Cambridge Ave | W Outer Dr |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4103 | Rutherford St | Saint Martins Ave | Pembroke Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2858 | Pembroke Ave | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3141 | Ardmore St | Pembroke Ave | Chippewa St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
1984 | Chippewa St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4584 | Vassar Ave | Robson St | Lauder St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
3122 | Fenmore St | Fargo St | Trojan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2971 | Havana St | W Lantz St | Fernhill St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
2481 | Ferguson St | Trojan St | Hessel Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6394 | Strathmoor St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5894 | Northlawn St | Clarita St | Wendel V Hall Blvd & W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8912 | Santa Clara St | Prairie St | Monica St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6444 | Margareta St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6091 | Lindsay St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5368 | Whitcomb St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7931 | San Juan Dr | London Ave | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5820 | Prairie St | Clarita St | W 7 Mile Rd |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8629 | Covington Dr | Manderson Rd | 3rd St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7366 | Saint Marys St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9026 | Coyle St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7823 | Wisconsin St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7081 | Prest St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6843 | Margareta St | Littlefield St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7871 | Ilene St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8610 | Manderson Rd | Whitmore Rd | Covington Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8424 | Coyle St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7630 | Ohio St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6613 | Steel St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5184 | Woodingham Dr | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7320 | Pinehurst St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7507 | Margareta St | Fenmore St | Archdale St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8116 | Ardmore St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6969 | Strathmoor St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6607 | Saint Marys St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8434 | Kentucky St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6443 | Lauder St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8348 | Santa Barbara Dr | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8847 | Fenmore St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5388 | Winthrop St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8494 | Birwood St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7844 | Kentucky St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6575 | Monte Vista St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9366 | Sorrento St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7616 | Lauder St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5939 | Kentucky St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5164 | Pennington Ave | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6539 | Ilene St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6895 | Harlow St | Clarita St | W 7 Mile Rd |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7875 | Prest St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4920 | Sorrento St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8523 | Pinehurst St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8621 | Ferguson St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4842 | Pinehurst St | Cambridge Ave | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9340 | Mansfield St | Thatcher St | Curtis St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4846 | Prevost St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8074 | Lesure St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7417 | Margareta St | Biltmore St | Ferguson St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6468 | Cherrylawn St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6467 | Margareta St | Cherrylawn St | Northlawn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9351 | Steel St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7532 | Curtis St | Livernois Ave | Warrington Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9487 | Quincy St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6856 | Gilchrist St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7031 | Ohio St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5358 | Kentucky St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8493 | Thatcher St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7617 | Northlawn St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8456 | Washburn St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7859 | Whitcomb St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9076 | Prest St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8609 | Asbury Park | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7483 | Margareta St | Harlow St | Oakfield St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8096 | Stansbury St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8387 | Lauder St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8522 | Thatcher St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9433 | Lesure St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7860 | Washburn St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8634 | Littlefield St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7846 | Sussex St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8410 | Ohio St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8842 | Lesure St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7331 | Monte Vista St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6932 | Stoepel St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7554 | Freeland St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6360 | Stoepel St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6558 | Birwood St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8596 | Murray Hill St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6880 | Pickford St | Warrington Dr | Oak Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8942 | Santa Clara St | Woodingham Dr | Santa Barbara Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9061 | Covington Dr | 2nd Blvd | Woodward Ave | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6904 | Clarita St | Archdale St | Harlow St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6525 | Washburn St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7975 | Sorrento St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6483 | Margareta St | Wisconsin St | Ohio St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8600 | Sorrento St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7622 | Cherrylawn St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5372 | Washburn St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6424 | Margareta St | Woodingham Dr | Santa Barbara Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6618 | Murray Hill St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7956 | Mansfield St | Pickford St | Margareta St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9097 | Santa Clara St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8843 | Covington Dr | 3rd St | 2nd Blvd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4941 | Cambridge Ave | W Outer Dr | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9471 | Oak Dr | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5985 | Mendota St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8608 | Curtis St | Asbury Park | Murray Hill St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8931 | Pennington Ave | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7355 | Mansfield St | Margareta St | Clarita St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7629 | Robson St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6975 | Fenmore St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4831 | Cambridge Ave | Mendota St | Birwood St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7384 | Sorrento St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8408 | Robson St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6974 | Clarita St | Fenmore St | Archdale St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9122 | Pinehurst St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8095 | Curtis St | Stansbury St | Lesure St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7587 | Strathmoor St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7898 | Mendota St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6338 | Clarita St | Stansbury St | Lesure St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9072 | Santa Clara St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8930 | Santa Clara St | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6940 | Freeland St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8560 | Curtis St | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6514 | Whitcomb St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6048 | Ferguson St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6905 | Archdale St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7449 | Margareta St | Lindsay St | Gilchrist St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8615 | Thatcher St | W Outer Dr | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6598 | Mansfield St | Clarita St | W 7 Mile Rd |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5337 | Cherrylawn St | W 7 Mile Rd | S Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7929 | Manor St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9121 | Santa Clara St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7522 | Stansbury St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6537 | Prest St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4860 | Rutherford St | Vassar Ave | Saint Martins Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8465 | Thatcher St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9353 | Murray Hill St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7886 | Birwood St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6100 | Oakfield St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7952 | Appoline St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6564 | Mendota St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8525 | Curtis St | Forrer St | Winthrop St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8971 | W Parkhurst Pl | Woodward Ave | John R St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8117 | Thatcher St | Stoepel St | Livernois Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8017 | Fenmore St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6853 | Snowden St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8585 | Curtis St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7891 | W Montana St | Woodward Ave | John R St | Yes | 4 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8646 | Cedarhurst Pl | Woodward Ave & Merrill Plaisance St | W Longwood Pl | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6821 | Asbury Park | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5576 | Fenmore St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8135 | Curtis St | Freeland St | Ardmore St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8010 | Snowden St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5376 | Ilene St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8358 | Woodingham Dr | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7825 | Coyle St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8893 | Santa Clara St | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9519 | Stoepel St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5993 | Pinehurst St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6600 | Appoline St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8960 | Santa Clara St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7484 | Harlow St | Margareta St | Clarita St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5621 | Stoepel St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7845 | Pickford St | Sussex St | Coyle St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5332 | Cambridge Ave | Robson St | Lauder St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6499 | Margareta St | Kentucky St | Indiana St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6322 | Clarita St | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7024 | Cherrylawn St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8052 | Harlow St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6818 | Sorrento St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7335 | Margareta St | Prevost St | Forrer St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8067 | Archdale St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7919 | Monte Vista St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9034 | Kentucky St | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8936 | Santa Barbara Dr | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7075 | Pickford St | Washburn St | Wyoming St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5956 | Washburn St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7396 | Pickford St | W Outer Dr | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5155 | San Juan Dr | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6342 | Margareta St | Warrington Dr | Oak Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8943 | Woodingham Dr | Santa Clara St | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8325 | Mark Twain St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6397 | Margareta St | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8345 | Curtis St | Strathmoor St | Mark Twain St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7076 | Washburn St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6382 | Mark Twain St | Clarita St | W 7 Mile Rd | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8590 | Thatcher St | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6860 | Birchcrest Dr | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8082 | Worcester Pl | Woodward Ave | John R St | Yes | 4 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9137 | Edgevale St | John R St | Brush St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8573 | Mansfield St | Curtis St | Pickford St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7108 | Mendota St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7508 | Fenmore St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8591 | Steel St | Thatcher St | Curtis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
4908 | Cambridge Ave | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6449 | Northlawn St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7575 | Mark Twain St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7909 | Pinehurst St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6864 | Margareta St | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5066 | Stansbury St | Cambridge Ave | Vassar Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8346 | Strathmoor St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9144 | Santa Clara St | Manor St | Pinehurst St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
5822 | W Golden Gate Ave | Woodward Ave | Charleston St | Yes | 4 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7963 | Steel St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7060 | Kentucky St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7359 | Appoline St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7424 | Snowden St | Pickford St | Margareta St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6335 | Fenmore St | W 7 Mile Rd | Cambridge Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6844 | Littlefield St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6954 | Mark Twain St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6326 | W Grixdale Ave | Woodward Ave | Charleston St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7874 | Pickford St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
6500 | Kentucky St | Margareta St | Clarita St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
7543 | Stoepel St | Curtis St | Pickford St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
8684 | Santa Clara St | Quincy St | Oak Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12001 | Florence St | Cheyenne St | Ward St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9588 | Coyle St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10094 | Santa Barbara Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10896 | Monica St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10388 | Prest St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12984 | Lesure St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10024 | Quincy St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10378 | Kentucky St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9908 | Asbury Park | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12395 | Mendota St | James Couzens Fwy | Florence St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12556 | Washburn St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14071 | Littlefield St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14026 | Appoline St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13468 | Princeton St | Midland St | Puritan St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9558 | Santa Maria St | Pennington Ave | San Juan Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13987 | Pinehurst St | Pilgrim St | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11026 | Grove St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12010 | Littlefield St | Florence St | Grove St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13145 | Ohio St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13594 | Midland St | Petoskey Ave | Quincy St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13020 | Cruse St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9994 | Fairfield St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11953 | Appoline St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10427 | Birwood St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11007 | Grove St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10884 | Stoepel St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11849 | Kentucky St | Marygrove Dr | Florence St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10879 | Whitcomb St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14030 | Midland St | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9632 | Kentucky St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11890 | Florence St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9901 | Manor St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11869 | Washburn St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13470 | Ward St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12870 | Appoline St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14031 | Steel St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10560 | Inverness St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11930 | Florence St | Pinehurst St | Mendota St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13467 | Midland St | Princeton St | Linwood St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10410 | Ilene St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11865 | Pinehurst St | Pinehurst St | Grove St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11921 | Mendota St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11961 | Steel St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11073 | Appoline St | Grove St | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10453 | Santa Maria St | Rutherford St | Prevost St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12428 | Stoepel St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12507 | Roselawn St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11531 | Stoepel St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11910 | Florence St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10933 | Prevost St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10449 | Pinehurst St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12525 | Ohio St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10897 | Prest St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11376 | La Salle Ave | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13938 | Fairfield St | Hughes St | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10102 | Woodingham Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9909 | Santa Maria St | Meyers Rd | Manor St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11901 | Griggs St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12511 | Northlawn St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12880 | Steel St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9976 | Hartwell St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12089 | Baylis St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13833 | Normandy St | Hughes St | Pilgrim St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9638 | Prest St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9882 | Pinehurst St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13931 | Washburn St | James Couzens Fwy & Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12913 | Cheyenne St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12114 | Normandy St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11353 | Littlefield St | Grove St | Verne St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11891 | Ilene St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10077 | San Juan Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10122 | Steel St | James Couzens Fwy | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10838 | Fairfield St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13489 | Midland St | Alden St | Lawton St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11050 | Grove St | Manor St | Monte Vista St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11911 | Birwood St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10018 | Oak Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10985 | Grove St | Ilene St | Washburn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13624 | Midland St | Santa Rosa Dr | Stoepel St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10446 | Prevost St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12103 | Florence St | Cruse St | Stansbury St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13562 | Midland St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9959 | Santa Maria St | Littlefield St | Ward St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11084 | Steel St | Grove St | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11977 | Sorrento St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13595 | Petoskey Ave | Puritan St | Midland St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12077 | Florence St | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9900 | Santa Maria St | Manor St | Pinehurst St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9975 | Santa Maria St | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10377 | Whitcomb St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9546 | San Juan Dr | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9568 | Woodingham Dr | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10086 | Pennington Ave | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13450 | Steel St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9996 | Belden St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9559 | Pennington Ave | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13579 | Quincy St | Midland St | Puritan St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10010 | Birchcrest Dr | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10396 | Washburn St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11360 | Florence St | Inverness St | Baylis St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12547 | Kentucky St | Florence St | Puritan St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11463 | Florence St | Muirland St | Fairfield St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10574 | La Salle Ave | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10565 | Baylis St | Grove St | W McNichols Rd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9651 | Washburn St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13015 | Normandy St | Pilgrim St | Puritan St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13007 | Stansbury St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9851 | Birwood St | Santa Maria St | Santa Clara St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9858 | Prevost St | W Outer Dr | Thatcher St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12904 | Ward St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13354 | Washburn St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14048 | Ward St | Midland St | Pilgrim St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12971 | Tracey St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9883 | Mansfield St | W Outer Dr | Thatcher St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
9970 | Snowden St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12461 | San Juan Dr | Puritan St | W McNichols Rd |  | 6 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12891 | Sorrento St | Puritan St | Florence St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10432 | Santa Maria St | Forrer St | Winthrop St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
13440 | Appoline St | Pilgrim St | Puritan St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10463 | Santa Maria St | Saint Marys St | Mansfield St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10433 | Forrer St | Santa Maria St | W Outer Dr | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
10057 | Stoepel St | W McNichols Rd | Santa Maria St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
11446 | Florence St | Parkside St | Wildemere St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
12059 | Tracey St | Florence St | Grove St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15836 | Monte Vista St | Fenkell St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15392 | Desoto St | Greenlawn St | Tuller St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14468 | Ilene St | Keeler Ave | James Couzens Fwy | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15984 | Chalfonte St | Cruse St | Stansbury St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16423 | Birwood St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15150 | Ward St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16155 | Roselawn St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14568 | Keeler Ave | Steel St | Appoline St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17080 | Clements St | Linwood St | La Salle Blvd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14868 | Keeler Ave | Cruse St | Stansbury St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15180 | Snowden St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15565 | Chalfonte St | Roselawn St | Greenlawn St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16496 | Clements St | 14th St | Rosa Parks Blvd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
18454 | Waverly | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15156 | Ellsworth St | Wyoming St | Cherrylawn St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15122 | Appoline St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15949 | Tracey St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14610 | Littlefield St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14569 | Steel St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16161 | Steel St | Hillview St | Chalfonte St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16896 | Clements St | La Salle Blvd | 14th St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15081 | Pinehurst St | Keeler Ave | Fenkell St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15428 | Desoto St | Cherrylawn St | Greenlawn St |  | 3 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17958 | Pasadena St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14609 | Keeler Ave | Littlefield St | Cheyenne St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
18461 | Wildemere St | W Buena Vista St | Tyler St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14592 | Ward St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16452 | La Belle St | Linwood St | La Salle Blvd | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15334 | Hartwell St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17011 | Kentucky St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14633 | Hartwell St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17594 | Kendall St | Livernois Ave | Holmur St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
18062 | W Grand St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15630 | Washburn St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17051 | Birwood St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16560 | Hartwell St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
18460 | W Buena Vista St | Wildemere St | Lawton St |  | 1 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14558 | Appoline St | Keeler Ave | Midland St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
18083 | Pasadena St | Petoskey Ave | Holmur St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15959 | Chalfonte St | Lesure St | Tracey St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14591 | Keeler Ave | Ward St | Sorrento St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15125 | Ellsworth St | Cherrylawn St | Greenlawn St | Yes | 3 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15022 | Washburn St | Fenkell St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17354 | W Grand St | Lawton St | Linwood St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17644 | Clements St | Wildemere St | Lawton St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15459 | Desoto St | Wyoming St | Cherrylawn St |  | 3 | 2020 Carryover | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15682 | Pinehurst St | Fenkell St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15431 | Holmur St | Chalfonte St | Fenkell St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15092 | Ellsworth St | Greenlawn St | Tuller St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15897 | Cheyenne St | Chalfonte St | Fenkell St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14632 | Keeler Ave | Hartwell St | Snowden St | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
15924 | Hartwell St | Chalfonte St | Fenkell St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
17472 | Clements St | Lawton St | Linwood St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
14518 | Pinehurst St | Midland St | Keeler Ave | Yes | 1 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16574 | Tracey St | Eaton St | Chalfonte St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
16972 | Roselawn St | Lyndon St | Eaton St | Yes | 2 | Will be Installed 2021 | 2 | [17 empty] | District 2 |  |  |  | 119775.9774
20545 | Elmhurst St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
19565 | Sturtevant St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
21069 | Webb St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
21587 | Lawrence St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
19901 | Cortland St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
20941 | Tuxedo St | Dexter | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
20011 | Richton St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A _1 | Procurement | Dexter-Linwood | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-09
27427 | Heyden St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_158 | Procurement | W. Chicago Stout to Evergreen | 0.19281 | Repair | CS-1909A | Water | W. Chicago | Stout | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27414 | Vaughan St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_158 | Procurement | W. Chicago Stout to Evergreen | 0.19281 | Repair | CS-1909A | Water | W. Chicago | Stout | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27575 | Ashton Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_160 | Procurement | Cathedral Grandville to Southfield Freeway | 0.25597 | Repair | CS-1909A | Water | Cathedral | Grandville | Southfield Freeway | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27103 | Westfield St | Faust Ave | Penrod St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_164 | Procurement | Faust W. Chicago to Cathedral | 0.23763 | Repair | CS-1909A | Water | Faust | W. Chicago | Cathedral | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26100 | Pierson St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26049 | Vaughan St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26870 | Westwood | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26088 | Braile St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
26081 | Patton St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_206 | Procurement | Orangelawn Burt to Westwood | 0.75794 | Repair | CS-1909A | Water | Orangelawn | Burt | Westwood | 2020 | 2022 | 2019-05-13 | 8 | 7 | Franklin Park
27877 | Cloverlawn St | Joy Rd | Stawell St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_215 | Procurement | Joy Road Wyoming to Livernois | 1.0003 | Repair | CS-1909A | Water | Joy Road | Wyoming | Livernois | 2020 | 2022 | 2019-05-13 | 8 | 6 | Barton-McFarland
27868 | Roselawn St | Joy Rd | Stawell St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_215 | Procurement | Joy Road Wyoming to Livernois | 1.0003 | Repair | CS-1909A | Water | Joy Road | Wyoming | Livernois | 2020 | 2022 | 2019-05-13 | 8 | 6 | Barton-McFarland
25438 | Braile St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_216 | Procurement | Plymouth Redford City Limit to Evergreen | 1.5501 | Repair | CS-1909A | Water | Plymouth | Redford City Limit | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | West Outer Drive
24935 | W Parkway St | Plymouth Rd | Wadsworth St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_216 | Procurement | Plymouth Redford City Limit to Evergreen | 1.5501 | Repair | CS-1909A | Water | Plymouth | Redford City Limit | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | West Outer Drive
24906 | Chatham St | Plymouth Rd | Wadsworth St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_216 | Procurement | Plymouth Redford City Limit to Evergreen | 1.5501 | Repair | CS-1909A | Water | Plymouth | Redford City Limit | Evergreen | 2020 | 2022 | 2019-05-13 | 8 | 7 | West Outer Drive
23610 | Hartwell St | Plymouth Rd | Wadsworth St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_217 | Procurement | Plymouth Schaefer to Wyoming | 1.0046 | Repair | CS-1909A | Water | Plymouth | Schaefer | Wyoming | 2020 | 2022 | 2019-05-13 | 8 | 7 | Pride Area Community
28037 | Hartwell St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_25 | Procurement | Barton-McFarland | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
24471 | Hartwell St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_25 | Procurement | Barton-McFarland | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
27096 | W Parkway St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_32 | Procurement | West Outer Drive | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood | Tireman | Plymouth | 2020 | 2021 | 2020-01-10 | 8 | 7 | West Outer Drive
28995 | Prest St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_33 | Procurement | Fiskhorn | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
28988 | Whitcomb St | Mackenzie St | Joy Rd | Yes | 2 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_33 | Procurement | Fiskhorn | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
29918 | Trinity St | Constance Ave | Van Buren Ave | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_38 | Procurement | Rouge Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
28946 | Trinity St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_38 | Procurement | Rouge Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood |  |  | 2020 | 2021 | 2020-01-10
32477 | Pierson St | W Warren Rd | Sawyer St | Yes | 3 | Will be Installed 2021 | 7 |  |  |  |  | DWSD | [12 empty] | District 7 |  |  |  | 144454.0173 | [13 empty] | CS-1909A_38 | Procurement | Rouge Park | 0 | Condition Assessment | CS-1909A | Water | Within Neighborhood | Parkland | Heyden | 2020 | 2021 | 2020-01-10 | 8 | 7
18514 | Clements St | Petoskey Ave | Holmur St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
18379 | Clements St | Holmur St | Dexter Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
18978 | Glendale St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
15532 | Chalfonte St | San Juan Dr | Prairie St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
15504 | Chalfonte St | Stoepel St | Livernois Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
15548 | Chalfonte St | Cloverdale St | Turner St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
18033 | Clements St | Dexter Ave | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
18934 | Clements St | Livernois Ave | Petoskey Ave | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
18596 | Roselawn St | Schoolcraft St | Intervale St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
22408 | Hartwell St | Capitol St | Foley St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23644 | Cedarlawn St | Mendota St | Griggs St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23609 | Stahelin Ave | Wadsworth St | Dead End or Start | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
22855 | Capitol St | Rutherford St | Forrer St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23129 | Wadsworth St | Hubbell St | Strathmoor St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20480 | Petoskey Ave | Cortland St | Sturtevant St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20563 | Fullerton St | Old Mill Pl | Broadstreet Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
19408 | Indiana St | W Davison St | Schoolcraft St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23406 | Wadsworth St | Prest St | Whitcomb St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23430 | Montrose St | Wadsworth St | Capitol St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23045 | Wadsworth St | Shirley Ave | Schaefer Hwy | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
22911 | Castleton St | Shirley Ave | Schaefer Hwy | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23368 | Petoskey Ave | W Boston Blvd | Collingwood St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23422 | Winthrop St | Wadsworth St | Capitol St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23046 | Shirley Ave | Wadsworth St | Castleton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20049 | Leslie St | Broadstreet Ave | Petoskey Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20466 | Fullerton St | Broadstreet Ave | Petoskey Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20906 | Fullerton St | Livernois | Old Mill Pl | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23065 | Collingwood St | Broadstreet Ave | N Martindale St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
19426 | Fullerton St | Dexter | Wildemere St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
21505 | Northlawn St | Cortland St | Fullerton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23407 | Prest St | Wadsworth St | Castleton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
21545 | Kentucky St | Cortland St | Fullerton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
22369 | Washburn St | Grand River Ave | Fullerton St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23121 | Strathmoor St | Wadsworth St | Capitol St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20992 | Indiana St | Fullerton St | W Buena Vista St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23453 | Wadsworth St | Rutherford St | Forrer St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23351 | Wadsworth St | Lauder St | Marlowe St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
19943 | Fullerton St | Petoskey Ave | Holmur St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23387 | Sussex | Wadsworth St | Castleton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23020 | Hartwell St | Wadsworth St | Capitol St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20072 | W Buena Vista St | Birwood St | Griggs St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23536 | W Boston Blvd | N Martindale St | Otsego St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23429 | Wadsworth St | Montrose St | Winthrop St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23361 | Wadsworth St | Robson St | Terry St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
21539 | Indiana St | Cortland St | Fullerton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23386 | Wadsworth St | Sussex | Coyle St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
20453 | Leslie St | Old Mill Pl | Broadstreet Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23001 | Collingwood St | N Martindale St | Petoskey Ave | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24415 | Steel St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26624 | Piedmont St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25645 | Abington Ave | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27080 | Ashton Ave | Westfield St | Fitzpatrick St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23956 | Sussex | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27904 | Vaughan St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26921 | Vaughan St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24497 | Auburn St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26465 | Mettetal St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26617 | Warwick St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27399 | Plainview Ave | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27614 | Stahelin Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25136 | Westwood | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26039 | Decatur St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27673 | Grandville Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27361 | Grandville Ave | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23990 | Winthrop St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25976 | Cheyenne St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25384 | Vaughan St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25010 | Archdale St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26917 | Robson St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26859 | Grandville Ave | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27940 | Patton St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27507 | Trinity St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27535 | Dawes St | Wyoming St | Stawell St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27627 | Artesian St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25131 | Grandville Ave | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28069 | Dover St | Greenview Ave | Faust Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24569 | Lauder St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27113 | Stahelin Ave | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26514 | Rutland St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24459 | Littlefield St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25098 | Warwick St | Elmira St | Fitzpatrick St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26613 | Hartwell St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25990 | Littlefield St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25359 | Decatur St | Orangelawn St | Keal St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25867 | Rutland St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27518 | Hartwell St | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28442 | Trinity St | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26006 | Hartwell St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28079 | Stahelin Ave | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28363 | Plainview Ave | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24994 | Rutland St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26116 | N Martindale St | Grand River Ave | Joy Rd | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27867 | Rutherford St | Ellis St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25551 | Morley | Griggs St | Wyoming St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28070 | Greenview Ave | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28364 | Robson St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25127 | Hartwell St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27374 | Westwood | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25939 | Appoline | W Chicago St | Elmira St | Yes | 4 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28372 | Vaughan St | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25463 | Lauder St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25033 | Elmira St | Rosemont Ave | Ashton Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27922 | Esper St | Joy Rd | Otto St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27977 | Trinity St | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25073 | Sorrento St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27612 | Sussex | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27860 | Westwood | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27087 | Westfield St | Rosemont Ave | Ashton Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25023 | Elmira St | Ashton Ave | Southfield Service Drive | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26969 | Winthrop St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26861 | Carlin St | Westfield St | W Chicago St & Carlin Ave | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26956 | Patton St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26528 | Longacre St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28032 | Littlefield St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24877 | Winthrop St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28082 | Artesian St | Dover St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24425 | Sorrento St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23885 | Strathmoor St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25378 | Elmira St | Plainview Ave | Auburn St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28368 | Coyle St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26948 | Prest St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25034 | Rosemont Ave | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25537 | Winthrop St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27407 | Northlawn St | Stawell St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24562 | Marlowe St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24532 | Fielding St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26519 | Archdale St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27883 | Plainview Ave | Cathedral St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26895 | Ohio St | Dawes St | Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25142 | Carlin Ave | Orangelawn St | Keal St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27613 | Cathedral St | Stahelin Ave | Brace St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25994 | Westwood | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27404 | Robson St | Cathedral St | Unknown & Westfield St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27129 | Warwick St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27587 | W Parkway St | Hazelton Ave | Meadow Park | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26026 | Carlin Ave | W Chicago St & Carlin St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27593 | Robson St | Ellis St | Cathedral St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28024 | Cheyenne St | Joy Rd | Ellis St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26572 | Sorrento St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25887 | Archdale St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27663 | Winthrop St | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26119 | Lauder St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26142 | Coyle St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27637 | Prest St | Ellis St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23949 | Coyle St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25104 | Littlefield St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26478 | Asbury Park | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26395 | Winthrop St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24449 | Cheyenne St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28468 | W Parkway St | Dover Ave | Meadow Park St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25094 | Cheyenne St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25456 | Marlowe St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25118 | Piedmont St | Elmira St | Plymouth Rd | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28058 | Dover St | Penrod St | Rosemont Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27586 | Esper St | Otto St | Stawell St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26110 | Marlowe St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
27395 | Cloverlawn St | Stawell St | Westfield St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26542 | Manor | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25985 | Grandville Ave | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26373 | Prest St | W Chicago St | Orangelawn St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
23984 | Prest St | Plymouth Rd | Wadsworth St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
26905 | Lauder St | Westfield St | W Chicago St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
24593 | Ohio St | Orangelawn St | Beechdale St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25973 | Piedmont St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
25507 | Whitcomb St | Orangelawn St | Elmira St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32047 | Grandmont Ave | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32939 | Montrose St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32963 | Saint Marys St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32974 | Whitlock St | Asbury Park | Mettetal St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
30978 | Forrer St | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32046 | Woodmont Ave | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31525 | Woodmont Ave | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
28905 | Patton St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32052 | Abington Ave | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32975 | Asbury Park | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31009 | Woodmont Ave | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
29928 | Saint Marys St | Belton St | Constance St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32955 | Mansfield St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
29587 | Whitcomb St | Belton St | Mackenzie St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31531 | Grandmont Ave | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
30452 | Saint Marys St | Tireman St | Belton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33021 | Archdale St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32025 | Mansfield St | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31542 | Memorial St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32942 | Forrer St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33000 | Memorial St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31022 | Abington Ave | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31039 | Rutland St | Diversey | Rutland Ave & Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
29449 | Trinity St | Van Buren Ave | Joy Rd | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31030 | Memorial St | Diversey | Tireman St & Memorial Ave | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
29038 | W Parkway St | Joy Rd | Dover St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31491 | Rutherford St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32984 | Grandmont Ave | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31540 | Pierson St | Sawyer St | Dead End or Start | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31538 | Abington Ave | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32935 | Winthrop St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
30467 | Asbury Park | Tireman St | Belton Ave & Belton St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31014 | Grandmont Ave | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32056 | Memorial St | W Warren Ave | Majestic St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31508 | Mettetal St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
30481 | Abington Ave | Tireman St | Belton Ave | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
30999 | Mettetal St | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
30988 | Mansfield St | Diversey | Tireman St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33016 | Longacre St | Whitlock St | W Warren Ave | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
29594 | Prest St | Belton St | Mackenzie St | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31496 | Mansfield St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
31560 | Rutland St | Majestic St | Diversey | Yes | 2 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
32954 | Whitlock St | Mansfield St | Rutherford St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33961 | Rutland St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33931 | Asbury Park | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33915 | Mansfield St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33436 | Winthrop St | Radcliffe St | Whitlock St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33894 | Winthrop St | Paul Dr | Radcliffe St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33948 | Abington Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33962 | Longacre St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33942 | Grandmont Ave | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33975 | Archdale St | City/Twp Line | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33920 | Saint Marys St | Paul Dr | Whitlock St | Yes | 3 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33899 | Montrose St | Paul Dr | Radcliffe St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173
33439 | Montrose St | Radcliffe St | Whitlock St | Yes | 1 | Will be Installed 2021 | 7 | [17 empty] | District 7 |  |  |  | 144454.0173