## Sheet1
OBJECTID | lrs_link | district_new | RDNAME | FROMDESC | TODESC | SURFTYPE | Selected_Blocks | Site Marked Date | Milling Complete Date | Speed Hump Installed Date | Temp Pavement Marking Date | Permanent Marking Date | Sign Confirmed Date | Type of Traffic Calming | 2021 fire route | DTE Coordination | DWSD Coordination | DPW Coordination | Utlility Coordination | Proceed | Field Concerns | Flyer Date | field concern resolved | Round 1 | Round 2 | Round 3
87 | 16022048200101582000695 | 3 | Albany St | Amrad St | Hamlet St | Asphalt | Yes | 2021-08-04 15:50 | 2021-08-25 22:10 | 2021-08-31 14:21 |  |  | 2021-08-31 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:50 |  | yes | no | no
446 | 16300058200506482004436 | 3 | Albany St | E Hildale St | E Robinwood St | Asphalt | Yes | 2021-05-11 17:33 | 2021-06-04 12:25 | 2021-06-07 21:07 |  | 2021-07-15 16:30 | 2021-06-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 18:31 |  | yes | no | no
378 | 16300058200443682003764 | 3 | Albany St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-11 17:35 | 2021-06-04 12:50 | 2021-06-07 21:07 |  | 2021-07-15 16:32 | 2021-06-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 18:31 |  | yes | no | no
2244 | 16300058200299082002413 | 3 | Albany St | Emery St | E Lantz St | Asphalt | Yes | 2021-08-04 15:44 | 2021-08-26 15:53 | 2021-08-31 20:06 |  |  | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:44 |  | yes | no | no
2245 | 16300058200299082002413 | 3 | Albany St | Emery St | E Lantz St | Asphalt | Yes | 2021-08-04 15:45 | 2021-08-26 16:48 | 2021-08-31 15:43 |  |  | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:45 |  | yes | no | no
64 | 16022048200069550041445 | 3 | Albany St | Hamlet St | 8 Mile Rd | Asphalt | Yes | 2021-08-04 15:51 | 2021-08-25 21:44 | 2021-08-31 14:27 |  |  | 2021-08-31 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:51 |  | yes | no | no
587 | 16304018200700382006460 | 3 | Albion St | Clough St | Gietzen St | Asphalt | Yes | 2021-05-14 11:24 | 2021-06-08 19:30 | 2021-06-17 17:26 |  | 2021-07-25 18:50 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 17:17 |  | yes | no | no
2413 | 16304018200840782007589 | 3 | Albion St | E McNichols Rd | Sauer St | Asphalt | Yes | 2021-05-14 11:25 | 2021-06-09 12:15 | 2021-06-17 18:11 |  | 2021-07-25 18:47 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 16:49 |  | yes | no | no
334 | 16304018200397082003357 | 3 | Albion St | Eastwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-13 15:08 | 2021-06-04 20:16 | 2021-06-17 13:58 |  | 2021-07-25 18:59 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 18:29 |  | yes | no | no
542 | 16304018200646082005843 | 3 | Albion St | Gietzen St | Greiner St | Asphalt | Yes | 2021-05-13 19:45 | 2021-06-07 20:16 | 2021-06-17 16:18 |  | 2021-07-25 18:52 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 17:51 |  | yes | no | no
495 | 16304018200584382005240 | 3 | Albion St | Greiner St | Park Grove St | Asphalt | Yes | 2021-05-13 19:44 | 2021-06-07 19:25 | 2021-06-17 15:57 |  | 2021-07-25 18:54 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 17:52 |  | yes | no | no
370 | 16304018200456782003970 | 3 | Albion St | Linnhurst St | Eastwood St | Asphalt | Yes | 2021-05-13 19:07 | 2021-06-04 20:52 | 2021-06-17 15:16 |  | 2021-07-25 18:58 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 18:10 |  | yes | no | no
441 | 16304018200524082004567 | 3 | Albion St | Park Grove St | Linnhurst St | Asphalt | Yes | 2021-05-13 19:44 | 2021-06-07 18:22 | 2021-06-17 15:43 |  | 2021-07-25 18:56 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 17:52 |  | yes | no | no
646 | 16304018200758982007003 | 3 | Albion St | Sauer St | Clough St | Asphalt | Yes | 2021-05-14 11:25 | 2021-06-09 12:59 | 2021-06-17 17:50 |  | 2021-07-25 18:49 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 17:05 |  | yes | no | no
257 | 16024078200314782002662 | 3 | Alcoy St | E 7 Mile Rd | Lappin St | Asphalt | Yes | 2021-05-14 18:52 | 2021-06-16 21:13 | 2021-06-24 13:24 |  | 2021-07-30 21:03 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 19:34 |  | yes | no | no
108 | 16024078200131782000995 | 3 | Alcoy St | E State Fair St | Fairmount Dr | Asphalt | Yes | 2021-05-17 12:54 | 2021-06-17 14:18 | 2021-06-23 21:45 |  | 2021-07-31 15:14 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 18:31 |  | yes | no | no
195 | 16024078200266282002251 | 3 | Alcoy St | Lappin St | Pinewood St | Asphalt | Yes | 2021-05-17 14:20 | 2021-06-17 12:16 | 2021-06-24 12:49 |  | 2021-07-30 21:07 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 19:33 |  | yes | no | no
150 | 16024078200225182001717 | 3 | Alcoy St | Pinewood St | Manning St | Asphalt | Yes | 2021-05-17 13:59 | 2021-06-17 12:42 | 2021-06-24 12:30 |  | 2021-07-30 21:08 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 19:33 |  | yes | no | no
343 | 16303038200402482003411 | 3 | Algonac St | Eastwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-13 15:17 | 2021-06-10 15:42 | 2021-06-21 20:11 |  | 2021-07-30 14:21 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 12:37 |  | yes | no | no
5642 | 16303038200589382005282 | 3 | Algonac St | Greiner St | Park Grove St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
453 | 16303038200528282004637 | 3 | Algonac St | Park Grove St | Linnhurst St | Asphalt | Yes | 2021-05-13 14:35 | 2021-06-10 18:53 | 2021-06-21 21:03 |  | 2021-07-30 14:23 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 13:17 |  | yes | no | no
4728 | 17163038200895382008283 | 3 | Anglin St | Jerome St | Stender St | Asphalt | Yes Round 2 | 2021-09-09 14:22 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:22 |  | no | yes | no
4981 | 17163038200739082006558 | 3 | Anglin St | Minnesota St | E Nevada St | Asphalt | Yes Round 2 | 2021-09-09 14:16 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:16 |  | no | yes | no
4982 | 17163038200739082006558 | 3 | Anglin St | Minnesota St | E Nevada St | Asphalt | Yes Round 2 | 2021-09-09 14:13 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:13 |  | no | yes | no
5609 | 16304048200110982000805 | 3 | Annott St | Fairmount Dr | Bringard Dr | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
535 | 16340088200642182005807 | 3 | Annott St | Gietzen St | Greiner St | Asphalt | Yes | 2021-05-14 14:16 | 2021-06-11 14:59 | 2021-06-22 12:27 |  | 2021-07-30 15:39 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 15:13 |  | yes | no | no
5540 | 47058748201348482013472 | 3 | Arcola St | Carrie St | Eldon St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5541 | 47058748201348482013472 | 3 | Arcola St | Carrie St | Eldon St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
4826 | 15865078201779182017770 | 3 | Badger St | Maxwell St | Erwin Ave | Asphalt 2020 | Yes Round 2 | 2021-09-09 15:58 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 15:58 |  | no | yes | no
2348 | 16341018200654882005744 | 3 | Barlow St | Sauer St | Greiner St | Asphalt | Yes | 2021-05-14 12:30 | 2021-06-14 17:37 | 2021-06-22 15:22 |  | 2021-07-30 15:44 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 14:01 |  | yes | no | no
2349 | 16341018200654882005744 | 3 | Barlow St | Sauer St | Greiner St | Asphalt | Yes | 2021-05-14 12:30 | 2021-06-14 16:54 | 2021-06-22 15:22 | 2021-07-30 15:42 | 2021-07-30 15:42 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 14:01 |  | yes | no | no
4713 | 16303058200704282006485 | 3 | Beland St | Clough St | Gietzen St | Asphalt | Yes Round 2 | 2021-09-08 15:44 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:44 |  | no | yes | no
2415 | 16303058200846182007644 | 3 | Beland St | E McNichols Rd | Sauer St | Asphalt | Yes | 2021-05-13 14:57 | 2021-06-10 17:57 | 2021-06-21 18:12 |  | 2021-07-30 14:40 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 13:48 |  | yes | no | no
339 | 16303058200400982003395 | 3 | Beland St | Eastwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-13 15:08 | 2021-06-10 15:02 | 2021-06-21 19:33 |  | 2021-07-30 14:29 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 12:24 |  | yes | no | no
4716 | 16303058200648582005884 | 3 | Beland St | Gietzen St | Greiner St | Asphalt | Yes Round 2 | 2021-09-08 15:46 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:46 |  | no | yes | no
2216 | 16303068200283582002309 | 3 | Beland St | Lappin St | Sturgis St | Asphalt | Yes | 2021-05-13 14:35 | 2021-06-10 17:10 | 2021-06-21 19:51 |  | 2021-07-30 19:02 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 17:18 |  | yes | no | no
379 | 16303058200462182004009 | 3 | Beland St | Linnhurst St | Eastwood St | Asphalt | Yes | 2021-05-13 14:30 | 2021-06-10 14:57 | 2021-06-21 18:42 |  | 2021-07-30 14:26 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes | Resolved | 2021-05-14 14:43 |  | yes | no | no
149 | 16021028200191182001364 | 3 | Binder St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-05-21 17:57 | 2021-05-25 20:52 | 2021-06-04 15:58 |  | 2021-06-06 14:31 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 17:57 |  | yes | no | no
2132 | 16021028200136482000910 | 3 | Binder St | E Remington St | E Winchester Ave | Asphalt | Yes | 2021-05-21 18:13 | 2021-06-01 11:39 | 2021-06-04 17:39 |  | 2021-06-06 14:31 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 18:13 |  | yes | no | no
2133 | 16021028200136482000910 | 3 | Binder St | E Remington St | E Winchester Ave | Asphalt | Yes | 2021-05-21 18:13 | 2021-06-01 12:12 | 2021-06-04 17:39 |  | 2021-06-06 14:31 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 18:13 |  | yes | no | no
83 | 16021028200091050041481 | 3 | Binder St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-24 12:32 | 2021-06-01 12:39 | 2021-06-04 18:20 |  | 2021-06-06 14:30 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 12:32 |  | yes | no | no
4273 | 16306098201256182011392 | 3 | Bloom St | Carpenter St | Charles St | Asphalt | Yes | 2021-05-11 13:22 | 2021-05-24 12:51 | 2021-08-13 13:05 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:32 |  | yes | no | no
4275 | 16306098201256182011392 | 3 | Bloom St | Carpenter St | Charles St | Asphalt | Yes | 2021-05-11 13:24 | 2021-08-30 17:37 | 2021-08-31 16:25 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:32 |  | yes | no | no
4669 | 16299108200512082004477 | 3 | Bloom St | E Hildale St | E Robinwood St | Asphalt | Yes Round 2 | 2021-09-08 16:42 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:42 |  | no | yes | no
2248 | 16021108200302582002438 | 3 | Bloom St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-25 12:07 | 2021-06-03 19:39 | 2021-06-07 17:25 |  | 2021-07-15 13:51 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 12:07 |  | yes | no | no
2249 | 16021108200302582002438 | 3 | Bloom St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-25 12:07 | 2021-06-03 20:03 | 2021-06-07 18:00 |  | 2021-07-15 13:52 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 12:07 |  | yes | no | no
1428 | 16306098201090482010617 | 3 | Bloom St | Rowley St | Rupert St | Asphalt | Yes | 2021-05-11 15:01 | 2021-05-19 18:40 | 2021-05-20 19:35 |  | 2021-06-04 15:40 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:41 |  | yes | no | no
19 | 16026018200049782000394 | 3 | Boulder St | Bringard Dr | Edmore Dr | Asphalt | Yes | 2021-06-01 18:10 | 2021-06-10 20:14 | 2021-06-11 18:11 |  | 2021-08-02 15:11 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 18:10 |  | yes | no | no
54 | 16342038200079182000478 | 3 | Bradford St | Bringard Dr | Collingham Dr | Asphalt | Yes | 2021-05-14 13:36 | 2021-06-11 18:37 | 2021-06-23 12:40 |  | 2021-07-31 14:58 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 18:57 |  | yes | no | no
2387 | 16340098200787482007071 | 3 | Bradford St | E McNichols Rd | Sauer St | Asphalt | Yes | 2021-05-14 12:24 | 2021-06-12 13:07 | 2021-06-22 12:42 |  | 2021-07-30 15:31 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 15:05 |  | yes | no | no
5598 | 16342038200110082000791 | 3 | Bradford St | Fairmount Dr | Bringard Dr | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
217 | 16304058200282082002383 | 3 | Bradford St | Lappin St | Pinewood St | Asphalt | Yes | 2021-05-14 13:12 | 2021-06-11 17:20 | 2021-06-22 19:56 |  | 2021-07-30 19:49 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes | Concrete | 2021-05-19 13:27 |  | yes | no | no
35 | 15915078200059182000578 | 3 | Bringard Dr | Anvil St | Regent Dr | Asphalt | Yes | 2021-08-04 16:40 | 2021-08-27 16:46 | 2021-09-01 18:21 |  |  | 2021-09-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 16:40 |  | yes | no | no
36 | 15915078200060282000591 | 3 | Bringard Dr | Hoyt St | Anvil St | Asphalt | Yes | 2021-08-04 16:38 | 2021-08-27 16:30 | 2021-09-01 18:15 |  |  | 2021-09-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 16:38 |  | yes | no | no
33 | 15915078200057882000570 | 3 | Bringard Dr | Regent Dr | Marbud St | Asphalt | Yes | 2021-05-19 13:31 | 2021-06-15 14:29 | 2021-06-17 20:15 |  | 2021-07-31 17:58 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 18:49 |  | yes | no | no
5629 | 16297058200569182004940 | 3 | Brinker St | E Grixdale St | E Robinwood St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2356 | 16297058200655282005691 | 3 | Brinker St | E Nevada St | E Grixdale St | Asphalt | Yes | 2021-05-10 15:18 | 2021-05-25 15:42 | 2021-06-01 23:14 |  | 2021-06-10 16:44 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 15:18 |  | yes | no | no
2357 | 16297058200655282005691 | 3 | Brinker St | E Nevada St | E Grixdale St | Asphalt | Yes | 2021-05-10 15:11 | 2021-05-25 15:17 | 2021-06-01 22:28 |  | 2021-06-10 16:59 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 15:10 |  | yes | no | no
599 | 17159088200692482006906 | 3 | Buhr St | Carrie St | Cliff St | Asphalt | Yes | 2021-05-11 18:00 | 2021-08-26 11:46 | 2021-08-31 17:23 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 18:26 |  | yes | no | no
2366 | 17159088200695482006924 | 3 | Buhr St | Sherwood St | Carrie St | Asphalt | Yes | 2021-05-11 18:08 | 2021-08-26 12:16 | 2021-08-31 19:51 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 18:26 |  | yes | no | no
2367 | 17159088200695482006924 | 3 | Buhr St | Sherwood St | Carrie St | Asphalt | Yes | 2021-05-11 18:04 | 2021-08-26 12:42 | 2021-08-31 18:06 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 18:26 |  | yes | no | no
5550 | 16309088201405682013556 | 3 | Burnside St | Dequindre St | Goddard St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5551 | 16309088201405682013556 | 3 | Burnside St | Dequindre St | Goddard St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2840 | 16314048201296982012443 | 3 | Caely St | Conant St | Carpenter St | Asphalt | Yes | 2021-05-11 14:11 | 2021-05-22 12:13 | 2021-05-25 16:35 |  | 2021-06-02 17:30 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:11 |  | yes | no | no
2841 | 16314048201296982012443 | 3 | Caely St | Conant St | Carpenter St | Asphalt | Yes | 2021-05-12 18:48 | 2021-05-22 12:14 | 2021-05-25 17:01 |  | 2021-06-02 17:34 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:11 |  | yes | no | no
2326 | 16295108200429682003424 | 3 | Cameron St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-06 18:39 | 2021-05-12 19:34 | 2021-05-13 19:53 |  | 2021-05-24 16:37 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 19:36 |  | yes | no | no
2327 | 16295108200429682003424 | 3 | Cameron St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-06 18:40 | 2021-05-12 20:23 | 2021-05-13 20:19 |  | 2021-05-24 16:10 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 19:36 |  | yes | no | no
2242 | 16295108200278782002213 | 3 | Cameron St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-06 19:04 | 2021-05-13 12:58 | 2021-05-13 21:52 |  | 2021-05-24 16:00 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 19:34 |  | yes | no | no
2243 | 16295108200278782002213 | 3 | Cameron St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-06 19:04 | 2021-05-13 12:58 | 2021-05-13 22:01 |  | 2021-05-24 15:49 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 19:35 |  | yes | no | no
2282 | 16295108200342482002787 | 3 | Cameron St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-06 18:56 | 2021-05-12 20:54 | 2021-05-13 20:45 |  | 2021-05-24 16:04 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 19:35 |  | yes | no | no
2283 | 16295108200342482002787 | 3 | Cameron St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-06 19:04 | 2021-05-12 21:23 | 2021-05-13 21:10 |  | 2021-05-24 16:00 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 19:35 |  | yes | no | no
524 | 16296038200588082005138 | 3 | Cardoni St | E Grixdale Ave | E Robinwood St | Asphalt | Yes | 2021-05-07 12:11 | 2021-05-12 19:04 | 2021-05-14 14:41 |  | 2021-05-24 22:04 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 19:36 |  | yes | no | no
2372 | 16296038200690582005880 | 3 | Cardoni St | E Nevada St | E Grixdale Ave | Asphalt | Yes | 2021-05-07 11:53 | 2021-05-12 17:57 | 2021-05-14 13:46 |  | 2021-05-24 21:04 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 12:37 |  | yes | no | no
2373 | 16296038200690582005880 | 3 | Cardoni St | E Nevada St | E Grixdale Ave | Asphalt | Yes | 2021-05-07 11:57 | 2021-05-12 18:29 | 2021-05-14 14:10 |  | 2021-05-24 21:04 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 12:37 |  | yes | no | no
4 | 16337058200029682000280 | 3 | Carlisle St | Anvil St | Regent Dr | Asphalt | Yes | 2021-05-17 15:54 | 2021-06-15 12:54 | 2021-06-16 19:20 |  | 2021-07-31 17:45 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:44 |  | yes | no | no
5 | 16337058200030482000296 | 3 | Carlisle St | Hoyt St | Anvil St | Asphalt | Yes | 2021-05-17 15:17 | 2021-06-15 12:23 | 2021-06-16 19:37 |  | 2021-07-31 17:43 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:44 |  | yes | no | no
6 | 16337058200031582000304 | 3 | Carlisle St | Reno St | Hoyt St | Asphalt | Yes | 2021-05-17 15:10 | 2021-06-15 11:45 | 2021-06-16 20:14 |  | 2021-07-31 17:40 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:44 |  | yes | no | no
7 | 16337058200032882000315 | 3 | Carlisle St | Schoenherr St | Reno St | Asphalt | Yes | 2021-05-17 15:07 | 2021-06-15 11:16 | 2021-06-16 20:23 |  | 2021-07-31 17:40 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:44 |  | yes | no | no
1442 | 16314068201256182012508 | 3 | Carpenter St | Bloom St | Buffalo St | Asphalt | Yes | 2021-05-11 13:18 | 2021-05-20 17:13 | 2021-05-24 15:36 |  | 2021-06-02 17:03 | 2021-05-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:32 |  | yes | no | no
1439 | 16314068201238282012443 | 3 | Carpenter St | Bristow St | Caely St | Asphalt | Yes | 2021-05-11 14:29 | 2021-05-20 19:16 | 2021-05-21 19:59 |  | 2021-06-02 16:26 | 2021-05-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:20 |  | yes | no | no
1440 | 16314068201247182012361 | 3 | Carpenter St | Conant St | Justine St | Asphalt | Yes | 2021-05-11 13:04 | 2021-05-20 19:52 | 2021-05-21 19:32 |  | 2021-06-02 16:26 | 2021-05-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:29 |  | yes | no | no
1441 | 16314068201246382012520 | 3 | Carpenter St | Fenelon St | Commor St | Asphalt | Yes | 2021-05-11 14:29 | 2021-05-20 18:16 | 2021-05-21 20:29 |  | 2021-06-02 16:59 | 2021-05-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:20 |  | yes | no | no
1444 | 16314068201253682012566 | 3 | Carpenter St | Radom St | Moenart St | Asphalt | Yes | 2021-05-11 14:30 | 2021-05-20 17:42 | 2021-05-21 20:49 |  | 2021-06-02 17:01 | 2021-05-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:42 |  | yes | no | no
2850 | 17118108201393682013503 | 3 | Casmere St | Conant St | Fenelon St | Asphalt | Yes | 2021-05-11 12:44 | 2021-05-21 14:45 | 2021-05-25 13:33 |  | 2021-06-01 21:31 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 12:44 |  | yes | no | no
2851 | 17118108201393682013503 | 3 | Casmere St | Conant St | Fenelon St | Asphalt | Yes | 2021-05-11 12:44 | 2021-05-21 15:03 | 2021-05-25 13:56 |  | 2021-06-01 21:26 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 12:44 |  | yes | no | no
2844 | 17118108201350382013007 | 3 | Casmere St | Fenelon St | Buffalo St | Asphalt | Yes | 2021-05-11 12:43 | 2021-05-21 15:25 | 2021-05-25 14:21 |  | 2021-06-01 21:05 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 12:43 |  | yes | no | no
2845 | 17118108201350382013007 | 3 | Casmere St | Fenelon St | Buffalo St | Asphalt | Yes | 2021-05-11 12:43 | 2021-05-21 16:13 | 2021-05-25 15:00 |  | 2021-06-01 20:44 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 12:43 |  | yes | no | no
5528 | 16020058200197682001399 | 3 | Charest St | E Outer Dr | E Remington St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5529 | 16020058200197682001399 | 3 | Charest St | E Outer Dr | E Remington St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
4609 | 16020058200094350041490 | 3 | Charest St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 17:25 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:25 |  | no | yes | no
2830 | 17157018201222682011375 | 3 | Charest St | Halleck St | Lawley St | Asphalt | Yes | 2021-05-10 17:17 | 2021-05-20 13:08 | 2021-05-21 18:19 |  | 2021-06-01 14:26 | 2021-05-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 17:50 |  | yes | no | no
2831 | 17157018201222682011375 | 3 | Charest St | Halleck St | Lawley St | Asphalt | Yes | 2021-05-10 17:17 | 2021-05-19 15:55 | 2021-05-21 18:19 |  | 2021-06-01 14:26 | 2021-05-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 17:07 |  | yes | no | no
2380 | 17162028200735782006525 | 3 | Charest St | Minnesota St | E Nevada St | Asphalt | Yes | 2021-05-10 16:08 | 2021-05-25 17:35 | 2021-06-01 21:46 |  | 2021-06-10 15:32 | 2021-06-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 16:08 |  | yes | no | no
2381 | 17162028200735782006525 | 3 | Charest St | Minnesota St | E Nevada St | Asphalt | Yes | 2021-05-10 16:08 | 2021-05-25 16:36 | 2021-06-01 21:33 |  | 2021-06-10 15:26 | 2021-06-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 16:08 |  | yes | no | no
112 | 16018058200107682000902 | 3 | Charleston St | Colton St | Alameda St | Asphalt | Yes | 2021-05-06 16:10 | 2021-05-12 12:06 | 2021-05-13 13:56 |  | 2021-05-20 14:05 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 16:31 |  | yes | no | no
145 | 16018058200165282001218 | 3 | Charleston St | W Remington Ave | W Winchester Ave | Asphalt | Yes | 2021-05-06 16:20 | 2021-05-12 12:35 | 2021-05-13 14:19 |  | 2021-05-20 15:03 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 16:31 |  | yes | no | no
12 | 15915098200038682000375 | 3 | Collingham Dr | Anvil St | Regent Dr | Asphalt | Yes | 2021-05-17 15:54 | 2021-06-15 19:17 | 2021-06-17 12:58 |  | 2021-07-31 17:33 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 15:45 |  | yes | no | no
13 | 15915098200039682000386 | 3 | Collingham Dr | Hoyt St | Anvil St | Asphalt | Yes | 2021-05-17 15:17 | 2021-06-15 19:47 | 2021-06-17 12:42 |  | 2021-07-31 17:35 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 15:45 |  | yes | no | no
10 | 15915098200037582000362 | 3 | Collingham Dr | Regent Dr | Marbud St | Asphalt | Yes | 2021-05-17 15:38 | 2021-06-15 18:48 | 2021-06-17 13:21 |  | 2021-07-31 17:32 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 15:46 |  | yes | no | no
4626 | 15915098200040382000396 | 3 | Collingham Dr | Reno St | Hoyt St | Asphalt | Yes Round 2 | 2021-09-08 15:27 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:27 |  | no | yes | no
4993 | 47112408209832182012732 | 3 | Commor St | Conant St | Fenelon St | Asphalt | Yes Round 2 | 2021-09-09 15:07 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 15:07 |  | no | yes | no
4994 | 47112408209832182012732 | 3 | Commor St | Conant St | Fenelon St | Asphalt | Yes Round 2 | 2021-09-09 15:05 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 15:05 |  | no | yes | no
2180 | 16022108200232882001718 | 3 | Concord St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 17:40 | 2021-06-08 11:59 | 2021-06-10 13:33 |  | 2021-07-15 17:33 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 18:00 |  | yes | no | no
2181 | 16022108200232882001718 | 3 | Concord St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 17:37 | 2021-06-08 12:31 | 2021-06-10 13:27 |  | 2021-07-15 17:25 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 18:01 |  | yes | no | no
4911 | 16299058200386582003050 | 3 | Conley St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 16:48 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:48 |  | no | yes | no
4912 | 16299058200386582003050 | 3 | Conley St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 16:50 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:51 |  | no | yes | no
4941 | 16299058200246082001866 | 3 | Conley St | E Lantz St | E Outer Dr | Asphalt | Yes Round 2 | 2021-09-08 16:55 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:55 |  | no | yes | no
4942 | 16299058200246082001866 | 3 | Conley St | E Lantz St | E Outer Dr | Asphalt | Yes Round 2 | 2021-09-08 16:57 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:58 |  | no | yes | no
390 | 16299068200450882003860 | 3 | Conley St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-11 17:22 | 2021-06-03 14:00 | 2021-06-07 16:54 |  | 2021-07-15 13:08 | 2021-06-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 17:51 |  | yes | no | no
5512 | 16299058200305082002460 | 3 | Conley St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5513 | 16299058200305082002460 | 3 | Conley St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
4550 | 15886028200227482002203 | 3 | Coram St | Gratiot Ave | Queen St | Asphalt | Yes Round 2 | 2021-09-08 14:19 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:19 |  | no | yes | no
4551 | 15886028200227482002203 | 3 | Coram St | Gratiot Ave | Queen St | Asphalt | Yes Round 2 | 2021-09-08 14:14 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:14 |  | no | yes | no
4552 | 15886028200227482002203 | 3 | Coram St | Gratiot Ave | Queen St | Asphalt | Yes Round 2 | 2021-09-08 14:08 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:08 |  | no | yes | no
4553 | 15886028200227482002203 | 3 | Coram St | Gratiot Ave | Queen St | Asphalt | Yes Round 2 | 2021-09-08 14:02 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:06 |  | no | yes | no
17 | 16026028200048982000384 | 3 | Cordell St | Bringard Dr | Edmore Dr | Asphalt | Yes | 2021-06-01 17:51 | 2021-06-10 19:44 | 2021-06-11 18:42 |  | 2021-08-02 15:13 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 17:51 |  | yes | no | no
5600 | 16026028200029282000207 | 3 | Cordell St | Collingham Dr | Carlisle St | Asphalt | Yes Round 3 | 2021-09-30 17:24 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-30 17:24 |  |  |  | Yes
60 | 16026028200091682000785 | 3 | Cordell St | Rossini Dr | Fairmount Dr | Asphalt | Yes | 2021-06-01 17:38 | 2021-06-10 19:20 | 2021-06-11 19:15 |  | 2021-08-02 15:25 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 17:38 |  | yes | no | no
2128 | 16018108200112063081431 | 3 | Coventry St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-06 17:38 | 2021-05-12 16:53 | 2021-05-13 18:39 |  | 2021-05-20 18:13 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 17:33 |  | yes | no | no
2129 | 16018108200112063081431 | 3 | Coventry St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-06 17:20 | 2021-05-12 16:54 | 2021-05-13 18:25 |  | 2021-05-20 18:13 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 17:34 |  | yes | no | no
144 | 16025088200218382001950 | 3 | Crusade St | Coram St | Novara St | Asphalt | Yes | 2021-06-01 13:29 | 2021-06-10 13:08 | 2021-06-15 20:13 |  | 2021-08-02 18:48 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 13:29 |  | yes | no | no
122 | 16025088200172382001507 | 3 | Crusade St | Liberal St | Manning St | Asphalt | Yes | 2021-06-01 13:25 | 2021-06-10 12:46 | 2021-06-15 20:30 |  | 2021-08-02 18:49 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 13:25 |  | yes | no | no
181 | 16025088200266482002440 | 3 | Crusade St | Maddelein St | Lappin St | Asphalt | Yes | 2021-06-01 13:30 | 2021-06-10 13:25 | 2021-06-15 19:37 |  | 2021-08-02 16:35 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 13:30 |  | yes | no | no
97 | 16025088200128982001157 | 3 | Crusade St | Tacoma St | E State Fair St | Asphalt | Yes | 2021-06-01 13:25 | 2021-06-10 12:29 | 2021-06-16 13:43 |  | 2021-08-02 18:56 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 13:25 |  | yes | no | no
15 | 16026048200046382000361 | 3 | Cushing St | Bringard Dr | Edmore Dr | Asphalt | Yes | 2021-06-01 19:14 | 2021-06-09 19:13 | 2021-06-11 14:15 |  | 2021-08-02 15:16 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 16:35 |  | yes | no | no
1 | 16026048200027182000194 | 3 | Cushing St | Collingham Dr | Carlisle St | Asphalt | Yes | 2021-06-01 19:26 | 2021-06-09 18:42 | 2021-06-11 13:47 |  | 2021-08-02 15:18 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 16:59 |  | yes | no | no
37 | 16026048200075082000571 | 3 | Cushing St | Fairmount Dr | Eastburn St | Asphalt | Yes | 2021-06-01 19:06 | 2021-06-09 19:41 | 2021-06-11 14:39 |  | 2021-08-02 15:21 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 16:02 |  | yes | no | no
2304 | 16021048200397282003115 | 3 | Dean St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 13:26 | 2021-06-01 19:22 | 2021-06-05 13:04 |  | 2021-07-14 16:26 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 13:26 |  | yes | no | no
2305 | 16021048200397282003115 | 3 | Dean St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 13:27 | 2021-06-01 19:51 | 2021-06-05 13:48 |  | 2021-07-14 16:28 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 13:27 |  | yes | no | no
472 | 16021048200526782004688 | 3 | Dean St | E Hildale St | E Robinwood St | Asphalt | Yes | 2021-05-10 16:09 | 2021-06-01 18:50 | 2021-06-05 11:23 |  | 2021-07-14 18:29 | 2021-06-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 16:07 |  | yes | no | no
2210 | 16021048200251582001951 | 3 | Dean St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 14:04 | 2021-06-02 12:56 | 2021-06-05 14:59 |  | 2021-07-14 16:54 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 14:04 |  | yes | no | no
2211 | 16021048200251582001951 | 3 | Dean St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 14:04 | 2021-06-02 13:19 | 2021-06-05 14:59 |  | 2021-07-14 16:54 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 14:04 |  | yes | no | no
2258 | 16021048200311582002515 | 3 | Dean St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-24 13:43 | 2021-06-01 20:28 | 2021-06-05 13:49 |  | 2021-07-14 16:48 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 13:43 |  | yes | no | no
2259 | 16021048200311582002515 | 3 | Dean St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-24 13:43 | 2021-06-02 12:25 | 2021-06-05 14:11 |  | 2021-07-14 18:32 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 13:43 |  | yes | no | no
1425 | 16305088201029682009873 | 3 | Dean St | Luce St | E Davison St | Asphalt | Yes | 2021-05-11 14:43 | 2021-05-19 16:34 | 2021-05-20 14:35 |  | 2021-06-04 15:29 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:46 |  | yes | no | no
517 | 16021048200585582005267 | 3 | Dean St | Stockton St | E Hildale St | Asphalt | Yes | 2021-05-10 15:56 | 2021-06-01 17:39 | 2021-06-04 21:23 |  | 2021-07-14 18:28 | 2021-06-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 15:56 |  | yes | no | no
2152 | 16018088200163382001140 | 3 | Derby St | W Remington Ave | W Winchester Ave | Asphalt | Yes | 2021-05-06 16:50 | 2021-05-12 14:00 | 2021-05-13 15:52 |  | 2021-05-20 16:30 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 17:32 |  | yes | no | no
2153 | 16018088200163382001140 | 3 | Derby St | W Remington Ave | W Winchester Ave | Asphalt | Yes | 2021-05-06 16:43 | 2021-05-12 14:24 | 2021-05-13 16:41 |  | 2021-05-20 16:31 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 17:33 |  | yes | no | no
2196 | 16018088200233582001633 | 3 | Derby St | W State Fair St | W Remington Ave | Asphalt | Yes | 2021-05-06 17:09 | 2021-05-12 13:08 | 2021-05-13 14:45 |  | 2021-05-20 16:19 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 16:32 |  | yes | no | no
2197 | 16018088200233582001633 | 3 | Derby St | W State Fair St | W Remington Ave | Asphalt | Yes | 2021-05-06 17:08 | 2021-05-12 13:22 | 2021-05-13 15:17 |  | 2021-05-20 16:19 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 17:32 |  | yes | no | no
2130 | 16018088200114063081430 | 3 | Derby St | W Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-06 16:37 | 2021-05-12 14:48 | 2021-05-13 17:23 |  | 2021-05-20 16:32 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 17:33 |  | yes | no | no
2131 | 16018088200114063081430 | 3 | Derby St | W Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-06 16:35 | 2021-05-12 15:12 | 2021-05-13 17:41 |  | 2021-05-20 16:50 | 2021-05-13 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-06 17:33 |  | yes | no | no
52 | 47105098200078482000477 | 3 | Dresden St | Bringard Dr | Collingham Dr | Asphalt | Yes | 2021-05-14 13:36 | 2021-06-11 19:17 | 2021-06-23 12:57 |  | 2021-07-31 15:14 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 18:56 |  | yes | no | no
529 | 16024018200639982005793 | 3 | Dresden St | Gietzen St | Greiner St | Asphalt | Yes | 2021-05-14 14:16 | 2021-06-12 12:21 | 2021-06-22 14:42 |  | 2021-07-30 15:47 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 14:47 |  | yes | no | no
4644 | 16024018200694182006399 | 3 | Dresden St | Sauer St | Gietzen St | Asphalt | Yes Round 2 | 2021-09-08 15:35 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:35 |  | no | yes | no
1438 | 47050038201244182011785 | 3 | Dwyer St | Casmere St | Sobieski St | Asphalt | Yes | 2021-06-01 12:54 | 2021-08-26 14:33 | 2021-09-01 19:49 |  |  | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-06-01 12:54 |  | yes | no | no
4645 | 16300088200624482005728 | 3 | Dwyer St | E Nevada St | Stockton St | Asphalt | Yes Round 2 | 2021-09-08 16:36 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:36 |  | no | yes | no
4595 | 16300088200439282003719 | 3 | Dwyer St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 16:32 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:32 |  | no | yes | no
1435 | 47050038201178582011297 | 3 | Dwyer St | Sobieski St | Charles St | Asphalt | Yes | 2021-06-01 12:45 | 2021-08-26 19:18 | 2021-08-31 17:02 |  |  | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-06-01 12:45 |  | yes | no | no
2286 | 15871068200389582089316 | 3 | E Brentwood St | Packard St | Van Dyke St | Asphalt | Yes | 2021-05-11 18:19 | 2021-06-09 12:40 | 2021-06-10 23:21 |  | 2021-07-25 20:31 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:11 |  | yes | no | no
2287 | 15871068200389582089316 | 3 | E Brentwood St | Packard St | Van Dyke St | Asphalt | Yes | 2021-05-11 18:18 | 2021-06-09 12:23 | 2021-06-10 22:58 |  | 2021-07-25 20:32 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:09 |  | yes | no | no
475 | 15870108200527482005267 | 3 | E Hildale St | Ryan Rd | Dean St | Asphalt | Yes | 2021-05-10 15:48 | 2021-06-02 11:32 | 2021-06-04 21:48 |  | 2021-07-14 18:29 | 2021-06-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 15:48 |  | yes | no | no
470 | 15870108200525882005251 | 3 | E Hildale St | Sunset St | Shields St | Asphalt | Yes | 2021-05-11 17:10 | 2021-06-02 11:51 | 2021-06-04 22:40 |  | 2021-07-14 18:29 | 2021-06-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 17:30 |  | yes | no | no
272 | 16383038200285082002838 | 3 | E Lantz St | Andover St | Irvington St | Asphalt | Yes | 2021-06-01 11:27 | 2021-08-25 20:11 | 2021-09-01 19:06 |  |  | 2021-09-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-06-01 11:28 |  | yes | no | no
194 | 15872048200242882002424 | 3 | E Lantz St | Buffalo St | Caldwell St | Asphalt | Yes | 2021-05-25 12:26 | 2021-06-04 13:39 | 2021-06-07 18:27 |  | 2021-07-15 13:52 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 12:25 |  | yes | no | no
276 | 16383038200287582002863 | 3 | E Lantz St | Coventry St | Keating St | Asphalt | Yes | [6 empty] | HMA | No |  |  | Resurfacing is required | Yes | No | poor pavement |  |  | yes | no | no
199 | 15872048200246782002460 | 3 | E Lantz St | Fenelon St | Conley St | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | No | poor pavement |  |  | yes | no | no
203 | 15872048200247782002471 | 3 | E Lantz St | Healy St | Lamont St | Asphalt | Yes | 2021-05-24 17:15 | 2021-06-03 11:38 | 2021-06-05 17:41 |  | 2021-07-14 19:27 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 17:15 |  | yes | no | no
2164 | 47111328200224482002220 | 3 | E Lantz St | Kempa St | E Outer Dr | Asphalt | Yes | 2021-05-13 12:39 | 2021-06-09 14:05 | 2021-06-10 21:13 |  | 2021-07-25 16:54 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 16:41 |  | yes | no | no
2165 | 47111328200224482002220 | 3 | E Lantz St | Kempa St | E Outer Dr | Asphalt | Yes | 2021-05-13 12:41 | 2021-06-09 14:32 | 2021-06-10 21:30 |  | 2021-07-25 16:55 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 16:41 |  | yes | no | no
4586 | 47111328209791382002262 | 3 | E Lantz St | Van Dyke St | Terrell St | Asphalt | Yes Round 2 | 2021-09-08 16:20 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:20 |  | no | yes | no
268 | 16383038200282882002819 | 3 | E Lantz St | Yacama Rd | Omira St | Asphalt | Yes | 2021-05-10 14:18 | 2021-08-25 19:18 | 2021-08-31 13:21 |  |  | 2021-08-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 14:18 |  | yes | no | no
129 | 47103038200142182001411 | 3 | E Remington St | Anglin St | Harned St | Asphalt | Yes | 2021-05-21 12:25 | 2021-05-24 15:12 | 2021-06-02 17:05 |  | 2021-07-10 17:37 | 2021-06-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 12:28 |  | yes | no | no
132 | 47103038200143882001427 | 3 | E Remington St | Goddard St | Mackay St | Asphalt | Yes | 2021-05-10 13:23 | 2021-05-24 14:45 | 2021-06-02 17:05 |  | 2021-07-10 17:36 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:23 |  | yes | no | no
135 | 47103038200145282001445 | 3 | E Remington St | Lumpkin St | Fleming St | Asphalt | Yes | 2021-05-10 13:23 | 2021-05-24 14:26 | 2021-06-02 15:16 |  | 2021-07-10 17:36 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:23 |  | yes | no | no
4646 | 16311028200499982004982 | 3 | E Robinwood St | Marx St | Dequindre St | Asphalt | Yes Round 2 | 2021-09-08 18:41 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 18:42 |  | no | yes | no
4531 | 15871048200419882004161 | 3 | E Robinwood St | Packard St | Van Dyke St | Asphalt | Yes Round 2 | 2021-09-08 16:08 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:08 |  | no | yes | no
4614 | 15871048200419882004161 | 3 | E Robinwood St | Packard St | Van Dyke St | Asphalt | Yes Round 2 | 2021-09-08 16:06 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:06 |  | no | yes | no
4624 | 17090098200096182000957 | 3 | E Winchester Ave | Anglin St | Harned St | Asphalt | Yes Round 2 | 2021-09-08 19:44 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:44 |  | no | yes | no
4584 | 17090098200097482000967 | 3 | E Winchester Ave | Goddard St | Mackay St | Asphalt | Yes Round 2 | 2021-09-08 19:41 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:41 |  | no | yes | no
104 | 16311058200104682001037 | 3 | E Winchester Ave | Hull St | Greeley St | Asphalt | Yes | [6 empty] | HMA | No |  |  | Resurfacing is required | Yes | No | poor pavement |  |  | yes | no | no
98 | 16311058200100582000998 | 3 | E Winchester Ave | Marx St | Dequindre St | Asphalt | Yes | 2021-05-10 12:34 | 2021-05-13 15:32 | 2021-05-19 14:29 |  | 2021-05-21 12:58 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 12:34 |  | yes | no | no
107 | 16311058200105682001052 | 3 | E Winchester Ave | Russell St | Hanna St | Asphalt | Yes | 2021-05-10 14:37 | 2021-05-13 16:47 | 2021-05-14 15:29 |  | 2021-05-20 20:37 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 14:37 |  | yes | no | no
5608 | 15887028200079582000778 | 3 | Eastburn St | Anvil St | Regent Dr | Asphalt | Yes Round 3 | 2021-09-30 17:01 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-30 17:01 |  |  |  | Yes
31 | 15887028200059382000587 | 3 | Eastburn St | Boulder St | Cordell St | Asphalt | Yes | 2021-06-01 18:43 | 2021-06-09 21:34 | 2021-06-11 17:27 |  | 2021-08-02 15:07 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 14:46 |  | yes | no | no
29 | 15887028200058782000576 | 3 | Eastburn St | Cordell St | Shakespeare St | Asphalt | Yes | 2021-06-01 18:53 | 2021-06-09 20:57 | 2021-06-11 15:37 |  | 2021-08-02 15:06 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 15:21 |  | yes | no | no
47 | 15887028200081782000795 | 3 | Eastburn St | Hoyt St | Anvil St | Asphalt | Yes | 2021-05-19 13:31 | 2021-06-15 20:20 | 2021-06-17 19:18 |  | 2021-08-02 13:05 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 17:34 |  | yes | no | no
41 | 15887028200074982000721 | 3 | Eastburn St | Marbud St | Gratiot Ave | Asphalt | Yes | 2021-05-17 17:37 | 2021-06-11 19:52 | 2021-06-16 17:18 |  | 2021-07-31 18:12 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 16:11 |  | yes | no | no
32 | 15887028200060982000593 | 3 | Eastburn St | Redmond St | Boulder St | Asphalt | Yes | 2021-06-01 18:23 | 2021-06-10 20:33 | 2021-06-11 17:28 |  | 2021-08-02 15:09 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 14:07 |  | yes | no | no
4572 | 15887028200082782000817 | 3 | Eastburn St | Reno St | Hoyt St | Asphalt | Yes Round 2 | 2021-09-08 14:56 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:57 |  | no | yes | no
28 | 15887028200057682000571 | 3 | Eastburn St | Shakespeare St | Cushing St | Asphalt | Yes | 2021-06-01 19:02 | 2021-06-09 20:26 | 2021-06-11 15:08 |  | 2021-08-02 15:22 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 15:58 |  | yes | no | no
342 | 15915038200402482004009 | 3 | Eastwood St | Algonac St | Beland St | Asphalt | Yes | 2021-05-13 15:23 | 2021-06-04 19:25 | 2021-06-17 13:25 |  | 2021-07-25 19:54 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 12:21 |  | yes | no | no
328 | 15885048200385682003844 | 3 | Eastwood St | Barlow St | Waltham St | Asphalt | Yes | 2021-05-14 14:46 | 2021-06-14 15:38 | 2021-06-22 17:15 |  | 2021-07-30 17:06 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 17:23 |  | yes | no | no
345 | 15915038200405182004035 | 3 | Eastwood St | Blackmoor St | Gruebner St | Asphalt | Yes | 2021-05-13 14:28 | 2021-06-04 18:36 | 2021-06-17 13:24 |  | 2021-07-30 14:22 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 12:00 |  | yes | no | no
327 | 15885048200382582003804 | 3 | Eastwood St | Goulburn St | Westphalia St | Asphalt | Yes | 2021-06-01 14:22 | 2021-06-14 19:01 | 2021-06-22 17:18 |  | 2021-07-30 17:05 | 2021-06-22 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-06-01 14:22 |  | yes | no | no
336 | 15915038200398582003970 | 3 | Eastwood St | Runyon St | Albion St | Asphalt | Yes | 2021-05-13 15:38 | 2021-06-08 20:47 | 2021-06-17 13:58 |  | 2021-07-25 19:33 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 18:28 |  | yes | no | no
330 | 15885048200388782003874 | 3 | Eastwood St | Strasburg St | Hamburg St | Asphalt | Yes | 2021-05-14 14:46 | 2021-06-14 14:10 | 2021-06-22 16:55 |  | 2021-07-30 17:07 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 17:24 |  | yes | no | no
3883 | 17167038200919382009147 | 3 | Edgevale St | John R St | Brush St | Asphalt | Yes | 2021-05-10 19:06 | 2021-08-25 17:16 | 2021-08-30 20:56 |  |  | 2021-08-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 19:06 |  | yes | no | no
3884 | 17167038200919382009147 | 3 | Edgevale St | John R St | Brush St | Asphalt | Yes | 2021-05-10 19:06 | 2021-08-25 17:58 | 2021-08-30 21:06 |  |  | 2021-08-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 19:06 |  | yes | no | no
3885 | 17167038200919382009147 | 3 | Edgevale St | John R St | Brush St | Asphalt | Yes | 2021-05-10 19:07 | 2021-08-25 17:37 | 2021-08-31 12:53 |  |  | 2021-08-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 19:07 |  | yes | no | no
5663 | 15880038201643982016408 | 3 | Edgewood Ave | Crane St | Rohns St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
23 | 16337048200049582000480 | 3 | Edmore Dr | Anvil St | Regent Dr | Asphalt | Yes | 2021-05-17 15:28 | 2021-06-15 18:03 | 2021-06-17 13:46 |  | 2021-07-31 18:01 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 17:58 |  | yes | no | no
4913 | 15887058200045182000434 | 3 | Edmore Dr | Gratiot Ave | Hayes St | Asphalt | Yes Round 2 | 2021-09-08 13:36 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:07 |  | no | yes | no
4914 | 15887058200045182000434 | 3 | Edmore Dr | Gratiot Ave | Hayes St | Asphalt | Yes Round 2 | 2021-09-08 13:36 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:07 |  | no | yes | no
26 | 16337048200050582000495 | 3 | Edmore Dr | Hoyt St | Anvil St | Asphalt | Yes | 2021-05-17 15:17 | 2021-06-15 17:35 | 2021-06-17 14:04 |  | 2021-07-31 18:03 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 17:59 |  | yes | no | no
4573 | 16337048200051682000505 | 3 | Edmore Dr | Reno St | Hoyt St | Asphalt | Yes Round 2 | 2021-09-08 15:15 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:15 |  | no | yes | no
2846 | 16314028201348682013000 | 3 | Eldridge Ave | Conant St | Fenelon St | Asphalt | Yes | 2021-05-12 18:48 | 2021-05-21 20:19 | 2021-05-25 12:40 |  | 2021-06-02 15:00 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:53 |  | yes | no | no
2847 | 16314028201348682013000 | 3 | Eldridge Ave | Conant St | Fenelon St | Asphalt | Yes | 2021-05-11 12:44 | 2021-05-21 21:04 | 2021-05-25 12:57 |  | 2021-06-02 15:34 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:53 |  | yes | no | no
5595 | 16311038200305082003041 | 3 | Emery St | Conley St | Keystone St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
4576 | 16311038200306882003062 | 3 | Emery St | Healy St | Lamont St | Asphalt | Yes Round 2 | 2021-09-08 17:05 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:05 |  | no | yes | no
4613 | 15871108200296882002961 | 3 | Emery St | Spencer St | Stotter St | Asphalt | Yes Round 2 | 2021-09-08 16:15 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:15 |  | no | yes | no
2202 | 16298058200248882001910 | 3 | Eureka St | E Lantz St | E Outer Dr | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | No | poor pavement |  |  | yes | no | no
2203 | 16298058200248882001910 | 3 | Eureka St | E Lantz St | E Outer Dr | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | No | poor pavement |  |  | yes | no | no
48 | 15887018200086082000836 | 3 | Fairmount Dr | Brock St | Crusade St | Asphalt | Yes | 2021-05-25 17:32 | 2021-06-10 21:07 | 2021-06-16 14:07 |  | 2021-08-02 14:45 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes | Resolved | 2021-05-25 17:32 |  | yes | no | no
5601 | 15887018200083682000828 | 3 | Fairmount Dr | Crusade St | Rex St | Asphalt | Yes Round 3 | 2021-09-30 18:04 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-30 18:04 |  |  |  | Yes
63 | 15887018200089082000879 | 3 | Fairmount Dr | Gratiot Ave | Queen St | Asphalt | Yes | 2021-05-25 17:00 | 2021-06-11 18:36 | 2021-06-16 16:12 |  | 2021-08-02 14:56 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 17:00 |  | yes | no | no
70 | 15887018200094282000925 | 3 | Fairmount Dr | Hoyt St | Anvil St | Asphalt | Yes | 2021-05-19 13:30 | 2021-06-15 21:26 | 2021-06-17 19:05 |  | 2021-08-02 13:08 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 17:21 |  | yes | no | no
66 | 15887018200089882000890 | 3 | Fairmount Dr | Marbud St | Gratiot Ave | Asphalt | Yes | 2021-05-17 17:38 | 2021-06-11 18:58 | 2021-06-16 16:42 |  | 2021-08-02 13:16 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 16:11 |  | yes | no | no
2118 | 15887018200087982000866 | 3 | Fairmount Dr | Queen St | Hayes St | Asphalt | Yes | 2021-05-25 17:19 | 2021-06-11 18:11 | 2021-06-16 15:55 |  | 2021-08-02 14:51 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 17:19 |  | yes | no | no
2119 | 15887018200087982000866 | 3 | Fairmount Dr | Queen St | Hayes St | Asphalt | Yes | 2021-05-25 17:18 | 2021-06-11 17:15 | 2021-06-16 15:21 |  | 2021-08-02 14:51 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 17:18 |  | yes | no | no
4616 | 15887018200090782000898 | 3 | Fairmount Dr | Regent Dr | Marbud St | Asphalt | Yes Round 2 | 2021-09-08 14:32 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:32 |  | no | yes | no
72 | 15887018200096382000942 | 3 | Fairmount Dr | Reno St | Hoyt St | Asphalt | Yes | 2021-05-17 18:56 | 2021-06-16 16:21 | 2021-06-17 18:35 |  | 2021-08-02 13:07 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 17:21 |  | yes | no | no
20 | 16024058200044250041352 | 3 | Fairport St | Collingham Dr | 8 Mile Rd | Asphalt | Yes | 2021-05-14 13:41 | 2021-06-16 14:55 | 2021-06-23 21:08 |  | 2021-07-31 15:07 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 18:15 |  | yes | no | no
262 | 16024058200317582002709 | 3 | Fairport St | E 7 Mile Rd | Lappin St | Asphalt | Yes | 2021-05-14 13:56 | 2021-06-16 17:34 | 2021-06-23 19:09 |  | 2021-07-30 20:59 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 17:10 |  | yes | no | no
4712 | 16024058200566382005062 | 3 | Fairport St | Greiner St | Park Grove St | Asphalt | Yes Round 2 | 2021-09-08 15:27 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:27 |  | no | yes | no
200 | 16024058200270982002285 | 3 | Fairport St | Lappin St | Pinewood St | Asphalt | Yes | 2021-05-14 15:50 | 2021-08-30 16:59 | 2021-09-01 16:39 |  |  | 2021-09-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 17:11 |  | yes | no | no
128 | 16024058200173382001334 | 3 | Fairport St | Manning St | E State Fair St | Asphalt | Yes | 2021-05-14 15:49 | 2021-06-16 15:33 | 2021-06-23 20:55 |  | 2021-07-30 20:53 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 17:12 |  | yes | no | no
151 | 16024058200228582001733 | 3 | Fairport St | Pinewood St | Manning St | Asphalt | Yes | 2021-05-14 15:50 | 2021-06-16 16:45 | 2021-06-23 19:35 |  | 2021-07-30 20:55 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 17:11 |  | yes | no | no
2194 | 16299038200246782001876 | 3 | Fenelon St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 18:43 | 2021-06-03 16:03 | 2021-06-06 16:24 |  | 2021-07-15 13:14 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 18:43 |  | yes | no | no
2195 | 16299038200246782001876 | 3 | Fenelon St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 18:42 | 2021-06-03 16:27 | 2021-06-06 16:24 |  | 2021-07-15 13:14 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 18:42 |  | yes | no | no
2838 | 17121048201300082012732 | 3 | Fenelon St | Eldridge Ave | Commor St | Asphalt | Yes | 2021-08-04 15:30 | 2021-08-26 18:21 | 2021-08-31 16:39 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 15:30 |  | yes | no | no
366 | 16301028200432982003674 | 3 | Filer St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-25 15:04 | 2021-06-08 11:25 | 2021-06-10 14:18 |  | 2021-07-15 16:55 | 2021-06-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 15:04 |  | yes | no | no
2224 | 16296108200265282002085 | 3 | Fleming St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-10 13:44 | 2021-05-25 11:21 | 2021-06-03 17:16 |  | 2021-07-10 18:20 | 2021-06-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:43 |  | yes | no | no
2225 | 16296108200265282002085 | 3 | Fleming St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-10 13:45 | 2021-05-25 11:40 | 2021-06-03 17:39 |  | 2021-07-10 18:20 | 2021-06-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:45 |  | yes | no | no
2442 | 17164018200914182008308 | 3 | Fleming St | E McNichols Rd | Stender St | Asphalt | Yes Round 2 | 2021-09-09 13:58 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 13:58 |  | no | yes | no
3500 | 17164018200914182008308 | 3 | Fleming St | E McNichols Rd | Stender St | Asphalt | Yes Round 2 | 2021-09-09 14:02 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:02 |  | no | yes | no
4987 | 17164018200830882007433 | 3 | Fleming St | Stender St | Minnesota St | Asphalt | Yes Round 2 | 2021-09-09 14:04 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:04 |  | no | yes | no
4988 | 17164018200830882007433 | 3 | Fleming St | Stender St | Minnesota St | Asphalt | Yes Round 2 | 2021-09-09 14:07 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:07 |  | no | yes | no
4599 | 15885068200337282003338 | 3 | Fordham St | Reno St | Rondo St | Asphalt | Yes Round 2 | 2021-09-08 14:49 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:49 |  | no | yes | no
273 | 15885068200333882003307 | 3 | Fordham St | Rondo St | Gratiot Ave | Asphalt | Yes | 2021-05-25 15:31 | 2021-06-16 20:17 | 2021-06-17 21:04 |  | 2021-07-31 17:11 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 15:31 |  | yes | no | no
4772 | 16314078201218782012162 | 3 | Fredro St | Fenelon St | Radom St | Asphalt | Yes Round 2 | 2021-09-09 15:00 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 15:00 |  | no | yes | no
4671 | 47075158200949882008823 | 3 | Gable St | Desner St | E McNichols Rd | Asphalt | Yes Round 2 | 2021-09-09 15:26 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 15:27 |  | no | yes | no
2284 | 16300068200373582002974 | 3 | Gable St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-25 13:21 | 2021-06-04 16:59 | 2021-06-08 17:34 |  | 2021-07-15 16:16 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 13:21 |  | yes | no | no
2285 | 16300068200373582002974 | 3 | Gable St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-25 13:21 | 2021-06-04 16:23 | 2021-06-08 17:16 |  | 2021-07-15 16:16 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 13:21 |  | yes | no | no
659 | 16300068200744782006827 | 3 | Gable St | E Davison St | Iowa St | Asphalt | Yes | 2021-05-11 15:51 | 2021-05-22 18:23 | 2021-06-01 18:50 |  | 2021-06-04 21:13 | 2021-06-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 17:14 |  | yes | no | no
2188 | 16300068200240182001791 | 3 | Gable St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-25 13:35 | 2021-06-04 14:58 | 2021-06-08 15:36 |  | 2021-07-15 16:06 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 13:35 |  | yes | no | no
2189 | 16300068200240182001791 | 3 | Gable St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-25 13:34 | 2021-06-04 14:22 | 2021-06-08 15:36 |  | 2021-07-15 16:05 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 13:34 |  | yes | no | no
2434 | 47103248208935182007914 | 3 | Gable St | E McNichols Rd | Brimson St | Asphalt | Yes | 2021-05-11 15:40 | 2021-05-22 15:52 | 2021-06-01 20:24 |  | 2021-06-04 21:01 | 2021-06-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 17:09 |  | yes | no | no
2435 | 47103248208935182007914 | 3 | Gable St | E McNichols Rd | Brimson St | Asphalt | Yes | 2021-05-11 15:39 | 2021-05-22 16:29 | 2021-06-01 19:23 |  | 2021-06-04 21:06 | 2021-06-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 17:09 |  | yes | no | no
2240 | 16300068200297482002401 | 3 | Gable St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-25 12:54 | 2021-06-04 15:49 | 2021-06-08 16:37 |  | 2021-07-15 16:12 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 12:54 |  | yes | no | no
2241 | 16300068200297482002401 | 3 | Gable St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-25 12:54 | 2021-06-04 15:27 | 2021-06-08 15:36 |  | 2021-07-15 16:08 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-25 12:54 |  | yes | no | no
590 | 16300068200682782006253 | 3 | Gable St | Iowa St | E Nevada St | Asphalt | Yes | 2021-05-11 15:51 | 2021-05-22 18:35 | 2021-06-01 18:50 |  | 2021-06-04 21:14 | 2021-06-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 17:14 |  | yes | no | no
2839 | 17157028201285182012110 | 3 | Gallagher St | Carpenter St | Halleck St | Asphalt | Yes | 2021-05-10 17:23 | 2021-05-20 12:15 | 2021-05-20 22:18 |  | 2021-06-04 12:22 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 17:50 |  | yes | no | no
2310 | 16020068200404482003184 | 3 | Gallagher St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-21 15:35 | 2021-05-24 19:49 | 2021-06-03 14:25 |  | 2021-06-06 17:17 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 15:35 |  | yes | no | no
2311 | 16020068200404482003184 | 3 | Gallagher St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-21 15:35 | 2021-05-24 19:22 | 2021-06-03 13:34 |  | 2021-06-06 17:12 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 15:35 |  | yes | no | no
507 | 16297098200562882005247 | 3 | Gallagher St | E Grixdale St | E Hildale St | Asphalt | Yes | 2021-05-10 16:09 | 2021-05-25 18:40 | 2021-06-02 14:04 |  | 2021-06-10 17:58 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 16:09 |  | yes | no | no
2220 | 16020068200256882002022 | 3 | Gallagher St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-21 14:40 | 2021-05-24 17:54 | 2021-06-02 19:12 |  | 2021-06-06 16:59 | 2021-06-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 14:40 |  | yes | no | no
2221 | 16020068200256882002022 | 3 | Gallagher St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-21 14:40 | 2021-05-24 17:33 | 2021-06-02 19:12 |  | 2021-06-06 16:29 | 2021-06-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 14:40 |  | yes | no | no
2158 | 16020068200196882001397 | 3 | Gallagher St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-05-21 14:25 | 2021-05-24 16:46 | 2021-06-02 17:58 |  | 2021-06-06 16:56 | 2021-06-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 14:25 |  | yes | no | no
2159 | 16020068200196882001397 | 3 | Gallagher St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-05-21 14:25 | 2021-05-24 16:03 | 2021-06-02 17:58 |  | 2021-06-06 15:51 | 2021-06-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 14:25 |  | yes | no | no
5602 | 16297098200479982004395 | 3 | Gallagher St | E Robinwood St | E Brentwood St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2264 | 16020068200318482002568 | 3 | Gallagher St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-21 15:20 | 2021-05-24 18:52 | 2021-06-03 13:34 |  | 2021-06-06 17:09 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 15:20 |  | yes | no | no
2265 | 16020068200318482002568 | 3 | Gallagher St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-21 15:19 | 2021-05-24 18:24 | 2021-06-02 19:12 |  | 2021-06-06 17:06 | 2021-06-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 15:19 |  | yes | no | no
1432 | 17157028201126083017719 | 3 | Gallagher St | Lawley St | E Davison St | Asphalt | Yes | 2021-05-10 17:27 | 2021-05-24 11:20 | 2021-08-13 12:32 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 17:51 |  | yes | no | no
4985 | 17161108200734982006520 | 3 | Gallagher St | Minnesota St | E Nevada St | Asphalt | Yes Round 2 | 2021-09-09 14:32 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:32 |  | no | yes | no
4986 | 17161108200734982006520 | 3 | Gallagher St | Minnesota St | E Nevada St | Asphalt | Yes Round 2 | 2021-09-09 14:37 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:37 |  | no | yes | no
214 | 16019108200244882002071 | 3 | Goddard St | Conant St | E Outer Dr | Asphalt | Yes | 2021-05-10 13:46 | 2021-05-25 12:15 | 2021-06-03 18:06 |  | 2021-07-10 17:38 | 2021-06-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:46 |  | yes | no | no
5538 | 17163098200913182008302 | 3 | Goddard St | E McNichols Rd | Stender St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5539 | 17163098200913182008302 | 3 | Goddard St | E McNichols Rd | Stender St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
4979 | 16297018200496382004107 | 3 | Goddard St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 18:37 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 18:37 |  | no | yes | no
4980 | 16297018200496382004107 | 3 | Goddard St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 18:07 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 18:07 |  | no | yes | no
5536 | 17163098200830282007421 | 3 | Goddard St | Stender St | Minnesota St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5537 | 17163098200830282007421 | 3 | Goddard St | Stender St | Minnesota St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2324 | 16019048200418682003360 | 3 | Greeley St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-07 15:03 | 2021-05-14 14:05 | 2021-05-14 20:40 |  | 2021-05-21 14:08 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:20 |  | yes | no | no
2325 | 16019048200418682003360 | 3 | Greeley St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-07 15:06 | 2021-05-14 14:17 | 2021-05-14 20:50 |  | 2021-05-21 14:13 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:20 |  | yes | no | no
2234 | 16019048200271882002155 | 3 | Greeley St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 15:27 | 2021-05-14 16:14 | 2021-05-17 12:56 |  | 2021-05-21 14:25 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:19 |  | yes | no | no
2235 | 16019048200271882002155 | 3 | Greeley St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 15:27 | 2021-05-14 17:31 | 2021-05-17 13:13 |  | 2021-05-21 14:26 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:19 |  | yes | no | no
5384 | 16019048200685582005824 | 3 | Greeley St | E Nevada St | E Grixdale Ave | Asphalt | Yes Round 2 | 2021-09-30 14:34 | [5 empty] | HMA |  |  |  |  | No | Yes |  | 2021-09-30 14:34 |  | No | Yes | no
5385 | 16019048200685582005824 | 3 | Greeley St | E Nevada St | E Grixdale Ave | Asphalt | Yes Round 2 | 2021-09-30 15:01 | [5 empty] | HMA |  |  |  |  | No | Yes |  | 2021-09-30 15:02 |  | No | Yes | no
2146 | 16019048200151182001037 | 3 | Greeley St | E Remington Ave | E Winchester Ave | Asphalt | Yes | 2021-05-07 14:10 | 2021-05-14 18:31 | 2021-05-17 14:28 |  | 2021-05-21 15:38 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:18 |  | yes | no | no
2147 | 16019048200151182001037 | 3 | Greeley St | E Remington Ave | E Winchester Ave | Asphalt | Yes | 2021-05-07 14:28 | 2021-05-14 18:45 | 2021-05-17 17:05 |  | 2021-05-21 15:53 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:13 |  | yes | no | no
5532 | 16019048200506882004186 | 3 | Greeley St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5533 | 16019048200506882004186 | 3 | Greeley St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2184 | 16019048200215582001511 | 3 | Greeley St | E State Fair St | E Remington Ave | Asphalt | Yes | 2021-05-07 16:09 | 2021-05-14 17:32 | 2021-05-17 13:38 |  | 2021-05-21 14:31 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:18 |  | yes | no | no
2185 | 16019048200215582001511 | 3 | Greeley St | E State Fair St | E Remington Ave | Asphalt | Yes | 2021-05-07 16:09 | 2021-05-14 17:55 | 2021-05-17 14:05 |  | 2021-05-21 15:05 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:18 |  | yes | no | no
102 | 16019048200103763081441 | 3 | Greeley St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-07 14:44 | 2021-05-14 19:35 | 2021-05-17 17:21 |  | 2021-05-21 15:54 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 15:38 |  | yes | no | no
2278 | 16019048200336082002718 | 3 | Greeley St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-07 15:13 | 2021-05-14 15:44 | 2021-05-14 21:05 |  | 2021-05-21 14:20 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:19 |  | yes | no | no
2279 | 16019048200336082002718 | 3 | Greeley St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-07 15:16 | 2021-05-14 15:44 | 2021-05-14 21:58 |  | 2021-05-21 14:23 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:19 |  | yes | no | no
454 | 16303018200529982004652 | 3 | Gruebner St | Park Grove St | Linnhurst St | Asphalt | Yes | 2021-05-13 15:17 | 2021-06-10 19:52 | 2021-06-21 21:03 |  | 2021-07-30 14:21 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 12:59 |  | yes | no | no
271 | 16024038200326182002769 | 3 | Hamburg St | E 7 Mile Rd | Lappin St | Asphalt | Yes | 2021-05-14 12:46 | 2021-06-14 14:52 | 2021-06-23 14:31 |  | 2021-07-30 20:00 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 20:32 |  | yes | no | no
137 | 16024038200178382001387 | 3 | Hamburg St | Manning St | E State Fair St | Asphalt | Yes | 2021-05-14 13:12 | 2021-06-12 18:15 | 2021-06-23 15:03 |  | 2021-07-30 20:08 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 19:14 |  | yes | no | no
162 | 16024038200235882001783 | 3 | Hamburg St | Pinewood St | Manning St | Asphalt | Yes | 2021-05-14 14:48 | 2021-06-12 19:19 | 2021-06-23 15:03 |  | 2021-07-30 20:00 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 19:14 |  | yes | no | no
5001 | 16019028200421782003383 | 3 | Hanna St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 18:58 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 18:58 |  | no | yes | no
5002 | 16019028200421782003383 | 3 | Hanna St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 18:56 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 18:56 |  | no | yes | no
5526 | 16019028200152982001052 | 3 | Hanna St | E Remington Ave | E Winchester Ave | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5527 | 16019028200152982001052 | 3 | Hanna St | E Remington Ave | E Winchester Ave | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
4997 | 16019028200217882001529 | 3 | Hanna St | E State Fair St | E Remington Ave | Asphalt | Yes Round 2 | 2021-09-08 19:17 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:17 |  | no | yes | no
4998 | 16019028200217882001529 | 3 | Hanna St | E State Fair St | E Remington Ave | Asphalt | Yes Round 2 | 2021-09-08 19:20 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:20 |  | no | yes | no
2280 | 16019028200338382002737 | 3 | Hanna St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-10 14:28 | 2021-05-13 20:23 | 2021-05-14 20:03 |  | 2021-05-24 19:19 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 14:28 |  | yes | no | no
2281 | 16019028200338382002737 | 3 | Hanna St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-10 14:28 | 2021-05-14 13:16 | 2021-05-14 20:12 |  | 2021-05-24 19:23 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 14:28 |  | yes | no | no
2316 | 16020038200408982003216 | 3 | Harned St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-21 13:43 | 2021-05-25 13:05 | 2021-06-03 14:25 |  | 2021-07-14 12:56 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 13:43 |  | yes | no | no
2317 | 16020038200408982003216 | 3 | Harned St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-21 13:43 | 2021-05-25 13:20 | 2021-06-03 15:06 |  | 2021-07-14 12:56 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 13:43 |  | yes | no | no
5518 | 16020038200199482001411 | 3 | Harned St | E Outer Dr | E Remington St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5519 | 16020038200199482001411 | 3 | Harned St | E Outer Dr | E Remington St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5524 | 16020038200321682002595 | 3 | Harned St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5525 | 16020038200321682002595 | 3 | Harned St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
511 | 16298108200579582005207 | 3 | Healy St | Stockton St | E Hildale St | Asphalt | Yes | [6 empty] | HMA | No |  |  | Resurfacing is required | Yes | No | poor pavement | 2021-05-11 17:33 |  | yes | no | no
4578 | 16023018200073650041427 | 3 | Helen St | Savage St | 8 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 16:34 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:34 |  | no | yes | no
39 | 47109488200066282000426 | 3 | Hickory St | Bringard Dr | Collingham Dr | Asphalt | Yes | 2021-05-17 12:28 | 2021-06-17 14:56 | 2021-06-24 15:29 |  | 2021-07-30 22:12 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:06 |  | yes | no | no
106 | 47109488200130482000989 | 3 | Hickory St | E State Fair St | Fairmount Dr | Asphalt | Yes | 2021-05-17 12:52 | 2021-06-17 15:51 | 2021-06-24 13:41 |  | 2021-07-30 22:08 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:05 |  | yes | no | no
74 | 47109488200098982000662 | 3 | Hickory St | Fairmount Dr | Bringard Dr | Asphalt | Yes | 2021-05-17 12:50 | 2021-06-17 15:25 | 2021-06-24 15:13 |  | 2021-07-30 22:10 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:06 |  | yes | no | no
471 | 47109488209729282005010 | 3 | Hickory St | Greiner St | Park Grove St | Asphalt | Yes | 2021-05-14 14:59 | 2021-06-17 17:58 | 2021-06-22 19:30 |  | 2021-07-30 16:17 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 12:18 |  | yes | no | no
1272 | 17136048201765082016863 | 3 | Holcomb Ave | Georgia St | Marcus Ave | Asphalt | Yes | 2021-06-02 12:21 | 2021-06-17 22:10 | 2021-06-22 17:18 |  | 2021-08-02 21:12 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 12:21 |  | yes | no | no
14 | 16025018200039682000304 | 3 | Hoyt St | Collingham Dr | Carlisle St | Asphalt | Yes | 2021-05-17 15:10 | 2021-06-15 16:07 | 2021-06-16 21:00 |  | 2021-07-31 17:37 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 14:50 |  | yes | no | no
5504 | 16019038200420082003377 | 3 | Hull St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5505 | 16019038200420082003377 | 3 | Hull St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2236 | 16019038200272882002165 | 3 | Hull St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 13:24 | 2021-05-13 19:47 | 2021-05-14 18:49 |  | 2021-05-21 20:41 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:22 |  | yes | no | no
2237 | 16019038200272882002165 | 3 | Hull St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 13:21 | 2021-05-13 18:42 | 2021-05-14 18:29 |  | 2021-05-21 20:10 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:21 |  | yes | no | no
2148 | 16019038200152282001046 | 3 | Hull St | E Remington Ave | E Winchester Ave | Asphalt | Yes | 2021-05-07 14:04 | 2021-05-13 14:47 | 2021-05-14 17:58 |  | 2021-05-20 21:12 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:12 |  | yes | no | no
2149 | 16019038200152282001046 | 3 | Hull St | E Remington Ave | E Winchester Ave | Asphalt | Yes | 2021-05-07 13:56 | 2021-05-13 13:48 | 2021-05-14 17:58 |  | 2021-05-20 21:12 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 13:38 |  | yes | no | no
105 | 16019038200104663081440 | 3 | Hull St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-07 13:35 | 2021-05-13 12:59 | 2021-05-14 17:13 |  | 2021-05-20 20:42 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:10 |  | yes | no | no
4939 | 16295068200159282001103 | 3 | Irvington St | E Remington Ave | E Winchester Ave | Asphalt 2020 | Yes Round 2 | 2021-09-08 19:06 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:06 |  | no | yes | no
4940 | 16295068200159282001103 | 3 | Irvington St | E Remington Ave | E Winchester Ave | Asphalt 2020 | Yes Round 2 | 2021-09-08 19:10 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:10 |  | no | yes | no
320 | 16304068200377282003160 | 3 | Joann St | Eastwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-14 16:56 | 2021-06-16 18:07 | 2021-06-22 17:50 |  | 2021-07-30 17:03 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 15:37 |  | yes | no | no
355 | 16304068200437982003772 | 3 | Joann St | Linnhurst St | Eastwood St | Asphalt | Yes | 2021-05-14 16:57 | 2021-06-16 18:39 | 2021-06-22 19:11 |  | 2021-07-30 17:02 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 15:37 |  | yes | no | no
409 | 16304068200504682004379 | 3 | Joann St | Park Grove St | Linnhurst St | Asphalt | Yes | 2021-05-14 16:57 | 2021-06-16 20:19 | 2021-06-22 18:19 |  | 2021-07-30 16:58 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 15:36 |  | yes | no | no
2204 | 16298048200249382001919 | 3 | Justine St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 15:29 | 2021-06-02 16:12 | 2021-06-08 12:44 |  | 2021-07-14 19:14 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 15:29 |  | yes | no | no
2205 | 16298048200249382001919 | 3 | Justine St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 15:28 | 2021-06-02 15:49 | 2021-06-07 22:04 |  | 2021-07-14 19:14 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 15:28 |  | yes | no | no
121 | 16021088200140482001069 | 3 | Keystone St | Cordova St | Amrad St | Asphalt | Yes | 2021-09-30 16:11 | [5 empty] | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-30 16:11 |  | yes | no | no
2296 | 16299078200385182003041 | 3 | Keystone St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 19:20 | 2021-06-03 14:28 | 2021-06-07 13:22 |  | 2021-07-15 13:29 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 19:20 |  | yes | no | no
2297 | 16299078200385182003041 | 3 | Keystone St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 19:20 | 2021-06-03 14:54 | 2021-06-07 13:38 |  | 2021-07-15 13:30 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 19:20 |  | yes | no | no
142 | 16021088208938582001404 | 3 | Keystone St | E Outer Dr | Cordova St | Asphalt | Yes | 2021-09-30 15:40 | [5 empty] | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-30 15:40 |  | yes | no | no
2252 | 16299078200304182002453 | 3 | Keystone St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-24 19:01 | 2021-06-03 15:15 | 2021-06-07 14:14 |  | 2021-07-15 13:33 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 19:01 |  | yes | no | no
2253 | 16299078200304182002453 | 3 | Keystone St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-24 19:00 | 2021-06-03 15:41 | 2021-06-07 14:24 |  | 2021-07-15 13:36 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 19:00 |  | yes | no | no
4915 | 16020078200403882003178 | 3 | Klinger St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 17:41 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:41 |  | no | yes | no
4916 | 16020078200403882003178 | 3 | Klinger St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 17:44 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:44 |  | no | yes | no
2156 | 16020078200195982001391 | 3 | Klinger St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-05-21 16:48 | 2021-06-01 13:14 | 2021-06-03 19:34 |  | 2021-06-06 15:38 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 16:48 |  | yes | no | no
2157 | 16020078200195982001391 | 3 | Klinger St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-05-21 16:48 | 2021-06-01 13:38 | 2021-06-03 19:35 |  | 2021-06-06 15:40 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 16:48 |  | yes | no | no
4971 | 16020078200139182000934 | 3 | Klinger St | E Remington St | E Winchester Ave | Asphalt | Yes Round 2 | 2021-09-08 16:53 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:53 |  | no | yes | no
4972 | 16020078200139182000934 | 3 | Klinger St | E Remington St | E Winchester Ave | Asphalt | Yes Round 2 | 2021-09-08 17:05 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:05 |  | no | yes | no
86 | 16020078200093450041487 | 3 | Klinger St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-21 12:39 | 2021-06-01 14:16 | 2021-06-03 20:05 |  | 2021-06-06 15:45 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 12:39 |  | yes | no | no
4919 | 16020078200317882002562 | 3 | Klinger St | Emery St | E Lantz St | Asphalt | Yes Round 2 | 2021-09-08 17:46 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:46 |  | no | yes | no
4920 | 16020078200317882002562 | 3 | Klinger St | Emery St | E Lantz St | Asphalt | Yes Round 2 | 2021-09-08 17:49 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:49 |  | no | yes | no
2298 | 16299018200388282003062 | 3 | Lamont St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 17:59 | 2021-06-03 13:05 | 2021-06-06 16:23 |  | 2021-07-15 13:24 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 17:59 |  | yes | no | no
2299 | 16299018200388282003062 | 3 | Lamont St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 18:00 | 2021-06-03 12:44 | 2021-06-06 16:23 |  | 2021-07-15 13:24 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 18:00 |  | yes | no | no
2198 | 16299018200247182001886 | 3 | Lamont St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 17:29 | 2021-06-02 18:15 | 2021-06-05 16:43 |  | 2021-07-15 12:19 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 17:29 |  | yes | no | no
2199 | 16299018200247182001886 | 3 | Lamont St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 17:29 | 2021-06-02 17:55 | 2021-06-05 16:12 |  | 2021-07-15 12:19 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 17:29 |  | yes | no | no
2254 | 16299018200306282002471 | 3 | Lamont St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-24 17:48 | 2021-06-03 12:21 | 2021-06-06 16:22 |  | 2021-07-15 13:20 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 17:48 |  | yes | no | no
2255 | 16299018200306282002471 | 3 | Lamont St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-24 17:47 | 2021-06-03 11:57 | 2021-06-05 18:44 |  | 2021-07-15 13:20 | 2021-06-05 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 17:47 |  | yes | no | no
152 | 16325028200240582002422 | 3 | Lappin St | Boulder St | Kelly Rd | Asphalt | Yes | 2021-06-01 15:12 | 2021-06-10 16:39 | 2021-06-11 20:53 |  | 2021-08-02 16:30 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 15:21 |  | yes | no | no
160 | 16325028200244082002430 | 3 | Lappin St | Crusade St | Rex St | Asphalt | Yes | 2021-06-01 13:58 | 2021-06-10 15:29 | 2021-06-11 22:39 |  | 2021-08-02 16:35 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes | Resolved | 2021-06-01 13:58 |  | yes | no | no
5291 | 15885098200254782002511 | 3 | Lappin St | Gratiot Ave | Monarch St | Asphalt | Yes Round 2 | 2021-09-08 14:23 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:23 |  | no | yes | no
5292 | 15885098200254782002511 | 3 | Lappin St | Gratiot Ave | Monarch St | Asphalt | Yes Round 2 | 2021-09-08 14:26 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:26 |  | no | yes | no
5293 | 15885098200254782002511 | 3 | Lappin St | Gratiot Ave | Monarch St | Asphalt | Yes Round 2 | 2021-09-08 14:28 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:28 |  | no | yes | no
2176 | 15885098200248682002465 | 3 | Lappin St | Queen St | Hayes St | Asphalt | Yes | 2021-05-25 17:52 | 2021-06-11 15:36 | 2021-06-15 16:54 |  | 2021-08-02 19:33 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 17:52 |  | yes | no | no
2177 | 15885098200248682002465 | 3 | Lappin St | Queen St | Hayes St | Asphalt | Yes | 2021-05-25 17:52 | 2021-06-11 15:13 | 2021-06-15 16:45 |  | 2021-08-02 19:32 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 17:52 |  | yes | no | no
154 | 16325028200242082002405 | 3 | Lappin St | Redmond St | Boulder St | Asphalt | Yes | 2021-06-01 14:44 | 2021-06-10 16:19 | 2021-06-11 21:30 |  | 2021-08-02 16:30 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 15:00 |  | yes | no | no
158 | 16325028200243082002420 | 3 | Lappin St | Rex St | Redmond St | Asphalt | Yes | 2021-06-01 14:11 | 2021-06-10 15:53 | 2021-06-11 22:09 |  | 2021-08-02 16:32 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 14:11 |  | yes | no | no
185 | 15885108200257082002561 | 3 | Lappin St | Schoenherr St | Mapleview St | Asphalt | Yes | 2021-05-17 14:20 | 2021-06-11 14:13 | 2021-06-15 14:13 |  | 2021-07-30 22:04 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 12:30 |  | yes | no | no
1431 | 17120038201126082011071 | 3 | Lawley St | Gallagher St | Klinger St | Asphalt | Yes | 2021-05-10 17:33 | 2021-05-19 15:14 | 2021-05-20 21:24 |  | 2021-06-01 14:57 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 17:50 |  | yes | no | no
4621 | 16325098200167282001657 | 3 | Liberal St | Boulder St | Cordell St | Asphalt | Yes Round 2 | 2021-09-08 13:14 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 13:14 |  | no | yes | no
4622 | 15886068208918982001750 | 3 | Liberal St | Gratiot Ave | Monarch St | Asphalt | Yes Round 2 | 2021-09-08 13:50 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:07 |  | no | yes | no
347 | 15884108200426882004219 | 3 | Linnhurst St | Reno St | Gratiot Ave | Asphalt | Yes | 2021-05-25 15:25 | 2021-06-16 20:51 | 2021-06-17 22:07 |  | 2021-07-30 17:37 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 15:25 |  | yes | no | no
1424 | 16321028201029682010286 | 3 | Luce St | Dean St | Sunset St | Asphalt | Yes | 2021-05-11 14:43 | 2021-05-18 19:49 | 2021-05-20 15:03 |  | 2021-06-04 15:27 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:46 |  | yes | no | no
1422 | 16321028201024882010231 | 3 | Luce St | Eureka St | Hasse St | Asphalt | Yes | 2021-05-11 14:47 | 2021-05-18 21:17 | 2021-05-20 15:46 |  | 2021-06-04 15:34 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:45 |  | yes | no | no
1421 | 16321028201021782010204 | 3 | Luce St | Fenelon St | Conley St | Asphalt | Yes | 2021-05-11 14:49 | 2021-05-19 17:36 | 2021-05-20 16:05 |  | 2021-06-04 15:36 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:45 |  | yes | no | no
1420 | 16321028201018482010173 | 3 | Luce St | Moenart St | Bloom St | Asphalt | Yes | 2021-05-11 14:58 | 2021-05-19 18:10 | 2021-05-20 18:46 |  | 2021-06-04 15:38 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:27 |  | yes | no | no
1423 | 16321028201027482010259 | 3 | Luce St | Shields St | Justine St | Asphalt | Yes | 2021-05-11 14:45 | 2021-05-18 20:34 | 2021-05-20 15:19 |  | 2021-06-04 15:32 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:46 |  | yes | no | no
1418 | 16321028201009982010080 | 3 | Luce St | Syracuse St | Mound Rd | Asphalt | Yes | 2021-05-11 15:25 | 2021-05-22 12:58 | 2021-05-25 21:47 |  | 2021-06-04 19:16 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 15:43 |  | yes | no | no
4983 | 17164048200831882007446 | 3 | Lumpkin St | Stender St | Minnesota St | Asphalt | Yes Round 2 | 2021-09-09 13:49 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 13:49 |  | no | yes | no
4984 | 17164048200831882007446 | 3 | Lumpkin St | Stender St | Minnesota St | Asphalt | Yes Round 2 | 2021-09-09 13:45 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 13:45 |  | no | yes | no
514 | 16297028200571382004959 | 3 | Mackay St | E Grixdale St | E Robinwood St | Asphalt | Yes | 2021-05-10 14:53 | 2021-05-25 13:58 | 2021-06-01 23:40 |  | 2021-06-10 19:37 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 14:53 |  | yes | no | no
4955 | 16020018200262582002061 | 3 | Mackay St | E Lantz St | E Outer Dr | Asphalt | Yes Round 2 | 2021-09-08 17:56 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:56 |  | no | yes | no
4956 | 16020018200262582002061 | 3 | Mackay St | E Lantz St | E Outer Dr | Asphalt | Yes Round 2 | 2021-09-08 17:59 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:59 |  | no | yes | no
180 | 15885088200266482002648 | 3 | Maddelein St | Crusade St | Rex St | Asphalt | Yes | 2021-06-01 13:43 | 2021-06-10 14:24 | 2021-06-15 19:18 |  | 2021-08-02 16:38 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 13:43 |  | yes | no | no
5294 | 15885088200279882002734 | 3 | Maddelein St | Gratiot Ave | Monarch St | Asphalt | Yes Round 2 | 2021-09-08 14:45 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:45 |  | no | yes | no
5295 | 15885088200279882002734 | 3 | Maddelein St | Gratiot Ave | Monarch St | Asphalt | Yes Round 2 | 2021-09-08 14:41 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:41 |  | no | yes | no
5296 | 15885088200279882002734 | 3 | Maddelein St | Gratiot Ave | Monarch St | Asphalt | Yes Round 2 | 2021-09-08 14:38 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:38 |  | no | yes | no
5599 | 15885088200273482002713 | 3 | Maddelein St | Monarch St | Queen St | Asphalt | Yes Round 3 | 2021-09-30 18:45 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-30 18:45 |  |  |  | Yes
2192 | 15885088200271382002685 | 3 | Maddelein St | Queen St | Hayes St | Asphalt | Yes | 2021-05-25 18:09 | 2021-06-11 15:58 | 2021-06-15 16:24 |  | 2021-08-02 19:37 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 18:09 |  | yes | no | no
2193 | 15885088200271382002685 | 3 | Maddelein St | Queen St | Hayes St | Asphalt | Yes | 2021-05-25 18:09 | 2021-06-11 16:29 | 2021-06-15 16:24 |  | 2021-08-02 19:37 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 18:09 |  | yes | no | no
2341 | 16297038200570782004955 | 3 | Maine St | E Grixdale St | E Robinwood St | Asphalt | Yes | 2021-05-10 15:04 | 2021-05-25 14:41 | 2021-06-02 13:27 |  | 2021-06-10 18:54 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 15:04 |  | yes | no | no
115 | 16326018200150782001495 | 3 | Manning St | Crusade St | Rex St | Asphalt | Yes | 2021-06-01 16:17 | 2021-06-10 18:30 | 2021-06-15 21:00 |  | 2021-08-02 18:52 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 16:37 |  | yes | no | no
113 | 16326018200149582001480 | 3 | Manning St | Rex St | Redmond St | Asphalt | Yes | 2021-06-01 15:42 | 2021-06-10 18:19 | 2021-06-16 13:23 |  | 2021-08-02 18:52 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 15:59 |  | yes | no | no
5003 | 16019088200413982003322 | 3 | Marx St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 18:45 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 18:45 |  | no | yes | no
5004 | 16019088200413982003322 | 3 | Marx St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 18:47 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 18:47 |  | no | yes | no
5530 | 16019088200681182005753 | 3 | Marx St | E Nevada St | E Grixdale Ave | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5531 | 16019088200681182005753 | 3 | Marx St | E Nevada St | E Grixdale Ave | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2332 | 16019088200499982004139 | 3 | Marx St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-10 11:37 | 2021-05-17 22:40 | 2021-05-18 20:30 |  | 2021-05-27 18:59 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 11:36 |  | yes | no | no
2333 | 16019088200499982004139 | 3 | Marx St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-10 11:56 | 2021-05-17 23:05 | 2021-05-18 20:10 |  | 2021-05-27 18:59 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 11:55 |  | yes | no | no
2274 | 16019088200332282002681 | 3 | Marx St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-10 12:24 | 2021-05-17 22:09 | 2021-05-18 17:37 |  | 2021-05-27 18:52 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 12:23 |  | yes | no | no
2275 | 16019088200332282002681 | 3 | Marx St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-10 12:24 | 2021-05-17 22:09 | 2021-05-18 17:12 |  | 2021-05-27 18:50 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 12:24 |  | yes | no | no
4642 | 16019088200729382006811 | 3 | Marx St | Minnesota St | E Nevada St | Asphalt | Yes Round 2 | 2021-09-09 13:39 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 13:39 |  | no | yes | no
96 | 15872088200114382001135 | 3 | Milbank St | Spencer St | Stotter St | Asphalt | Yes | 2021-05-12 15:43 | 2021-06-09 11:33 | 2021-06-09 16:17 |  | 2021-07-15 20:41 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:37 |  | yes | no | no
2314 | 16020048200406982003201 | 3 | Mitchell St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-21 14:01 | 2021-05-24 21:19 | 2021-06-03 16:17 |  | 2021-06-10 20:28 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 14:01 |  | yes | no | no
2315 | 16020048200406982003201 | 3 | Mitchell St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-21 14:01 | 2021-05-24 20:25 | 2021-06-03 16:07 |  | 2021-06-10 20:24 | 2021-06-03 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 14:01 |  | yes | no | no
2160 | 16020048200198382001406 | 3 | Mitchell St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-08-04 16:02 | 2021-08-26 17:29 | 2021-08-31 13:54 |  |  | 2021-08-31 04:00 | HMA | No | Coordinate with DTE GRP | No conflict |  | No | Yes |  | 2021-08-04 16:02 |  | yes | no | no
2161 | 16020048200198382001406 | 3 | Mitchell St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-08-04 16:01 | 2021-08-25 20:51 | 2021-08-31 13:45 |  |  | 2021-08-31 04:00 | HMA | No | Coordinate with DTE GRP | No conflict |  | No | Yes |  | 2021-08-04 16:01 |  | yes | no | no
4608 | 16020048200094950041491 | 3 | Mitchell St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 17:40 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:41 |  | no | yes | no
5522 | 16020048200320182002585 | 3 | Mitchell St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5523 | 16020048200320182002585 | 3 | Mitchell St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
4785 | 17157058201256682012154 | 3 | Moenart St | Carpenter St | Fredro St | Asphalt | Yes Round 2 | 2021-09-09 14:57 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:57 |  | no | yes | no
2294 | 16299098200383782003035 | 3 | Moenart St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 19:50 | 2021-06-03 18:31 | 2021-06-07 16:25 |  | 2021-07-15 13:52 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 19:50 |  | yes | no | no
2295 | 16299098200383782003035 | 3 | Moenart St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 19:50 | 2021-06-03 18:00 | 2021-06-07 15:48 |  | 2021-07-15 13:52 | 2021-06-07 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 19:50 |  | yes | no | no
386 | 16299098200448182003837 | 3 | Moenart St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-11 17:26 | 2021-06-03 18:58 | 2021-06-07 16:25 |  | 2021-07-15 14:00 | 2021-06-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 17:51 |  | yes | no | no
5520 | 16299098200303582002447 | 3 | Moenart St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5521 | 16299098200303582002447 | 3 | Moenart St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
1429 | 16306088201088982010184 | 3 | Moenart St | Rowley St & Lasky Park Entrance | Luce St | Asphalt | Yes | 2021-05-11 14:53 | 2021-05-19 19:27 | 2021-05-20 19:40 |  | 2021-06-04 19:17 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:41 |  | yes | no | no
4766 | 17157058201189382011665 | 3 | Moenart St | Sobieski St | Garvin St | Asphalt | Yes Round 2 | 2021-09-09 14:54 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:54 |  | no | yes | no
30 | 15887038200056282000473 | 3 | Mohican St | Bringard Dr | Edmore Dr | Asphalt | Yes | 2021-05-17 17:10 | 2021-06-15 14:03 | 2021-06-16 17:42 |  | 2021-07-31 17:54 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:59 |  | yes | no | no
8 | 15887038200035182000262 | 3 | Mohican St | Collingham Dr | Carlisle St | Asphalt | Yes | 2021-05-17 17:10 | 2021-06-15 13:33 | 2021-06-16 18:51 |  | 2021-07-31 17:51 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 13:59 |  | yes | no | no
2834 | 16305078201251182011733 | 3 | Moran St | Carpenter St | Halleck St | Asphalt | Yes | 2021-05-10 18:32 | 2021-05-19 11:37 | 2021-05-19 18:50 |  | 2021-06-01 17:41 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:42 |  | yes | no | no
2835 | 16305078201251182011733 | 3 | Moran St | Carpenter St | Halleck St | Asphalt | Yes | 2021-05-10 18:31 | 2021-05-20 11:31 | 2021-05-20 20:39 |  | 2021-06-01 17:09 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:42 |  | yes | no | no
2816 | 16305078201026882009516 | 3 | Moran St | E Davison St | Victoria St | Asphalt | Yes | 2021-05-10 17:57 | 2021-05-18 18:05 | 2021-05-19 17:52 |  | 2021-06-01 15:56 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:06 |  | yes | no | no
2817 | 16305078201026882009516 | 3 | Moran St | E Davison St | Victoria St | Asphalt | Yes | 2021-05-10 17:46 | 2021-05-18 17:58 | 2021-05-19 15:40 |  | 2021-06-01 15:53 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:06 |  | yes | no | no
2826 | 16305078201173382011029 | 3 | Moran St | Halleck St | Lawley St | Asphalt | Yes | 2021-05-10 18:24 | 2021-05-19 12:23 | 2021-05-19 19:15 |  | 2021-06-01 16:06 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:25 |  | yes | no | no
2827 | 16305078201173382011029 | 3 | Moran St | Halleck St | Lawley St | Asphalt | Yes | 2021-05-10 18:24 | 2021-05-19 12:47 | 2021-05-19 19:32 |  | 2021-06-01 16:04 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:25 |  | yes | no | no
2824 | 16305078201102982010268 | 3 | Moran St | Lawley St | E Davison St | Asphalt | Yes | 2021-05-10 18:18 | 2021-05-19 13:23 | 2021-05-19 19:57 |  | 2021-06-01 16:02 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:17 |  | yes | no | no
2825 | 16305078201102982010268 | 3 | Moran St | Lawley St | E Davison St | Asphalt | Yes | 2021-05-10 18:07 | 2021-05-19 14:01 | 2021-05-20 13:55 |  | 2021-06-01 16:00 | 2021-05-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:16 |  | yes | no | no
867 | 16305078200951682009046 | 3 | Moran St | Victoria St | E McNichols Rd | Asphalt | Yes | 2021-05-10 18:17 | 2021-05-18 17:28 | 2021-05-19 15:25 |  | 2021-06-01 15:51 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 18:07 |  | yes | no | no
2214 | 16020098200254882002001 | 3 | Norwood St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-21 17:15 | 2021-05-25 19:50 | 2021-06-04 14:32 |  | 2021-07-14 13:15 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 17:15 |  | yes | no | no
2215 | 16020098200254882002001 | 3 | Norwood St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-21 17:15 | 2021-05-25 20:04 | 2021-06-04 14:51 |  | 2021-07-14 13:15 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 17:15 |  | yes | no | no
4715 | 17105078200715782006776 | 3 | Norwood St | Minnesota St | Milo St | Asphalt | Yes Round 2 | 2021-09-09 14:42 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 14:42 |  | no | yes | no
2328 | 16295098200435082003481 | 3 | Omira St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-06 18:19 | [5 empty] | HMA | No |  |  | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
2329 | 16295098200435082003481 | 3 | Omira St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-06 18:19 | [5 empty] | HMA | No |  |  | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
5516 | 16295098200281982002250 | 3 | Omira St | E Lantz St | E State Fair St | Asphalt | Yes Round 3 | [6 empty] | HMA |  |  |  | Coordinate with DPW Residential Resurfacing | Yes | No | [5 empty] | Yes
5517 | 16295098200281982002250 | 3 | Omira St | E Lantz St | E State Fair St | Asphalt | Yes Round 3 | [6 empty] | HMA |  |  |  | Coordinate with DPW Residential Resurfacing | Yes | No | [5 empty] | Yes
2320 | 16019078200414982003336 | 3 | Orleans St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-07 17:46 | 2021-05-17 17:29 | 2021-05-18 14:02 |  | 2021-05-24 17:53 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:24 |  | yes | no | no
2321 | 16019078200414982003336 | 3 | Orleans St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-07 18:00 | 2021-05-17 18:06 | 2021-05-18 14:38 |  | 2021-05-24 17:55 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:23 |  | yes | no | no
2228 | 16019078200269882002126 | 3 | Orleans St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 18:55 | 2021-05-17 20:09 | 2021-05-18 16:30 |  | 2021-05-24 18:03 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:23 |  | yes | no | no
2229 | 16019078200269882002126 | 3 | Orleans St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 18:55 | 2021-05-17 21:56 | 2021-05-18 16:49 |  | 2021-05-24 18:06 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:22 |  | yes | no | no
2276 | 16019078200333682002698 | 3 | Orleans St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-07 18:23 | 2021-05-17 19:16 | 2021-05-18 14:46 |  | 2021-05-24 17:58 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 22:00 |  | yes | no | no
2277 | 16019078200333682002698 | 3 | Orleans St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-07 18:34 | 2021-05-17 19:53 | 2021-05-18 16:17 |  | 2021-05-24 18:01 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:23 |  | yes | no | no
325 | 16302028208944782002975 | 3 | Packard St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-12 15:13 | 2021-06-08 19:33 | 2021-06-09 22:22 |  | 2021-07-25 15:23 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 14:13 |  | yes | no | no
2174 | 16302028200228682001680 | 3 | Packard St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 15:19 | 2021-06-08 20:45 | 2021-06-10 12:30 |  |  | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 15:24 |  | yes | no | no
2175 | 16302028200228682001680 | 3 | Packard St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 15:20 | 2021-06-08 21:14 | 2021-06-10 12:51 |  |  | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 15:24 |  | yes | no | no
2238 | 16302028200297582002286 | 3 | Packard St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-12 15:15 | 2021-06-08 19:56 | 2021-06-09 22:22 |  | 2021-07-25 15:38 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 14:31 |  | yes | no | no
2239 | 16302028200297582002286 | 3 | Packard St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-12 15:17 | 2021-06-08 20:23 | 2021-06-09 22:53 |  | 2021-07-25 15:40 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 15:15 |  | yes | no | no
4589 | 47000448200486082004846 | 3 | Park Grove St | Reno St | Gratiot Ave | Asphalt | Yes Round 2 | 2021-09-08 15:04 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:04 |  | no | yes | no
4623 | 47000448200488482004860 | 3 | Park Grove St | Schoenherr St | Reno St | Asphalt | Yes Round 2 | 2021-09-08 15:20 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:21 |  | no | yes | no
148 | 15883108200221182001689 | 3 | Pelkey St | Pinewood St | Manning St | Asphalt | Yes | 2021-05-17 14:35 | 2021-06-11 12:53 | 2021-06-15 13:27 |  | 2021-07-30 21:23 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 12:44 |  | yes | no | no
118 | 15883108200148482001287 | 3 | Pelkey St | Tacoma St | E State Fair St | Asphalt | Yes | 2021-05-17 14:49 | 2021-06-11 12:03 | 2021-06-15 12:58 |  | 2021-07-30 21:30 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 19:44 |  | yes | no | no
1277 | 47058608201799582017915 | 3 | Peter Hunt St | May St | Robert St | Asphalt | Yes | 2021-06-02 12:43 | 2021-06-17 22:36 | 2021-06-22 17:51 |  | 2021-08-02 21:23 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 12:43 |  | yes | no | no
147 | 15886038200219982002177 | 3 | Pinewood St | Schoenherr St | Reno St | Asphalt | Yes | 2021-05-17 14:21 | 2021-06-11 13:25 | 2021-06-15 13:51 |  | 2021-07-30 22:02 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes | Resolved | 2021-05-20 12:36 |  | yes | no | no
4782 | 16313088201397882013607 | 3 | Prescott St | Prescott Ave & Ellery St | Buffalo St | Asphalt | Yes Round 2 | 2021-09-09 15:13 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 15:13 |  | no | yes | no
4937 | 15871028200455982004527 | 3 | Quinn St | Packard St | Van Dyke St | Asphalt | Yes Round 2 | 2021-09-08 15:56 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:56 |  | no | yes | no
4938 | 15871028200455982004527 | 3 | Quinn St | Packard St | Van Dyke St | Asphalt | Yes Round 2 | 2021-09-08 16:01 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 16:01 |  | no | yes | no
202 | 16025108200281682002622 | 3 | Redmond St | E 7 Mile Rd & Moross Rd | Maddelein St | Asphalt | Yes | 2021-06-01 14:16 | 2021-06-10 15:06 | 2021-06-15 17:33 |  | 2021-08-02 16:41 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 14:16 |  | yes | no | no
34 | 16025048200057882000480 | 3 | Regent Dr | Bringard Dr | Edmore Dr | Asphalt | Yes | 2021-05-19 13:31 | 2021-06-15 14:58 | 2021-06-17 15:41 |  | 2021-07-31 17:14 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 18:05 |  | yes | no | no
11 | 16025048200037582000280 | 3 | Regent Dr | Collingham Dr | Carlisle St | Asphalt | Yes | 2021-05-17 15:45 | 2021-06-15 15:33 | 2021-06-17 15:26 |  | 2021-07-31 18:05 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 15:55 |  | yes | no | no
91 | 16025048200121482001095 | 3 | Regent Dr | E State Fair St | Rossini Dr | Asphalt | Yes | 2021-05-17 17:10 | 2021-06-16 16:57 | 2021-06-17 16:25 |  | 2021-08-02 13:13 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 14:07 |  | yes | no | no
68 | 16025048200090782000778 | 3 | Regent Dr | Fairmount Dr | Eastburn St | Asphalt | Yes | 2021-05-19 13:31 | 2021-06-15 20:56 | 2021-06-17 16:03 |  | 2021-08-02 13:10 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 18:16 |  | yes | no | no
2155 | 16020088200194982001385 | 3 | Revere St | E Outer Dr | E Remington St | Asphalt | Yes | 2021-05-21 13:27 | 2021-06-01 17:01 | 2021-06-04 13:50 |  | 2021-06-06 15:21 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 13:27 |  | yes | no | no
2134 | 16020088200138582000930 | 3 | Revere St | E Remington St | E Winchester Ave | Asphalt | Yes | 2021-05-21 13:04 | 2021-06-01 16:04 | 2021-06-04 13:31 |  | 2021-06-06 15:19 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 13:10 |  | yes | no | no
2135 | 16020088200138582000930 | 3 | Revere St | E Remington St | E Winchester Ave | Asphalt | Yes | 2021-05-21 13:04 | 2021-06-01 15:38 | 2021-06-03 21:03 |  | 2021-06-06 14:38 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 13:09 |  | yes | no | no
85 | 16020088200093050041486 | 3 | Revere St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes | 2021-05-21 12:49 | 2021-06-01 15:08 | 2021-06-03 20:42 |  | 2021-06-06 14:38 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-21 12:49 |  | yes | no | no
204 | 16025098200283682002648 | 3 | Rex St | E 7 Mile Rd | Maddelein St | Asphalt | Yes | 2021-06-01 13:46 | 2021-06-10 14:45 | 2021-06-15 18:47 |  | 2021-08-02 16:39 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-01 13:46 |  | yes | no | no
2322 | 16019058200416882003349 | 3 | Riopelle St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-07 17:18 | 2021-05-17 14:24 | 2021-05-17 20:59 |  | 2021-05-27 16:05 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:24 |  | yes | no | no
2323 | 16019058200416882003349 | 3 | Riopelle St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-07 17:04 | 2021-05-17 14:06 | 2021-05-17 20:59 |  | 2021-05-27 16:02 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:24 |  | yes | no | no
5617 | 16019058200579882005047 | 3 | Riopelle St | E Grixdale Ave | E Robinwood St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2230 | 16019058200271182002140 | 3 | Riopelle St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 16:57 | 2021-05-17 13:40 | 2021-05-17 20:06 |  | 2021-05-27 15:59 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:22 |  | yes | no | no
2231 | 16019058200271182002140 | 3 | Riopelle St | E Lantz St | E State Fair St | Asphalt | Yes | 2021-05-07 16:49 | 2021-05-17 13:05 | 2021-05-17 17:56 |  | 2021-05-27 15:59 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:22 |  | yes | no | no
5023 | 16019058200684682005798 | 3 | Riopelle St | E Nevada St | E Grixdale Ave | Asphalt | Yes Round 2 | 2021-09-09 12:35 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 12:35 |  | no | yes | no
5024 | 16019058200684682005798 | 3 | Riopelle St | E Nevada St | E Grixdale Ave | Asphalt | Yes Round 2 | 2021-09-09 12:20 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 12:20 |  | no | yes | no
4999 | 16019058200150382001026 | 3 | Riopelle St | E Remington Ave | E Winchester Ave | Asphalt | Yes Round 2 | 2021-09-08 19:28 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:28 |  | no | yes | no
5000 | 16019058200150382001026 | 3 | Riopelle St | E Remington Ave | E Winchester Ave | Asphalt | Yes Round 2 | 2021-09-08 19:35 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:35 |  | no | yes | no
2334 | 16019058200504782004168 | 3 | Riopelle St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-07 17:38 | 2021-05-17 16:40 | 2021-05-18 13:32 |  | 2021-05-27 16:41 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:24 |  | yes | no | no
2335 | 16019058200504782004168 | 3 | Riopelle St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-07 17:35 | 2021-05-17 15:59 | 2021-05-18 13:10 |  | 2021-05-27 18:12 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:24 |  | yes | no | no
2182 | 16019058200214082001503 | 3 | Riopelle St | E State Fair St | E Remington Ave | Asphalt | Yes | 2021-05-07 16:26 | 2021-05-17 12:23 | 2021-05-17 18:50 |  | 2021-05-27 15:45 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:21 |  | yes | no | no
2183 | 16019058200214082001503 | 3 | Riopelle St | E State Fair St | E Remington Ave | Asphalt | Yes | 2021-05-07 16:26 | 2021-05-17 11:52 | 2021-05-17 18:23 |  | 2021-05-27 15:39 | 2021-05-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:21 |  | yes | no | no
4583 | 16019058200102663081442 | 3 | Riopelle St | E Winchester Ave | 8 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 19:34 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 19:34 |  | no | yes | no
2142 | 16023038208935782001156 | 3 | Rogge St | E Outer Dr | Milbank St | Asphalt | Yes | 2021-05-12 17:09 | 2021-06-08 15:08 | 2021-06-10 15:26 |  | 2021-07-15 18:40 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 16:37 |  | yes | no | no
2143 | 16023038208935782001156 | 3 | Rogge St | E Outer Dr | Milbank St | Asphalt | Yes | 2021-05-12 17:10 | 2021-06-08 15:08 | 2021-06-10 15:26 |  | 2021-07-15 18:40 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 16:38 |  | yes | no | no
2126 | 16023038200115682000709 | 3 | Rogge St | Milbank St | Savage St | Asphalt | Yes | 2021-05-12 17:23 | 2021-06-08 15:28 | 2021-06-10 16:05 |  | 2021-07-15 18:42 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 17:14 |  | yes | no | no
2127 | 16023038200115682000709 | 3 | Rogge St | Milbank St | Savage St | Asphalt | Yes | 2021-05-12 17:24 | 2021-06-08 15:58 | 2021-06-10 16:15 |  | 2021-07-15 18:44 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 17:15 |  | yes | no | no
61 | 16023038200070950041423 | 3 | Rogge St | Savage St | 8 Mile Rd | Asphalt | Yes | 2021-05-12 17:26 | 2021-06-08 16:30 | 2021-06-10 16:38 |  | 2021-07-15 18:50 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 17:40 |  | yes | no | no
146 | 15872058200202082001999 | 3 | Rolyat St | Kempa St | E Outer Dr | Asphalt | Yes | 2021-05-13 12:37 | 2021-06-09 14:59 | 2021-06-10 20:14 |  | 2021-07-25 16:52 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 16:57 |  | yes | no | no
78 | 15886108200110882001095 | 3 | Rossini Dr | Anvil St | Regent Dr | Asphalt | Yes | 2021-05-17 17:54 | 2021-06-16 17:42 | 2021-06-17 16:51 |  | 2021-08-02 13:19 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 14:36 |  | yes | no | no
71 | 47058568200099082001004 | 3 | Rossini Dr | Brock St | Hayes St | Asphalt | Yes | 2021-05-25 18:44 | 2021-06-10 21:47 | 2021-06-16 14:30 |  | 2021-08-02 14:48 | 2021-06-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 18:44 |  | yes | no | no
5508 | 47058568200100482001032 | 3 | Rossini Dr | Hayes St | Queen St | Asphalt | Yes Round 3 | 2021-09-30 18:24 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-30 18:25 |  |  |  | Yes
5509 | 47058568200100482001032 | 3 | Rossini Dr | Hayes St | Queen St | Asphalt | Yes Round 3 | 2021-09-30 18:31 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-30 18:31 |  |  |  | Yes
80 | 15886108200112182001108 | 3 | Rossini Dr | Hoyt St | Anvil St | Asphalt | Yes | 2021-05-17 17:54 | 2021-06-16 19:00 | 2021-06-17 18:17 |  | 2021-08-02 13:21 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 14:36 |  | yes | no | no
5611 | 47058568200094182000956 | 3 | Rossini Dr | Redmond St | Rex St | Asphalt | Yes Round 3 | 2021-09-30 17:51 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-30 17:51 |  |  |  | Yes
4977 | 15886108200109582001060 | 3 | Rossini Dr | Regent Dr | Gratiot Ave | Asphalt | Yes Round 2 | 2021-09-08 14:21 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:21 |  | no | yes | no
4978 | 15886108200109582001060 | 3 | Rossini Dr | Regent Dr | Gratiot Ave | Asphalt | Yes Round 2 | 2021-09-08 14:06 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:07 |  | no | yes | no
82 | 15886108200113882001121 | 3 | Rossini Dr | Reno St | Hoyt St | Asphalt | Yes | 2021-05-17 17:54 | 2021-06-16 19:46 | 2021-06-17 18:20 |  | 2021-08-02 13:22 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-20 14:36 |  | yes | no | no
59 | 47058568200090182000916 | 3 | Rossini Dr | Shakespeare St | Cordell St | Asphalt | Yes | 2021-06-01 19:45 | 2021-06-10 19:03 | 2021-06-11 19:47 |  | 2021-08-02 15:05 | 2021-06-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 17:43 |  | yes | no | no
58 | 16304038200081682089195 | 3 | Rowe St | Bringard Dr | Groesbeck Hwy & Collingham Dr | Asphalt | Yes | 2021-05-14 13:26 | 2021-06-10 20:56 | 2021-06-23 12:24 |  | 2021-07-31 14:52 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 12:01 |  | yes | no | no
280 | 16304038200333582002831 | 3 | Rowe St | E 7 Mile Rd | Lappin St | Asphalt | Yes | 2021-05-14 13:17 | 2021-06-11 14:03 | 2021-06-22 21:27 |  | 2021-07-30 19:45 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 13:03 |  | yes | no | no
84 | 16304038200111382000816 | 3 | Rowe St | Fairmount Dr | Bringard Dr | Asphalt | Yes | 2021-05-14 13:22 | 2021-06-11 12:45 | 2021-06-23 12:07 |  | 2021-07-31 14:21 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 11:56 |  | yes | no | no
220 | 16304038200283182002393 | 3 | Rowe St | Lappin St | Pinewood St | Asphalt | Yes | 2021-05-14 13:17 | 2021-06-11 13:15 | 2021-06-22 20:12 |  | 2021-07-30 19:47 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 13:19 |  | yes | no | no
5616 | 16303098200701782006470 | 3 | Runyon St | Clough St | Gietzen St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5626 | 16303098200842982007606 | 3 | Runyon St | E McNichols Rd | Sauer St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
337 | 16303098200398582003376 | 3 | Runyon St | Eastwood St | E 7 Mile Rd | Asphalt | Yes | 2021-05-13 15:38 | 2021-06-09 16:42 | 2021-06-17 20:54 |  | 2021-07-25 19:35 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 15:13 |  | yes | no | no
498 | 16303098200585482005255 | 3 | Runyon St | Greiner St | Park Grove St | Asphalt | Yes | 2021-05-13 19:34 | 2021-06-09 15:20 | 2021-06-17 19:59 |  | 2021-07-25 19:40 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 15:35 |  | yes | no | no
373 | 16303098200458582003985 | 3 | Runyon St | Linnhurst St | Eastwood St | Asphalt | Yes | 2021-05-13 15:17 | 2021-06-09 17:16 | 2021-06-17 20:54 |  | 2021-07-25 19:37 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 15:23 |  | yes | no | no
444 | 16303098200525582004585 | 3 | Runyon St | Park Grove St | Linnhurst St | Asphalt | Yes | 2021-05-13 19:34 | 2021-06-09 15:26 | 2021-06-17 20:00 |  | 2021-07-25 19:38 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 15:30 |  | yes | no | no
651 | 16303098200760682007017 | 3 | Runyon St | Sauer St | Clough St | Asphalt | Yes | 2021-05-13 19:35 | 2021-06-09 14:03 | 2021-06-17 18:53 |  | 2021-07-25 19:44 | 2021-06-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 15:51 |  | yes | no | no
4662 | 16296058200585982005113 | 3 | Russell St | E Grixdale Ave | E Robinwood St | Asphalt | Yes Round 2 | 2021-09-09 12:11 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 12:11 |  | no | yes | no
2150 | 16296048200153882001056 | 3 | Russell St | E Remington Ave | E Winchester Ave | Asphalt | Yes | 2021-05-07 13:02 | 2021-05-13 17:47 | 2021-05-14 16:27 |  | 2021-05-20 20:34 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:12 |  | yes | no | no
2151 | 16296048200153882001056 | 3 | Russell St | E Remington Ave | E Winchester Ave | Asphalt | Yes | 2021-05-07 13:02 | 2021-05-13 17:16 | 2021-05-14 15:48 |  | 2021-05-20 20:33 | 2021-05-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-07 18:12 |  | yes | no | no
2318 | 16296078200412682003293 | 3 | Saint Aubin St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-10 12:53 | 2021-05-18 11:59 | 2021-05-18 21:13 |  | 2021-05-27 21:19 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 12:53 |  | yes | no | no
2319 | 16296078200412682003293 | 3 | Saint Aubin St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-10 13:05 | 2021-05-18 12:55 | 2021-05-18 21:46 |  | 2021-05-27 21:18 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:04 |  | yes | no | no
2468 | 16296078200916682008323 | 3 | Saint Aubin St | E McNichols Rd | Stender St | Asphalt | Yes Round 2 | 2021-09-09 13:55 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 13:55 |  | no | yes | no
3929 | 16296078200916682008323 | 3 | Saint Aubin St | E McNichols Rd | Stender St | Asphalt | Yes Round 2 | 2021-09-09 13:52 | [5 empty] | HMA | No |  |  |  |  | Yes |  | 2021-09-09 13:52 |  | no | yes | no
5510 | 16296078200205882001462 | 3 | Saint Aubin St | E Outer Dr | E Remington St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5511 | 16296078200205882001462 | 3 | Saint Aubin St | E Outer Dr | E Remington St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
136 | 16296078200146282001178 | 3 | Saint Aubin St | E Remington St | Conant St & Pointer St | Asphalt | Yes | 2021-05-10 13:23 | 2021-05-18 14:29 | 2021-05-19 13:44 |  | 2021-05-27 19:57 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:22 |  | yes | no | no
2272 | 16296078200329382002666 | 3 | Saint Aubin St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-10 13:12 | 2021-05-18 13:24 | 2021-05-18 22:03 |  | 2021-05-27 21:15 | 2021-05-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:12 |  | yes | no | no
2273 | 16296078200329382002666 | 3 | Saint Aubin St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-10 13:18 | 2021-05-18 13:58 | 2021-05-19 13:14 |  | 2021-05-27 20:38 | 2021-05-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 13:18 |  | yes | no | no
4735 | 16296078200745182006689 | 3 | Saint Aubin St | Minnesota St | E Nevada St | Asphalt | Yes Round 2 | 2021-09-09 13:38 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-09 13:38 |  | no | yes | no
4907 | 15885028200399682003943 | 3 | Saratoga St | Reno St | Gratiot Ave | Asphalt | Yes Round 2 | 2021-09-08 14:56 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:56 |  | no | yes | no
4908 | 15885028200399682003943 | 3 | Saratoga St | Reno St | Gratiot Ave | Asphalt | Yes Round 2 | 2021-09-08 15:00 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 15:00 |  | no | yes | no
4575 | 15885028200402682003996 | 3 | Saratoga St | Schoenherr St | Reno St | Asphalt | Yes Round 2 | 2021-09-08 14:53 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:53 |  | no | yes | no
62 | 15872098200072382000709 | 3 | Savage St | Carrie St | Rogge St | Asphalt | Yes | 2021-05-12 17:33 | 2021-06-08 13:26 | 2021-06-10 18:11 |  | 2021-07-15 18:46 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 17:40 |  | yes | no | no
65 | 15872098200073782000736 | 3 | Savage St | Concord St | Helen St | Asphalt | Yes | 2021-05-12 17:34 | 2021-06-08 13:00 | 2021-06-10 17:40 |  | 2021-07-15 18:55 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 17:44 |  | yes | no | no
55 | 15872098200068382000674 | 3 | Savage St | Spencer St | Stotter St | Asphalt | Yes | 2021-05-12 16:04 | 2021-06-08 14:16 | 2021-06-09 15:29 |  | 2021-07-15 18:53 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:45 |  | yes | no | no
4370 | 16335038202097582019314 | 3 | Sherwood St | Strong St | Miller St | Asphalt | Yes | 2021-06-02 13:14 | 2021-06-17 13:28 | 2021-06-22 21:09 |  | 2021-08-06 13:26 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 13:14 |  | yes | no | no
4371 | 16335038202097582019314 | 3 | Sherwood St | Strong St | Miller St | Asphalt | Yes | 2021-06-02 13:06 | 2021-06-17 13:04 | 2021-06-22 21:01 |  | 2021-08-06 13:27 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 13:06 |  | yes | no | no
4372 | 16335038202097582019314 | 3 | Sherwood St | Strong St | Miller St | Asphalt | Yes | 2021-06-02 13:01 | 2021-06-17 12:44 | 2021-06-22 19:27 |  | 2021-08-06 13:28 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 13:01 |  | yes | no | no
4373 | 16335038202097582019314 | 3 | Sherwood St | Strong St | Miller St | Asphalt | Yes | 2021-06-02 12:59 | 2021-06-17 12:11 | 2021-06-22 19:14 |  | 2021-08-06 13:29 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 12:59 |  | yes | no | no
138 | 15872068200180482001789 | 3 | Sirron St | Kempa St | E Outer Dr | Asphalt | Yes | 2021-05-12 17:53 | 2021-06-09 16:34 | 2021-06-10 19:54 |  | 2021-07-25 16:48 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 16:57 |  | yes | no | no
139 | 15872068200182482001804 | 3 | Sirron St | Terrell St | Kempa St | Asphalt | Yes | 2021-05-12 17:52 | 2021-06-09 15:57 | 2021-06-10 19:36 |  | 2021-07-25 16:45 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 11:57 |  | yes | no | no
141 | 15872068200184082001824 | 3 | Sirron St | Van Dyke St | Terrell St | Asphalt | Yes | 2021-05-12 17:48 | 2021-06-09 15:34 | 2021-06-10 19:15 |  | 2021-07-25 16:42 | 2021-06-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 18:27 |  | yes | no | no
1437 | 16314088201199882011964 | 3 | Sobieski St | Conant St | Justine St | Asphalt | Yes | 2021-05-11 13:51 | 2021-05-24 12:22 | 2021-05-25 18:08 |  | 2021-06-04 13:53 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:33 |  | yes | no | no
2828 | 16314088201192982011893 | 3 | Sobieski St | Fenelon St | Moenart St | Asphalt | Yes | 2021-05-11 13:39 | 2021-05-20 14:58 | 2021-05-25 18:47 |  | 2021-06-04 13:59 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:55 |  | yes | no | no
2829 | 16314088201192982011893 | 3 | Sobieski St | Fenelon St | Moenart St | Asphalt | Yes | 2021-05-11 13:32 | 2021-05-20 16:46 | 2021-05-25 20:11 |  | 2021-06-04 14:00 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:55 |  | yes | no | no
1436 | 16314088201196482011929 | 3 | Sobieski St | Justine St | Fenelon St | Asphalt | Yes | 2021-05-11 14:29 | 2021-05-20 14:14 | 2021-05-25 18:14 |  | 2021-06-04 13:55 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 14:55 |  | yes | no | no
1433 | 17158058201136182010590 | 3 | Sparling St | Charles St & Sparling Ave | Rupert St | Asphalt | Yes | 2021-05-11 15:07 | 2021-05-19 20:29 | 2021-05-25 22:33 |  | 2021-06-04 19:17 | 2021-05-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 15:33 |  | yes | no | no
322 | 16302038200356182002968 | 3 | Spencer St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-12 15:31 | 2021-06-08 19:03 | 2021-06-09 18:54 |  | 2021-07-25 15:49 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 14:09 |  | yes | no | no
2172 | 16302038200227982001671 | 3 | Spencer St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 15:28 | 2021-06-08 18:36 | 2021-06-09 18:31 |  | 2021-07-25 15:45 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 14:04 |  | yes | no | no
2173 | 16302038200227982001671 | 3 | Spencer St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 15:25 | 2021-06-08 18:12 | 2021-06-09 17:35 |  | 2021-07-25 15:44 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 14:02 |  | yes | no | no
2138 | 16023058208935582001143 | 3 | Spencer St | E Outer Dr | Milbank St | Asphalt | Yes | 2021-05-12 15:45 | 2021-06-07 14:40 | 2021-06-08 18:21 |  | 2021-07-15 20:40 | 2021-06-08 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:33 |  | yes | no | no
2139 | 16023058208935582001143 | 3 | Spencer St | E Outer Dr | Milbank St | Asphalt | Yes | 2021-05-12 15:56 | 2021-06-07 15:02 | 2021-06-08 19:14 |  | 2021-07-15 20:40 | 2021-06-08 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:35 |  | yes | no | no
2122 | 16023058200114382000683 | 3 | Spencer St | Milbank St | Savage St | Asphalt | Yes | 2021-05-12 16:01 | 2021-06-07 15:22 | 2021-06-09 13:34 |  | 2021-07-15 19:57 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:37 |  | yes | no | no
2123 | 16023058200114382000683 | 3 | Spencer St | Milbank St | Savage St | Asphalt | Yes | 2021-05-12 16:01 | 2021-06-07 15:48 | 2021-06-09 13:34 |  | 2021-07-15 19:52 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:42 |  | yes | no | no
56 | 16023058200068350042146 | 3 | Spencer St | Savage St | 8 Mile Rd | Asphalt | Yes | 2021-05-12 16:06 | 2021-06-07 16:08 | 2021-06-09 13:49 |  | 2021-07-15 19:50 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:48 |  | yes | no | no
526 | 16316038200601882006005 | 3 | Stockton St | Norwood St | Wexford St | Asphalt | Yes | 2021-05-10 15:43 | 2021-05-25 19:03 | 2021-06-02 14:54 |  | 2021-06-10 14:25 | 2021-06-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-10 15:43 |  | yes | no | no
319 | 16023068200355382002961 | 3 | Stotter St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-11 18:31 | 2021-06-07 12:18 | 2021-06-09 19:42 |  | 2021-07-25 15:52 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:16 |  | yes | no | no
2168 | 16023068200226682001665 | 3 | Stotter St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 13:12 | 2021-06-07 13:46 | 2021-06-09 21:14 |  | 2021-07-25 16:37 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 12:07 |  | yes | no | no
2169 | 16023068200226682001665 | 3 | Stotter St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-12 13:15 | 2021-06-07 14:19 | 2021-06-09 21:27 |  | 2021-07-25 16:37 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:25 |  | yes | no | no
2136 | 47058768208936182001135 | 3 | Stotter St | E Outer Dr | Milbank St | Asphalt | Yes | 2021-05-12 13:25 | 2021-06-07 19:43 | 2021-06-09 17:10 |  | 2021-07-15 20:41 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 14:00 |  | yes | no | no
2137 | 47058768208936182001135 | 3 | Stotter St | E Outer Dr | Milbank St | Asphalt | Yes | 2021-05-12 13:25 | 2021-06-07 18:52 | 2021-06-09 16:42 |  | 2021-07-15 20:41 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:58 |  | yes | no | no
2232 | 16023068200296182002266 | 3 | Stotter St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-11 18:30 | 2021-06-07 12:42 | 2021-06-09 19:42 |  | 2021-07-25 15:54 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:19 |  | yes | no | no
2233 | 16023068200296182002266 | 3 | Stotter St | Emery St | E Lantz St | Asphalt | Yes | 2021-05-11 18:30 | 2021-06-07 13:18 | 2021-06-09 20:01 |  | 2021-07-25 16:34 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:21 |  | yes | no | no
2120 | 47058768200113582000674 | 3 | Stotter St | Milbank St | Savage St | Asphalt | Yes | 2021-05-12 13:25 | 2021-06-07 18:24 | 2021-06-09 15:57 |  | 2021-07-15 20:41 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:56 |  | yes | no | no
2121 | 47058768200113582000674 | 3 | Stotter St | Milbank St | Savage St | Asphalt | Yes | 2021-05-12 13:25 | 2021-06-07 18:03 | 2021-06-09 15:29 |  | 2021-07-15 20:45 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:54 |  | yes | no | no
53 | 47058768200067450041416 | 3 | Stotter St | Savage St | 8 Mile Rd | Asphalt | Yes | 2021-05-12 13:19 | 2021-06-07 17:42 | 2021-06-09 15:29 |  | 2021-07-15 20:45 | 2021-06-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-12 13:51 |  | yes | no | no
274 | 47058578200327482002791 | 3 | Strasburg St | E 7 Mile Rd | Lappin St | Asphalt | Yes | 2021-05-14 14:47 | 2021-06-14 13:03 | 2021-06-23 14:08 |  | 2021-07-30 19:56 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 20:33 |  | yes | no | no
2376 | 47058578208919782006778 | 3 | Strasburg St | E McNichols Rd | Sauer St | Asphalt | Yes | 2021-05-14 12:26 | 2021-06-12 14:19 | 2021-06-22 13:27 |  | 2021-07-30 15:29 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 14:14 |  | yes | no | no
525 | 47058578200639082005775 | 3 | Strasburg St | Gietzen St | Greiner St | Asphalt | Yes | 2021-05-14 14:16 | 2021-06-12 15:12 | 2021-06-22 13:38 |  | 2021-07-30 15:17 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 14:25 |  | yes | no | no
488 | 47058578200577582005168 | 3 | Strasburg St | Greiner St | Park Grove St | Asphalt | Yes | 2021-05-14 14:33 | 2021-06-12 15:48 | 2021-06-22 14:42 |  | 2021-07-30 15:18 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 13:48 |  | yes | no | no
215 | 47058578200279182002367 | 3 | Strasburg St | Lappin St | Pinewood St | Asphalt | Yes | 2021-05-14 13:01 | 2021-06-14 11:44 | 2021-06-22 21:51 |  | 2021-07-30 19:56 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 20:32 |  | yes | no | no
164 | 47058578200236782001793 | 3 | Strasburg St | Pinewood St | Manning St | Asphalt | Yes | 2021-05-14 14:47 | 2021-06-12 17:22 | 2021-06-22 22:25 |  | 2021-07-30 19:56 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 19:14 |  | yes | no | no
2302 | 16021058200396282003104 | 3 | Sunset St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 13:08 | 2021-06-02 15:17 | 2021-06-04 20:50 |  | 2021-07-14 16:18 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 13:08 |  | yes | no | no
2303 | 16021058200396282003104 | 3 | Sunset St | E 7 Mile Rd | Emery St | Asphalt | Yes | 2021-05-24 13:08 | 2021-06-02 14:47 | 2021-06-04 20:16 |  | 2021-07-14 14:19 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 13:08 |  | yes | no | no
2208 | 16021058200251282001942 | 3 | Sunset St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 12:51 | 2021-06-02 14:15 | 2021-06-04 19:11 |  | 2021-07-14 14:04 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 12:51 |  | yes | no | no
2209 | 16021058200251282001942 | 3 | Sunset St | E Lantz St | E Outer Dr | Asphalt | Yes | 2021-05-24 12:51 | 2021-06-02 13:54 | 2021-06-04 18:51 |  | 2021-07-14 14:03 | 2021-06-04 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-05-24 12:51 |  | yes | no | no
4598 | 16021058200465582003962 | 3 | Sunset St | E Robinwood St | E 7 Mile Rd | Asphalt | Yes Round 2 | 2021-09-08 17:11 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:11 |  | no | yes | no
5514 | 16021058200310482002512 | 3 | Sunset St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5515 | 16021058200310482002512 | 3 | Sunset St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
90 | 16022038200102182000704 | 3 | Syracuse St | Amrad St | Hamlet St | Asphalt | Yes | 2021-06-01 12:05 | 2021-06-07 11:36 | 2021-06-08 13:59 |  | 2021-07-15 16:24 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-06-01 12:05 |  | yes | no | no
450 | 16300048200507582004445 | 3 | Syracuse St | E Hildale St | E Robinwood St | Asphalt | Yes | 2021-05-11 17:29 | 2021-06-03 20:58 | 2021-06-07 19:59 |  | 2021-07-15 16:21 | 2021-06-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 18:32 |  | yes | no | no
2436 | 16307028200885882007939 | 3 | Syracuse St | E McNichols Rd | E Davison St | Asphalt | Yes | 2021-05-11 15:33 | 2021-05-24 13:47 | 2021-06-01 17:29 |  | 2021-06-04 21:01 | 2021-06-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:54 |  | yes | no | no
2437 | 16307028200885882007939 | 3 | Syracuse St | E McNichols Rd | E Davison St | Asphalt | Yes | 2021-05-11 15:36 | 2021-08-26 15:12 | 2021-08-31 16:05 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 16:55 |  | yes | no | no
1430 | 17157108201108382010823 | 3 | Syracuse St | Emeline St | Rowley St | Asphalt | Yes | 2021-05-11 15:29 | 2021-05-22 13:06 | 2021-05-25 20:47 |  | 2021-06-04 19:17 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 15:11 |  | yes | no | no
67 | 16022038200070450041447 | 3 | Syracuse St | Hamlet St | 8 Mile Rd | Asphalt | Yes | 2021-06-01 12:13 | 2021-06-07 11:10 | 2021-06-08 13:59 |  | 2021-07-15 14:47 | 2021-06-08 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-06-01 12:13 |  | yes | no | no
1419 | 17157108201009982009529 | 3 | Syracuse St | Luce St | Desner St | Asphalt | Yes | 2021-05-11 15:23 | 2021-05-22 14:30 | 2021-05-25 21:59 |  | 2021-06-04 19:16 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 15:43 |  | yes | no | no
1426 | 17157108201058382010350 | 3 | Syracuse St | Rupert St | Simon K St | Asphalt | Yes | 2021-05-11 15:27 | 2021-05-22 13:33 | 2021-05-25 21:09 |  | 2021-06-04 19:16 | 2021-05-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 15:11 |  | yes | no | no
501 | 16300048200567682005075 | 3 | Syracuse St | Stockton St | E Hildale St | Asphalt | Yes | 2021-05-11 17:31 | 2021-06-03 21:19 | 2021-06-07 20:22 |  | 2021-07-15 16:24 | 2021-06-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 18:32 |  | yes | no | no
119 | 15886088200150882001498 | 3 | Tacoma St | Alcoy St | Hickory St | Asphalt | Yes | 2021-05-17 13:28 | 2021-06-17 13:17 | 2021-06-24 13:23 |  | 2021-07-30 22:20 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 18:40 |  | yes | no | no
88 | 16326038200125782001249 | 3 | Tacoma St | Boulder St | Cordell St | Asphalt | Yes | 2021-06-01 17:17 | 2021-06-10 17:44 | 2021-06-17 23:18 |  | 2021-08-02 16:01 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 18:13 |  | yes | no | no
100 | 16338098208919282001321 | 3 | Tacoma St | Hayes St | Brock St | Asphalt | Yes | 2021-05-25 18:31 | 2021-06-11 14:45 | 2021-06-17 23:18 |  | 2021-08-02 19:26 | 2021-06-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-25 18:31 |  | yes | no | no
117 | 15886088200148482001469 | 3 | Tacoma St | Pelkey St | Schoenherr St | Asphalt | Yes | 2021-05-17 14:48 | 2021-06-11 12:26 | 2021-06-15 13:08 |  | 2021-07-30 21:28 | 2021-06-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 19:44 |  | yes | no | no
4633 | 15886088200146982001458 | 3 | Tacoma St | Schoenherr St | Reno St | Asphalt | Yes Round 2 | 2021-09-08 14:45 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 14:45 |  | no | yes | no
2848 | 16314018201369782013270 | 3 | Talbot St | Conant St | Fenelon St | Asphalt | Yes | 2021-05-11 12:55 | 2021-05-21 19:37 | 2021-05-24 20:10 |  | 2021-06-01 12:19 | 2021-05-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:18 |  | yes | no | no
2849 | 16314018201369782013270 | 3 | Talbot St | Conant St | Fenelon St | Asphalt | Yes | 2021-05-12 18:48 | 2021-05-21 18:53 | 2021-05-24 19:17 |  | 2021-06-01 21:37 | 2021-05-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:19 |  | yes | no | no
4276 | 16314018201327082012675 | 3 | Talbot St | Fenelon St | Buffalo St | Asphalt | Yes | 2021-05-12 18:47 | 2021-05-21 18:36 | 2021-05-24 18:31 |  | 2021-06-01 21:51 | 2021-05-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:19 |  | yes | no | no
4277 | 16314018201327082012675 | 3 | Talbot St | Fenelon St | Buffalo St | Asphalt | Yes | 2021-05-12 18:47 | 2021-05-21 18:30 | 2021-05-24 17:51 |  | 2021-06-01 21:51 | 2021-05-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:19 |  | yes | no | no
4278 | 16314018201327082012675 | 3 | Talbot St | Fenelon St | Buffalo St | Asphalt | Yes | 2021-05-11 12:54 | 2021-05-21 17:04 | 2021-05-24 16:42 |  | 2021-06-01 21:55 | 2021-05-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-11 13:19 |  | yes | no | no
596 | 16303078200703282006476 | 3 | Teppert St | Clough St | Gietzen St | Asphalt | Yes | 2021-05-13 17:17 | 2021-06-10 12:03 | 2021-06-21 17:20 |  | 2021-07-30 14:34 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 14:08 |  | yes | no | no
499 | 16303078200586882005263 | 3 | Teppert St | Greiner St | Park Grove St | Asphalt | Yes | 2021-05-13 17:17 | 2021-06-09 23:01 | 2021-06-21 15:46 |  | 2021-07-30 14:33 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 14:17 |  | yes | no | no
374 | 16303078200460482003997 | 3 | Teppert St | Linnhurst St | Eastwood St | Asphalt | Yes | 2021-05-13 19:06 | 2021-06-09 18:10 | 2021-06-21 15:24 |  | 2021-07-30 14:32 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 14:29 |  | yes | no | no
448 | 16303078200526382004604 | 3 | Teppert St | Park Grove St | Linnhurst St | Asphalt | Yes | 2021-05-13 19:06 | 2021-06-09 18:41 | 2021-06-21 15:24 |  | 2021-07-30 14:29 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 14:28 |  | yes | no | no
652 | 16303078200762282007032 | 3 | Teppert St | Sauer St | Clough St | Asphalt | Yes | 2021-05-13 17:17 | 2021-06-10 13:02 | 2021-06-21 17:52 |  | 2021-07-30 14:36 | 2021-06-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-14 13:48 |  | yes | no | no
3961 | 15867018201549482015424 | 3 | Traverse St | McClellan St | Raymond Ave | Asphalt | Yes | 2021-06-02 11:21 | 2021-06-17 19:57 | 2021-06-22 14:51 |  | 2021-08-02 20:46 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 11:40 |  | yes | no | no
3962 | 15867018201549482015424 | 3 | Traverse St | McClellan St | Raymond Ave | Asphalt | Yes | 2021-06-02 11:23 | 2021-06-17 20:36 | 2021-06-22 14:41 |  | 2021-08-02 20:46 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 11:40 |  | yes | no | no
3963 | 15867018201549482015424 | 3 | Traverse St | McClellan St | Raymond Ave | Asphalt | Yes | 2021-06-02 11:23 | 2021-06-17 20:55 | 2021-06-22 14:17 |  | 2021-08-02 20:46 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 11:40 |  | yes | no | no
45 | 16023195004140882000651 | 3 | Veach St | 8 Mile Rd | Savage St & Conner St | Asphalt | Yes | 2021-05-13 12:31 | 2021-06-09 17:07 | 2021-08-13 14:18 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 17:32 |  | yes | no | no
42 | 47109478200070782000449 | 3 | Westphalia St | Bringard Dr | Collingham Dr | Asphalt | Yes | 2021-05-14 13:48 | 2021-06-16 14:16 | 2021-06-23 16:08 |  | 2021-07-31 15:10 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 17:58 |  | yes | no | no
264 | 47109478200318582002716 | 3 | Westphalia St | E 7 Mile Rd | Lappin St | Asphalt | Yes | 2021-05-14 14:59 | 2021-06-15 20:41 | 2021-06-23 18:53 |  | 2021-07-30 20:44 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 19:13 |  | yes | no | no
77 | 47109478200102882000707 | 3 | Westphalia St | Fairmount Dr | Bringard Dr | Asphalt | Yes | 2021-05-14 13:49 | 2021-06-16 13:28 | 2021-06-23 16:26 |  | 2021-07-31 15:11 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-19 17:57 |  | yes | no | no
201 | 47109478200271682002299 | 3 | Westphalia St | Lappin St | Pinewood St | Asphalt | Yes | 2021-05-14 15:15 | 2021-06-15 21:07 | 2021-06-23 18:36 |  | 2021-07-30 20:46 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 18:58 |  | yes | no | no
130 | 47109478200174782001340 | 3 | Westphalia St | Manning St | E State Fair St | Asphalt | Yes | 2021-05-14 15:49 | 2021-06-16 12:28 | 2021-06-23 16:50 |  | 2021-07-30 20:53 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 18:57 |  | yes | no | no
155 | 47109478200229982001747 | 3 | Westphalia St | Pinewood St | Manning St | Asphalt | Yes | 2021-05-14 15:15 | 2021-06-16 11:59 | 2021-06-23 17:11 |  | 2021-07-30 20:48 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-17 18:57 |  | yes | no | no
3964 | 15866098201577282015696 | 3 | Woodlawn Ave | McClellan St | Raymond Ave | Asphalt | Yes | 2021-06-02 11:55 | 2021-06-17 21:42 | 2021-06-22 15:24 |  | 2021-08-02 20:47 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 11:55 |  | yes | no | no
3966 | 15866098201577282015696 | 3 | Woodlawn Ave | McClellan St | Raymond Ave | Asphalt | Yes | 2021-06-02 12:02 | 2021-06-17 21:19 | 2021-06-22 15:36 |  | 2021-08-02 20:51 | 2021-06-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-02 12:02 |  | yes | no | no
2186 | 15872028200243282002376 | 3 | Yolanda St | Kempa St | E Outer Dr | Asphalt | Yes | 2021-05-13 14:00 | 2021-06-09 13:37 | 2021-06-10 22:12 |  | 2021-07-25 17:19 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 16:04 |  | yes | no | no
2187 | 15872028200243282002376 | 3 | Yolanda St | Kempa St | E Outer Dr | Asphalt | Yes | 2021-05-13 14:00 | 2021-06-09 13:19 | 2021-06-10 21:55 |  | 2021-07-25 16:58 | 2021-06-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-05-13 16:41 |  | yes | no | no
4975 | 16298028200400882003152 | 3 | Yonka St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 17:31 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:31 |  | no | yes | no
4976 | 16298028200400882003152 | 3 | Yonka St | E 7 Mile Rd | Emery St | Asphalt | Yes Round 2 | 2021-09-08 17:33 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-08 17:33 |  | no | yes | no
5506 | 16298028200315282002544 | 3 | Yonka St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5507 | 16298028200315282002544 | 3 | Yonka St | Emery St | E Lantz St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
1028 | 16385078201257582011953 | 4 | 3 Mile Dr | E Outer Dr | Linville St | Asphalt | Yes | 2021-07-27 16:34 | 2021-08-04 13:31 | 2021-08-09 16:56 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:47 |  | yes | no | no
997 | 16385078201195382011488 | 4 | 3 Mile Dr | Linville St | Harper Ave | Asphalt | Yes | 2021-07-27 16:32 | 2021-08-04 13:11 | 2021-08-13 16:52 |  |  | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-07-29 15:49 |  | yes | no | no
5672 | 16385078201740782016817 | 4 | 3 Mile Dr | Windsor St | Bremen St | Asphalt | Yes Round 3 | 2021-10-05 15:01 | 2021-10-07 21:29 | 2021-10-11 20:42 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 15:01 |  |  |  | Yes
847 | 16339098200960282009289 | 4 | Algonac St | Kenmoor St | Kennebec St | Asphalt | Yes | 2021-09-10 12:50 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 12:49 |  | yes | no | no
891 | 16339098201012982009834 | 4 | Algonac St | Nashville St | Engleside St | Asphalt | Yes | 2021-09-10 12:35 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 12:34 |  | yes | no | no
1743 | 16347068203093982030340 | 4 | Algonquin | Avondale St | Essex Ave | Asphalt | Yes | 2021-07-23 15:22 | 2021-08-14 17:57 | 2021-08-17 15:55 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 15:20 |  | yes | no | no
4321 | 16347068203034082029308 | 4 | Algonquin | Essex Ave | Freud St | Asphalt | Yes | 2021-07-23 15:22 | 2021-08-14 17:26 | 2021-08-17 16:20 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 15:19 |  | yes | no | no
4323 | 16347068203034082029308 | 4 | Algonquin | Essex Ave | Freud St | Asphalt | Yes | 2021-07-23 15:22 | 2021-08-14 16:57 | 2021-08-17 16:25 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 15:02 |  | yes | no | no
4378 | 16347068202930882027852 | 4 | Algonquin | Freud St | E Jefferson Ave | Asphalt | Yes | 2021-07-23 15:21 | 2021-08-14 15:59 | 2021-08-17 16:38 |  |  | 2021-08-20 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 15:02 |  | yes | no | no
4379 | 16347068202930882027852 | 4 | Algonquin | Freud St | E Jefferson Ave | Asphalt | Yes | 2021-07-23 15:21 | 2021-08-14 15:34 | 2021-08-17 16:47 |  |  | 2021-08-20 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 14:39 |  | yes | no | no
4380 | 16347068202930882027852 | 4 | Algonquin | Freud St | E Jefferson Ave | Asphalt | Yes | 2021-07-23 14:14 | 2021-08-14 14:59 | 2021-08-17 17:06 |  |  | 2021-08-20 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 14:38 |  | yes | no | no
4381 | 16347068202930882027852 | 4 | Algonquin | Freud St | E Jefferson Ave | Asphalt | Yes | 2021-07-23 14:14 | 2021-08-14 14:18 | 2021-08-17 17:14 |  |  | 2021-08-20 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 14:19 |  | yes | no | no
638 | 16324048200764082007605 | 4 | Alma St | Queen St | Hayes St | Asphalt | Yes | 2021-07-27 18:50 | 2021-08-03 16:12 | 2021-08-13 20:36 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:26 |  | yes | no | no
4554 | 16350028202827082026107 | 4 | Ashland St | Jefferson | Essex Ave | Asphalt | Yes Round 2 | 2021-09-10 15:25 | 2021-10-02 19:35 | 2021-10-05 21:08 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:25 |  | no | yes | no
4555 | 16350028202827082026107 | 4 | Ashland St | Jefferson | Essex Ave | Asphalt | Yes Round 2 | 2021-09-10 15:23 | 2021-10-02 19:00 | 2021-10-05 21:06 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:23 |  | no | yes | no
4556 | 16350028202827082026107 | 4 | Ashland St | Jefferson | Essex Ave | Asphalt | Yes Round 2 | 2021-09-10 15:21 | 2021-10-02 18:31 | 2021-10-05 20:47 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:21 |  | no | yes | no
4557 | 16350028202827082026107 | 4 | Ashland St | Jefferson | Essex Ave | Asphalt | Yes Round 2 | 2021-09-10 15:19 | 2021-10-02 17:58 | 2021-10-05 20:36 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:19 |  | no | yes | no
5370 | 16350028202827082026107 | 4 | Ashland St | Jefferson | Essex Ave | Asphalt | Yes Round 2 | 2021-09-10 15:15 | 2021-10-02 16:38 | 2021-10-05 20:34 |  |  | 2021-10-09 04:00 | HMA |  |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-09-10 15:15 |  | no | Yes | no
4399 | 16394078201476682014059 | 4 | Audubon Rd | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-09-21 16:20 | 2021-09-29 21:33 | 2021-10-05 13:02 |  | 2021-10-11 16:44 | 2021-10-06 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 16:19 |  | yes | No | no
4406 | 16394078201829382017462 | 4 | Audubon Rd | Mack Ave | Rosewood St | Asphalt | Yes | 2021-08-04 11:41 | 2021-08-07 15:43 | 2021-08-11 13:32 |  | 2021-10-09 21:56 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 12:49 |  | yes | No | no
4409 | 16394078201829382017462 | 4 | Audubon Rd | Mack Ave | Rosewood St | Asphalt | Yes | 2021-08-04 11:39 | 2021-08-07 15:16 | 2021-08-11 13:37 |  | 2021-10-09 21:52 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 12:49 |  | yes | No | no
4404 | 16394078201746282016650 | 4 | Audubon Rd | Rosewood St | Wallingford St | Asphalt | Yes | 2021-08-04 11:42 | 2021-08-07 17:00 | 2021-08-11 13:32 |  | 2021-10-09 22:00 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 12:37 |  | yes | No | no
4405 | 16394078201746282016650 | 4 | Audubon Rd | Rosewood St | Wallingford St | Asphalt | Yes | 2021-08-04 11:44 | 2021-08-07 17:30 | 2021-08-10 21:46 |  | 2021-10-09 22:04 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 12:37 |  | yes | No | no
4402 | 16394078201665082015784 | 4 | Audubon Rd | Wallingford St | Waveney St | Asphalt | Yes | 2021-09-21 15:35 | 2021-09-29 19:39 | 2021-10-01 19:43 | 2021-10-01 19:43 | 2021-10-09 22:11 | 2021-10-02 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 15:35 |  | yes | No | no
4403 | 16394078201665082015784 | 4 | Audubon Rd | Wallingford St | Waveney St | Asphalt | Yes | 2021-09-21 15:24 | 2021-09-29 18:57 | 2021-10-05 13:13 |  | 2021-10-09 22:08 | 2021-10-06 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 15:24 |  | yes | No | no
4398 | 16394078201578482014766 | 4 | Audubon Rd | Waveney St | Cornwall St | Asphalt | Yes | 2021-09-21 16:09 | 2021-09-29 21:00 | 2021-10-01 19:25 | 2021-10-01 19:25 | 2021-10-09 22:21 | 2021-10-02 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 16:08 |  | yes | No | no
4401 | 16394078201578482014766 | 4 | Audubon Rd | Waveney St | Cornwall St | Asphalt | Yes | 2021-09-21 15:56 | 2021-09-29 20:35 | 2021-10-01 19:25 | 2021-10-01 19:26 | 2021-10-09 22:18 | 2021-10-02 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 15:55 |  | yes | No | no
4410 | 16394078201578482014766 | 4 | Audubon Rd | Waveney St | Cornwall St | Asphalt | Yes | 2021-09-21 15:47 | 2021-09-29 20:08 | 2021-10-01 19:26 | 2021-10-01 19:26 | 2021-10-09 22:15 | 2021-10-02 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 15:47 |  | yes | No | no
1710 | 17145078203003982029952 | 4 | Averhill Ct | Drexel St | New Town St | Asphalt | Yes | 2021-07-23 16:01 | 2021-08-14 18:40 | 2021-08-17 14:03 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 17:20 |  | yes | no | no
1706 | 17145078202980082029684 | 4 | Averhill Ct | Piper Blvd | Eastlawn St | Asphalt | Yes | 2021-07-23 16:01 | 2021-08-14 19:03 | 2021-08-17 14:03 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 17:20 |  | yes | no | no
989 | 47103968201174582011186 | 4 | Balfour Rd | Berkshire St | Haverhill St | Asphalt | Yes | 2021-07-27 15:12 | 2021-07-31 16:47 | 2021-08-04 17:56 |  | 2021-09-14 19:43 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 17:29 |  | yes | no | no
3832 | 16330058200632982005152 | 4 | Balfour Rd | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 17:16 | 2021-07-27 20:24 | 2021-08-04 14:49 |  | 2021-09-15 20:08 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:08 |  | yes | no | no
3833 | 16330058200632982005152 | 4 | Balfour Rd | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 17:15 | 2021-07-27 19:54 | 2021-08-04 14:49 |  | 2021-09-15 20:09 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:03 |  | yes | no | no
3834 | 16330058200632982005152 | 4 | Balfour Rd | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 17:15 | 2021-07-27 19:21 | 2021-08-04 13:07 |  | 2021-09-15 20:10 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:00 |  | yes | no | no
892 | 47103968201039282089014 | 4 | Balfour Rd | Courville St | Whittier St | Asphalt | Yes | 2021-07-27 15:12 | 2021-07-31 15:55 | 2021-08-04 16:11 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 17:25 |  | yes | no | no
1077 | 16394018201351482012895 | 4 | Balfour Rd | E Outer Dr | Linville St | Asphalt | Yes | 2021-07-27 17:34 | 2021-08-02 16:58 | 2021-08-07 13:51 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 18:21 |  | yes | no | no
5544 | 47103968201118682010392 | 4 | Balfour Rd | Haverhill St | Courville St | Asphalt | Yes Round 3 | 2021-10-05 17:37 | 2021-10-09 16:52 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:37 |  |  |  | Yes
5545 | 47103968201118682010392 | 4 | Balfour Rd | Haverhill St | Courville St | Asphalt | Yes Round 3 | 2021-10-05 17:39 | 2021-10-09 17:45 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:39 |  |  |  | Yes
556 | 16330058200692282006329 | 4 | Balfour Rd | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 17:16 | 2021-07-28 16:54 | 2021-08-04 15:09 |  |  | 2021-08-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:11 |  | yes | no | no
2460 | 16339078200982482009079 | 4 | Balfour Rd | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-27 13:37 | 2021-07-31 12:01 | 2021-08-04 15:51 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 17:17 |  | yes | no | no
2461 | 16339078200982482009079 | 4 | Balfour Rd | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-27 13:37 | 2021-07-31 12:15 | 2021-08-04 15:51 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 17:14 |  | yes | no | no
770 | 16339078200907982008550 | 4 | Balfour Rd | Yorkshire Rd | Grayton St | Asphalt | Yes | 2021-07-27 13:16 | 2021-07-31 12:45 | 2021-08-04 15:24 |  |  | 2021-08-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 17:10 |  | yes | no | no
4013 | 15780098201561282015335 | 4 | Barrett St | Evanston St | Camden Ave | Asphalt | Yes | 2021-09-09 16:37 | 2021-10-04 19:32 | 2021-10-09 14:04 |  |  | 2021-10-11 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 16:37 |  | yes | no | no
4316 | 15780098201504582014804 | 4 | Barrett St | Wade St | Maiden St | Asphalt | Yes | 2021-09-09 16:42 | 2021-10-04 20:25 | 2021-10-09 13:53 |  |  | 2021-10-11 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 16:42 |  | yes | no | no
969 | 47103998201133982010762 | 4 | Beaconsfield St | Berkshire St | Haverhill St | Asphalt | Yes | 2021-07-27 15:22 | 2021-07-31 17:24 | 2021-08-04 19:23 |  | 2021-09-14 19:36 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 18:12 |  | yes | no | no
862 | 47103998200999282009489 | 4 | Beaconsfield St | Courville St | Whittier St | Asphalt | Yes | 2021-07-27 15:22 | 2021-07-31 17:47 | 2021-08-04 19:12 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:49 |  | yes | no | no
4989 | 47103998201076282009992 | 4 | Beaconsfield St | Haverhill St | Courville St | Asphalt | Yes Round 2 | 2021-09-09 14:57 | 2021-09-30 21:29 | 2021-10-09 16:26 |  |  | 2021-10-11 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 14:57 |  | no | yes | no
4990 | 47103998201076282009992 | 4 | Beaconsfield St | Haverhill St | Courville St | Asphalt | Yes Round 2 | 2021-09-09 15:10 | 2021-10-09 19:25 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-09 15:10 |  | no | yes | no
1259 | 16351088201692882016317 | 4 | Bedford St | Bremen St | Waveney St | Asphalt | Yes | 2021-08-04 11:59 | 2021-08-09 14:25 | 2021-08-11 19:11 |  | 2021-10-11 14:19 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 13:46 |  | yes | no | no
1274 | 16351088201812582017541 | 4 | Bedford St | Brunswick St | Windsor St | Asphalt | Yes | 2021-08-04 11:55 | 2021-08-07 18:30 | 2021-08-11 14:05 |  | 2021-10-11 14:11 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 13:27 |  | yes | no | no
1181 | 16351088201518282014521 | 4 | Bedford St | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-09-21 16:58 | 2021-09-30 18:06 | 2021-10-05 13:42 |  | 2021-10-11 14:26 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 16:58 |  | yes | no | no
4774 | 16351088201269282012065 | 4 | Bedford St | E Outer Dr | Linville St | Asphalt | Yes Round 2 | 2021-09-10 13:59 | 2021-09-30 19:44 | 2021-10-05 15:06 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 13:59 |  | no | yes | no
1132 | 16351088201452182013861 | 4 | Bedford St | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-31 17:14 | 2021-08-04 18:27 | 2021-08-09 15:10 |  |  | 2021-08-10 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:12 |  | yes | no | no
4796 | 16351088201386182013300 | 4 | Bedford St | Frankfort St | Southampton St | Asphalt | Yes Round 2 | 2021-09-10 13:55 | 2021-09-30 18:56 | 2021-10-05 13:56 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 13:55 |  | no | yes | no
1002 | 16351088201206582011660 | 4 | Bedford St | Linville St | Harper Ave | Asphalt | Yes | 2021-07-27 16:51 | 2021-08-04 12:25 | 2021-08-09 13:28 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:01 |  | yes | no | no
1204 | 16351088201570282015182 | 4 | Bedford St | Munich St | Cornwall St | Asphalt | Yes | 2021-09-21 16:50 | 2021-09-30 16:53 | 2021-10-05 13:29 |  | 2021-10-11 14:23 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 16:50 |  | yes | no | no
1068 | 16351088201330082012839 | 4 | Bedford St | Southampton St | E Outer Dr | Asphalt | Yes | 2021-07-27 16:36 | 2021-08-03 21:01 | 2021-08-09 14:56 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:01 |  | yes | no | no
1234 | 16351088201631782015702 | 4 | Bedford St | Waveney St | Munich St | Asphalt | Yes | 2021-08-04 12:02 | 2021-08-10 19:45 | 2021-08-11 19:11 |  | 2021-10-11 14:21 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 13:55 |  | yes | no | no
5674 | 16351088201754182016928 | 4 | Bedford St | Windsor St | Bremen St | Asphalt | Yes Round 3 | 2021-10-05 14:57 | 2021-10-07 21:51 | 2021-10-11 20:57 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 14:58 |  |  |  | Yes
1178 | 16399038201508582014426 | 4 | Berkshire St | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-27 17:20 | 2021-08-03 15:01 | 2021-08-06 16:24 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:58 |  | yes | no | no
1129 | 16399038201442682013795 | 4 | Berkshire St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 17:22 | 2021-08-02 20:35 | 2021-08-06 16:33 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 17:01 |  | yes | no | no
5386 | 16344058202343082021701 | 4 | Bewick St | E Canfield St | E Warren Ave | Asphalt | Yes Round 3 | 2021-10-05 16:53 | 2021-10-11 14:02 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 16:52 |  |  |  | Yes
5387 | 16344058202343082021701 | 4 | Bewick St | E Canfield St | E Warren Ave | Asphalt | Yes Round 3 | 2021-10-05 16:52 | [5 empty] | HMA | [5 empty] | Yes | Car | 2021-10-05 16:52 |  |  |  | Yes
5388 | 16344058202343082021701 | 4 | Bewick St | E Canfield St | E Warren Ave | Asphalt | Yes Round 3 | 2021-10-05 16:52 | 2021-10-11 14:03 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 16:52 |  |  |  | Yes
5389 | 16344058202343082021701 | 4 | Bewick St | E Canfield St | E Warren Ave | Asphalt | Yes Round 3 | 2021-10-05 16:43 | [5 empty] | HMA | [5 empty] | Yes | Car | 2021-10-05 16:43 |  |  |  | Yes
895 | 16386018201048982009948 | 4 | Bishop St | Berden St | Harper Ave | Asphalt | Yes | 2021-07-27 15:27 | 2021-08-07 12:07 | 2021-08-13 13:09 |  | 2021-10-06 20:13 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:23 |  | yes | no | no
5647 | 16386018201164782011072 | 4 | Bishop St | Chandler Park Dr | Linville St | Asphalt | Yes Round 3 | 2021-10-05 14:54 | 2021-10-06 22:00 | 2021-10-11 20:07 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 14:54 |  |  |  | Yes
1101 | 16386018201401182013411 | 4 | Bishop St | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-07-31 18:55 | 2021-08-05 17:25 | 2021-08-11 15:52 |  | 2021-10-09 17:19 | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 16:48 |  | yes | no | no
5655 | 16386018201341182012785 | 4 | Bishop St | E Warren Ave | Frankfort St | Asphalt | Yes Round 3 | 2021-10-05 15:26 | 2021-10-07 16:25 | 2021-10-11 19:33 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 15:26 |  |  |  | Yes
788 | 17149058200932182008960 | 4 | Bishop St | King Richard St | McKinney Ave | Asphalt | Yes | 2021-07-27 14:53 | 2021-07-31 15:08 | 2021-08-06 12:31 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes | Resolved | 2021-07-28 11:33 |  | yes | no | no
2694 | 16386018201756082016799 | 4 | Bishop St | Mack Ave | Rosewood St | Asphalt | Yes | 2021-09-21 15:06 | 2021-09-28 19:53 | 2021-10-01 14:12 | 2021-10-01 15:51 | 2021-10-07 21:06 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 15:06 |  | yes | no | no
2695 | 16386018201756082016799 | 4 | Bishop St | Mack Ave | Rosewood St | Asphalt | Yes | 2021-09-21 14:53 | 2021-09-28 19:46 | 2021-10-01 14:12 | 2021-10-01 15:51 | 2021-10-09 17:34 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 14:53 |  | yes | no | no
2682 | 16386018201679982015900 | 4 | Bishop St | Rosewood St | Wallingford St | Asphalt | Yes | 2021-09-21 14:39 | 2021-09-28 19:09 | 2021-10-01 13:25 | 2021-10-01 15:52 | 2021-10-09 17:31 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 14:39 |  | yes | no | no
2683 | 16386018201679982015900 | 4 | Bishop St | Rosewood St | Wallingford St | Asphalt | Yes | 2021-09-21 14:30 | 2021-09-28 18:44 | 2021-10-01 13:24 | 2021-10-01 15:52 | 2021-10-09 17:30 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 14:29 |  | yes | no | no
4776 | 16386018201216182011765 | 4 | Bishop St | Southampton St | Chandler Park Dr | Asphalt | Yes Round 2 | 2021-09-10 12:51 | 2021-09-28 13:35 | 2021-09-29 18:21 |  | 2021-10-06 22:02 | 2021-09-30 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 12:51 |  | no | yes | no
819 | 17149058200970582009321 | 4 | Bishop St | W I 94 Service Drive | King Richard St | Asphalt | Yes | 2021-07-27 14:53 | 2021-07-31 13:39 | 2021-08-06 12:19 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:38 |  | yes | no | no
2670 | 16386018201590082015175 | 4 | Bishop St | Wallingford St | Waveney St | Asphalt | Yes | 2021-09-21 14:19 | 2021-09-28 18:21 | 2021-10-01 13:03 | 2021-10-01 15:52 | 2021-10-09 17:26 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 14:19 |  | yes | no | no
2671 | 16386018201590082015175 | 4 | Bishop St | Wallingford St | Waveney St | Asphalt | Yes | 2021-09-21 14:11 | 2021-09-28 17:52 | 2021-10-01 13:03 | 2021-10-01 15:52 | 2021-10-09 17:25 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 14:10 |  | yes | no | no
5715 | 16386018201517582014011 | 4 | Bishop St | Waveney St | Cornwall St | Asphalt | Yes Round 3 | 2021-10-05 15:44 | 2021-10-07 13:53 | 2021-10-11 17:10 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 15:44 |  |  |  | Yes
5716 | 16386018201517582014011 | 4 | Bishop St | Waveney St | Cornwall St | Asphalt | Yes Round 3 | 2021-10-05 15:42 | 2021-10-07 13:12 | 2021-10-11 17:22 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 15:42 |  |  |  | Yes
5717 | 16386018201517582014011 | 4 | Bishop St | Waveney St | Cornwall St | Asphalt | Yes Round 3 | 2021-10-05 15:41 | 2021-10-07 12:38 | 2021-10-11 17:34 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 15:41 |  |  |  | Yes
2452 | 16405018200985482009016 | 4 | Bluehill St | Berden St | Harper Ave | Asphalt | Yes | 2021-07-27 13:29 | 2021-08-11 13:19 | 2021-08-13 13:38 |  | 2021-10-06 18:36 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 13:28 |  | yes | no | no
2453 | 16405018200985482009016 | 4 | Bluehill St | Berden St | Harper Ave | Asphalt | Yes | 2021-07-27 13:31 | 2021-08-30 15:02 | 2021-09-01 13:35 |  | 2021-10-06 18:37 | 2021-09-02 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 13:28 |  | yes | no | no
928 | 16405018201099282010393 | 4 | Bluehill St | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-27 13:26 | 2021-08-11 13:46 | 2021-08-13 13:39 |  | 2021-10-06 18:31 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 13:22 |  | yes | no | no
884 | 16405018201039382009854 | 4 | Bluehill St | Linville St | Berden St | Asphalt | Yes | 2021-07-27 13:27 | 2021-08-30 11:51 | 2021-09-01 13:24 |  | 2021-10-06 18:35 | 2021-09-02 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 13:26 |  | yes | no | no
901 | 16338018201046482010213 | 4 | Bonita St | Wayburn St | Whitehill St | Asphalt | Yes | 2021-07-27 15:34 | 2021-07-31 20:01 | 2021-08-04 21:17 |  | 2021-09-14 19:25 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:08 |  | yes | no | no
751 | 47058548200873382008469 | 4 | Bradford St | Engleside St | Kenmoor St | Asphalt | Yes | 2021-07-23 14:14 | 2021-07-28 22:12 | 2021-08-04 16:54 |  | 2021-09-08 15:43 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:20 |  | yes | no | no
724 | 47058548200846982008174 | 4 | Bradford St | Kenmoor St | Kennebec St | Asphalt | Yes | 2021-07-23 14:13 | 2021-07-28 21:42 | 2021-08-04 15:33 |  | 2021-09-08 15:41 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:20 |  | yes | no | no
782 | 47058548200899482008733 | 4 | Bradford St | Nashville St | Engleside St | Asphalt | Yes | 2021-07-23 14:18 | 2021-07-30 15:21 | 2021-08-04 17:44 |  | 2021-09-08 16:14 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:20 |  | yes | no | no
1270 | 17143068201772182017610 | 4 | Bremen St | Balfour Rd | Chatsworth St | Asphalt | Yes | 2021-08-04 12:28 | 2021-08-09 16:46 | 2021-08-13 19:21 |  | 2021-10-11 16:20 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 14:30 |  | yes | no | no
1258 | 17143068201692882016817 | 4 | Bremen St | Bedford St | 3 Mile Dr | Asphalt | Yes | 2021-08-04 11:58 | 2021-08-07 18:57 | 2021-08-11 19:30 |  | 2021-10-11 14:18 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 14:09 |  | yes | no | no
1269 | 17143068201749582017366 | 4 | Bremen St | Berkshire St | Buckingham Ave | Asphalt | Yes | 2021-10-09 14:29 | 2021-10-09 15:16 | 2021-10-11 21:25 |  | 2021-10-11 11:16 |  | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-08-04 14:30 |  | yes | no | no
1266 | 17143068201721782017057 | 4 | Bremen St | Haverhill St | Devonshire Rd | Asphalt | Yes | 2021-08-04 12:22 | 2021-08-09 15:10 | 2021-08-11 19:39 |  | 2021-10-11 14:18 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 14:24 |  | yes | no | no
1273 | 17143068201801482017852 | 4 | Bremen St | Nottingham Rd | Somerset Ave | Asphalt | Yes | 2021-08-04 12:30 | 2021-08-10 18:03 | 2021-08-13 19:32 |  | 2021-10-11 16:22 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 14:30 |  | yes | no | no
681 | 17148038200827282007922 | 4 | Britain St | King Richard St | McKinney Ave | Asphalt | Yes | 2021-07-27 14:41 | 2021-07-31 14:05 | 2021-08-05 20:51 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:32 |  | yes | no | no
5383 | 16394048201736682016773 | 4 | Buckingham Ave | Bremen St | Waveney St | Asphalt | Yes | 2021-09-21 17:12 | 2021-09-30 14:17 | 2021-10-05 16:00 |  | 2021-10-11 16:11 | 2021-10-06 04:00 | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 17:12 |  | Yes | No | no
1058 | 16394048201311982012469 | 4 | Buckingham Ave | E Outer Dr | Linville St | Asphalt | Yes | 2021-07-27 17:13 | 2021-08-03 17:18 | 2021-08-06 15:20 |  |  | 2021-08-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:50 |  | yes | no | no
1171 | 16394048201495882014268 | 4 | Buckingham Ave | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-27 17:09 | 2021-08-03 15:39 | 2021-08-06 15:55 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:43 |  | yes | no | no
1029 | 16394048201246982012182 | 4 | Buckingham Ave | Linville St | Hern Ave | Asphalt | Yes | 2021-07-27 17:15 | 2021-08-03 17:59 | 2021-08-06 13:24 |  |  | 2021-08-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:53 |  | yes | no | no
1092 | 16394048201365982013256 | 4 | Buckingham Ave | Southampton St | E Outer Dr | Asphalt | Yes | 2021-07-27 17:11 | 2021-08-03 16:55 | 2021-08-06 15:31 |  |  | 2021-08-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:45 |  | yes | no | no
510 | 15884018200614782006206 | 4 | Cedargrove St | Brock St | Kelly Rd | Asphalt | Yes | 2021-07-27 18:50 | 2021-08-03 14:39 | 2021-08-16 13:41 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:37 |  | yes | no | no
509 | 15884018200617482006147 | 4 | Cedargrove St | Hayes St | Brock St | Asphalt | Yes | 2021-07-27 18:49 | 2021-08-03 15:08 | 2021-08-16 13:15 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:33 |  | yes | no | no
1211 | 16399028201576482015219 | 4 | Chatsworth St | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-08-04 13:09 | 2021-08-10 19:10 | 2021-08-13 19:05 |  | 2021-10-11 16:05 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 14:53 |  | yes | no | no
1186 | 16399028201521982014580 | 4 | Chatsworth St | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-27 17:26 | 2021-08-02 19:43 | 2021-08-06 16:41 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 17:37 |  | yes | no | no
1136 | 16399028201458082013925 | 4 | Chatsworth St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 17:24 | 2021-08-10 18:31 | 2021-08-13 18:54 |  |  | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-07-29 17:21 |  | yes | no | no
5666 | 16394028201936182018905 | 4 | Chatsworth St | Mack Ave | Brunswick St | Asphalt | Yes Round 3 | 2021-10-05 15:06 | 2021-10-09 15:51 | 2021-10-11 21:11 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 15:06 |  |  |  | Yes
1261 | 16399028201700482016371 | 4 | Chatsworth St | Waveney St | Munich St | Asphalt | Yes | 2021-08-04 13:06 | 2021-08-28 17:50 | 2021-09-01 14:58 |  | 2021-10-11 16:07 | 2021-09-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 14:52 |  | yes | no | no
1276 | 16394028201824282017610 | 4 | Chatsworth St | Windsor St | Bremen St | Asphalt | Yes | 2021-08-04 12:26 | 2021-08-09 17:11 | 2021-08-14 15:51 |  | 2021-10-11 16:14 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 14:10 |  | yes | no | no
4676 | 47054018200721782006690 | 4 | Chester St | Moross Rd | Chester Ave & Kingsville Ave | Asphalt | Yes Round 2 | 2021-09-09 18:56 | 2021-09-27 20:25 | 2021-09-29 15:41 |  |  | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 18:56 |  | no | yes | no
960 | 15914018201094582010661 | 4 | Christy St | Algonac St | Elmo St | Asphalt | Yes | 2021-07-23 15:04 | 2021-07-30 17:48 | 2021-08-05 15:48 |  | 2021-09-10 13:24 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 13:43 |  | yes | no | no
973 | 15914018201115882010945 | 4 | Christy St | Conner St | Algonac St | Asphalt | Yes | 2021-07-23 15:01 | 2021-07-30 17:21 | 2021-08-05 16:12 |  | 2021-09-10 13:17 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 13:20 |  | yes | no | no
916 | 15914038201040982010153 | 4 | College St | Algonac St | Elmo St | Asphalt | Yes | 2021-08-04 14:37 | [5 empty] | HMA | No | Coordinate with DTE GRP |  | Coordinate with DPW Residential Resurfacing | Yes | No |  | 2021-08-05 14:27 |  | yes | no | no
2464 | 15914038200973982009295 | 4 | College St | Gunston St | Bradford St | Asphalt | Yes | 2021-08-04 14:46 | 2021-08-17 14:32 | 2021-08-19 16:04 |  | 2021-09-10 13:08 | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 15:45 |  | yes | no | no
2465 | 15914038200973982009295 | 4 | College St | Gunston St | Bradford St | Asphalt | Yes | 2021-08-04 14:47 | 2021-08-17 14:06 | 2021-08-19 15:44 |  | 2021-09-10 13:07 | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 15:45 |  | yes | no | no
4861 | 16397098202251882022143 | 4 | Cooper St | E Warren Ave | Murray St | Asphalt | Yes Round 2 | 2021-09-10 15:04 | 2021-10-04 16:24 | 2021-10-09 13:02 |  |  | 2021-10-11 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:04 |  | no | yes | no
4771 | 47110198201539782014812 | 4 | Coplin St | Linville St | Hern St | Asphalt | Yes Round 2 | 2021-09-10 15:33 | 2021-10-05 17:54 | 2021-10-06 18:50 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:33 |  | no | yes | no
2613 | 16323058201370482013395 | 4 | Corbett Ave | Annsbury Ave | Park Dr | Asphalt | Yes | 2021-10-05 16:59 | 2021-10-11 19:14 |  |  |  |  | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-10-05 16:59 |  | yes | no | no
4991 | 16323058201447582014088 | 4 | Corbett Ave | Barrett St | Roseberry St | Asphalt | Yes Round 2 | 2021-09-09 16:50 | 2021-10-04 21:02 | 2021-10-06 21:19 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 16:50 |  | no | yes | no
4992 | 16323058201447582014088 | 4 | Corbett Ave | Barrett St | Roseberry St | Asphalt | Yes Round 2 | 2021-09-09 17:02 | 2021-10-04 21:45 | 2021-10-06 21:33 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 17:02 |  | no | yes | no
1096 | 17143098201385982013690 | 4 | Cornwall St | Grayton St | Harvard Rd | Asphalt | Yes | 2021-09-10 13:47 | 2021-09-28 17:16 | 2021-09-29 16:28 | 2021-09-29 16:28 | 2021-10-07 19:55 | 2021-09-29 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 13:47 |  | yes | no | no
1118 | 17143098201432682014161 | 4 | Cornwall St | Kensington Ave | Yorkshire Rd | Asphalt | Yes | 2021-07-31 18:54 | 2021-08-05 17:01 | 2021-08-10 13:37 |  | 2021-10-09 18:10 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:39 |  | yes | no | no
1160 | 16385088201491682014214 | 4 | Courville St | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-07-31 17:09 | 2021-08-04 18:01 | 2021-08-11 15:34 |  | 2021-10-11 13:52 | 2021-08-16 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:35 |  | yes | no | no
1014 | 16385088201241082011825 | 4 | Courville St | E Outer Dr | Linville St | Asphalt | Yes | 2021-07-27 16:27 | 2021-08-04 15:16 | 2021-08-09 15:55 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:41 |  | yes | no | no
1116 | 16385088201421482013584 | 4 | Courville St | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-31 17:05 | 2021-08-04 16:04 | 2021-08-09 15:29 |  |  | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:09 |  | yes | no | no
1085 | 16385088201358482013019 | 4 | Courville St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 16:19 | 2021-08-04 15:41 | 2021-08-09 15:48 |  |  | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:43 |  | yes | no | no
991 | 16385088201182582011276 | 4 | Courville St | Linville St | Harper Ave | Asphalt | Yes | 2021-07-27 16:30 | 2021-08-04 14:49 | 2021-08-09 16:08 |  |  | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:47 |  | yes | no | no
1278 | 16385088201846082017796 | 4 | Courville St | Mack Ave | Brunswick St | Asphalt | Yes | 2021-08-04 11:47 | 2021-08-07 17:51 | 2021-08-11 13:50 |  | 2021-10-11 14:01 | 2021-08-16 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 13:17 |  | yes | no | no
5657 | 16385088201301982012586 | 4 | Courville St | Southampton St | E Outer Dr | Asphalt | Yes Round 3 | 2021-10-05 17:02 | 2021-10-09 12:44 | 2021-10-11 20:25 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:02 |  |  |  | Yes
4825 | 16394068201828582017655 | 4 | Devonshire Rd | Brunswick St | Windsor St | Asphalt | Yes Round 2 | 2021-09-10 14:45 | 2021-09-30 12:53 | 2021-10-05 15:27 |  | 2021-10-11 18:13 | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:45 |  | no | yes | no
1035 | 16394068201283682012194 | 4 | Devonshire Rd | E Outer Dr | Linville St | Asphalt | Yes | 2021-07-27 16:53 | 2021-08-04 14:12 | 2021-08-09 13:14 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:04 |  | yes | no | no
1009 | 16394068201219482011831 | 4 | Devonshire Rd | Linville St | Harper Ave | Asphalt | Yes | 2021-07-27 16:55 | 2021-08-04 11:37 | 2021-08-09 13:14 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:04 |  | yes | no | no
1719 | 17145098203036482030039 | 4 | Drexel St | Avondale St | Averhill Ct | Asphalt | Yes | 2021-10-05 17:51 | [5 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 17:51 |  | yes | no | no
4850 | 16348048201605982015505 | 4 | Drexel St | Chandler Park Dr | Linville St | Asphalt | Yes Round 2 | 2021-09-10 15:37 | 2021-10-05 16:27 | 2021-10-06 18:02 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:37 |  | no | yes | no
1268 | 16348048201735982016720 | 4 | Drexel St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-28 17:15 | 2021-08-05 17:32 | 2021-08-13 18:49 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:46 |  | yes | no | no
1745 | 17145098203101282030364 | 4 | Drexel St | Korte St & Riverside Dr | Avondale St | Asphalt | Yes | 2021-10-05 17:51 | [5 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 17:51 |  | yes | no | no
3805 | 47104788200479782003503 | 4 | Duchess St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:11 | 2021-07-29 15:09 | 2021-08-02 18:35 |  | 2021-09-15 18:48 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:59 |  | yes | no | no
3806 | 47104788200479782003503 | 4 | Duchess St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:11 | 2021-07-28 20:55 | 2021-08-02 18:36 |  | 2021-09-15 18:49 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:55 |  | yes | no | no
3807 | 47104788200479782003503 | 4 | Duchess St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:11 | 2021-07-28 20:48 | 2021-08-02 18:44 |  | 2021-09-15 18:51 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:50 |  | yes | no | no
430 | 47104788200538082004797 | 4 | Duchess St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 18:10 | 2021-07-29 15:48 | 2021-08-02 18:35 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 14:00 |  | yes | no | no
674 | 16339048200823682007723 | 4 | Duprey St | Cadieux Rd | Morang Dr | Asphalt | Yes | 2021-07-27 14:29 | 2021-07-31 14:29 | 2021-08-05 20:37 |  |  | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:30 |  | yes | no | no
3847 | 16329108200705882005830 | 4 | Duprey St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:18 | 2021-07-28 13:02 | 2021-08-05 18:27 |  | 2021-09-15 21:18 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:29 |  | yes | no | no
3848 | 16329108200705882005830 | 4 | Duprey St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:36 | 2021-07-28 12:34 | 2021-08-05 18:40 |  |  | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:28 |  | yes | no | no
3849 | 16329108200705882005830 | 4 | Duprey St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:36 | 2021-07-28 12:34 | 2021-08-05 18:52 |  | 2021-09-15 21:20 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:25 |  | yes | no | no
632 | 16329108200765582007058 | 4 | Duprey St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 15:18 | 2021-07-28 14:09 | 2021-08-05 18:19 |  |  | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:33 |  | yes | no | no
4803 | 16348108201511182014471 | 4 | Eastlawn St | Linville St | Hern St | Asphalt | Yes Round 2 | 2021-09-10 15:27 | 2021-10-05 18:50 | 2021-10-06 19:47 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:27 |  | no | yes | no
266 | 15885058200333482003296 | 4 | Eastwood St | Brock St | Morang Dr | Asphalt | Yes | 2021-07-27 17:35 | 2021-07-30 11:56 | 2021-07-31 19:38 |  | 2021-09-15 16:41 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:50 |  | yes | no | no
265 | 47058338208901782003297 | 4 | Eastwood St | Morang Dr | Rex St | Asphalt | Yes | 2021-07-27 17:35 | 2021-07-30 12:56 | 2021-08-02 15:24 |  |  | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:43 |  | yes | no | no
256 | 47058338200327982003260 | 4 | Eastwood St | Redmond St | Kelly Rd | Asphalt | Yes | 2021-07-27 17:34 | 2021-07-29 19:16 | 2021-08-02 12:18 |  | 2021-09-15 16:45 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:30 |  | yes | no | no
261 | 47058338200329782003279 | 4 | Eastwood St | Rex St | Redmond St | Asphalt | Yes | 2021-07-27 17:35 | 2021-07-29 19:59 | 2021-08-02 12:14 |  | 2021-09-15 16:44 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:36 |  | yes | no | no
2642 | 16323068201413682013756 | 4 | Elmdale St | Barrett St | Roseberry St | Asphalt | Yes | 2021-08-05 16:24 | 2021-08-17 17:37 | 2021-08-19 19:42 |  | 2021-09-10 20:13 | 2021-08-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-05 16:24 |  | yes | no | no
2643 | 16323068201413682013756 | 4 | Elmdale St | Barrett St | Roseberry St | Asphalt | Yes | 2021-08-05 16:25 | 2021-08-17 18:07 | 2021-08-21 13:48 |  | 2021-09-10 20:13 | 2021-08-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-05 16:25 |  | yes | no | no
954 | 16339108201092782010661 | 4 | Elmo St | Findlay St | Christy St | Asphalt | Yes | 2021-07-23 15:06 | 2021-07-30 16:48 | 2021-08-04 22:06 |  | 2021-09-10 13:30 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 13:44 |  | yes | no | no
814 | 16339108200926682009001 | 4 | Elmo St | Kenmoor St | Kennebec St | Asphalt | Yes | 2021-09-10 12:59 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 12:59 |  | yes | no | no
913 | 16339108201042782010153 | 4 | Elmo St | Minden St | College St | Asphalt | Yes | 2021-09-09 18:29 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-09 18:29 |  | yes | no | no
870 | 16339108200984082009584 | 4 | Elmo St | Nashville St | Engleside St | Asphalt | Yes | 2021-09-09 18:45 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-09 18:45 |  | yes | no | no
871 | 15914058200983482009584 | 4 | Engleside St | Algonac St | Elmo St | Asphalt | Yes | 2021-08-04 14:53 | 2021-08-17 12:20 | 2021-08-19 18:22 |  | 2021-09-10 12:52 | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 12:50 |  | yes | no | no
750 | 15914058200873382008487 | 4 | Engleside St | Bradford St | Dresden St | Asphalt | Yes | 2021-07-23 14:16 | 2021-07-30 15:02 | 2021-08-04 17:12 |  | 2021-09-09 18:19 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:34 |  | yes | no | no
894 | 15914058201011682009834 | 4 | Engleside St | Conner St | Algonac St | Asphalt | Yes | 2021-08-04 14:55 | 2021-08-17 11:59 | 2021-08-19 18:22 |  | 2021-09-10 12:52 | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 13:37 |  | yes | no | no
2456 | 15914058200958482009104 | 4 | Engleside St | Elmo St | Gunston St | Asphalt | Yes | 2021-08-04 14:51 | 2021-08-17 15:29 | 2021-08-19 17:55 |  | 2021-09-10 12:50 | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 11:40 |  | yes | no | no
2457 | 15914058200958482009104 | 4 | Engleside St | Elmo St | Gunston St | Asphalt | Yes | 2021-08-04 14:50 | 2021-08-17 12:55 | 2021-08-19 17:45 |  | 2021-09-10 12:49 | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 11:40 |  | yes | no | no
2438 | 15914058200910482008733 | 4 | Engleside St | Gunston St | Bradford St | Asphalt | Yes | 2021-07-23 14:24 | 2021-07-30 15:55 | 2021-08-04 18:19 |  | 2021-09-09 18:22 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:50 |  | yes | no | no
2439 | 15914058200910482008733 | 4 | Engleside St | Gunston St | Bradford St | Asphalt | Yes | 2021-07-23 14:22 | 2021-07-30 16:15 | 2021-08-04 18:06 |  | 2021-09-09 18:21 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:50 |  | yes | no | no
2659 | 16323018201499682014725 | 4 | Evanston St | Annsbury Ave | Park Dr | Asphalt | Yes | 2021-07-31 16:47 | 2021-08-04 13:53 | 2021-08-11 16:18 |  | 2021-09-10 21:01 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:02 |  | yes | no | no
1001 | 16323018201198982011905 | 4 | Evanston St | Balfour Rd | Berkshire St | Asphalt | Yes | 2021-07-28 16:39 | 2021-08-02 15:36 | 2021-08-06 13:10 |  | 2021-09-14 17:34 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 17:47 |  | yes | no | no
2650 | 16323018201436482013989 | 4 | Evanston St | Dickerson St | Coplin St | Asphalt | Yes | 2021-07-31 16:48 | 2021-08-04 14:52 | 2021-08-13 15:14 |  | 2021-09-14 15:43 | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:09 |  | yes | no | no
2651 | 16323018201436482013989 | 4 | Evanston St | Dickerson St | Coplin St | Asphalt | Yes | 2021-07-31 16:54 | 2021-08-04 15:16 | 2021-08-13 15:37 |  | 2021-09-14 15:42 | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:14 |  | yes | no | no
1052 | 16323018201287182012698 | 4 | Evanston St | E Outer Dr | Wayburn St | Asphalt | Yes | 2021-07-28 16:46 | 2021-08-02 14:22 | 2021-08-16 12:51 |  | 2021-09-14 17:08 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 17:58 |  | yes | no | no
1026 | 16323018201236882012248 | 4 | Evanston St | Greensboro St | Beaconsfield St | Asphalt | Yes | 2021-07-28 16:41 | 2021-08-02 15:07 | 2021-08-14 17:21 |  | 2021-09-14 17:31 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 17:45 |  | yes | no | no
2678 | 16323018201592782015612 | 4 | Evanston St | Gunston Ave | Barrett St | Asphalt | Yes | 2021-07-31 16:34 | 2021-08-03 21:05 | 2021-08-09 20:33 |  | 2021-09-14 14:00 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 13:41 |  | yes | no | no
2679 | 16323018201592782015612 | 4 | Evanston St | Gunston Ave | Barrett St | Asphalt | Yes | 2021-07-31 16:34 | 2021-08-03 20:45 | 2021-08-11 15:23 |  | 2021-09-14 13:59 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 13:51 |  | yes | no | no
2610 | 16323018201365582013376 | 4 | Evanston St | Newport St | Chalmers St | Asphalt | Yes | 2021-07-31 16:54 | 2021-08-05 13:12 | 2021-08-11 17:38 |  | 2021-09-14 15:36 | 2021-08-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:17 |  | yes | no | no
2611 | 16323018201365582013376 | 4 | Evanston St | Newport St | Chalmers St | Asphalt | Yes | 2021-07-31 16:54 | 2021-08-05 13:31 | 2021-08-11 17:55 |  | 2021-09-14 15:36 | 2021-08-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:23 |  | yes | no | no
2666 | 16323018201540282014996 | 4 | Evanston St | Norcross St | Annsbury Ave | Asphalt | Yes | 2021-07-31 16:40 | 2021-08-04 12:40 | 2021-08-11 16:03 |  | 2021-09-10 20:58 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 13:54 |  | yes | no | no
2667 | 16323018201540282014996 | 4 | Evanston St | Norcross St | Annsbury Ave | Asphalt | Yes | 2021-07-31 16:41 | 2021-08-04 13:20 | 2021-08-11 16:03 |  | 2021-09-10 20:59 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 13:57 |  | yes | no | no
1159 | 16323018201472582014364 | 4 | Evanston St | Park Dr | Dickerson St | Asphalt | Yes | 2021-07-31 16:48 | 2021-08-04 14:22 | 2021-08-11 16:42 |  | 2021-09-10 21:11 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:07 |  | yes | no | no
1036 | 16323018201269882012532 | 4 | Evanston St | Wayburn St | Lakepointe St | Asphalt | Yes | 2021-07-28 16:43 | 2021-08-02 14:53 | 2021-08-14 17:36 |  | 2021-09-14 17:10 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 17:44 |  | yes | no | no
324 | 47000468200390282003823 | 4 | Faircrest St | Morang Dr | Rex St | Asphalt | Yes | 2021-07-27 18:48 | 2021-07-29 17:34 | 2021-08-02 13:15 |  | 2021-09-15 17:06 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:04 |  | yes | no | no
313 | 47000468200382382003793 | 4 | Faircrest St | Rex St | Redmond St | Asphalt | Yes | 2021-07-27 18:48 | 2021-07-29 17:45 | 2021-08-02 14:51 |  | 2021-09-15 17:04 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:00 |  | yes | no | no
4374 | 47110918202390282022247 | 4 | Fairview St | Mack Ave | E Canfield St | Asphalt | Yes | 2021-08-04 14:14 | 2021-08-05 20:04 | 2021-08-16 20:29 |  |  | 2021-08-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 17:01 |  | yes | no | no
4375 | 47110918202390282022247 | 4 | Fairview St | Mack Ave | E Canfield St | Asphalt | Yes | 2021-08-04 14:13 | 2021-08-05 20:43 | 2021-08-16 19:26 |  |  | 2021-08-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 17:01 |  | yes | no | no
4376 | 47110918202390282022247 | 4 | Fairview St | Mack Ave | E Canfield St | Asphalt | Yes | 2021-08-04 14:11 | 2021-08-05 21:10 | 2021-08-16 18:47 |  |  | 2021-08-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 17:04 |  | yes | no | no
4377 | 47110918202390282022247 | 4 | Fairview St | Mack Ave | E Canfield St | Asphalt | Yes | 2021-08-04 14:10 | 2021-08-05 21:40 | 2021-08-16 18:14 |  |  | 2021-08-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 17:04 |  | yes | no | no
825 | 16386068200986182009245 | 4 | Farmbrook St | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-10-06 13:38 | 2021-10-07 17:57 | 2021-10-09 16:46 |  |  |  | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-06 13:38 |  | yes | no | no
972 | 16386068201152382010938 | 4 | Farmbrook St | E Warren Ave | Frankfort St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | No |  |  |  | yes | no | no
771 | 16386068200924582008666 | 4 | Farmbrook St | Linville St | Berden St | Asphalt | Yes | 2021-10-06 13:51 | 2021-10-07 18:27 | 2021-10-09 16:57 |  |  |  | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-06 13:51 |  | yes | no | no
4829 | 17133058201939782019193 | 4 | Felch St | McClellan St | Cooper St | Asphalt | Yes Round 2 | 2021-09-10 14:32 | 2021-10-04 21:47 | 2021-10-09 13:16 |  |  | 2021-10-11 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:33 |  | no | yes | no
2528 | 15913108201190682011508 | 4 | Flanders St | Elmo St | Gunston St | Asphalt | Yes | 2021-07-23 15:09 | 2021-07-30 18:55 | 2021-08-05 17:09 |  | 2021-09-10 13:38 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 14:08 |  | yes | no | no
2529 | 15913108201190682011508 | 4 | Flanders St | Elmo St | Gunston St | Asphalt | Yes | 2021-07-23 15:11 | 2021-07-30 19:20 | 2021-08-05 16:46 |  | 2021-09-10 13:39 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 14:08 |  | yes | no | no
239 | 15885078200310082003082 | 4 | Fordham St | Brock St | Morang Dr | Asphalt | Yes | 2021-07-27 17:20 | 2021-07-30 12:55 | 2021-07-31 19:07 |  | 2021-09-15 15:19 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 13:06 |  | yes | no | no
263 | 15885078200325082003218 | 4 | Fordham St | Chalmers St | Celestine St | Asphalt | Yes | 2021-07-28 18:13 | 2021-08-03 13:29 | 2021-08-16 17:17 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 18:56 |  | yes | no | no
245 | 15885078200313082003100 | 4 | Fordham St | Hayes St | Brock St | Asphalt | Yes | 2021-07-27 17:20 | 2021-07-30 12:09 | 2021-07-31 19:19 |  | 2021-09-15 15:17 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:56 |  | yes | no | no
2222 | 15885078200308282003052 | 4 | Fordham St | Morang Dr | Rex St | Asphalt | Yes | 2021-07-27 17:19 | 2021-07-29 22:15 | 2021-07-31 19:07 |  | 2021-09-15 15:21 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 13:21 |  | yes | no | no
2223 | 15885078200308282003052 | 4 | Fordham St | Morang Dr | Rex St | Asphalt | Yes | 2021-07-27 17:19 | 2021-07-29 21:33 | 2021-07-31 18:42 |  | 2021-09-15 15:33 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 13:25 |  | yes | no | no
226 | 15885078200303082003005 | 4 | Fordham St | Redmond St | Moross Rd | Asphalt | Yes | 2021-07-27 17:19 | 2021-07-29 20:36 | 2021-07-31 18:06 |  | 2021-09-15 15:38 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 13:56 |  | yes | no | no
232 | 15885078200305282003030 | 4 | Fordham St | Rex St | Redmond St | Asphalt | Yes | 2021-07-27 17:19 | 2021-07-29 21:08 | 2021-07-31 18:29 |  | 2021-09-15 15:36 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 13:54 |  | yes | no | no
1413 | 15782068200966282009338 | 4 | Frankfort Ave | Gateshead St | Lannoo St | Asphalt | Yes | 2021-07-27 12:07 | 2021-08-13 18:28 | 2021-08-17 12:53 |  | 2021-10-06 13:48 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 16:01 |  | yes | no | no
1408 | 15782068200903882008750 | 4 | Frankfort Ave | Hillcrest St | Moross Rd | Asphalt | Yes | 2021-07-27 12:05 | 2021-08-13 19:17 | 2021-08-17 12:53 |  | 2021-10-06 13:37 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 16:13 |  | yes | no | no
856 | 15782068201013182009850 | 4 | Frankfort Ave | Lafontaine St | Ashley Ave | Asphalt | Yes | 2021-07-27 12:12 | 2021-08-13 17:02 | 2021-08-16 19:55 |  | 2021-10-06 13:57 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 16:09 |  | yes | no | no
2454 | 16396058200999382009662 | 4 | Gateshead St | Gateshead Dr & Mack Ave | Frankfort Ave | Asphalt | Yes | 2021-07-27 12:10 | 2021-08-13 17:53 | 2021-08-16 20:17 |  | 2021-10-06 13:53 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 16:07 |  | yes | no | no
2455 | 16396058200999382009662 | 4 | Gateshead St | Gateshead Dr & Mack Ave | Frankfort Ave | Asphalt | Yes | 2021-07-27 12:09 | 2021-08-13 17:25 | 2021-08-17 12:24 |  | 2021-10-06 13:50 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 16:06 |  | yes | no | no
2443 | 15880108200940382009020 | 4 | Glenfield Ave | Newport St | Chalmers St | Asphalt | Yes | 2021-07-23 16:11 | 2021-08-02 12:00 | 2021-08-06 14:03 |  | 2021-09-14 14:24 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 15:01 |  | yes | no | no
1280 | 16347108201901582018380 | 4 | Gray St | E Forest Ave | E Warren Ave | Asphalt | Yes | 2021-07-28 17:11 | 2021-08-05 18:45 | 2021-08-13 19:19 |  |  | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:52 |  | yes | no | no
885 | 16394088201037582009767 | 4 | Grayton St | Berden St | Harper Ave | Asphalt | Yes | 2021-07-27 14:13 | 2021-08-06 18:32 | 2021-08-13 12:28 |  | 2021-10-06 20:03 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:11 |  | yes | no | no
971 | 16394088201152182010920 | 4 | Grayton St | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-27 14:57 | 2021-08-07 11:32 | 2021-08-13 12:59 |  | 2021-10-06 20:07 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:21 |  | yes | no | no
5649 | 16394088201263682012023 | 4 | Grayton St | Frankfort St | Southampton St | Asphalt | Yes Round 3 | 2021-10-05 15:25 | 2021-10-07 19:49 | 2021-10-11 19:50 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 15:25 |  |  |  | Yes
933 | 16394088201092082010375 | 4 | Grayton St | Linville St | Berden St | Asphalt | Yes | 2021-07-27 14:55 | 2021-08-06 19:10 | 2021-08-13 12:43 |  | 2021-10-06 20:04 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:24 |  | yes | no | no
4767 | 16394088201202382011633 | 4 | Grayton St | Southampton St | Chandler Park Dr | Asphalt | Yes Round 2 | 2021-09-10 12:47 | 2021-09-28 12:51 | 2021-09-29 18:33 |  | 2021-10-06 22:06 | 2021-09-30 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 12:47 |  | no | yes | no
966 | 17148098201123182010631 | 4 | Greensboro St | Berkshire St | Haverhill St | Asphalt | Yes | 2021-07-27 15:22 | 2021-07-31 17:45 | 2021-08-04 20:44 |  | 2021-09-14 19:33 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:53 |  | yes | no | no
850 | 17148098200985582009317 | 4 | Greensboro St | Courville St | Whittier St | Asphalt | Yes | 2021-07-27 15:22 | 2021-07-31 18:17 | 2021-08-04 20:55 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:58 |  | yes | no | no
820 | 47054058200976682009150 | 4 | Guilford St | Berden St | Minerva St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
918 | 47054058201085282010294 | 4 | Guilford St | Chandler Park Dr | Linville St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
1056 | 16394108201313682012531 | 4 | Guilford St | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-10-05 14:18 | 2021-10-07 20:33 | 2021-10-11 16:49 |  |  |  | HMA | No | Coordinate with DTE GRP | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 14:18 |  | yes | no | no
2470 | 16352108201025082009542 | 4 | Harvard Rd | Berden St | Harper Ave | Asphalt | Yes | 2021-07-27 13:56 | 2021-08-06 17:23 | 2021-08-11 18:12 |  | 2021-10-06 19:56 | 2021-08-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:08 |  | yes | no | no
2471 | 16352108201025082009542 | 4 | Harvard Rd | Berden St | Harper Ave | Asphalt | Yes | 2021-07-27 14:08 | 2021-08-06 18:03 | 2021-08-13 12:14 |  | 2021-10-06 19:57 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:11 |  | yes | no | no
961 | 16352108201136882010751 | 4 | Harvard Rd | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-27 13:51 | 2021-08-06 15:13 | 2021-08-11 16:39 |  | 2021-10-06 19:50 | 2021-08-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:16 |  | yes | no | no
1088 | 16352108201369082013098 | 4 | Harvard Rd | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-07-31 17:24 | 2021-08-06 13:07 | 2021-08-10 21:18 |  | 2021-10-07 20:00 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 16:00 |  | yes | no | no
1053 | 16352108201309882012456 | 4 | Harvard Rd | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-31 17:24 | 2021-08-06 14:02 | 2021-08-11 16:15 |  | 2021-10-06 22:14 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 16:20 |  | yes | no | no
1020 | 16352108201245682011883 | 4 | Harvard Rd | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 13:48 | 2021-08-06 14:28 | 2021-08-11 16:15 |  | 2021-10-06 22:12 | 2021-08-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:30 |  | yes | no | no
702 | 17149078200854082008203 | 4 | Harvard Rd | King Richard St | McKinney Ave | Asphalt | Yes | 2021-07-27 14:40 | 2021-07-31 15:23 | 2021-08-05 21:05 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:35 |  | yes | no | no
919 | 16352108201075182010250 | 4 | Harvard Rd | Linville St | Berden St | Asphalt | Yes | 2021-07-27 13:55 | 2021-08-06 15:38 | 2021-08-11 17:46 |  | 2021-10-06 19:53 | 2021-08-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:04 |  | yes | no | no
2688 | 16352108201722882016455 | 4 | Harvard Rd | Mack Ave | Rosewood St | Asphalt | Yes | 2021-07-31 17:48 | 2021-08-05 18:45 | 2021-08-10 17:38 |  | 2021-10-07 21:01 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:17 |  | yes | no | no
2689 | 16352108201722882016455 | 4 | Harvard Rd | Mack Ave | Rosewood St | Asphalt | Yes | 2021-07-31 17:48 | 2021-08-05 18:45 | 2021-08-10 17:52 |  | 2021-10-07 20:59 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:15 |  | yes | no | no
2680 | 16352108201645582015627 | 4 | Harvard Rd | Rosewood St | Wallingford St | Asphalt | Yes | 2021-07-31 17:48 | 2021-08-05 19:53 | 2021-08-10 19:52 |  | 2021-10-07 20:52 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:22 |  | yes | no | no
2681 | 16352108201645582015627 | 4 | Harvard Rd | Rosewood St | Wallingford St | Asphalt | Yes | 2021-07-31 17:33 | 2021-08-05 19:53 | 2021-08-10 19:52 |  | 2021-10-07 20:49 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:27 |  | yes | no | no
992 | 16352108201188382011484 | 4 | Harvard Rd | Southampton St | Chandler Park Dr | Asphalt | Yes | 2021-07-27 13:50 | 2021-08-06 14:50 | 2021-08-11 16:30 |  | 2021-10-06 22:09 | 2021-08-12 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:35 |  | yes | no | no
2418 | 17149078200907682008540 | 4 | Harvard Rd | W I 94 Service Drive | King Richard St | Asphalt | Yes | 2021-07-27 14:40 | 2021-07-31 14:28 | 2021-08-06 12:05 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:40 |  | yes | no | no
2419 | 17149078200907682008540 | 4 | Harvard Rd | W I 94 Service Drive | King Richard St | Asphalt | Yes | 2021-07-27 14:40 | 2021-07-31 14:06 | 2021-08-06 11:43 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:38 |  | yes | no | no
2668 | 16352108201562782014874 | 4 | Harvard Rd | Wallingford St | Waveney St | Asphalt | Yes | 2021-07-31 17:33 | 2021-08-06 11:44 | 2021-08-10 19:59 |  | 2021-10-07 17:23 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:34 |  | yes | no | no
2669 | 16352108201562782014874 | 4 | Harvard Rd | Wallingford St | Waveney St | Asphalt | Yes | 2021-07-31 17:32 | 2021-08-05 20:20 | 2021-08-10 20:11 |  | 2021-10-07 17:24 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:37 |  | yes | no | no
3949 | 16352108201487482013690 | 4 | Harvard Rd | Waveney St | Cornwall St | Asphalt | Yes | 2021-07-31 17:25 | 2021-08-07 14:39 | 2021-08-10 20:59 |  | 2021-10-07 19:23 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:45 |  | yes | no | no
3950 | 16352108201487482013690 | 4 | Harvard Rd | Waveney St | Cornwall St | Asphalt | Yes | 2021-07-31 17:25 | 2021-08-06 12:19 | 2021-08-10 20:59 |  | 2021-10-07 19:52 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:50 |  | yes | no | no
3951 | 16352108201487482013690 | 4 | Harvard Rd | Waveney St | Cornwall St | Asphalt | Yes | 2021-07-31 17:25 | 2021-08-06 12:40 | 2021-08-10 21:18 |  | 2021-10-07 19:55 | 2021-08-12 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:54 |  | yes | no | no
4843 | 16394058201721782016628 | 4 | Haverhill St | Bremen St | Waveney St | Asphalt | Yes Round 2 | 2021-09-10 14:20 | 2021-09-30 13:44 | 2021-10-05 15:40 |  | 2021-10-11 15:50 | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:20 |  | no | yes | no
1195 | 16394058201543182014836 | 4 | Haverhill St | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-07-31 19:41 | 2021-08-03 20:30 | 2021-08-09 12:45 |  | 2021-10-11 15:58 | 2021-08-10 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:16 |  | yes | no | no
5615 | 47058298200961982009913 | 4 | Haverhill St | Duchess St | Whitehill St | Asphalt | Yes Round 3 | 2021-10-05 17:07 | 2021-10-09 20:03 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:07 |  |  |  | Yes
1049 | 16394058201298182012318 | 4 | Haverhill St | E Outer Dr | Linville St | Asphalt | Yes | 2021-07-27 17:03 | 2021-08-03 19:19 | 2021-08-09 12:22 |  |  | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:34 |  | yes | no | no
5660 | 16394058201483682014138 | 4 | Haverhill St | E Warren Ave | Frankfort St | Asphalt | Yes Round 3 | 2021-10-05 17:10 | 2021-10-09 13:25 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:10 |  |  |  | Yes
1111 | 16394058201413882013543 | 4 | Haverhill St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 16:59 | 2021-08-03 20:04 | 2021-08-09 12:38 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 16:40 |  | yes | no | no
1016 | 16394058201231882012002 | 4 | Haverhill St | Linville St | Hern Ave | Asphalt | Yes | 2021-07-27 17:05 | 2021-08-03 18:44 | 2021-08-13 17:05 |  |  | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-07-29 16:32 |  | yes | no | no
982 | 47058298201130982011619 | 4 | Haverhill St | McKinney Ave | Evanston St | Asphalt | Yes | 2021-07-27 13:47 | 2021-07-31 15:55 | 2021-08-06 12:48 |  | 2021-09-14 19:44 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:01 |  | yes | no | no
4844 | 16394058201596682015431 | 4 | Haverhill St | Munich St | Cornwall St | Asphalt | Yes Round 2 | 2021-09-10 14:10 | 2021-09-30 20:39 | 2021-10-05 15:49 |  | 2021-10-11 15:54 | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:10 |  | no | yes | no
1081 | 16394058201354382013121 | 4 | Haverhill St | Southampton St | E Outer Dr | Asphalt | Yes | 2021-07-27 17:00 | 2021-08-03 19:39 | 2021-08-13 17:25 |  |  | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-07-29 16:36 |  | yes | no | no
5681 | 16394058201662882015966 | 4 | Haverhill St | Waveney St | Munich St | Asphalt | Yes Round 3 | 2021-10-05 17:16 | 2021-10-09 14:13 | 2021-10-11 21:47 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:16 |  |  |  | Yes
873 | 47058298200991382010087 | 4 | Haverhill St | Whitehill St | Stratman St | Asphalt | Yes | 2021-07-27 15:34 | 2021-07-31 18:27 | 2021-08-04 21:27 |  | 2021-09-14 19:22 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:10 |  | yes | no | no
521 | 15883098200646982006448 | 4 | Hazelridge St | Hayes St | Brock St | Asphalt | Yes | 2021-07-27 18:50 | 2021-08-30 15:31 | 2021-09-01 15:31 |  |  | 2021-09-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:30 |  | yes | no | no
4740 | 15883098200648782006469 | 4 | Hazelridge St | Queen St | Hayes St | Asphalt | Yes Round 2 | 2021-09-09 13:54 | 2021-10-11 16:49 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-09 13:54 |  | no | yes | no
773 | 16386038200923082008704 | 4 | Hereford St | Berden St | Minerva St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | No |  |  |  | yes | no | no
880 | 16386038201039982009810 | 4 | Hereford St | Chandler Park Dr | Linville St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | No |  |  |  | yes | no | no
3910 | 16386038201203782010949 | 4 | Hereford St | E Warren Ave | Southampton St | Asphalt | Yes | 2021-10-05 13:37 | 2021-10-06 14:56 | 2021-10-09 18:54 |  |  | 2021-10-11 04:00 | HMA | No | Coordinate with DTE GRP | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 13:37 |  | yes | no | no
3911 | 16386038201203782010949 | 4 | Hereford St | E Warren Ave | Southampton St | Asphalt | Yes | 2021-10-05 13:32 | 2021-10-06 15:26 | 2021-10-09 18:44 |  |  | 2021-10-11 04:00 | HMA | No | Coordinate with DTE GRP | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 13:31 |  | yes | no | no
3912 | 16386038201203782010949 | 4 | Hereford St | E Warren Ave | Southampton St | Asphalt | Yes | 2021-10-05 13:29 | 2021-10-06 15:54 | 2021-10-09 18:30 |  |  | 2021-10-11 04:00 | HMA | No | Coordinate with DTE GRP | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 13:29 |  | yes | no | no
833 | 16386038200981082009230 | 4 | Hereford St | Linville St | Berden St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | No |  |  |  | yes | no | no
716 | 16386038200870482008180 | 4 | Hereford St | Minerva St | Chester St | Asphalt | Yes | 2021-10-05 13:01 | 2021-10-06 18:37 | 2021-10-11 14:37 |  |  |  | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 13:01 |  | yes | no | no
3925 | 16386038201332982012037 | 4 | Hereford St | Munich St | E Warren Ave | Asphalt | Yes | 2021-10-05 14:03 | 2021-10-06 12:58 | 2021-10-09 19:34 |  |  | 2021-10-11 04:00 | HMA | No | Coordinate with DTE GRP | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 14:03 |  | yes | no | no
3926 | 16386038201332982012037 | 4 | Hereford St | Munich St | E Warren Ave | Asphalt | Yes | 2021-10-05 14:03 | 2021-10-06 14:08 | 2021-10-09 19:34 |  |  | 2021-10-11 04:00 | HMA | No | Coordinate with DTE GRP | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 14:03 |  | yes | no | no
3927 | 16386038201332982012037 | 4 | Hereford St | Munich St | E Warren Ave | Asphalt | Yes | 2021-10-05 13:52 | 2021-10-06 14:11 | 2021-10-09 19:05 |  |  | 2021-10-11 04:00 | HMA | No | Coordinate with DTE GRP | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 13:52 |  | yes | no | no
926 | 16386038201094982010473 | 4 | Hereford St | Southampton St | Chandler Park Dr | Asphalt | Yes | 2021-10-05 13:16 | 2021-10-06 17:07 | 2021-10-09 18:18 |  |  | 2021-10-11 04:00 | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 13:16 |  | yes | no | no
705 | 16396078200874082008410 | 4 | Hillcrest St | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-08-20 16:24 | 2021-08-28 12:09 | 2021-08-31 21:28 |  | 2021-10-06 13:31 | 2021-09-01 04:00 | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-08-20 16:24 |  | yes | no | no
1409 | 16396078200903882008740 | 4 | Hillcrest St | Frankfort Ave | Chandler Park Dr | Asphalt | Yes | 2021-08-20 16:11 | 2021-08-30 14:20 | 2021-08-31 21:40 |  | 2021-10-06 13:34 | 2021-09-01 04:00 | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-08-20 16:11 |  | yes | no | no
1410 | 16396078200936682009038 | 4 | Hillcrest St | Hillcrest Dr & Mack Ave | Frankfort Ave | Asphalt | Yes | 2021-08-20 16:00 | 2021-08-28 12:42 | 2021-08-31 21:48 |  | 2021-10-06 13:40 | 2021-09-01 04:00 | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-08-20 16:00 |  | yes | no | no
678 | 16396078200841082008087 | 4 | Hillcrest St | Linville St | Rolandale St | Asphalt | Yes | 2021-08-20 16:42 | 2021-08-28 11:48 | 2021-08-31 21:28 |  | 2021-10-06 13:27 | 2021-09-01 04:00 | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-08-20 16:42 |  | yes | no | no
3184 | 47104428202359382025140 | 4 | Hurlbut St | E Canfield St | Sylvester St | Asphalt | Yes | 2021-07-23 13:32 | 2021-08-16 12:50 | 2021-08-17 20:30 |  |  | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:32 |  | yes | no | no
3185 | 47104428202359382025140 | 4 | Hurlbut St | E Canfield St | Sylvester St | Asphalt | Yes | 2021-07-23 13:33 | 2021-08-16 12:50 | 2021-08-17 20:22 |  |  | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:32 |  | yes | no | no
3046 | 47104428202100782021903 | 4 | Hurlbut St | Moffat St | E Warren Ave | Asphalt | Yes | [6 empty] | HMA | No |  |  |  | No | No | poor pavement |  |  | yes | no | no
3047 | 47104428202100782021903 | 4 | Hurlbut St | Moffat St | E Warren Ave | Asphalt | Yes | [6 empty] | HMA | No |  |  |  | No | No | poor pavement |  |  | yes | no | no
846 | 15914068200960282009266 | 4 | Kenmoor St | Algonac St | Elmo St | Asphalt | Yes | 2021-09-10 13:37 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 13:37 |  | yes | no | no
876 | 15914068200985782009602 | 4 | Kenmoor St | Conner St | Algonac St | Asphalt | Yes | 2021-09-10 13:50 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 13:50 |  | yes | no | no
2444 | 15914068200926682008865 | 4 | Kenmoor St | Elmo St | Gunston St | Asphalt | Yes | 2021-09-10 13:28 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 13:28 |  | yes | no | no
2445 | 15914068200926682008865 | 4 | Kenmoor St | Elmo St | Gunston St | Asphalt | Yes | 2021-09-10 13:10 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 13:10 |  | yes | no | no
5534 | 15914068200886582008469 | 4 | Kenmoor St | Gunston St | Bradford St | Asphalt | Yes Round 3 | 2021-10-05 16:24 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 16:24 |  |  |  | Yes
5535 | 15914068200886582008469 | 4 | Kenmoor St | Gunston St | Bradford St | Asphalt | Yes Round 3 | 2021-10-05 16:26 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 16:26 |  |  |  | Yes
817 | 15914078200928982009001 | 4 | Kennebec St | Algonac St | Elmo St | Asphalt | Yes | 2021-07-23 13:57 | 2021-07-28 20:03 | 2021-08-03 21:44 |  | 2021-09-08 15:30 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 18:30 |  | yes | no | no
696 | 15914078200817482008026 | 4 | Kennebec St | Bradford St | Dresden St | Asphalt | Yes | 2021-07-23 14:11 | 2021-07-28 17:45 | 2021-08-04 15:58 |  | 2021-09-08 15:39 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 18:16 |  | yes | no | no
854 | 15914078200964782009289 | 4 | Kennebec St | Conner St | Algonac St | Asphalt | Yes | 2021-07-23 14:04 | 2021-07-28 20:40 | 2021-08-03 21:23 |  | 2021-09-08 15:29 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 18:30 |  | yes | no | no
2432 | 15914078200900182008573 | 4 | Kennebec St | Elmo St | Gunston St | Asphalt | Yes | 2021-07-23 13:56 | 2021-07-28 19:31 | 2021-08-04 13:39 |  | 2021-09-08 15:32 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:32 |  | yes | no | no
2433 | 15914078200900182008573 | 4 | Kennebec St | Elmo St | Gunston St | Asphalt | Yes | 2021-07-23 13:52 | 2021-07-28 21:10 | 2021-08-04 13:48 |  | 2021-09-08 15:37 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:32 |  | yes | no | no
2416 | 15914078200857382008174 | 4 | Kennebec St | Gunston St | Bradford St | Asphalt | Yes | 2021-07-23 14:08 | 2021-07-28 19:02 | 2021-08-04 14:32 |  | 2021-09-08 15:37 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 18:16 |  | yes | no | no
2417 | 15914078200857382008174 | 4 | Kennebec St | Gunston St | Bradford St | Asphalt | Yes | 2021-07-23 14:09 | 2021-07-28 18:06 | 2021-08-04 14:54 |  | 2021-09-08 15:38 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 18:16 |  | yes | no | no
993 | 16352048201191482011335 | 4 | Kensington Ave | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-27 15:21 | 2021-08-04 19:45 | 2021-08-09 18:16 |  | 2021-10-06 20:21 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:30 |  | yes | no | no
1119 | 16352048201432682013672 | 4 | Kensington Ave | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-07-31 18:55 | 2021-08-05 11:49 | 2021-08-09 18:44 |  | 2021-10-09 18:09 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:02 |  | yes | no | no
1089 | 16352048201367282013093 | 4 | Kensington Ave | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-31 18:55 | 2021-08-04 20:49 | 2021-08-11 18:44 |  | 2021-10-06 21:59 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 16:56 |  | yes | no | no
1054 | 16352048201309382012454 | 4 | Kensington Ave | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 15:17 | 2021-08-04 20:27 | 2021-08-09 18:30 |  | 2021-10-06 21:53 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:39 |  | yes | no | no
2700 | 16352048201783782017071 | 4 | Kensington Ave | Kensington Rd & Mack Ave | Rosewood St | Asphalt | Yes | 2021-07-31 17:49 | 2021-08-05 15:30 | 2021-08-10 17:19 |  |  | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:07 |  | yes | no | no
2701 | 16352048201783782017071 | 4 | Kensington Ave | Kensington Rd & Mack Ave | Rosewood St | Asphalt | Yes | 2021-07-31 17:49 | 2021-08-05 15:07 | 2021-08-10 16:59 |  | 2021-10-09 18:24 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:00 |  | yes | no | no
2486 | 16352048201133582010382 | 4 | Kensington Ave | Linville St | Harper Ave | Asphalt | Yes | 2021-07-27 15:23 | 2021-08-04 19:04 | 2021-08-09 17:57 |  | 2021-10-06 21:44 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:32 |  | yes | no | no
2487 | 16352048201133582010382 | 4 | Kensington Ave | Linville St | Harper Ave | Asphalt | Yes | 2021-07-27 15:24 | 2021-08-04 19:24 | 2021-08-09 17:47 |  | 2021-10-06 21:46 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:36 |  | yes | no | no
2686 | 16352048201707182016238 | 4 | Kensington Ave | Rosewood St | Wallingford St | Asphalt | Yes | 2021-07-31 18:21 | 2021-08-05 14:44 | 2021-08-10 16:45 |  | 2021-10-09 18:22 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:51 |  | yes | no | no
2687 | 16352048201707182016238 | 4 | Kensington Ave | Rosewood St | Wallingford St | Asphalt | Yes | 2021-07-31 18:21 | 2021-08-05 14:22 | 2021-08-10 16:36 |  | 2021-10-09 18:20 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:47 |  | yes | no | no
1024 | 16352048201245482012038 | 4 | Kensington Ave | Southampton St | Chandler Park Dr | Asphalt | Yes | 2021-07-27 15:19 | 2021-08-04 20:09 | 2021-08-09 18:23 |  | 2021-10-06 21:49 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:45 |  | yes | no | no
2676 | 16352048201623882015463 | 4 | Kensington Ave | Wallingford St | Waveney St | Asphalt | Yes | 2021-07-31 18:21 | 2021-08-05 14:02 | 2021-08-10 16:25 |  | 2021-10-09 18:19 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:35 |  | yes | no | no
2677 | 16352048201623882015463 | 4 | Kensington Ave | Wallingford St | Waveney St | Asphalt | Yes | 2021-07-31 18:22 | 2021-08-05 13:12 | 2021-08-10 14:44 |  | 2021-10-09 18:15 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:31 |  | yes | no | no
3958 | 16352048201546382014326 | 4 | Kensington Ave | Waveney St | Cornwall St | Asphalt | Yes | 2021-07-31 18:32 | 2021-08-05 12:50 | 2021-08-10 14:14 |  | 2021-10-09 18:11 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:28 |  | yes | no | no
3959 | 16352048201546382014326 | 4 | Kensington Ave | Waveney St | Cornwall St | Asphalt | Yes | 2021-07-31 18:32 | 2021-08-05 12:29 | 2021-08-10 14:12 |  | 2021-10-09 18:10 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:19 |  | yes | no | no
3960 | 16352048201546382014326 | 4 | Kensington Ave | Waveney St | Cornwall St | Asphalt | Yes | 2021-07-31 18:54 | 2021-08-05 12:10 | 2021-08-10 13:55 |  | 2021-10-09 18:10 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 17:11 |  | yes | no | no
2516 | 15880098201178082011460 | 4 | Kilbourne Ave | Barrett St | Roseberry St | Asphalt | Yes | 2021-07-23 15:27 | 2021-07-30 21:25 | 2021-08-05 20:34 |  | 2021-09-10 14:37 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 16:41 |  | yes | no | no
2517 | 15880098201178082011460 | 4 | Kilbourne Ave | Barrett St | Roseberry St | Asphalt | Yes | 2021-07-23 15:26 | 2021-07-30 21:44 | 2021-08-05 19:37 |  | 2021-09-10 14:38 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 16:41 |  | yes | no | no
2508 | 15880098200938082009406 | 4 | Kilbourne Ave | Chalmers St | Leroy Ave | Asphalt | Yes Round 2 | 2021-09-09 14:40 | 2021-10-11 18:10 |  |  |  |  | HMA | No |  |  |  |  | Yes |  | 2021-09-09 14:41 |  | No | yes | no
2473 | 15880098201006382009730 | 4 | Kilbourne Ave | Coplin St | Newport St | Asphalt | Yes | 2021-07-23 16:05 | 2021-07-30 22:38 | 2021-08-06 13:42 |  | 2021-09-14 14:54 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 15:28 |  | yes | no | no
2538 | 15880098201205382011780 | 4 | Kilbourne Ave | Gratiot Ave | Barrett St | Asphalt | Yes | 2021-07-23 15:31 | 2021-07-30 20:41 | 2021-08-05 21:38 |  | 2021-09-10 14:34 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 16:52 |  | yes | no | no
2539 | 15880098201205382011780 | 4 | Kilbourne Ave | Gratiot Ave | Barrett St | Asphalt | Yes | 2021-07-23 15:30 | 2021-07-30 21:01 | 2021-08-05 20:53 |  | 2021-09-10 14:37 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 16:52 |  | yes | no | no
2459 | 15880098200973082009380 | 4 | Kilbourne Ave | Newport St | Chalmers St | Asphalt | Yes | 2021-07-23 16:08 | 2021-08-02 12:37 | 2021-08-06 13:58 |  | 2021-09-14 14:27 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 15:27 |  | yes | no | no
936 | 15880098201075082010424 | 4 | Kilbourne Ave | Park Dr | Dickerson St | Asphalt | Yes | 2021-07-23 15:36 | 2021-07-30 22:16 | 2021-08-06 13:22 |  | 2021-09-10 14:45 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 15:59 |  | yes | no | no
1726 | 17145068203049682030377 | 4 | Korte St | Newport St | Lakewood St | Asphalt | Yes | 2021-07-23 16:00 | 2021-08-16 12:19 | 2021-08-17 13:47 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 15:45 |  | yes | no | no
1744 | 17145068203101282030806 | 4 | Korte St | Riverside Dr & Drexel St | Piper Blvd | Asphalt | Yes | 2021-07-23 16:00 | 2021-08-16 11:45 | 2021-08-17 13:48 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-24 15:45 |  | yes | no | no
857 | 16396038201013182009890 | 4 | Lafontaine St | Frankfort Ave | Canyon Ave | Asphalt | Yes | 2021-07-27 12:14 | 2021-08-13 15:58 | 2021-08-16 19:38 |  | 2021-10-06 14:04 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:56 |  | yes | no | no
2706 | 16393098201877982017736 | 4 | Lakepointe St | Lozier St | Waveney St | Asphalt | Yes | 2021-08-04 12:37 | 2021-08-10 12:49 | 2021-08-14 13:04 |  | 2021-10-11 19:45 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:11 |  | yes | no | no
2707 | 16393098201877982017736 | 4 | Lakepointe St | Lozier St | Waveney St | Asphalt | Yes | 2021-08-04 12:38 | 2021-08-10 13:07 | 2021-08-14 13:05 |  | 2021-10-11 19:42 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:11 |  | yes | no | no
3967 | 16393098201980982018779 | 4 | Lakepointe St | Mack Ave | Lozier St | Asphalt | Yes | 2021-08-04 12:33 | 2021-08-09 17:54 | 2021-08-13 19:48 |  | 2021-10-11 19:55 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:22 |  | yes | no | no
3968 | 16393098201980982018779 | 4 | Lakepointe St | Mack Ave | Lozier St | Asphalt | Yes | 2021-08-04 12:34 | 2021-08-09 18:15 | 2021-08-14 12:51 |  | 2021-10-11 19:53 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:22 |  | yes | no | no
3969 | 16393098201980982018779 | 4 | Lakepointe St | Mack Ave | Lozier St | Asphalt | Yes | 2021-08-04 12:35 | 2021-08-09 18:41 | 2021-08-14 12:51 |  | 2021-10-11 19:50 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:22 |  | yes | no | no
2698 | 16393098201773682016891 | 4 | Lakepointe St | Waveney St | Voight St | Asphalt | Yes | 2021-08-04 12:39 | 2021-08-10 13:28 | 2021-08-14 13:08 |  | 2021-10-11 19:38 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:03 |  | yes | no | no
2699 | 16393098201773682016891 | 4 | Lakepointe St | Waveney St | Voight St | Asphalt | Yes | 2021-08-04 12:41 | 2021-08-10 13:45 | 2021-08-14 13:17 |  | 2021-10-11 19:32 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:03 |  | yes | no | no
4798 | 47110188201526682014656 | 4 | Lakeview St | Linville St | Hern St | Asphalt | Yes Round 2 | 2021-09-10 15:30 | 2021-10-11 20:31 |  |  |  |  | HMA | [5 empty] | Yes | Car | 2021-09-10 15:30 |  | no | yes | no
1248 | 47110188201640082015840 | 4 | Lakeview St | Southampton St | Chandler Park Dr | Asphalt | Yes | 2021-07-28 17:19 | 2021-08-05 16:51 | 2021-08-13 18:21 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:41 |  | yes | no | no
4817 | 16349048201540482014821 | 4 | Lakewood St | Chandler Park Dr | Linville St | Asphalt | Yes Round 2 | 2021-09-10 15:21 | 2021-10-05 19:51 | 2021-10-06 20:01 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:21 |  | no | yes | no
5348 | 16349048202172682020440 | 4 | Lakewood St | Charlevoix St | Mack Ave | Asphalt | Yes Round 2 | 2021-09-10 14:49 | 2021-10-01 18:37 | 2021-10-06 16:19 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:49 |  | no | yes | no
5349 | 16349048202172682020440 | 4 | Lakewood St | Charlevoix St | Mack Ave | Asphalt | Yes Round 2 | 2021-09-10 14:46 | 2021-10-01 18:13 | 2021-10-06 16:29 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:46 |  | no | yes | no
5350 | 16349048202172682020440 | 4 | Lakewood St | Charlevoix St | Mack Ave | Asphalt | Yes Round 2 | 2021-09-10 14:43 | 2021-10-01 17:39 | 2021-10-06 16:39 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:42 |  | no | yes | no
4566 | 16349048202657582023465 | 4 | Lakewood St | E Jefferson Ave | Kercheval St | Asphalt | Yes Round 2 | 2021-09-10 15:11 | 2021-10-02 15:57 | 2021-10-06 13:24 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:11 |  | no | yes | no
4567 | 16349048202657582023465 | 4 | Lakewood St | E Jefferson Ave | Kercheval St | Asphalt | Yes Round 2 | 2021-09-10 15:09 | 2021-10-02 15:29 | 2021-10-06 13:39 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:09 |  | no | yes | no
4568 | 16349048202657582023465 | 4 | Lakewood St | E Jefferson Ave | Kercheval St | Asphalt | Yes Round 2 | 2021-09-10 15:07 | 2021-10-02 14:51 | 2021-10-06 13:51 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:07 |  | no | yes | no
4569 | 16349048202657582023465 | 4 | Lakewood St | E Jefferson Ave | Kercheval St | Asphalt | Yes Round 2 | 2021-09-10 15:04 | 2021-10-02 14:00 | 2021-10-06 14:03 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:05 |  | no | yes | no
4570 | 16349048202657582023465 | 4 | Lakewood St | E Jefferson Ave | Kercheval St | Asphalt | Yes Round 2 | 2021-09-10 15:02 | 2021-10-02 13:25 | 2021-10-06 14:12 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:02 |  | no | yes | no
5165 | 16349048202273182021726 | 4 | Lakewood St | E Vernor Hwy | Charlevoix St | Asphalt | Yes Round 2 | 2021-09-10 14:57 | 2021-10-01 19:40 | 2021-10-06 14:35 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:57 |  | no | yes | no
5166 | 16349048202273182021726 | 4 | Lakewood St | E Vernor Hwy | Charlevoix St | Asphalt | Yes Round 2 | 2021-09-10 14:55 | 2021-10-01 19:15 | 2021-10-06 16:02 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:55 |  | no | yes | no
4859 | 16349048202346582022731 | 4 | Lakewood St | Kercheval St | E Vernor Hwy | Asphalt | Yes Round 2 | 2021-09-10 15:00 | 2021-10-02 12:46 | 2021-10-06 14:24 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:00 |  | no | yes | no
1535 | 16349048202044082019837 | 4 | Lakewood St | Mack Ave | Lozier St | Asphalt | Yes | 2021-07-28 17:02 | 2021-08-05 19:23 | 2021-08-13 19:51 |  |  | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 15:31 |  | yes | no | no
3853 | 16329098200718782005986 | 4 | Lanark St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:18 | 2021-07-28 13:02 | 2021-08-05 20:21 |  | 2021-09-15 21:22 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 16:37 |  | yes | no | no
3854 | 16329098200718782005986 | 4 | Lanark St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:03 | 2021-07-28 12:00 | 2021-08-05 20:20 |  | 2021-09-15 21:23 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 16:38 |  | yes | no | no
3855 | 16329098200718782005986 | 4 | Lanark St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:03 | 2021-07-28 12:28 | 2021-08-05 20:08 |  | 2021-09-15 21:24 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 16:43 |  | yes | no | no
1414 | 16396068200971082009338 | 4 | Lannoo St | Lannoo Dr & Mack Ave | Frankfort Ave | Asphalt | Yes | 2021-08-20 15:45 | 2021-08-28 13:05 | 2021-09-01 12:36 |  | 2021-10-06 13:44 | 2021-09-02 04:00 | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-08-20 15:45 |  | yes | no | no
2344 | 16331038200654482005811 | 4 | Lansdowne St | Britain St | Morang Dr | Asphalt | Yes | 2021-07-26 18:24 | 2021-07-30 14:20 | 2021-08-04 11:56 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:43 |  | yes | no | no
2345 | 16331038200654482005811 | 4 | Lansdowne St | Britain St | Morang Dr | Asphalt | Yes | 2021-07-26 18:24 | 2021-07-30 13:53 | 2021-08-04 12:01 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:46 |  | yes | no | no
5297 | 16331038200525482003948 | 4 | Lansdowne St | Casino St | Moross Rd | Asphalt | Yes Round 2 | 2021-09-09 13:07 | 2021-09-27 16:04 | 2021-09-29 14:30 |  |  | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 13:08 |  | no | yes | no
5298 | 16331038200525482003948 | 4 | Lansdowne St | Casino St | Moross Rd | Asphalt | Yes Round 2 | 2021-09-09 13:16 | 2021-09-27 16:48 | 2021-09-29 14:30 |  |  | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 13:16 |  | no | yes | no
5299 | 16331038200525482003948 | 4 | Lansdowne St | Casino St | Moross Rd | Asphalt | Yes Round 2 | 2021-09-09 13:22 | 2021-09-27 18:00 | 2021-09-29 14:29 |  |  | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 13:22 |  | no | yes | no
2364 | 16331038200733382006544 | 4 | Lansdowne St | Grayton St | Britain St | Asphalt | Yes | 2021-07-26 18:25 | 2021-07-30 15:24 | 2021-08-03 21:34 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:34 |  | yes | no | no
2365 | 16331038200733382006544 | 4 | Lansdowne St | Grayton St | Britain St | Asphalt | Yes | 2021-07-26 18:25 | 2021-07-30 14:52 | 2021-08-03 21:58 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:37 |  | yes | no | no
284 | 16331038200361682003405 | 4 | Lansdowne St | McCormick St | Lansdowne Ave & Kingsville Ave | Asphalt | Yes | 2021-08-04 16:54 | 2021-08-30 12:54 | 2021-08-31 21:01 |  | 2021-09-15 15:45 | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 16:54 |  | yes | no | no
727 | 16331038200865882008027 | 4 | Lansdowne St | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-26 18:54 | 2021-07-30 17:27 | 2021-08-03 21:10 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:22 |  | yes | no | no
662 | 16331038200802782007333 | 4 | Lansdowne St | Yorkshire Rd | Grayton St | Asphalt | Yes | 2021-07-26 18:54 | 2021-07-30 16:01 | 2021-08-03 21:24 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:27 |  | yes | no | no
5678 | 47053978201872582018036 | 4 | Lenox St | E Forest Ave | E Warren Ave | Asphalt | Yes Round 3 | 2021-10-05 16:30 | 2021-10-11 21:08 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 16:30 |  |  |  | Yes
4478 | 47053978202747982024867 | 4 | Lenox St | E Jefferson Ave | Kercheval St | Asphalt | Yes | 2021-07-23 16:45 | 2021-08-14 13:15 | 2021-08-17 19:11 |  |  | 2021-08-20 04:00 | HMA |  |  |  |  | No | Yes |  | 2021-07-24 13:57 |  | yes | No | no
4479 | 47053978202747982024867 | 4 | Lenox St | E Jefferson Ave | Kercheval St | Asphalt | Yes | 2021-07-23 16:46 | 2021-08-14 12:44 | 2021-08-17 19:20 |  |  | 2021-08-20 04:00 | HMA |  |  |  |  | No | Yes |  | 2021-07-24 13:57 |  | yes | No | no
4480 | 47053978202747982024867 | 4 | Lenox St | E Jefferson Ave | Kercheval St | Asphalt | Yes | 2021-07-23 16:46 | 2021-08-14 12:20 | 2021-08-17 19:36 |  |  | 2021-08-20 04:00 | HMA |  |  |  |  | No | Yes |  | 2021-07-24 13:30 |  | yes | No | no
4481 | 47053978202747982024867 | 4 | Lenox St | E Jefferson Ave | Kercheval St | Asphalt | Yes | 2021-07-23 16:46 | 2021-08-14 11:57 | 2021-08-17 19:48 |  |  | 2021-08-20 04:00 | HMA |  |  |  |  | No | Yes |  | 2021-07-24 13:29 |  | yes | No | no
4482 | 47053978202747982024867 | 4 | Lenox St | E Jefferson Ave | Kercheval St | Asphalt | Yes | 2021-07-23 16:46 | 2021-08-14 11:40 | 2021-08-17 19:55 |  |  | 2021-08-20 04:00 | HMA |  |  |  |  | No | Yes |  | 2021-07-24 12:55 |  | yes | No | no
4558 | 16393078202207682020590 | 4 | Lillibridge St | E Canfield St | E Warren Ave | Asphalt 2020 | Yes Round 2 | 2021-09-10 15:59 | 2021-10-11 11:42 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-10 15:58 |  | no | yes | no
4559 | 16393078202207682020590 | 4 | Lillibridge St | E Canfield St | E Warren Ave | Asphalt 2020 | Yes Round 2 | 2021-09-10 15:49 | 2021-10-11 21:32 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-10 15:49 |  | no | yes | no
4560 | 16393078202207682020590 | 4 | Lillibridge St | E Canfield St | E Warren Ave | Asphalt 2020 | Yes Round 2 | 2021-09-10 15:42 | 2021-10-11 21:16 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-10 15:43 |  | no | yes | no
4561 | 16393078202207682020590 | 4 | Lillibridge St | E Canfield St | E Warren Ave | Asphalt 2020 | Yes Round 2 | 2021-09-10 15:36 | 2021-10-11 21:15 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-10 15:37 |  | no | yes | no
4562 | 16393078202368082022076 | 4 | Lillibridge St | Mack Ave | E Canfield St | Asphalt 2020 | Yes Round 2 | 2021-09-10 16:34 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:34 |  | no | yes | no
4563 | 16393078202368082022076 | 4 | Lillibridge St | Mack Ave | E Canfield St | Asphalt 2020 | Yes Round 2 | 2021-09-10 16:31 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:31 |  | no | yes | no
4564 | 16393078202368082022076 | 4 | Lillibridge St | Mack Ave | E Canfield St | Asphalt 2020 | Yes Round 2 | 2021-09-10 16:24 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:24 |  | no | yes | no
4565 | 16393078202368082022076 | 4 | Lillibridge St | Mack Ave | E Canfield St | Asphalt 2020 | Yes Round 2 | 2021-09-10 16:13 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:13 |  | no | yes | no
333 | 47000458208901582004181 | 4 | Linnhurst St | Rex St | Kelly Rd | Asphalt | Yes | 2021-07-27 18:49 | 2021-07-29 17:15 | 2021-08-02 15:20 |  | 2021-09-15 17:07 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:53 |  | yes | no | no
975 | 16399048201162982011061 | 4 | Lodewyck St | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-27 12:34 | 2021-08-28 14:14 | 2021-09-01 12:49 |  | 2021-10-06 15:24 | 2021-09-02 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:35 |  | yes | no | no
938 | 16399048201106182010517 | 4 | Lodewyck St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 12:36 | 2021-08-13 12:35 | 2021-08-16 19:25 |  | 2021-10-06 15:22 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:44 |  | yes | no | no
889 | 16399048201051782010059 | 4 | Lodewyck St | Southampton St | Chandler Park Dr | Asphalt | Yes | 2021-07-27 12:37 | 2021-08-13 12:56 | 2021-08-16 16:38 |  | 2021-10-06 15:19 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:44 |  | yes | no | no
2578 | 16323078201306082012677 | 4 | Longview St | Annsbury Ave | Park Dr | Asphalt | Yes | 2021-09-09 15:46 | 2021-10-05 14:00 | 2021-10-06 20:39 |  |  | 2021-10-07 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 15:46 |  | yes | no | no
2654 | 16323078201471682014187 | 4 | Longview St | Conner St | Gunston Ave | Asphalt | Yes | 2021-09-09 17:34 | 2021-10-05 12:43 | 2021-10-06 21:03 |  |  | 2021-10-07 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 17:33 |  | yes | no | no
2655 | 16323078201471682014187 | 4 | Longview St | Conner St | Gunston Ave | Asphalt | Yes | 2021-09-09 17:45 | 2021-10-05 13:12 | 2021-10-06 20:55 |  |  | 2021-10-07 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 17:45 |  | yes | no | no
5378 | 16323078201267782012289 | 4 | Longview St | Park Dr | Dickerson St | Asphalt | Yes | 2021-09-09 15:40 | 2021-10-05 14:51 | 2021-10-06 20:30 |  |  | 2021-10-07 04:00 | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 15:40 |  | Yes | No | no
5379 | 16323078201267782012289 | 4 | Longview St | Park Dr | Dickerson St | Asphalt | Yes | 2021-09-09 15:36 | 2021-10-05 15:21 | 2021-10-06 20:15 |  |  | 2021-10-07 04:00 | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 15:35 |  | Yes | No | no
2548 | 16323048201250982012121 | 4 | Maiden St | Newport St | Chalmers St | Asphalt | Yes | 2021-08-04 13:32 | 2021-08-05 14:16 | 2021-08-09 16:59 |  | 2021-09-14 15:18 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 16:52 |  | yes | no | no
2549 | 16323048201250982012121 | 4 | Maiden St | Newport St | Chalmers St | Asphalt | Yes | 2021-08-04 13:31 | 2021-08-05 13:56 | 2021-08-09 20:32 |  | 2021-09-14 15:19 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 16:52 |  | yes | no | no
1164 | 17144068201485382014166 | 4 | Manistique St | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-28 16:52 | 2021-08-02 20:27 | 2021-08-07 13:23 |  | 2021-10-11 21:44 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:33 |  | yes | no | no
2574 | 16404028201303582012106 | 4 | Manistique St | Evanston St | Wade St | Asphalt | Yes | 2021-07-28 17:27 | 2021-08-02 13:00 | 2021-08-14 18:15 |  | 2021-09-14 16:51 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 18:33 |  | yes | no | no
2575 | 16404028201303582012106 | 4 | Manistique St | Evanston St | Wade St | Asphalt | Yes | 2021-07-28 17:46 | 2021-08-02 12:27 | 2021-08-14 18:21 |  | 2021-09-14 16:52 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 18:43 |  | yes | no | no
1226 | 17144068201593182015411 | 4 | Manistique St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-28 16:49 | 2021-08-02 19:13 | 2021-08-07 12:56 |  | 2021-10-11 21:52 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:38 |  | yes | no | no
1198 | 17144068201541182014933 | 4 | Manistique St | Southampton St | Chandler Park Dr | Asphalt | Yes | 2021-07-28 16:51 | 2021-08-02 19:50 | 2021-08-07 13:09 |  | 2021-10-11 21:50 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 14:34 |  | yes | no | no
1010 | 16404028201210682011527 | 4 | Manistique St | Wade St | Elmdale St | Asphalt | Yes | 2021-07-28 17:48 | 2021-08-02 13:15 | 2021-08-14 18:31 |  | 2021-09-14 16:54 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 18:54 |  | yes | no | no
5213 | 16349068203099982030060 | 4 | Marlborough St | Scripps St | Korte St | Asphalt | Yes Round 2 | 2021-09-10 15:30 | 2021-10-04 15:04 | 2021-10-06 17:02 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:30 |  | no | yes | no
5214 | 16349068203099982030060 | 4 | Marlborough St | Scripps St | Korte St | Asphalt | Yes Round 2 | 2021-09-10 15:29 | 2021-10-04 14:21 | 2021-10-05 21:25 |  |  | 2021-10-07 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:29 |  | no | yes | no
3844 | 16330018200689882005659 | 4 | Marne St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:52 | 2021-07-28 14:30 | 2021-08-05 17:48 |  | 2021-09-15 21:09 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:41 |  | yes | no | no
3845 | 16330018200689882005659 | 4 | Marne St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:52 | 2021-07-28 15:09 | 2021-08-05 17:27 |  | 2021-09-15 21:11 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:42 |  | yes | no | no
3846 | 16330018200689882005659 | 4 | Marne St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:36 | 2021-07-28 15:30 | 2021-08-05 16:16 |  | 2021-09-15 21:18 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:45 |  | yes | no | no
610 | 16330018200748082006898 | 4 | Marne St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 15:52 | 2021-07-28 14:11 | 2021-08-05 17:57 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 11:37 |  | yes | no | no
983 | 16395048201173682011180 | 4 | Marseilles St | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-27 12:32 | 2021-08-13 11:59 | 2021-08-16 16:21 |  | 2021-10-06 15:30 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:26 |  | yes | no | no
5372 | 16395048201118082010639 | 4 | Marseilles St | Frankfort St | Southampton St | Asphalt | Yes Round 2 | 2021-09-10 12:39 | 2021-09-27 21:33 | 2021-09-29 16:08 |  | 2021-10-06 16:52 | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 12:39 |  | no | Yes | no
898 | 16395048201063982010201 | 4 | Marseilles St | Southampton St | Chandler Park Dr | Asphalt | Yes | 2021-07-27 12:30 | 2021-08-11 19:38 | 2021-08-16 16:30 |  | 2021-10-06 15:37 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:31 |  | yes | no | no
2708 | 16350068201893582017873 | 4 | Maryland St | Lozier St | Waveney St | Asphalt | Yes | 2021-08-04 12:46 | 2021-08-10 15:46 | 2021-08-14 15:12 |  | 2021-10-11 20:04 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:47 |  | yes | no | no
2709 | 16350068201893582017873 | 4 | Maryland St | Lozier St | Waveney St | Asphalt | Yes | 2021-08-04 12:45 | 2021-08-10 15:22 | 2021-08-14 15:01 |  | 2021-10-11 20:05 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:48 |  | yes | no | no
3970 | 16350068201988982018935 | 4 | Maryland St | Maryland Ave & Mack Ave | Lozier St | Asphalt | Yes | 2021-08-04 12:50 | 2021-08-10 16:27 | 2021-08-14 15:34 |  | 2021-10-11 19:58 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:34 |  | yes | no | no
3972 | 16350068201988982018935 | 4 | Maryland St | Maryland Ave & Mack Ave | Lozier St | Asphalt | Yes | 2021-08-04 12:49 | 2021-08-10 16:13 | 2021-08-14 15:34 |  | 2021-10-11 20:00 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:34 |  | yes | no | no
2702 | 16350068201787382017023 | 4 | Maryland St | Waveney St | Voight St | Asphalt | Yes | 2021-08-04 12:44 | 2021-08-10 14:34 | 2021-08-14 14:55 |  | 2021-10-11 20:08 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:48 |  | yes | no | no
2703 | 16350068201787382017023 | 4 | Maryland St | Waveney St | Voight St | Asphalt | Yes | 2021-08-04 12:42 | 2021-08-10 14:14 | 2021-08-14 14:50 |  | 2021-10-11 20:11 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:48 |  | yes | no | no
612 | 15883028200727982007356 | 4 | Mayfield St | Hayes St | Kelly Rd | Asphalt | Yes | 2021-08-04 13:24 | 2021-08-17 19:29 | 2021-08-19 14:44 |  |  | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 16:17 |  | yes | no | no
606 | 15883028200732382007279 | 4 | Mayfield St | Queen St | Hayes St | Asphalt | Yes | 2021-08-04 13:26 | 2021-08-17 18:55 | 2021-08-19 13:46 |  |  | 2021-08-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 16:15 |  | yes | no | no
2312 | 16324098200480982004400 | 4 | McCormick St | Balfour Rd | Beaconsfield Rd | Asphalt | Yes | 2021-07-26 14:22 | 2021-07-27 19:33 | 2021-08-03 14:59 |  | 2021-09-15 15:57 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:34 |  | yes | no | no
2313 | 16324098200480982004400 | 4 | McCormick St | Balfour Rd | Beaconsfield Rd | Asphalt | Yes | 2021-07-26 14:21 | 2021-07-27 18:49 | 2021-08-03 15:09 |  | 2021-09-15 15:57 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:30 |  | yes | no | no
2288 | 16324098200440082003926 | 4 | McCormick St | Beaconsfield Rd | Rossiter St | Asphalt | Yes | 2021-07-26 14:21 | 2021-07-27 18:02 | 2021-08-03 15:16 |  | 2021-09-15 15:50 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:27 |  | yes | no | no
2289 | 16324098200440082003926 | 4 | McCormick St | Beaconsfield Rd | Rossiter St | Asphalt | Yes | 2021-07-26 14:21 | 2021-07-27 18:00 | 2021-08-03 15:29 |  | 2021-09-15 15:49 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:23 |  | yes | no | no
429 | 16324098200546882005244 | 4 | McCormick St | Duprey St | Peerless St | Asphalt | Yes | 2021-07-26 14:46 | 2021-07-27 17:51 | 2021-08-03 12:58 |  | 2021-09-15 16:00 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 16:17 |  | yes | no | no
260 | 16324098200335582003108 | 4 | McCormick St | Laing St | Riad St | Asphalt | Yes | 2021-07-26 13:53 | 2021-07-27 15:40 | 2021-08-03 16:21 |  | 2021-09-15 15:43 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:09 |  | yes | no | no
285 | 16324098200361682003355 | 4 | McCormick St | Lansdowne St | Laing St | Asphalt | Yes | 2021-07-26 14:07 | 2021-07-27 16:41 | 2021-08-03 15:51 |  | 2021-09-15 15:44 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:17 |  | yes | no | no
2330 | 16324098200524482004809 | 4 | McCormick St | Peerless St | Balfour Rd | Asphalt | Yes | 2021-07-26 14:46 | 2021-07-27 15:52 | 2021-08-03 13:21 |  | 2021-09-15 15:59 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:53 |  | yes | no | no
2331 | 16324098200524482004809 | 4 | McCormick St | Peerless St | Balfour Rd | Asphalt | Yes | 2021-07-26 14:46 | 2021-07-28 19:19 | 2021-08-03 13:39 |  | 2021-09-15 15:58 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:49 |  | yes | no | no
233 | 16324098200310882002908 | 4 | McCormick St | Riad St | Kelly Rd | Asphalt | Yes | 2021-07-26 13:52 | 2021-07-27 15:40 | 2021-08-03 16:21 |  | 2021-09-15 15:41 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:04 |  | yes | no | no
312 | 16324098200392682003616 | 4 | McCormick St | Rossiter St | Lansdowne St | Asphalt | Yes | 2021-07-26 14:07 | 2021-07-27 17:57 | 2021-08-03 15:51 |  | 2021-09-15 15:47 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 15:19 |  | yes | no | no
483 | 16324098200606382005805 | 4 | McCormick St | S Harper Ave | Sanilac St | Asphalt | Yes | 2021-07-26 15:03 | 2021-07-27 18:45 | 2021-08-03 12:29 |  | 2021-09-15 16:02 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 16:12 |  | yes | no | no
464 | 16324098200580582005468 | 4 | McCormick St | Sanilac St | Duprey St | Asphalt | Yes | 2021-07-26 15:03 | 2021-07-27 18:08 | 2021-08-03 12:47 |  | 2021-09-15 16:01 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 16:21 |  | yes | no | no
943 | 15914028201068482010427 | 4 | Minden St | Algonac St | Elmo St | Asphalt | Yes | 2021-08-04 14:34 | 2021-08-17 15:07 | 2021-08-19 18:37 |  | 2021-09-10 13:13 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 15:09 |  | yes | no | no
2478 | 15914028201042782009987 | 4 | Minden St | Elmo St | Gunston St | Asphalt | Yes | 2021-09-09 18:16 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-09 18:16 |  | yes | no | no
2479 | 15914028201042782009987 | 4 | Minden St | Elmo St | Gunston St | Asphalt | Yes | 2021-08-04 14:33 | 2021-08-30 19:30 | 2021-09-01 16:12 |  | 2021-09-10 13:12 | 2021-09-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-05 15:51 |  | yes | no | no
2440 | 16338038200931982009052 | 4 | Mogul St | Duchess St | Lannette St & Hayes St | Asphalt | Yes | 2021-07-27 15:35 | 2021-08-02 12:49 | 2021-08-05 12:09 |  | 2021-09-14 19:18 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:21 |  | yes | no | no
836 | 16338038200969982009319 | 4 | Mogul St | Whitehill St | Duchess St | Asphalt | Yes | 2021-07-27 15:34 | 2021-08-02 12:38 | 2021-08-04 21:49 |  | 2021-09-14 19:20 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:17 |  | yes | no | no
781 | 15914048200899482008768 | 4 | Nashville St | Bradford St | Devon St | Asphalt | Yes | 2021-07-23 14:20 | 2021-07-30 14:35 | 2021-08-04 21:42 |  | 2021-09-10 13:04 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 12:38 |  | yes | no | no
914 | 15914048201037782010129 | 4 | Nashville St | Conner St | Algonac St | Asphalt | Yes | 2021-07-23 14:58 | 2021-07-30 12:49 | 2021-08-04 18:49 |  | 2021-09-10 12:56 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 11:22 |  | yes | no | no
2466 | 15914048200984082009442 | 4 | Nashville St | Elmo St | Gunston St | Asphalt | Yes | 2021-07-23 14:55 | 2021-07-30 13:19 | 2021-08-04 20:01 |  | 2021-09-10 12:58 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 11:36 |  | yes | no | no
2467 | 15914048200984082009442 | 4 | Nashville St | Elmo St | Gunston St | Asphalt | Yes | 2021-07-23 14:53 | 2021-07-30 13:52 | 2021-08-04 20:20 |  | 2021-09-10 12:59 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 11:36 |  | yes | no | no
2448 | 15914048200944282008994 | 4 | Nashville St | Gunston St | Bradford St | Asphalt | Yes | 2021-07-23 14:29 | 2021-07-30 14:07 | 2021-08-04 20:50 |  | 2021-09-10 13:01 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 12:06 |  | yes | no | no
2449 | 15914048200944282008994 | 4 | Nashville St | Gunston St | Bradford St | Asphalt | Yes | 2021-07-23 14:26 | 2021-08-17 13:13 | 2021-08-19 16:11 |  | 2021-09-10 13:03 | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 12:06 |  | yes | no | no
5390 | 16347058202944582027900 | 4 | Navahoe St | Freud St | E Jefferson Ave | Asphalt | Yes Round 3 | 2021-10-05 17:50 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 17:50 |  |  |  | Yes
5391 | 16347058202944582027900 | 4 | Navahoe St | Freud St | E Jefferson Ave | Asphalt | Yes Round 3 | 2021-10-05 17:43 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 17:43 |  |  |  | Yes
5392 | 16347058202944582027900 | 4 | Navahoe St | Freud St | E Jefferson Ave | Asphalt | Yes Round 3 | 2021-10-05 17:42 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 17:42 |  |  |  | Yes
5393 | 16347058202944582027900 | 4 | Navahoe St | Freud St | E Jefferson Ave | Asphalt | Yes Round 3 | 2021-10-05 17:22 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 17:22 |  |  |  | Yes
794 | 16353088200947282008894 | 4 | Neff Ave | Berden St | Minerva St | Asphalt | Yes | 2021-07-27 12:51 | 2021-08-11 16:24 | 2021-08-13 15:56 |  | 2021-10-06 18:18 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 17:10 |  | yes | no | no
893 | 16353088201056882009972 | 4 | Neff Ave | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-27 12:47 | 2021-08-11 17:58 | 2021-08-13 16:27 |  | 2021-10-06 18:10 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 17:05 |  | yes | no | no
851 | 16353088200997282009472 | 4 | Neff Ave | Linville St | Berden St | Asphalt | Yes | 2021-07-27 12:49 | 2021-08-11 16:56 | 2021-08-13 16:14 |  | 2021-10-06 18:10 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 17:09 |  | yes | no | no
736 | 16353088200889482008411 | 4 | Neff Ave | Minerva St | Chester St | Asphalt | Yes | 2021-07-27 12:53 | 2021-08-11 15:59 | 2021-08-13 15:56 |  | 2021-10-06 18:20 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 17:13 |  | yes | no | no
1246 | 16385048201634082015844 | 4 | Norcross St | Hern St | E I 94 Service Drive | Asphalt | Yes | 2021-08-04 13:42 | 2021-08-05 16:08 | 2021-08-13 16:15 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 19:06 |  | yes | no | no
1263 | 16385048201691682016340 | 4 | Norcross St | Olga St | Hern St | Asphalt | Yes | 2021-08-04 14:14 | 2021-08-05 15:39 | 2021-08-13 17:42 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 19:06 |  | yes | no | no
4483 | 16404108201111882010490 | 4 | Oldtown St | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-10-05 14:40 | 2021-10-06 21:32 | 2021-10-11 16:28 |  |  |  | HMA |  |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 14:40 |  | yes | No | no
4484 | 16404108201049082009182 | 4 | Oldtown St | Linville St | Harper Ave | Asphalt | Yes | 2021-10-05 14:40 | 2021-10-07 19:03 | 2021-10-11 15:53 |  |  |  | HMA |  |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 14:40 |  | yes | No | no
4485 | 16404108201049082009182 | 4 | Oldtown St | Linville St | Harper Ave | Asphalt | Yes | 2021-10-05 14:19 | 2021-10-06 20:30 | 2021-10-11 15:03 |  |  |  | HMA |  |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 14:18 |  | yes | No | no
4486 | 16404108201049082009182 | 4 | Oldtown St | Linville St | Harper Ave | Asphalt | Yes | 2021-10-05 14:28 | 2021-10-06 19:56 | 2021-10-11 14:55 |  |  |  | HMA |  |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 14:28 |  | yes | No | no
365 | 47000448200458982004562 | 4 | Park Grove St | Salter St | Morang Dr | Asphalt | Yes | 2021-07-27 18:49 | 2021-07-29 16:46 | 2021-08-02 15:41 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:53 |  | yes | no | no
3799 | 16331088200449982003254 | 4 | Payton St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:11 | 2021-07-29 15:48 | 2021-08-02 16:22 |  | 2021-09-15 18:38 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:32 |  | yes | no | no
3800 | 16331088200449982003254 | 4 | Payton St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:11 | 2021-07-29 15:17 | 2021-08-02 16:22 |  | 2021-09-15 18:40 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:38 |  | yes | no | no
3801 | 16331088200449982003254 | 4 | Payton St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:11 | 2021-07-29 14:53 | 2021-08-02 16:22 |  | 2021-09-15 18:43 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:44 |  | yes | no | no
3841 | 16330028200672882005500 | 4 | Peerless St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:59 | 2021-07-27 20:28 | 2021-08-05 15:33 |  | 2021-09-15 20:22 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 12:27 |  | yes | no | no
3842 | 16330028200672882005500 | 4 | Peerless St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:59 | 2021-07-27 20:51 | 2021-08-05 15:46 |  | 2021-09-15 20:22 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 12:32 |  | yes | no | no
3843 | 16330028200672882005500 | 4 | Peerless St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 15:59 | 2021-07-27 20:58 | 2021-08-05 16:02 |  | 2021-09-15 20:28 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 12:39 |  | yes | no | no
397 | 16330028200524482004993 | 4 | Peerless St | McCormick St | Peerless Ave & Kingsville Ave | Asphalt | Yes | 2021-07-26 14:46 | 2021-07-27 16:55 | 2021-08-03 13:11 |  | 2021-09-15 16:00 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-26 16:24 |  | yes | no | no
594 | 16330028200731182006728 | 4 | Peerless St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 15:58 | 2021-07-28 14:38 | 2021-08-05 15:20 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 12:22 |  | yes | no | no
1556 | 16344038202087082020410 | 4 | Pennsylvania St | Barker Ave | Chapin St | Asphalt | Yes | 2021-07-23 13:17 | 2021-08-16 14:06 | 2021-08-17 21:08 |  |  | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:18 |  | yes | no | no
2714 | 16344038202041082019539 | 4 | Pennsylvania St | Chapin St | Shoemaker St | Asphalt | Yes | 2021-07-23 13:15 | 2021-08-16 14:40 | 2021-08-18 15:43 |  |  | 2021-08-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:22 |  | yes | no | no
2715 | 16344038202041082019539 | 4 | Pennsylvania St | Chapin St | Shoemaker St | Asphalt | Yes | 2021-07-23 13:08 | 2021-08-16 14:56 | 2021-08-18 15:43 |  |  | 2021-08-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:22 |  | yes | no | no
3074 | 16344038202234382021339 | 4 | Pennsylvania St | E Warren Ave | Moffat St | Asphalt | Yes | 2021-07-23 13:20 | 2021-08-16 13:06 | 2021-08-17 20:42 |  |  | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:15 |  | yes | no | no
3075 | 16344038202234382021339 | 4 | Pennsylvania St | E Warren Ave | Moffat St | Asphalt | Yes | 2021-07-23 13:19 | 2021-08-16 13:28 | 2021-08-17 20:54 |  |  | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 17:15 |  | yes | no | no
1715 | 17145108203019382029848 | 4 | Piper Blvd | Avondale St | Averhill Ct | Asphalt | Yes | 2021-10-05 18:32 | [5 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 18:32 |  | yes | no | no
1736 | 17145108203080682030193 | 4 | Piper Blvd | Korte St | Avondale St | Asphalt | Yes | 2021-10-05 18:32 | [5 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 18:32 |  | yes | no | no
3448 | 17145108203179682030806 | 4 | Piper Blvd | Scripps St | Korte St | Asphalt | Yes | 2021-10-05 18:33 | [5 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 18:32 |  | yes | no | no
3449 | 17145108203179682030806 | 4 | Piper Blvd | Scripps St | Korte St | Asphalt | Yes | 2021-10-05 18:33 | [5 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-10-05 18:33 |  | yes | no | no
810 | 16323108200916782009041 | 4 | Portlance St | Canonbury St | Algonac St | Asphalt | Yes | 2021-07-23 13:42 | 2021-07-30 11:40 | 2021-08-03 20:15 |  | 2021-09-08 15:23 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:50 |  | yes | no | no
762 | 16323108200872682008390 | 4 | Portlance St | Elmo St | E McNichols Rd & Hoover St | Asphalt | Yes | 2021-07-23 13:46 | 2021-07-28 17:06 | 2021-08-03 21:05 |  | 2021-09-08 15:22 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:59 |  | yes | no | no
778 | 16323108200891282008726 | 4 | Portlance St | Simms St | Elmo St | Asphalt | Yes | 2021-07-23 13:44 | 2021-07-30 12:05 | 2021-08-03 20:48 |  | 2021-09-08 15:22 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:59 |  | yes | no | no
2531 | 15880048201199982011672 | 4 | Promenade Ave | Annsbury Ave | Park Dr | Asphalt | Yes | 2021-07-23 16:44 | 2021-08-28 19:16 | 2021-09-01 15:56 |  | 2021-09-10 17:27 | 2021-09-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 18:20 |  | yes | no | no
2566 | 15880048201276282012355 | 4 | Promenade Ave | Barrett St | Roseberry St | Asphalt | Yes | 2021-07-31 14:18 | 2021-08-02 18:45 | 2021-08-06 19:40 |  | 2021-09-10 16:54 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 13:26 |  | yes | no | no
2567 | 15880048201276282012355 | 4 | Promenade Ave | Barrett St | Roseberry St | Asphalt | Yes | 2021-07-31 14:18 | 2021-08-02 18:21 | 2021-08-06 19:18 |  | 2021-09-10 16:54 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 13:34 |  | yes | no | no
2474 | 47104768209178782010379 | 4 | Promenade Ave | Chalmers St | Queen St | Asphalt | Yes | 2021-07-28 17:58 | 2021-08-02 14:55 | 2021-08-11 13:13 |  | 2021-09-14 16:44 | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:08 |  | yes | no | no
2475 | 47104768209178782010379 | 4 | Promenade Ave | Chalmers St | Queen St | Asphalt | Yes | 2021-07-28 17:57 | 2021-08-02 14:10 | 2021-08-11 19:06 |  | 2021-09-14 16:42 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:14 |  | yes | no | no
3932 | 15880048201375182013193 | 4 | Promenade Ave | Conner St | Gunston Ave | Asphalt | Yes | 2021-07-31 12:05 | 2021-08-17 16:58 | 2021-08-19 19:09 |  | 2021-09-10 16:46 | 2021-08-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 12:26 |  | yes | no | no
3933 | 15880048201375182013193 | 4 | Promenade Ave | Conner St | Gunston Ave | Asphalt | Yes | 2021-07-31 12:05 | 2021-08-02 20:39 | 2021-08-09 11:47 |  | 2021-09-10 16:47 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 12:40 |  | yes | no | no
2485 | 15880048201100382010640 | 4 | Promenade Ave | Coplin St | Newport St | Asphalt | Yes | 2021-07-23 16:18 | 2021-08-02 15:38 | 2021-08-06 14:39 |  | 2021-09-14 15:04 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 17:44 |  | yes | no | no
2488 | 15880048201136082011003 | 4 | Promenade Ave | Dickerson St | Coplin St | Asphalt | Yes | 2021-07-23 16:39 | 2021-08-02 17:52 | 2021-08-06 15:07 |  | 2021-09-14 15:07 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 17:58 |  | yes | no | no
2489 | 15880048201136082011003 | 4 | Promenade Ave | Dickerson St | Coplin St | Asphalt | Yes | 2021-07-23 16:38 | 2021-08-02 15:47 | 2021-08-06 14:56 |  | 2021-09-14 15:05 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 17:57 |  | yes | no | no
2586 | 15880048201319382012762 | 4 | Promenade Ave | Gunston Ave | Barrett St | Asphalt | Yes | 2021-07-31 14:18 | 2021-08-02 20:22 | 2021-08-06 20:52 |  | 2021-09-10 16:50 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 12:56 |  | yes | no | no
2587 | 15880048201319382012762 | 4 | Promenade Ave | Gunston Ave | Barrett St | Asphalt | Yes | 2021-07-31 14:18 | 2021-08-02 19:52 | 2021-08-06 20:31 |  | 2021-09-10 18:43 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 13:05 |  | yes | no | no
2481 | 15880048201064082010349 | 4 | Promenade Ave | Newport St | Chalmers St | Asphalt | Yes | 2021-07-23 16:16 | 2021-08-02 15:17 | 2021-08-06 14:39 |  | 2021-09-14 15:02 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 17:27 |  | yes | no | no
2509 | 15880048201167282011360 | 4 | Promenade Ave | Park Dr | Dickerson St | Asphalt | Yes | 2021-07-23 16:41 | 2021-08-02 17:53 | 2021-08-06 15:52 |  | 2021-09-10 17:28 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 18:12 |  | yes | no | no
900 | 47104768201037982010446 | 4 | Promenade Ave | Queen St | Hayes St & Promenade St | Asphalt | Yes | 2021-07-28 17:55 | 2021-08-02 13:11 | 2021-08-11 18:41 |  | 2021-09-14 16:41 | 2021-08-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:17 |  | yes | no | no
2544 | 15880048201235582011999 | 4 | Promenade Ave | Roseberry St | Annsbury Ave | Asphalt | Yes | 2021-07-23 16:47 | 2021-08-02 17:57 | 2021-08-06 17:26 |  | 2021-09-10 17:26 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 18:35 |  | yes | no | no
2545 | 15880048201235582011999 | 4 | Promenade Ave | Roseberry St | Annsbury Ave | Asphalt | Yes | 2021-07-23 16:46 | 2021-08-02 17:56 | 2021-08-06 16:05 |  | 2021-09-10 17:26 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 18:35 |  | yes | no | no
930 | 47104768201063482010789 | 4 | Promenade St | Philip St | Manistique St | Asphalt | Yes | 2021-07-28 17:51 | 2021-08-02 14:25 | 2021-08-14 18:35 |  | 2021-09-14 16:38 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:23 |  | yes | no | no
915 | 47104768201044682010634 | 4 | Promenade St | Promenade Ave & Hayes St | Philip St | Asphalt | Yes | 2021-07-28 17:53 | 2021-08-02 13:30 | 2021-08-14 18:49 |  | 2021-09-14 16:39 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:20 |  | yes | no | no
3802 | 16331078200464382003382 | 4 | Riad St | Casino St | Moross Rd | Asphalt | Yes | 2021-09-09 12:48 | 2021-09-27 14:32 | 2021-09-29 13:46 | 2021-09-29 13:46 |  | 2021-09-29 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 12:48 |  | yes | no | no
3803 | 16331078200464382003382 | 4 | Riad St | Casino St | Moross Rd | Asphalt | Yes | 2021-09-09 12:45 | 2021-09-27 13:43 | 2021-09-29 13:34 | 2021-09-29 13:34 |  | 2021-09-29 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 12:44 |  | yes | no | no
3804 | 16331078200464382003382 | 4 | Riad St | Casino St | Moross Rd | Asphalt | Yes | 2021-09-09 12:31 | 2021-09-27 15:21 | 2021-09-29 13:19 | 2021-09-29 13:34 |  | 2021-09-29 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 12:31 |  | yes | no | no
415 | 16331078200526982004643 | 4 | Riad St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 18:12 | 2021-07-29 16:27 | 2021-08-02 16:40 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 14:09 |  | yes | no | no
669 | 17150048200807382007401 | 4 | Riad St | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-27 15:48 | 2021-07-30 17:24 | 2021-08-05 12:40 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:41 |  | yes | no | no
613 | 17150048200740182006764 | 4 | Riad St | Yorkshire Rd | Grayton St | Asphalt | Yes | 2021-07-27 15:49 | 2021-07-30 15:55 | 2021-08-05 12:41 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:46 |  | yes | no | no
3466 | 17145098203198882031012 | 4 | Riverside Dr | Scripps St | Korte St & Drexel St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
3467 | 17145098203198882031012 | 4 | Riverside Dr | Scripps St | Korte St & Drexel St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
4655 | 15883058200703782007014 | 4 | Rochelle St | Hayes St | Brock St | Asphalt | Yes Round 2 | 2021-09-09 13:38 | 2021-10-11 15:44 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-09 13:39 |  | no | yes | no
2497 | 15880078201141382011069 | 4 | Rosemary Ave | Annsbury Ave | Park Dr | Asphalt | Yes | 2021-08-10 13:57 | 2021-08-16 19:03 | 2021-08-18 17:19 |  | 2021-09-10 15:07 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 13:58 |  | yes | no | no
2536 | 15880078201209282011755 | 4 | Rosemary Ave | Barrett St | Roseberry St | Asphalt | Yes | 2021-08-10 12:51 | 2021-08-16 17:10 | 2021-08-18 16:24 |  | 2021-09-10 15:43 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 12:51 |  | yes | no | no
2537 | 15880078201209282011755 | 4 | Rosemary Ave | Barrett St | Roseberry St | Asphalt | Yes | 2021-08-10 12:51 | 2021-08-16 17:31 | 2021-08-18 16:35 |  | 2021-09-10 15:45 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 12:52 |  | yes | no | no
2477 | 15880078201036482010000 | 4 | Rosemary Ave | Coplin St | Newport St | Asphalt | Yes | 2021-08-10 16:00 | 2021-08-16 20:42 | 2021-08-19 13:04 |  | 2021-09-14 14:32 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 16:00 |  | yes | no | no
2482 | 15880078201070482010364 | 4 | Rosemary Ave | Dickerson St | Coplin St | Asphalt | Yes | 2021-08-10 15:26 | 2021-08-16 19:49 | 2021-08-19 12:35 |  | 2021-09-14 14:36 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 15:26 |  | yes | no | no
2483 | 15880078201070482010364 | 4 | Rosemary Ave | Dickerson St | Coplin St | Asphalt | Yes | 2021-08-10 15:28 | 2021-08-16 20:25 | 2021-08-19 12:48 |  | 2021-09-14 14:33 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 15:29 |  | yes | no | no
1047 | 15880078201261882012495 | 4 | Rosemary Ave | Gratiot Ave | Gunston Ave | Asphalt | Yes | 2021-08-10 11:49 | 2021-08-16 15:36 | 2021-08-18 15:44 |  | 2021-09-10 15:38 | 2021-08-27 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 11:49 |  | yes | no | no
2550 | 15880078201249582012092 | 4 | Rosemary Ave | Gunston Ave | Barrett St | Asphalt | Yes | 2021-08-10 12:09 | 2021-08-16 15:55 | 2021-08-18 15:59 |  | 2021-09-10 15:39 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 12:09 |  | yes | no | no
2551 | 15880078201249582012092 | 4 | Rosemary Ave | Gunston Ave | Barrett St | Asphalt | Yes | 2021-08-10 12:09 | 2021-08-16 16:56 | 2021-08-18 16:24 |  | 2021-09-10 15:41 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 12:09 |  | yes | no | no
2469 | 15880078201000082009687 | 4 | Rosemary Ave | Newport St | Chalmers St | Asphalt | Yes | 2021-08-10 16:00 | 2021-08-16 21:10 | 2021-08-19 13:07 |  | 2021-09-14 14:31 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 16:00 |  | yes | no | no
959 | 15880078201106982010704 | 4 | Rosemary Ave | Park Dr | Dickerson St | Asphalt | Yes | 2021-08-10 14:52 | 2021-08-16 19:27 | 2021-08-19 12:14 |  | 2021-09-10 15:05 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 14:52 |  | yes | no | no
2510 | 15880078201175582011413 | 4 | Rosemary Ave | Roseberry St | Annsbury Ave | Asphalt | Yes | 2021-08-10 13:19 | 2021-08-16 17:58 | 2021-08-18 17:03 |  | 2021-09-10 15:11 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 13:19 |  | yes | no | no
2511 | 15880078201175582011413 | 4 | Rosemary Ave | Roseberry St | Annsbury Ave | Asphalt | Yes | 2021-08-10 13:57 | 2021-08-16 18:25 | 2021-08-18 17:03 |  | 2021-09-10 15:09 | 2021-08-21 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-08-10 13:57 |  | yes | no | no
1250 | 17154018201663982016455 | 4 | Rosewood St | Grayton St | Harvard Rd | Asphalt | Yes | 2021-09-10 13:28 | 2021-09-29 16:56 | 2021-10-01 16:38 | 2021-10-01 18:20 | 2021-10-07 20:56 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 13:27 |  | yes | no | no
1262 | 17154018201707182016922 | 4 | Rosewood St | Kensington Ave | Yorkshire Rd | Asphalt | Yes | 2021-09-10 13:22 | 2021-09-29 16:20 | 2021-10-01 16:39 | 2021-10-01 18:19 | 2021-10-09 17:47 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 13:21 |  | yes | no | no
3814 | 16331018200547282004244 | 4 | Rossiter St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 17:47 | 2021-07-28 19:27 | 2021-08-03 18:36 |  | 2021-09-15 19:26 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:39 |  | yes | no | no
3815 | 16331018200547282004244 | 4 | Rossiter St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 17:47 | 2021-07-28 18:44 | 2021-08-03 18:22 |  | 2021-09-15 19:27 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:39 |  | yes | no | no
3816 | 16331018200547282004244 | 4 | Rossiter St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 17:47 | 2021-07-28 18:44 | 2021-08-03 18:21 |  | 2021-09-15 19:28 | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:43 |  | yes | no | no
496 | 16331018200607182005472 | 4 | Rossiter St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 17:47 | 2021-07-28 18:16 | 2021-08-03 18:43 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:33 |  | yes | no | no
760 | 16331018200895082008320 | 4 | Rossiter St | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-26 18:55 | 2021-07-30 18:42 | 2021-08-03 19:23 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:15 |  | yes | no | no
692 | 16331018200832082007654 | 4 | Rossiter St | Yorkshire Rd | Grayton St | Asphalt | Yes | 2021-07-26 18:55 | 2021-07-30 18:26 | 2021-08-03 19:06 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:11 |  | yes | no | no
4521 | 16344088202310782022282 | 4 | Saint Clair St | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-09-07 20:54 | 2021-10-11 15:05 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 20:54 |  | yes | No | no
4522 | 16344088202310782022282 | 4 | Saint Clair St | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-09-07 21:12 | 2021-10-11 16:07 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:12 |  | yes | No | no
4523 | 16344088202228282021407 | 4 | Saint Clair St | E Forest Ave | E Warren Ave | Asphalt | Yes | 2021-09-07 21:26 | 2021-10-11 16:07 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:26 |  | yes | No | no
4524 | 16344088202228282021407 | 4 | Saint Clair St | E Forest Ave | E Warren Ave | Asphalt | Yes | 2021-09-07 21:26 | 2021-10-11 16:07 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:26 |  | yes | No | no
4525 | 16344088202140782019517 | 4 | Saint Clair St | E Warren Ave | Shoemaker St | Asphalt | Yes | 2021-09-07 21:55 | 2021-10-11 19:49 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:55 |  | yes | No | no
4526 | 16344088202140782019517 | 4 | Saint Clair St | E Warren Ave | Shoemaker St | Asphalt | Yes | 2021-09-07 21:55 | 2021-10-11 19:48 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:55 |  | yes | No | no
4527 | 16344088202140782019517 | 4 | Saint Clair St | E Warren Ave | Shoemaker St | Asphalt | Yes | 2021-09-07 21:55 | 2021-10-11 19:48 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:55 |  | yes | No | no
4528 | 16344088202140782019517 | 4 | Saint Clair St | E Warren Ave | Shoemaker St | Asphalt | Yes | 2021-09-07 21:54 | 2021-10-11 19:48 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:54 |  | yes | No | no
4529 | 16344088202140782019517 | 4 | Saint Clair St | E Warren Ave | Shoemaker St | Asphalt | Yes | 2021-09-07 21:37 | 2021-10-11 19:47 |  |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 21:37 |  | yes | No | no
2492 | 15881058201125882010836 | 4 | Saint Patrick St | Gunston St | Bradford St | Asphalt | Yes | [6 empty] | HMA | No |  |  |  | No | No | poor pavement |  |  | yes | no | no
2493 | 15881058201125882010836 | 4 | Saint Patrick St | Gunston St | Bradford St | Asphalt | Yes | [6 empty] | HMA | No |  |  |  | No | No | poor pavement |  |  | yes | no | no
5542 | 15881068201177882011440 | 4 | Sanford St | Conner St | Elmo St | Asphalt | Yes Round 3 | 2021-10-05 16:46 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 16:46 |  |  |  | Yes
5543 | 15881068201177882011440 | 4 | Sanford St | Conner St | Elmo St | Asphalt | Yes Round 3 | 2021-10-05 16:39 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 16:38 |  |  |  | Yes
5546 | 15881068201144082011021 | 4 | Sanford St | Elmo St | Gunston St | Asphalt | Yes Round 3 | 2021-10-05 16:36 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 16:36 |  |  |  | Yes
5547 | 15881068201144082011021 | 4 | Sanford St | Elmo St | Gunston St | Asphalt | Yes Round 3 | 2021-10-05 16:33 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-10-05 16:33 |  |  |  | Yes
291 | 47058328200350482003544 | 4 | Saratoga St | Morang Dr | Rex St | Asphalt | Yes | 2021-07-27 18:48 | 2021-07-29 19:11 | 2021-08-02 13:03 |  | 2021-09-15 17:02 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:10 |  | yes | no | no
281 | 47058328200352382003507 | 4 | Saratoga St | Redmond St | Kelly Rd | Asphalt | Yes | 2021-07-27 18:48 | 2021-07-29 17:31 | 2021-08-02 12:32 |  | 2021-09-15 16:47 | 2021-08-03 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 12:19 |  | yes | no | no
286 | 47058328200354482003523 | 4 | Saratoga St | Rex St | Redmond St | Asphalt | Yes | 2021-07-27 18:48 | 2021-07-29 17:58 | 2021-08-02 12:52 |  | 2021-09-15 17:00 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:15 |  | yes | no | no
1757 | 17145058203160082031453 | 4 | Scripps St | Eastlawn St | Newport St | Asphalt | Yes | [6 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  |  |  | yes | no | no
984 | 47103978201159982011025 | 4 | Somerset Ave | Berkshire St | Haverhill St | Asphalt | Yes | 2021-07-27 15:12 | 2021-07-31 17:25 | 2021-08-04 18:09 |  | 2021-09-14 19:40 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 17:34 |  | yes | no | no
4846 | 47053788201785282017339 | 4 | Somerset Ave | Bremen St | Waveney St | Asphalt | Yes Round 2 | 2021-09-10 14:52 | 2021-09-30 15:17 | 2021-10-05 16:13 |  | 2021-10-11 16:27 | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:52 |  | no | yes | no
2368 | 16330068200759682006769 | 4 | Somerset Ave | Britain St | Morang Dr | Asphalt | Yes | 2021-07-27 12:06 | 2021-07-31 12:28 | 2021-08-04 12:17 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:55 |  | yes | no | no
2369 | 16330068200759682006769 | 4 | Somerset Ave | Britain St | Morang Dr | Asphalt | Yes | 2021-07-27 12:06 | 2021-07-31 12:55 | 2021-08-04 12:36 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 17:01 |  | yes | no | no
1281 | 47053788201916382018566 | 4 | Somerset Ave | Brunswick St | Windsor St | Asphalt | Yes | 2021-10-11 21:56 | [5 empty] | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-10-11 21:56 |  | yes | no | no
5706 | 16330068200619882005009 | 4 | Somerset Ave | Casino St | Moross Rd | Asphalt | Yes Round 3 | 2021-09-30 19:32 | 2021-10-11 13:47 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-30 19:32 |  |  |  | Yes
5707 | 16330068200619882005009 | 4 | Somerset Ave | Casino St | Moross Rd | Asphalt | Yes Round 3 | 2021-09-30 19:32 | 2021-10-11 13:49 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-30 19:32 |  |  |  | Yes
5708 | 16330068200619882005009 | 4 | Somerset Ave | Casino St | Moross Rd | Asphalt | Yes Round 3 | 2021-09-30 19:32 | 2021-10-11 14:05 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-30 19:32 |  |  |  | Yes
1169 | 47053788201490082014230 | 4 | Somerset Ave | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 17:29 | 2021-08-02 18:23 | 2021-08-06 18:53 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 17:53 |  | yes | no | no
5548 | 47103978201102582010267 | 4 | Somerset Ave | Haverhill St | Courville St | Asphalt | Yes Round 3 | 2021-10-05 17:36 | 2021-10-09 18:47 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:35 |  |  |  | Yes
5549 | 47103978201102582010267 | 4 | Somerset Ave | Haverhill St | Courville St | Asphalt | Yes Round 3 | 2021-10-05 17:34 | 2021-10-09 18:17 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:34 |  |  |  | Yes
1282 | 47053788201951482019163 | 4 | Somerset Ave | Mack Ave | Brunswick St | Asphalt | Yes | 2021-10-11 22:02 | [5 empty] | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-10-11 22:02 |  | yes | no | no
545 | 16330068200676982006198 | 4 | Somerset Ave | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 17:16 | 2021-07-28 17:56 | 2021-08-04 12:43 |  |  | 2021-08-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:27 |  | yes | no | no
1123 | 47053788201423082013764 | 4 | Somerset Ave | Southampton St | E Outer Dr | Asphalt | Yes | 2021-07-27 17:31 | 2021-08-02 17:32 | 2021-08-07 13:37 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 18:04 |  | yes | no | no
4847 | 47053788201733982016723 | 4 | Somerset Ave | Waveney St | Munich St | Asphalt | Yes Round 2 | 2021-09-10 14:54 | 2021-09-30 15:51 | 2021-10-05 16:23 |  | 2021-10-11 16:30 | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 14:54 |  | no | yes | no
2450 | 16330068200968282008946 | 4 | Somerset Ave | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-27 11:40 | 2021-08-03 14:15 | 2021-08-04 18:23 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:17 |  | yes | no | no
2451 | 16330068200968282008946 | 4 | Somerset Ave | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-27 11:41 | 2021-07-31 11:45 | 2021-08-04 18:37 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:21 |  | yes | no | no
1279 | 47053788201856682017852 | 4 | Somerset Ave | Windsor St | Bremen St | Asphalt | Yes | 2021-10-11 21:54 | [5 empty] | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-10-11 21:53 |  | yes | no | no
754 | 16330068200894682008373 | 4 | Somerset Ave | Yorkshire Rd | Grayton St | Asphalt | Yes | 2021-07-27 12:05 | 2021-07-30 19:01 | 2021-08-04 18:49 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 11:28 |  | yes | no | no
5217 | 47053868203071182029717 | 4 | Tennessee St | Essex Ave | Freud St | Asphalt | Yes Round 2 | 2021-09-10 15:37 | 2021-10-04 13:23 | 2021-10-06 17:22 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:37 |  | no | yes | no
5218 | 47053868203071182029717 | 4 | Tennessee St | Essex Ave | Freud St | Asphalt | Yes Round 2 | 2021-09-10 15:39 | 2021-10-04 12:53 | 2021-10-06 17:35 |  |  | 2021-10-06 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 15:40 |  | no | yes | no
486 | 15884028200588882005869 | 4 | Troester St | Brock St | Salter St | Asphalt | Yes | 2021-07-27 18:49 | 2021-08-03 14:19 | 2021-08-16 14:02 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:41 |  | yes | no | no
2336 | 15884028200610182006062 | 4 | Troester St | Gratiot Ave | Grover St | Asphalt | Yes | 2021-07-28 18:08 | 2021-08-03 12:01 | 2021-08-16 16:42 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 18:51 |  | yes | no | no
2337 | 15884028200610182006062 | 4 | Troester St | Gratiot Ave | Grover St | Asphalt | Yes | 2021-07-28 18:07 | 2021-08-03 12:19 | 2021-08-16 15:17 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 18:46 |  | yes | no | no
504 | 15884028200606282006048 | 4 | Troester St | Grover St | Peoria St | Asphalt | Yes | 2021-07-28 18:04 | 2021-08-03 12:47 | 2021-08-16 14:49 |  |  | 2021-08-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 18:45 |  | yes | no | no
490 | 15884028200591082005888 | 4 | Troester St | Hayes St | Brock St | Asphalt | Yes | 2021-07-27 18:49 | 2021-08-17 20:48 | 2021-08-19 15:42 |  |  | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:46 |  | yes | no | no
4675 | 16329018200697982006456 | 4 | Tyrone St | Moross Rd | Kingsville Ave & Tyrone Ave | Asphalt | Yes Round 2 | 2021-09-09 19:10 | 2021-09-27 20:07 | 2021-09-29 15:57 |  |  | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-09 19:10 |  | no | yes | no
864 | 16386048201026282009665 | 4 | University Pl | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-27 12:40 | 2021-08-11 18:39 | 2021-08-16 13:50 |  | 2021-10-06 18:07 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 16:55 |  | yes | no | no
1018 | 16386048201248382011870 | 4 | University Pl | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-07-27 12:24 | 2021-08-13 14:14 | 2021-08-16 14:17 |  | 2021-10-06 15:47 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:16 |  | yes | no | no
990 | 16386048201187082011311 | 4 | University Pl | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-27 12:27 | 2021-08-13 13:29 | 2021-08-16 14:17 |  | 2021-10-06 15:43 | 2021-08-20 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:21 |  | yes | no | no
5651 | 16386048201131182010775 | 4 | University Pl | Frankfort St | Southampton St | Asphalt | Yes Round 3 | 2021-10-05 13:19 | 2021-10-06 16:36 | 2021-10-11 14:12 |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 13:19 |  |  |  | Yes
812 | 16386048200966582009050 | 4 | University Pl | Linville St | Berden St | Asphalt | Yes | 2021-07-27 12:42 | 2021-08-11 19:06 | 2021-08-16 13:36 |  | 2021-10-06 18:03 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 16:52 |  | yes | no | no
3943 | 16386048208403482013141 | 4 | University Pl | Mack Ave | Munich St | Asphalt | Yes | 2021-07-27 12:19 | 2021-08-13 15:21 | 2021-08-16 15:59 |  | 2021-10-06 15:52 | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-27 15:08 |  | yes | no | no
3944 | 16386048208403482013141 | 4 | University Pl | Mack Ave | Munich St | Asphalt | Yes | 2021-07-27 12:21 | 2021-08-28 14:38 | 2021-09-01 13:04 |  |  | 2021-09-02 04:00 | HMA | No |  | No conflict |  | No | Yes | Car | 2021-07-27 15:09 |  | yes | no | no
3945 | 16386048208403482013141 | 4 | University Pl | Mack Ave | Munich St | Asphalt | Yes | 2021-07-27 12:22 | 2021-08-13 14:40 | 2021-08-16 15:41 |  |  | 2021-08-19 04:00 | HMA | No |  | No conflict |  | No | Yes | Car | 2021-07-27 15:13 |  | yes | no | no
2649 | 16323038201425182013889 | 4 | Wade St | Annsbury Ave | Park Dr | Asphalt | Yes | 2021-08-04 13:36 | 2021-08-05 14:49 | 2021-08-09 20:32 |  | 2021-09-14 15:48 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-04 17:00 |  | yes | no | no
1220 | 16323038201574282015437 | 4 | Wade St | Conner St | Gunston Ave | Asphalt | Yes | 2021-09-09 17:24 | 2021-10-04 18:55 | 2021-10-09 14:21 |  |  | 2021-10-08 04:00 | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-09 17:24 |  | yes | no | no
1172 | 17154038201501582014874 | 4 | Waveney St | Grayton St | Harvard Rd | Asphalt | Yes | 2021-07-31 17:33 | 2021-08-07 13:18 | 2021-08-10 20:21 |  | 2021-10-07 18:46 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 15:40 |  | yes | no | no
1196 | 17154038201546382015324 | 4 | Waveney St | Kensington Ave | Yorkshire Rd | Asphalt | Yes | 2021-07-31 18:31 | 2021-08-05 16:00 | 2021-08-10 14:44 | 2021-10-09 17:57 | 2021-10-09 17:58 | 2021-08-11 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-02 18:43 |  | yes | no | no
1133 | 16398068201448982013840 | 4 | Wayburn St | E Outer Dr | Linville St | Asphalt | Yes | 2021-07-27 18:07 | 2021-08-02 16:59 | 2021-08-07 12:34 |  | 2021-10-11 22:05 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:42 |  | yes | no | no
1236 | 16398068201625882015648 | 4 | Wayburn St | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-07-27 18:03 | 2021-08-02 18:52 | 2021-08-06 19:12 |  | 2021-10-11 21:58 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:26 |  | yes | no | no
976 | 47103988201147982010747 | 4 | Wayburn St | Elmdale St | Berkshire St | Asphalt | Yes | 2021-08-04 13:19 | 2021-08-11 12:27 | 2021-08-14 19:11 |  | 2021-09-14 17:25 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 16:02 |  | yes | no | no
1037 | 47103988201269882012074 | 4 | Wayburn St | Evanston St | Wade St | Asphalt | Yes | 2021-08-04 13:14 | 2021-08-10 20:27 | 2021-08-16 12:27 |  | 2021-09-14 17:12 | 2021-08-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:49 |  | yes | no | no
1205 | 16398068201564882015109 | 4 | Wayburn St | Frankfort St | Southampton St | Asphalt | Yes | 2021-07-27 18:04 | 2021-08-02 18:26 | 2021-08-06 19:23 |  | 2021-10-11 21:59 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:21 |  | yes | no | no
1100 | 16398068201384082013478 | 4 | Wayburn St | Linville St | Hern Ave | Asphalt | Yes | 2021-07-27 18:09 | 2021-08-02 15:47 | 2021-08-07 12:36 |  | 2021-10-11 22:07 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:39 |  | yes | no | no
2710 | 16350048201905582018038 | 4 | Wayburn St | Lozier St | Waveney St | Asphalt | Yes | 2021-09-10 15:03 | 2021-10-01 15:11 | 2021-10-05 18:38 |  | 2021-10-11 20:29 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 15:03 |  | yes | no | no
2711 | 16350048201905582018038 | 4 | Wayburn St | Lozier St | Waveney St | Asphalt | Yes | 2021-09-10 15:00 | 2021-10-01 14:43 | 2021-10-05 18:26 |  | 2021-10-11 20:27 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 15:00 |  | yes | no | no
2712 | 16350048201996082019055 | 4 | Wayburn St | Mack Ave | Lozier St | Asphalt | Yes | 2021-09-10 15:08 | 2021-10-01 16:18 | 2021-10-05 20:10 |  | 2021-10-11 20:35 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 15:08 |  | yes | no | no
2713 | 16350048201996082019055 | 4 | Wayburn St | Mack Ave | Lozier St | Asphalt | Yes | 2021-09-10 15:06 | 2021-10-01 15:44 | 2021-10-05 18:51 |  | 2021-10-11 20:34 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 15:05 |  | yes | no | no
1185 | 16398068201510982014605 | 4 | Wayburn St | Southampton St | E Outer Dr | Asphalt | Yes | 2021-07-27 18:05 | 2021-08-02 17:26 | 2021-08-06 19:43 |  | 2021-10-11 22:03 | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 14:17 |  | yes | no | no
2690 | 16350048201717082088987 | 4 | Wayburn St | Voight St | E Warren Ave | Asphalt | Yes | 2021-09-21 19:47 | 2021-10-01 12:50 | 2021-10-05 17:50 |  | 2021-10-11 20:18 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 17:46 |  | yes | no | no
2691 | 16350048201717082088987 | 4 | Wayburn St | Voight St | E Warren Ave | Asphalt | Yes | 2021-09-21 19:56 | 2021-10-01 12:25 | 2021-10-05 17:44 |  | 2021-10-11 20:15 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 17:47 |  | yes | no | no
1006 | 47103988201207482011479 | 4 | Wayburn St | Wade St | Elmdale St | Asphalt | Yes | 2021-08-04 13:16 | 2021-08-10 20:54 | 2021-08-14 19:19 |  | 2021-09-14 17:13 | 2021-08-18 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 15:56 |  | yes | no | no
2704 | 16350048201803882017170 | 4 | Wayburn St | Waveney St | Voight St | Asphalt | Yes | 2021-09-21 17:32 | 2021-10-01 13:46 | 2021-10-05 18:12 |  | 2021-10-11 20:24 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 17:31 |  | yes | no | no
2705 | 16350048201803882017170 | 4 | Wayburn St | Waveney St | Voight St | Asphalt | Yes | 2021-09-21 17:32 | 2021-10-01 13:20 | 2021-10-05 18:03 |  | 2021-10-11 20:22 | 2021-10-06 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 17:32 |  | yes | no | no
739 | 17148068200883482008184 | 4 | Wayburn St | Whittier St | Yorkshire Rd | Asphalt | Yes | 2021-07-26 18:54 | 2021-07-30 18:23 | 2021-08-03 20:53 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:56 |  | yes | no | no
675 | 17148068200818482007515 | 4 | Wayburn St | Yorkshire Rd | Grayton St | Asphalt | Yes | 2021-07-26 18:55 | 2021-07-30 17:56 | 2021-08-03 20:53 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:05 |  | yes | no | no
2342 | 16331048200639882005640 | 4 | Whitehill St | Britain St | Morang Dr | Asphalt | Yes | 2021-07-26 18:24 | 2021-07-30 14:24 | 2021-08-02 21:27 |  |  | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:05 |  | yes | no | no
2343 | 16331048200639882005640 | 4 | Whitehill St | Britain St | Morang Dr | Asphalt | Yes | 2021-07-26 18:24 | 2021-07-30 13:55 | 2021-08-02 21:27 |  |  | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:01 |  | yes | no | no
3811 | 16331048200508782003776 | 4 | Whitehill St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:10 | 2021-07-28 19:50 | 2021-08-02 19:28 |  | 2021-09-15 19:17 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:52 |  | yes | no | no
3812 | 16331048200508782003776 | 4 | Whitehill St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:10 | 2021-07-28 20:47 | 2021-08-02 19:11 |  | 2021-09-15 19:18 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:52 |  | yes | no | no
3813 | 16331048200508782003776 | 4 | Whitehill St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 18:10 | 2021-07-28 20:13 | 2021-08-02 19:04 |  | 2021-09-15 19:20 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:49 |  | yes | no | no
2360 | 16331048200718482006398 | 4 | Whitehill St | Grayton St | Britain St | Asphalt | Yes | 2021-07-26 18:24 | 2021-07-30 15:22 | 2021-08-02 21:48 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:14 |  | yes | no | no
2361 | 16331048200718482006398 | 4 | Whitehill St | Grayton St | Britain St | Asphalt | Yes | 2021-07-26 18:24 | 2021-07-30 15:00 | 2021-08-02 21:35 |  |  | 2021-08-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 15:10 |  | yes | no | no
462 | 16331048200564082005087 | 4 | Whitehill St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 18:10 | 2021-07-28 19:41 | 2021-08-02 20:52 |  |  | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:53 |  | yes | no | no
5627 | 16331048200851982007894 | 4 | Whitehill St | Whittier St | Yorkshire Rd | Asphalt | Yes Round 3 | 2021-10-05 17:30 | [5 empty] | HMA | [5 empty] | Yes | Car | 2021-10-05 17:30 |  |  |  | Yes
5631 | 16331048200789482007184 | 4 | Whitehill St | Yorkshire Rd | Grayton St | Asphalt | Yes Round 3 | 2021-10-05 17:28 | 2021-10-11 15:06 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 17:28 |  |  |  | Yes
2494 | 15881018201129382010875 | 4 | Wilfred St | Gratiot Ave | Roseberry St | Asphalt | Yes | 2021-07-23 15:18 | 2021-07-30 19:52 | 2021-08-05 18:15 |  | 2021-09-10 14:29 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 14:33 |  | yes | no | no
2495 | 15881018201129382010875 | 4 | Wilfred St | Gratiot Ave | Roseberry St | Asphalt | Yes | 2021-07-23 15:22 | 2021-07-30 20:11 | 2021-08-05 19:08 |  | 2021-09-10 14:28 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-24 14:33 |  | yes | no | no
2582 | 16323098201312782012740 | 4 | Wilshire Dr | Barrett St | Roseberry St | Asphalt | Yes | 2021-07-31 15:03 | 2021-08-02 22:27 | 2021-08-09 13:47 |  | 2021-09-10 19:42 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:54 |  | yes | no | no
2583 | 16323098201312782012740 | 4 | Wilshire Dr | Barrett St | Roseberry St | Asphalt | Yes | 2021-07-31 15:03 | 2021-08-03 19:51 | 2021-08-09 14:24 |  | 2021-09-10 19:44 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:50 |  | yes | no | no
3940 | 16323098201403882013513 | 4 | Wilshire Dr | Conner St | Gunston Ave | Asphalt | Yes | 2021-07-31 14:46 | 2021-08-02 21:15 | 2021-08-09 12:44 |  | 2021-09-10 19:35 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 12:14 |  | yes | no | no
3941 | 16323098201403882013513 | 4 | Wilshire Dr | Conner St | Gunston Ave | Asphalt | Yes | 2021-07-31 14:47 | 2021-08-02 21:38 | 2021-08-09 13:00 |  | 2021-09-10 19:37 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 12:07 |  | yes | no | no
3942 | 16323098201403882013513 | 4 | Wilshire Dr | Conner St | Gunston Ave | Asphalt | Yes | 2021-07-31 15:03 | 2021-08-02 22:07 | 2021-08-09 13:12 |  | 2021-09-10 19:39 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 12:02 |  | yes | no | no
2506 | 16323098201167982011331 | 4 | Wilshire Dr | Dickerson St | Coplin St | Asphalt | Yes | 2021-07-31 15:43 | 2021-08-03 17:35 | 2021-08-09 16:17 |  | 2021-09-14 15:09 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:37 |  | yes | no | no
2507 | 16323098201167982011331 | 4 | Wilshire Dr | Dickerson St | Coplin St | Asphalt | Yes | 2021-07-31 15:43 | 2021-08-03 17:16 | 2021-08-09 16:37 |  | 2021-09-14 15:10 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:30 |  | yes | no | no
5648 | 16323098201199382011679 | 4 | Wilshire Dr | Park Dr | Dickerson St | Asphalt | Yes Round 3 | 2021-10-05 16:54 | 2021-10-11 18:41 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-10-05 16:54 |  |  |  | Yes
2564 | 16323098201274082012336 | 4 | Wilshire Dr | Roseberry St | Annsbury Ave | Asphalt | Yes | 2021-07-31 15:22 | 2021-08-03 19:20 | 2021-08-09 15:16 |  | 2021-09-10 19:46 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:46 |  | yes | no | no
2565 | 16323098201274082012336 | 4 | Wilshire Dr | Roseberry St | Annsbury Ave | Asphalt | Yes | 2021-07-31 15:22 | 2021-08-03 18:59 | 2021-08-09 15:26 |  | 2021-09-10 19:46 | 2021-08-11 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-08-02 11:42 |  | yes | no | no
809 | 16405038200963282009027 | 4 | Woodhall St | Berden St | Minerva St | Asphalt | Yes | 2021-07-27 12:57 | 2021-08-11 15:36 | 2021-08-13 15:31 |  | 2021-10-06 18:23 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 13:16 |  | yes | no | no
903 | 16405038201071482010146 | 4 | Woodhall St | Chandler Park Dr | Linville St | Asphalt | Yes | 2021-07-27 13:04 | 2021-08-11 14:23 | 2021-08-13 15:20 |  | 2021-10-06 18:26 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 13:12 |  | yes | no | no
863 | 16405038201014682009632 | 4 | Woodhall St | Linville St | Berden St | Asphalt | Yes | 2021-07-27 12:59 | 2021-08-11 15:09 | 2021-08-16 13:15 |  | 2021-10-06 18:23 | 2021-08-18 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-07-28 13:15 |  | yes | no | no
3838 | 16330038200660682005390 | 4 | Worden St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 16:46 | 2021-07-28 15:37 | 2021-08-05 13:51 |  | 2021-09-15 20:19 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 13:24 |  | yes | no | no
3839 | 16330038200660682005390 | 4 | Worden St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 16:46 | 2021-07-28 16:44 | 2021-08-05 13:51 |  | 2021-09-15 20:19 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 12:52 |  | yes | no | no
3840 | 16330038200660682005390 | 4 | Worden St | Casino St | Moross Rd | Asphalt | Yes | 2021-07-26 16:46 | 2021-07-28 17:05 | 2021-08-05 13:51 |  | 2021-09-15 20:16 | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 12:55 |  | yes | no | no
577 | 16330038200718082006606 | 4 | Worden St | Morang Dr | Casino St | Asphalt | Yes | 2021-07-26 16:46 | 2021-07-28 15:06 | 2021-08-05 15:03 |  |  | 2021-08-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 12:47 |  | yes | no | no
4807 | 16385108201176782011206 | 4 | Yorkshire Rd | Chandler Park Dr | Linville St | Asphalt | Yes Round 2 | 2021-09-10 12:58 | 2021-09-28 14:27 | 2021-09-29 17:19 |  | 2021-10-06 21:39 | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 12:58 |  | no | yes | no
1108 | 16385108201416182013537 | 4 | Yorkshire Rd | Cornwall St | E Warren Ave | Asphalt | Yes | 2021-09-21 13:51 | 2021-09-28 15:50 | 2021-09-29 18:55 | 2021-09-29 18:55 | 2021-10-09 18:07 | 2021-09-29 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 12:20 |  | yes | no | no
1075 | 16385108201353782012925 | 4 | Yorkshire Rd | E Warren Ave | Frankfort St | Asphalt | Yes | 2021-08-20 15:14 | 2021-08-28 17:13 | 2021-09-01 14:45 |  | 2021-10-06 22:00 | 2021-09-02 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 15:14 |  | yes | no | no
4810 | 16385108201292582012290 | 4 | Yorkshire Rd | Frankfort St | Southampton St | Asphalt | Yes Round 2 | 2021-09-10 13:11 | 2021-09-28 15:03 | 2021-09-29 16:50 |  | 2021-10-06 22:00 | 2021-09-29 04:00 | HMA | [5 empty] | Yes |  | 2021-09-10 13:11 |  | no | yes | no
642 | 16324058200775182007574 | 4 | Yorkshire Rd | Laing St | Duchess St | Asphalt | Yes | 2021-07-27 15:49 | 2021-07-30 17:45 | 2021-08-02 21:48 |  |  | 2021-08-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-27 16:36 |  | yes | no | no
952 | 16385108201120682010603 | 4 | Yorkshire Rd | Linville St | Berden St | Asphalt | Yes | 2021-07-27 15:30 | 2021-08-07 12:35 | 2021-08-11 18:28 |  | 2021-10-06 20:16 | 2021-08-18 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-29 15:26 |  | yes | no | no
2696 | 16385108201769382016922 | 4 | Yorkshire Rd | Mack Ave | Rosewood St | Asphalt | Yes | 2021-09-21 13:39 | 2021-09-28 20:37 | 2021-10-01 17:02 | 2021-10-01 18:19 | 2021-10-09 17:38 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 13:39 |  | yes | no | no
2697 | 16385108201769382016922 | 4 | Yorkshire Rd | Mack Ave | Rosewood St | Asphalt | Yes | 2021-09-21 13:30 | 2021-09-29 13:42 | 2021-10-01 17:04 | 2021-10-01 18:19 | 2021-10-09 17:40 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 13:29 |  | yes | no | no
2684 | 16385108201692282016072 | 4 | Yorkshire Rd | Rosewood St | Wallingford St | Asphalt | Yes | 2021-09-21 13:21 | 2021-09-29 15:18 | 2021-10-01 18:19 | 2021-10-01 18:19 | 2021-10-09 17:47 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 13:21 |  | yes | no | no
2685 | 16385108201692282016072 | 4 | Yorkshire Rd | Rosewood St | Wallingford St | Asphalt | Yes | 2021-09-21 13:43 | 2021-09-29 15:08 | 2021-10-01 18:39 | 2021-10-01 18:39 | 2021-10-09 17:48 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 12:58 |  | yes | no | no
2674 | 16385108201607282015324 | 4 | Yorkshire Rd | Wallingford St | Waveney St | Asphalt | Yes | 2021-09-21 13:45 | 2021-09-29 17:57 | 2021-10-01 18:39 | 2021-10-01 18:39 | 2021-10-09 17:56 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 12:48 |  | yes | no | no
2675 | 16385108201607282015324 | 4 | Yorkshire Rd | Wallingford St | Waveney St | Asphalt | Yes | 2021-09-21 13:47 | 2021-09-29 18:27 | 2021-10-01 18:51 | 2021-10-01 18:51 | 2021-10-09 17:57 | 2021-10-02 04:00 | HMA | No | Coordinate with DTE GRP |  | Resurfacing Completed | Yes | Yes |  | 2021-09-21 12:35 |  | yes | no | no
5718 | 16385108201532482014161 | 4 | Yorkshire Rd | Waveney St | Cornwall St | Asphalt | Yes Round 3 | 2021-09-28 20:54 | 2021-10-07 15:09 | 2021-10-11 18:53 |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-28 20:54 |  |  |  | Yes
5719 | 16385108201532482014161 | 4 | Yorkshire Rd | Waveney St | Cornwall St | Asphalt | Yes Round 3 | 2021-09-28 21:03 | 2021-10-07 15:09 | 2021-10-11 18:02 |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-28 21:03 |  |  |  | Yes
5720 | 16385108201532482014161 | 4 | Yorkshire Rd | Waveney St | Cornwall St | Asphalt | Yes Round 3 | 2021-09-28 21:16 | 2021-10-07 15:36 | 2021-10-11 17:47 |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-28 21:15 |  |  |  | Yes
549 | 15883078200672582006693 | 4 | Young St | Hayes St | Brock St | Asphalt | Yes | 2021-07-27 18:50 | 2021-08-17 20:08 | 2021-08-19 15:00 |  |  | 2021-08-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-28 12:29 |  | yes | no | no
4718 | 15883078200676182006725 | 4 | Young St | Queen St | Hayes St | Asphalt | Yes Round 2 | 2021-09-09 14:02 | 2021-10-11 16:25 |  |  |  |  | HMA | [5 empty] | Yes |  | 2021-09-09 14:03 |  | no | yes | no
1808 | 16213028203243282031842 | 5 | 15th St | Marquette St | Ferry Park St | Asphalt | Yes | 2021-06-12 12:25 | 2021-07-19 19:55 | 2021-07-26 13:10 |  | 2021-08-15 17:40 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 15:28 |  | yes | no | no
1837 | 47057718203331682033504 | 5 | Agnes St | Parker St | Van Dyke St | Asphalt | Yes | 2021-06-21 14:54 | 2021-07-06 19:57 | 2021-07-09 12:08 |  | 2021-08-04 16:15 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 14:44 |  | yes | no | no
1823 | 47057718203310482033316 | 5 | Agnes St | Seminole St | Parker St | Asphalt | Yes | 2021-06-21 14:53 | 2021-07-06 19:34 | 2021-07-07 16:42 |  | 2021-08-04 15:43 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 14:44 |  | yes | no | no
3110 | 15980018202270582022202 | 5 | Alger St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-16 10:48 | 2021-06-23 15:02 | 2021-06-29 12:39 |  | 2021-08-17 14:03 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 16:39 |  | yes | no | no
3111 | 15980018202270582022202 | 5 | Alger St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-16 10:47 | 2021-06-23 15:25 | 2021-06-29 12:53 |  | 2021-08-17 14:06 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 16:39 |  | yes | no | no
1603 | 15980018202326882022900 | 5 | Alger St | John R St | Brush St | Asphalt | Yes | 2021-08-04 16:19 | 2021-08-24 19:20 | 2021-08-30 18:18 |  |  | 2021-08-31 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-04 16:19 |  | yes | no | no
3238 | 16259058202589482025326 | 5 | Atkinson St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 14:36 | 2021-07-13 20:31 | 2021-07-19 19:14 |  | 2021-08-13 18:38 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 13:23 |  | yes | no | no
3239 | 16259058202589482025326 | 5 | Atkinson St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 14:36 | 2021-07-13 20:54 | 2021-07-19 18:37 |  | 2021-08-13 18:36 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 13:23 |  | yes | no | no
3128 | 15979028202289082022438 | 5 | Atkinson St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 15:23 | 2021-06-22 16:41 | 2021-06-28 19:06 |  | 2021-08-16 15:03 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 16:05 |  | yes | no | no
3129 | 15979028202289082022438 | 5 | Atkinson St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 15:23 | 2021-06-22 15:31 | 2021-06-28 19:06 |  | 2021-08-16 15:04 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 16:05 |  | yes | no | no
3164 | 16259058202372482023353 | 5 | Atkinson St | Byron St | Hamilton | Asphalt | Yes | 2021-06-11 17:40 | 2021-06-30 15:10 | 2021-07-06 22:47 |  | 2021-08-13 18:28 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:33 |  | yes | no | no
3165 | 16259058202372482023353 | 5 | Atkinson St | Byron St | Hamilton | Asphalt | Yes | 2021-06-11 17:40 | 2021-06-30 15:35 | 2021-07-06 22:26 |  | 2021-08-13 18:27 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:33 |  | yes | no | no
3249 | 16259058202631182025894 | 5 | Atkinson St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-07-02 14:32 | 2021-07-13 20:06 | 2021-07-19 19:24 |  | 2021-08-13 18:41 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 17:24 |  | yes | no | no
3258 | 16259058202687882026311 | 5 | Atkinson St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 14:28 | 2021-07-13 19:42 | 2021-07-19 19:42 |  | 2021-08-13 18:44 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 17:01 |  | yes | no | no
3216 | 16259058202532682024412 | 5 | Atkinson St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 17:32 | 2021-06-30 12:44 | 2021-07-10 11:38 |  | 2021-08-13 18:34 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:51 |  | yes | no | no
3217 | 16259058202532682024412 | 5 | Atkinson St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 17:32 | 2021-06-30 13:09 | 2021-07-10 11:38 |  | 2021-08-13 18:33 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:51 |  | yes | no | no
3202 | 16259058202441282023724 | 5 | Atkinson St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:39 | 2021-06-30 14:03 | 2021-07-09 21:24 |  | 2021-08-13 18:31 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:42 |  | yes | no | no
3203 | 16259058202441282023724 | 5 | Atkinson St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:40 | 2021-06-30 14:40 | 2021-07-09 20:18 |  | 2021-08-13 18:31 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:42 |  | yes | no | no
1848 | 47057658203393782033344 | 5 | Baldwin St | Agnes St | Saint Paul St | Asphalt | Yes | 2021-06-21 15:33 | 2021-07-07 14:53 | 2021-07-09 12:50 |  | 2021-08-04 20:23 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 16:47 |  | yes | no | no
1597 | 15877088202337682023132 | 5 | Baldwin St | E Ferry St | E Palmer St | Asphalt | Yes | 2021-06-21 14:50 | 2021-07-01 12:48 | 2021-07-02 19:48 |  | 2021-08-04 23:36 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 14:50 |  | yes | no | no
1610 | 15877088202440182023844 | 5 | Baldwin St | Frederick St | E Kirby St | Asphalt | Yes | 2021-06-21 14:50 | 2021-07-01 12:17 | 2021-07-02 19:48 |  | 2021-08-04 23:32 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 14:50 |  | yes | no | no
1825 | 47057658203334482032714 | 5 | Baldwin St | Saint Paul St | Kercheval St | Asphalt | Yes | 2021-06-21 15:32 | 2021-07-07 15:19 | 2021-07-09 12:50 |  | 2021-08-04 20:27 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 17:01 |  | yes | no | no
3468 | 16392048203161482030701 | 5 | Beals St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 15:24 | 2021-07-08 18:09 | 2021-07-09 21:20 |  | 2021-08-03 21:16 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 13:44 |  | yes | no | no
3469 | 16392048203161482030701 | 5 | Beals St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 15:25 | 2021-07-08 17:46 | 2021-07-09 10:25 |  | 2021-08-03 21:15 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 13:44 |  | yes | no | no
1750 | 47055748203059582030266 | 5 | Beaubien St | E Ferry St | E Palmer St | Asphalt | Yes | 2021-06-16 10:51 | 2021-06-28 15:20 | 2021-07-01 16:21 |  | 2021-08-09 13:28 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:54 |  | yes | no | no
1740 | 47055748203026682029878 | 5 | Beaubien St | E Palmer St | Hendrie St | Asphalt | Yes | 2021-06-16 10:51 | 2021-06-28 14:53 | 2021-07-01 16:13 |  | 2021-08-09 13:31 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:53 |  | yes | no | no
1763 | 47055748203134882031034 | 5 | Beaubien St | Frederick Douglass Ave | E Kirby St | Asphalt | Yes | 2021-06-16 10:51 | 2021-06-28 15:55 | 2021-07-10 12:06 |  | 2021-08-09 13:13 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:54 |  | yes | no | no
1283 | 15879028202016682019537 | 5 | Belvidere St | Cairney St | Gratiot Ave | Asphalt | Yes | 2021-06-21 18:15 | 2021-07-06 13:31 | 2021-07-07 12:26 |  | 2021-08-03 12:44 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 18:15 |  | yes | no | no
2956 | 15977088201943182019040 | 5 | Burlingame St | 2nd Blvd | Woodward Ave & Englewood St | Asphalt | Yes | 2021-06-12 14:20 | 2021-06-19 13:08 | 2021-06-24 19:30 |  | 2021-08-16 13:22 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 13:25 |  | yes | no | no
2957 | 15977088201943182019040 | 5 | Burlingame St | 2nd Blvd | Woodward Ave & Englewood St | Asphalt | Yes | 2021-06-12 14:15 | 2021-06-19 12:42 | 2021-06-24 17:49 |  | 2021-08-16 13:18 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 13:26 |  | yes | no | no
2974 | 15977088201984682019431 | 5 | Burlingame St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 14:31 | 2021-06-19 14:14 | 2021-06-24 20:04 |  | 2021-08-16 13:23 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 12:55 |  | yes | no | no
2975 | 15977088201984682019431 | 5 | Burlingame St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 14:31 | 2021-06-19 13:25 | 2021-06-24 20:04 |  | 2021-08-16 13:22 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 12:55 |  | yes | no | no
2990 | 15977088208787082019846 | 5 | Burlingame St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 14:36 | 2021-06-21 14:53 | 2021-06-24 20:56 |  | 2021-08-16 13:25 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 12:46 |  | yes | no | no
2991 | 15977088208787082019846 | 5 | Burlingame St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 14:35 | 2021-06-21 15:16 | 2021-06-24 20:55 |  | 2021-08-16 13:25 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 12:47 |  | yes | no | no
3048 | 16261028202130982020935 | 5 | Burlingame St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 13:05 | 2021-06-24 20:18 | 2021-07-09 19:02 |  | 2021-08-13 13:46 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 13:01 |  | yes | no | no
3049 | 16261028202130982020935 | 5 | Burlingame St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 12:58 | 2021-06-24 20:51 | 2021-07-09 19:29 |  | 2021-08-13 13:14 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 13:01 |  | yes | no | no
3194 | 15779068202528282023737 | 5 | Burns St | Mack | E Warren Ave | Asphalt | Yes | 2021-06-21 13:57 | 2021-07-02 17:12 | 2021-07-06 18:08 |  | 2021-08-03 16:04 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:57 |  | yes | no | no
3195 | 15779068202528282023737 | 5 | Burns St | Mack | E Warren Ave | Asphalt | Yes | 2021-06-21 13:58 | 2021-07-02 17:33 | 2021-07-06 18:25 |  | 2021-08-03 16:03 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:58 |  | yes | no | no
1623 | 16254028202487182024246 | 5 | Byron St | Taylor St | Clairmount St | Asphalt | Yes | 2021-06-11 14:56 | 2021-06-30 16:10 | 2021-07-21 14:26 |  | 2021-08-14 12:37 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:43 |  | yes | no | no
5241 | 16342078203363682032883 | 5 | Canton St | Kercheval St | E Vernor Hwy | Asphalt | Yes Round 2 | 2021-09-10 16:13 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:13 |  | no | yes | no
5242 | 16342078203363682032883 | 5 | Canton St | Kercheval St | E Vernor Hwy | Asphalt | Yes Round 2 | 2021-09-10 16:09 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:10 |  | no | yes | no
3366 | 16175048202958882029152 | 5 | Carter St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 15:53 | 2021-07-12 18:50 | 2021-07-20 12:37 |  | 2021-08-14 18:09 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 15:14 |  | yes | no | no
3367 | 16175048202958882029152 | 5 | Carter St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 15:52 | 2021-07-12 19:56 | 2021-07-20 12:42 |  | 2021-08-14 18:09 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 15:14 |  | yes | no | no
1738 | 16175048202993682029588 | 5 | Carter St | Holmur St | Dexter Ave | Asphalt | Yes | 2021-07-02 15:57 | 2021-07-10 13:42 | 2021-07-14 16:36 |  | 2021-08-15 14:18 | 2021-07-14 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 15:02 |  | yes | no | no
3324 | 16175048202880182028423 | 5 | Carter St | Lawton St | Linwood St | Asphalt | Yes | 2021-07-02 15:32 | 2021-07-12 20:29 | 2021-07-21 12:03 |  | 2021-08-14 18:06 | 2021-07-21 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 17:50 |  | yes | no | no
3325 | 16175048202880182028423 | 5 | Carter St | Lawton St | Linwood St | Asphalt | Yes | 2021-07-02 15:30 | 2021-07-12 20:54 | 2021-07-21 12:37 |  | 2021-08-14 18:06 | 2021-07-21 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 17:25 |  | yes | no | no
3344 | 16175048202915282028801 | 5 | Carter St | Wildemere St | Lawton St | Asphalt | Yes | 2021-07-02 15:50 | 2021-07-12 19:57 | 2021-07-20 13:05 |  | 2021-08-14 18:08 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 18:39 |  | yes | no | no
3345 | 16175048202915282028801 | 5 | Carter St | Wildemere St | Lawton St | Asphalt | Yes | 2021-07-02 12:02 | 2021-07-12 20:10 | 2021-07-20 13:28 |  | 2021-08-14 18:07 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 18:38 |  | yes | no | no
3224 | 15980108202561382024846 | 5 | Chandler St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-14 15:39 | 2021-06-24 17:07 | 2021-06-30 12:49 |  | 2021-08-17 14:40 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 12:46 |  | yes | no | no
3225 | 15980108202561382024846 | 5 | Chandler St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-16 10:50 | 2021-06-24 17:34 | 2021-07-01 11:59 |  | 2021-08-17 14:40 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 12:46 |  | yes | no | no
1635 | 15980108202580882025613 | 5 | Chandler St | Brush St | Beaubien St | Asphalt | Yes | 2021-06-14 15:39 | 2021-06-24 15:59 | 2021-06-30 12:16 |  | 2021-08-17 14:41 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 12:46 |  | yes | no | no
1641 | 15980108202613882025808 | 5 | Chandler St | John R St | Brush St | Asphalt | Yes | 2021-06-14 15:22 | 2021-06-24 15:04 | 2021-06-30 12:16 |  | 2021-08-17 14:43 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 12:46 |  | yes | no | no
1649 | 15980108202654282026138 | 5 | Chandler St | Woodward Ave & Delaware St | John R St | Asphalt | Yes | 2021-06-14 12:07 | 2021-06-24 14:44 | 2021-06-29 19:08 |  | 2021-08-17 14:45 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 12:00 |  | yes | no | no
3410 | 16252068203040482029537 | 5 | Churchill St | W Grand Blvd | W Bethune St | Asphalt | Yes | 2021-06-12 16:46 | 2021-07-19 18:26 | 2021-07-21 20:29 |  | 2021-08-14 13:55 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 18:20 |  | yes | no | no
3411 | 16252068203040482029537 | 5 | Churchill St | W Grand Blvd | W Bethune St | Asphalt | Yes | 2021-06-12 16:46 | 2021-07-19 18:09 | 2021-07-21 19:58 |  | 2021-08-14 13:58 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 18:20 |  | yes | no | no
3312 | 16175088202867682028243 | 5 | Clairmount St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 16:19 | 2021-07-13 11:38 | 2021-07-15 13:01 |  | 2021-08-14 18:39 | 2021-07-16 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 12:14 |  | yes | no | no
3313 | 16175088202867682028243 | 5 | Clairmount St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 16:21 | 2021-07-13 11:59 | 2021-07-15 12:35 |  | 2021-08-14 18:40 | 2021-07-16 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 12:37 |  | yes | no | no
3302 | 16175088202824382027906 | 5 | Clairmount St | Wildemere St | Lawton St | Asphalt | Yes | 2021-07-02 16:34 | 2021-07-13 12:19 | 2021-07-15 13:11 |  | 2021-08-14 18:41 | 2021-07-15 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 12:52 |  | yes | no | no
3303 | 16175088202824382027906 | 5 | Clairmount St | Wildemere St | Lawton St | Asphalt | Yes | 2021-07-02 16:37 | 2021-07-13 12:40 | 2021-07-15 13:34 |  | 2021-08-14 18:41 | 2021-07-15 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 12:52 |  | yes | no | no
2924 | 16178018201842382017927 | 5 | Clements St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 14:20 | 2021-06-18 11:54 | 2021-06-23 14:53 |  | 2021-08-09 14:30 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 11:46 |  | yes | no | no
2925 | 16178018201842382017927 | 5 | Clements St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 14:20 | 2021-06-18 12:29 | 2021-06-23 15:47 |  | 2021-08-09 14:38 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 11:46 |  | yes | no | no
3114 | 16260068202257982022034 | 5 | Collingwood St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 13:59 | 2021-06-28 15:33 | 2021-07-02 16:00 |  | 2021-08-09 17:52 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 14:00 |  | yes | no | no
3115 | 16260068202257982022034 | 5 | Collingwood St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 14:00 | 2021-06-28 15:33 | 2021-07-02 16:18 |  | 2021-08-09 17:48 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 14:00 |  | yes | no | no
3002 | 15978028202042482020010 | 5 | Collingwood St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 15:12 | 2021-06-21 19:52 | 2021-06-28 15:05 |  | 2021-08-16 14:01 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:02 |  | yes | no | no
3003 | 15978028202042482020010 | 5 | Collingwood St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 15:12 | 2021-06-21 19:10 | 2021-06-28 14:54 |  | 2021-08-16 14:01 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:03 |  | yes | no | no
3020 | 15978028208787282020424 | 5 | Collingwood St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 15:12 | 2021-06-21 20:56 | 2021-06-28 16:05 |  | 2021-08-16 14:03 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:02 |  | yes | no | no
3021 | 15978028208787282020424 | 5 | Collingwood St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 15:12 | 2021-06-21 20:17 | 2021-06-28 15:20 |  | 2021-08-16 14:02 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:02 |  | yes | no | no
1595 | 16260068202274382022579 | 5 | Collingwood St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-11 13:59 | 2021-06-25 14:27 | 2021-07-02 15:37 |  | 2021-08-09 17:52 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 16:25 |  | yes | no | no
3502 | 15838108203171782031241 | 5 | Columbus St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-11 17:12 | 2021-07-12 16:23 | 2021-07-15 17:17 |  | 2021-08-15 15:50 | 2021-07-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:08 |  | yes | no | no
3503 | 15838108203171782031241 | 5 | Columbus St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-11 17:12 | 2021-07-12 15:51 | 2021-07-15 17:32 |  | 2021-08-15 15:50 | 2021-07-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:07 |  | yes | no | no
1796 | 15838108203206782031717 | 5 | Columbus St | Holmur St | Dexter Ave | Asphalt | Yes | 2021-06-11 17:11 | 2021-07-10 16:48 | 2021-07-14 20:21 |  | 2021-08-15 14:35 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 17:53 |  | yes | no | no
3450 | 15838108203084682030413 | 5 | Columbus St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-11 17:11 | 2021-07-12 18:19 | 2021-07-21 13:32 |  | 2021-08-15 15:47 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:02 |  | yes | no | no
3451 | 15838108203084682030413 | 5 | Columbus St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-11 17:11 | 2021-07-12 17:25 | 2021-07-21 13:10 |  | 2021-08-15 15:44 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:02 |  | yes | no | no
4327 | 15779018203558582034414 | 5 | Concord St | E Lafayette St | Saint Paul St | Asphalt | Yes | 2021-06-28 16:58 | 2021-07-08 20:14 | 2021-07-10 16:58 |  | 2021-08-04 20:13 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 17:45 |  | yes | no | no
4328 | 15779018203558582034414 | 5 | Concord St | E Lafayette St | Saint Paul St | Asphalt | Yes | 2021-06-28 16:57 | 2021-07-08 20:59 | 2021-07-10 16:29 |  | 2021-08-04 20:12 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 17:30 |  | yes | no | no
4329 | 15779018203558582034414 | 5 | Concord St | E Lafayette St | Saint Paul St | Asphalt | Yes | 2021-06-28 16:55 | 2021-07-09 11:52 | 2021-07-10 16:29 |  | 2021-08-04 20:10 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 17:01 |  | yes | no | no
3522 | 15779018203301082032139 | 5 | Concord St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-28 16:53 | 2021-07-09 14:29 | 2021-07-10 15:44 |  | 2021-08-04 20:06 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 17:00 |  | yes | no | no
3523 | 15779018203301082032139 | 5 | Concord St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-28 16:50 | 2021-07-09 14:05 | 2021-07-10 15:44 |  | 2021-08-04 20:05 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 17:00 |  | yes | no | no
1741 | 15779018203047382030075 | 5 | Concord St | Mack Ave | Pulford St | Asphalt | Yes | 2021-06-21 16:45 | 2021-06-29 13:37 | 2021-07-02 13:52 |  | 2021-08-04 20:00 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 15:45 |  | yes | no | no
1724 | 15779018203007582029651 | 5 | Concord St | Pulford St | Sylvester St | Asphalt | Yes | 2021-06-21 16:45 | 2021-06-29 14:23 | 2021-07-02 15:40 |  | 2021-08-04 19:59 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 15:46 |  | yes | no | no
1713 | 15779018202965182029203 | 5 | Concord St | Sylvester St | Stuart St | Asphalt | Yes | 2021-06-21 16:45 | 2021-06-29 14:57 | 2021-07-02 15:40 |  | 2021-08-04 19:57 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 15:49 |  | yes | no | no
3106 | 16177018202222182021617 | 5 | Cortland St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 15:56 | 2021-06-23 15:59 | 2021-07-01 12:23 |  | 2021-08-11 16:20 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 16:26 |  | yes | no | no
3107 | 16177018202222182021617 | 5 | Cortland St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 15:56 | 2021-06-23 15:25 | 2021-07-01 12:34 |  | 2021-08-11 16:17 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 16:26 |  | yes | no | no
3050 | 16177018202126682020906 | 5 | Cortland St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 16:04 | 2021-06-23 14:14 | 2021-07-01 13:45 |  | 2021-08-11 16:09 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:48 |  | yes | no | no
3051 | 16177018202126682020906 | 5 | Cortland St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 16:04 | 2021-06-23 13:49 | 2021-07-01 14:04 |  | 2021-08-11 16:11 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:48 |  | yes | no | no
3085 | 16177018202161782021266 | 5 | Cortland St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-10 16:04 | 2021-06-23 14:57 | 2021-07-01 13:06 |  | 2021-08-11 16:14 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 16:14 |  | yes | no | no
3168 | 15878078202455882023446 | 5 | Crane St | E Forest Ave | E Warren Ave | Asphalt | Yes | 2021-06-21 13:47 | 2021-07-06 12:16 | 2021-07-06 21:51 |  | 2021-08-03 16:00 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:47 |  | yes | no | no
3169 | 15878078202455882023446 | 5 | Crane St | E Forest Ave | E Warren Ave | Asphalt | Yes | 2021-06-21 13:47 | 2021-07-06 12:37 | 2021-07-07 12:10 |  | 2021-08-03 16:00 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:47 |  | yes | no | no
1669 | 47056208208743682027708 | 5 | Delaware St | Bethune Ct | 3rd St | Asphalt | Yes | 2021-09-30 14:01 | [5 empty] | HMA | No |  | Coordinate with DWSD - Water |  | Yes | Yes |  | 2021-09-30 14:01 |  | yes | no | no
1542 | 16311088202031382019674 | 5 | Dwyer St | Conant St | Farr St | Asphalt | Yes | 2021-06-10 13:48 | 2021-06-17 16:04 | 2021-06-22 22:55 |  | 2021-08-06 14:14 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 17:52 |  | yes | no | no
1530 | 16311088201967482019451 | 5 | Dwyer St | Farr St | Selkirk St | Asphalt | Yes | 2021-06-10 13:48 | 2021-06-17 16:32 | 2021-06-22 23:29 |  | 2021-08-06 14:13 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 17:44 |  | yes | no | no
1645 | 15981038202633082026061 | 5 | E Bethune St | Beaubien St | Saint Antoine St | Asphalt | Yes | 2021-06-14 14:55 | 2021-06-28 12:09 | 2021-07-01 15:22 |  | 2021-08-17 15:15 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 13:58 |  | yes | no | no
1648 | 15981038202655182026330 | 5 | E Bethune St | Brush St | Beaubien St | Asphalt | Yes | 2021-06-14 14:48 | 2021-06-28 11:40 | 2021-07-01 13:39 |  | 2021-08-17 15:12 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 13:58 |  | yes | no | no
1654 | 15981038202702382026551 | 5 | E Bethune St | John R St | Brush St | Asphalt | Yes | 2021-06-14 12:08 | 2021-06-24 21:00 | 2021-07-01 13:14 |  | 2021-08-17 15:11 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 13:58 |  | yes | no | no
5375 | 15981038202606182025823 | 5 | E Bethune St | Saint Antoine St | Oakland St | Asphalt | Yes Round 2 | 2021-09-10 16:45 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:45 |  | No | Yes | no
2982 | 47012798202010782019709 | 5 | E Boston Blvd | John R St | Brush St | Asphalt | Yes | 2021-06-14 17:07 | 2021-06-28 18:32 | 2021-06-29 12:18 |  | 2021-08-17 12:45 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 14:57 |  | yes | no | no
2983 | 47012798202010782019709 | 5 | E Boston Blvd | John R St | Brush St | Asphalt | Yes | 2021-06-14 17:07 | 2021-06-28 18:07 | 2021-06-29 12:10 |  | 2021-08-17 12:42 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 14:58 |  | yes | no | no
2984 | 47070828202016282019761 | 5 | E Boston Blvd | John R St | Brush St | Asphalt | Yes | 2021-06-14 17:05 | 2021-06-28 17:16 | 2021-06-28 21:53 |  | 2021-08-17 12:46 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 14:39 |  | yes | no | no
2985 | 47070828202016282019761 | 5 | E Boston Blvd | John R St | Brush St | Asphalt | Yes | 2021-06-14 17:06 | 2021-06-28 17:40 | 2021-06-28 21:53 |  | 2021-08-17 12:47 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 14:42 |  | yes | no | no
1739 | 15982038203026682030031 | 5 | E Palmer St | Beaubien St | Saint Antoine St | Asphalt | Yes | 2021-06-27 12:29 | 2021-06-28 14:34 | 2021-07-01 19:31 |  | 2021-08-06 16:22 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:53 |  | yes | no | no
1746 | 15982038203042982030266 | 5 | E Palmer St | Brush St | Beaubien St | Asphalt | Yes | 2021-06-27 13:03 | 2021-06-28 13:37 | 2021-07-01 19:10 |  | 2021-08-06 16:23 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:53 |  | yes | no | no
1755 | 15982038203079582030429 | 5 | E Palmer St | John R St | Brush St | Asphalt | Yes | 2021-06-16 10:51 | 2021-06-28 13:19 | 2021-07-01 16:36 |  | 2021-08-09 11:29 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:52 |  | yes | no | no
1613 | 15980048202390182023494 | 5 | E Philadelphia St | John R St | Brush St | Asphalt | Yes | 2021-06-16 10:48 | 2021-06-23 17:58 | 2021-06-29 13:45 |  | 2021-08-17 14:17 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 17:06 |  | yes | no | no
3228 | 16259068202551982024601 | 5 | Edison St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 13:25 | 2021-07-13 17:22 | 2021-07-19 18:22 |  | 2021-08-13 16:16 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 15:00 |  | yes | no | no
3229 | 16259068202551982024601 | 5 | Edison St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 13:27 | 2021-07-13 17:05 | 2021-07-19 18:18 |  | 2021-08-13 16:15 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 15:00 |  | yes | no | no
1606 | 16259068202339882023072 | 5 | Edison St | Byron St | S M 10 Service Drive | Asphalt | Yes | 2021-06-11 17:25 | 2021-06-29 19:00 | 2021-07-06 21:46 |  | 2021-08-13 16:05 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:50 |  | yes | no | no
3243 | 16259068202594182025519 | 5 | Edison St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-07-02 13:23 | 2021-07-13 18:28 | 2021-07-19 15:54 |  | 2021-08-13 16:18 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 15:32 |  | yes | no | no
3252 | 16259068202643582025941 | 5 | Edison St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 13:18 | 2021-07-13 19:11 | 2021-08-16 22:11 |  |  | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 15:59 |  | yes | no | no
3253 | 16259068202643582025941 | 5 | Edison St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 13:20 | 2021-07-14 18:55 | 2021-07-19 15:25 |  | 2021-08-13 16:19 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-13 18:54 |  | yes | no | no
3204 | 16259068202460182023848 | 5 | Edison St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-07-02 13:30 | 2021-07-13 16:34 | 2021-07-19 17:42 |  | 2021-08-13 16:13 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 14:38 |  | yes | no | no
3205 | 16259068202460182023848 | 5 | Edison St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-07-02 13:31 | 2021-07-13 16:23 | 2021-07-19 17:29 |  | 2021-08-13 16:11 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 14:38 |  | yes | no | no
3180 | 16259068202384882023398 | 5 | Edison St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:24 | 2021-06-30 12:04 | 2021-07-06 21:09 |  | 2021-08-13 16:08 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:14 |  | yes | no | no
3181 | 16259068202384882023398 | 5 | Edison St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:25 | 2021-06-30 11:38 | 2021-07-06 21:18 |  | 2021-08-13 16:07 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 13:14 |  | yes | no | no
3148 | 16176088202317582022653 | 5 | Elmhurst St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 19:02 | 2021-06-24 14:40 | 2021-07-09 14:22 |  | 2021-08-11 17:23 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:35 |  | yes | no | no
3149 | 16176088202317582022653 | 5 | Elmhurst St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 19:03 | 2021-06-24 14:17 | 2021-07-09 13:36 |  | 2021-08-11 17:21 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:35 |  | yes | no | no
3102 | 16176088202223782021738 | 5 | Elmhurst St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 19:12 | 2021-06-24 13:25 | 2021-07-09 13:12 |  | 2021-08-11 17:16 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:26 |  | yes | no | no
3103 | 16176088202223782021738 | 5 | Elmhurst St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 19:13 | 2021-06-24 12:56 | 2021-07-09 12:34 |  | 2021-08-11 17:13 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:25 |  | yes | no | no
3127 | 16176088202265382022237 | 5 | Elmhurst St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-10 19:03 | 2021-06-24 13:52 | 2021-07-09 13:19 |  | 2021-08-11 17:17 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:14 |  | yes | no | no
1854 | 47057498203411182033853 | 5 | Elmwood St | Hendricks St | Hunt St | Asphalt | Yes | 2021-06-21 17:37 | 2021-06-29 17:51 | 2021-07-02 13:14 |  | 2021-08-04 21:02 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes | Resolved | 2021-06-21 17:37 |  | yes | no | no
1683 | 47056928202834982028075 | 5 | Farnsworth St | Elmwood St | Moran St | Asphalt | Yes | 2021-06-21 15:49 | 2021-06-30 17:09 | 2021-07-01 21:38 |  | 2021-08-04 22:36 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 15:49 |  | yes | no | no
1533 | 16318088201977582019878 | 5 | Farr St | Klein St | Mount Elliott St | Asphalt | Yes | 2021-06-10 14:09 | 2021-06-17 15:03 | 2021-06-22 22:32 |  | 2021-08-06 14:09 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 18:10 |  | yes | no | no
2966 | 16318088201987882019843 | 5 | Farr St | Mount Elliott St | Consolidated Rail Corporation | Asphalt | Yes | 2021-06-10 13:38 | 2021-06-17 14:53 | 2021-06-22 22:19 |  | 2021-08-06 13:42 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 18:43 |  | yes | no | no
2967 | 16318088201987882019843 | 5 | Farr St | Mount Elliott St | Consolidated Rail Corporation | Asphalt | Yes | 2021-06-10 13:38 | 2021-06-17 14:09 | 2021-06-22 21:45 |  | 2021-08-06 13:41 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 18:43 |  | yes | no | no
1858 | 16342088203433182033759 | 5 | Field St | Agnes St | Saint Paul St | Asphalt | Yes | 2021-06-21 17:05 | 2021-07-07 18:29 | 2021-07-09 15:19 |  | 2021-08-04 20:19 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 16:19 |  | yes | no | no
3454 | 16342088203140482030539 | 5 | Field St | Charlevoix St | Goethe Ave | Asphalt | Yes | 2021-06-21 18:04 | 2021-07-07 20:56 | 2021-07-09 16:38 |  | 2021-08-03 21:36 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 13:18 |  | yes | no | no
3455 | 16342088203140482030539 | 5 | Field St | Charlevoix St | Goethe Ave | Asphalt | Yes | 2021-06-21 18:04 | 2021-07-08 14:41 | 2021-07-09 17:58 |  | 2021-08-03 21:37 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 13:18 |  | yes | no | no
3288 | 47057928202817882027337 | 5 | Field St | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-06-21 16:18 | 2021-06-30 18:15 | 2021-07-02 16:55 |  | 2021-08-03 18:38 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 12:11 |  | yes | no | no
3289 | 47057928202817882027337 | 5 | Field St | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-06-21 16:17 | 2021-06-30 17:49 | 2021-07-02 17:22 |  | 2021-08-03 18:37 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 12:11 |  | yes | no | no
1877 | 16342088203490582034331 | 5 | Field St | E Lafayette St | Agnes St | Asphalt | Yes | 2021-06-21 16:52 | 2021-07-07 18:00 | 2021-07-09 15:19 |  | 2021-08-04 20:16 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 16:35 |  | yes | no | no
3504 | 16342088203235782031404 | 5 | Field St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 17:55 | 2021-07-07 19:39 | 2021-07-09 16:38 |  | 2021-08-03 21:33 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 13:45 |  | yes | no | no
3505 | 16342088203235782031404 | 5 | Field St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 17:54 | 2021-07-07 20:20 | 2021-07-09 16:38 |  | 2021-08-03 21:35 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 13:44 |  | yes | no | no
3526 | 16342088203313082032357 | 5 | Field St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 17:33 | 2021-07-07 17:23 | 2021-07-09 15:53 |  | 2021-08-03 21:28 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 16:16 |  | yes | no | no
3527 | 16342088203313082032357 | 5 | Field St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 17:33 | 2021-07-07 19:10 | 2021-07-09 15:53 |  | 2021-08-03 21:31 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 16:16 |  | yes | no | no
1730 | 16342088203026082088784 | 5 | Field St | Preston St | Mack Ave | Asphalt | Yes | 2021-06-21 17:20 | 2021-07-08 15:26 | 2021-07-09 18:07 |  | 2021-08-03 19:07 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 13:05 |  | yes | no | no
1711 | 47057928202962282029094 | 5 | Field St | Pulford St | Sylvester St | Asphalt | Yes | 2021-06-21 17:19 | 2021-06-30 19:47 | 2021-07-02 16:21 |  | 2021-08-03 18:45 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 12:45 |  | yes | no | no
4318 | 47057928202909482028178 | 5 | Field St | Sylvester St | E Canfield St | Asphalt | Yes | 2021-06-21 17:05 | 2021-06-30 19:14 | 2021-07-02 16:21 |  | 2021-08-03 18:42 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 12:18 |  | yes | no | no
4320 | 47057928202909482028178 | 5 | Field St | Sylvester St | E Canfield St | Asphalt | Yes | 2021-06-21 16:46 | 2021-06-30 18:41 | 2021-07-02 16:54 |  | 2021-08-03 18:42 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 12:18 |  | yes | no | no
3218 | 15878068202597682024947 | 5 | Fischer Ave | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-06-21 14:13 | 2021-07-02 18:35 | 2021-07-06 21:31 |  | 2021-08-03 15:57 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 12:31 |  | yes | no | no
3219 | 15878068202597682024947 | 5 | Fischer Ave | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-06-21 14:14 | 2021-07-02 18:07 | 2021-07-06 21:37 |  | 2021-08-03 15:59 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 12:31 |  | yes | no | no
3280 | 15878068202815182027024 | 5 | Fischer Ave | Mack Ave | Sylvester St | Asphalt | Yes | 2021-06-21 14:08 | 2021-07-02 20:35 | 2021-07-06 19:08 |  | 2021-08-03 16:52 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:11 |  | yes | no | no
3281 | 15878068202815182027024 | 5 | Fischer Ave | Mack Ave | Sylvester St | Asphalt | Yes | 2021-06-21 14:10 | 2021-07-02 20:06 | 2021-07-06 20:18 |  | 2021-08-03 15:48 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:11 |  | yes | no | no
3246 | 15878068202702482025976 | 5 | Fischer Ave | Sylvester St | E Canfield St | Asphalt | Yes | 2021-06-21 14:11 | 2021-07-02 19:28 | 2021-07-06 20:56 |  | 2021-08-03 15:53 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 12:39 |  | yes | no | no
3247 | 15878068202702482025976 | 5 | Fischer Ave | Sylvester St | E Canfield St | Asphalt | Yes | 2021-06-21 14:12 | 2021-07-02 19:01 | 2021-07-06 21:16 |  | 2021-08-03 15:55 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 12:38 |  | yes | no | no
3072 | 16177038209029582021050 | 5 | Fullerton St | Dexter | Wildemere St | Asphalt | Yes | 2021-06-10 14:50 | 2021-06-21 13:55 | 2021-06-23 19:58 |  | 2021-08-11 15:04 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:39 |  | yes | no | no
3073 | 16177038209029582021050 | 5 | Fullerton St | Dexter | Wildemere St | Asphalt | Yes | 2021-06-10 14:50 | 2021-06-21 14:25 | 2021-06-23 19:59 |  | 2021-08-11 15:04 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:39 |  | yes | no | no
2978 | 16194068201986982019445 | 5 | Fullerton St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-10 22:56 | 2021-06-21 17:49 | 2021-06-24 14:43 |  | 2021-08-09 15:48 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:49 |  | yes | no | no
2979 | 16194068201986982019445 | 5 | Fullerton St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-10 22:57 | 2021-06-21 18:41 | 2021-06-24 15:01 |  | 2021-08-09 15:49 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:01 |  | yes | no | no
3022 | 16177038202073382087801 | 5 | Fullerton St | Lawton St | Linwood | Asphalt | Yes | 2021-06-10 15:01 | 2021-06-21 15:50 | 2021-06-24 13:25 |  | 2021-08-11 16:06 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:51 |  | yes | no | no
3023 | 16177038202073382087801 | 5 | Fullerton St | Lawton St | Linwood | Asphalt | Yes | 2021-06-10 15:01 | 2021-06-21 16:32 | 2021-06-24 13:44 |  | 2021-08-11 16:04 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:51 |  | yes | no | no
3004 | 16194068202033282019869 | 5 | Fullerton St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 22:56 | 2021-06-21 16:47 | 2021-06-24 14:34 |  | 2021-08-09 15:43 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:30 |  | yes | no | no
3005 | 16194068202033282019869 | 5 | Fullerton St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 22:56 | 2021-06-21 17:10 | 2021-06-24 14:35 |  | 2021-08-09 15:47 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:30 |  | yes | no | no
3045 | 16177038202105082020733 | 5 | Fullerton St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-10 15:01 | 2021-06-21 14:53 | 2021-06-23 23:18 |  | 2021-08-11 14:59 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:39 |  | yes | no | no
1733 | 47056828202995382030175 | 5 | Garfield St | Elmwood St | McDougall St | Asphalt | Yes | 2021-06-21 17:06 | 2021-06-30 15:35 | 2021-07-01 21:50 |  | 2021-08-04 22:49 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 17:06 |  | yes | no | no
3270 | 16259038202739982026816 | 5 | Gladstone St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 14:51 | 2021-07-14 21:57 | 2021-07-19 22:52 |  | 2021-08-14 15:36 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 14:58 |  | yes | no | no
3271 | 16259038202739982026816 | 5 | Gladstone St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 14:54 | 2021-07-14 22:12 | 2021-07-19 23:20 |  | 2021-08-14 15:36 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 14:57 |  | yes | no | no
3198 | 15979088202440382023709 | 5 | Gladstone St | 3rd St | 2nd Ave | Asphalt | Yes | 2021-06-12 15:22 | 2021-06-22 20:20 | 2021-06-28 20:27 |  | 2021-08-16 15:21 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 17:09 |  | yes | no | no
3199 | 15979088202440382023709 | 5 | Gladstone St | 3rd St | 2nd Ave | Asphalt | Yes | 2021-06-12 15:22 | 2021-06-22 17:19 | 2021-06-28 20:07 |  | 2021-08-16 15:18 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 17:09 |  | yes | no | no
3354 | 16175058202933182028932 | 5 | Gladstone St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 16:01 | 2021-07-12 21:54 | 2021-07-14 22:06 |  | 2021-08-14 18:14 | 2021-07-15 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 14:44 |  | yes | no | no
3355 | 16175058202933182028932 | 5 | Gladstone St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 16:05 | 2021-07-12 21:27 | 2021-07-14 22:39 |  | 2021-08-14 18:15 | 2021-07-15 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 14:44 |  | yes | no | no
1737 | 16175058202990682029653 | 5 | Gladstone St | Dumbarton Ave & Quincy St | Holmur St | Asphalt | Yes | 2021-06-11 16:29 | 2021-07-10 13:00 | 2021-07-14 14:42 |  | 2021-08-15 14:15 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 15:44 |  | yes | no | no
1729 | 16175058202965382029331 | 5 | Gladstone St | Holmur St | Dexter Ave | Asphalt | Yes | 2021-07-02 15:59 | 2021-07-10 12:01 | 2021-07-14 15:51 |  | 2021-08-15 14:15 | 2021-07-14 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 14:52 |  | yes | no | no
3293 | 16259038202788582027399 | 5 | Gladstone St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-07-02 14:50 | 2021-07-14 21:37 | 2021-07-19 22:42 |  | 2021-08-14 15:33 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 15:18 |  | yes | no | no
3300 | 16259038202824082027885 | 5 | Gladstone St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 14:46 | 2021-07-14 19:54 | 2021-07-19 21:02 |  | 2021-08-14 15:44 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 15:53 |  | yes | no | no
3301 | 16259038202824082027885 | 5 | Gladstone St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 14:48 | 2021-07-14 20:55 | 2021-07-19 21:19 |  |  | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 15:53 |  | yes | no | no
3038 | 16177058202094682020552 | 5 | Glendale St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 14:10 | 2021-06-19 11:57 | 2021-06-23 17:41 |  | 2021-08-11 14:43 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:05 |  | yes | no | no
3039 | 16177058202094682020552 | 5 | Glendale St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 14:26 | 2021-06-19 12:12 | 2021-06-23 17:41 |  | 2021-08-11 14:46 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:04 |  | yes | no | no
2994 | 16177058202019582019799 | 5 | Glendale St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 14:40 | 2021-06-19 13:44 | 2021-06-23 18:07 |  | 2021-08-11 14:52 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:38 |  | yes | no | no
2995 | 16177058202019582019799 | 5 | Glendale St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 14:40 | 2021-06-19 13:56 | 2021-06-23 18:07 |  | 2021-08-11 14:53 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:38 |  | yes | no | no
1561 | 16177058202055282098595 | 5 | Glendale St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-10 14:27 | 2021-06-19 12:48 | 2021-06-23 18:00 |  | 2021-08-11 14:52 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:39 |  | yes | no | no
3146 | 16260038202322282022695 | 5 | Glynn Ct | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 14:27 | 2021-06-28 16:25 | 2021-07-02 17:19 |  | 2021-08-13 14:24 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 15:22 |  | yes | no | no
3147 | 16260038202322282022695 | 5 | Glynn Ct | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 14:27 | 2021-06-28 16:48 | 2021-07-02 16:58 |  | 2021-08-13 14:24 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 15:42 |  | yes | no | no
3161 | 16260038202359982023222 | 5 | Glynn Ct | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-11 14:27 | 2021-06-28 15:55 | 2021-07-02 17:39 |  | 2021-08-13 14:21 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 14:45 |  | yes | no | no
3200 | 16260038202418882023599 | 5 | Glynn Ct | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-11 14:17 | 2021-06-28 15:39 | 2021-07-02 19:43 |  | 2021-08-13 14:20 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 14:27 |  | yes | no | no
3201 | 16260038202418882023599 | 5 | Glynn Ct | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-11 14:27 | 2021-06-28 15:40 | 2021-07-02 19:24 |  | 2021-08-13 14:21 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 14:27 |  | yes | no | no
4863 | 47056608202563182025018 | 5 | Glynn Ct | Wildemere St | Lawton St | Asphalt | Yes Round 2 | 2021-09-10 17:43 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 17:43 |  | no | yes | no
1742 | 16322048203053982030395 | 5 | Goethe Ave | Field St | Sheridan St | Asphalt | Yes | 2021-06-21 17:20 | 2021-07-08 15:06 | 2021-07-09 18:24 |  | 2021-08-03 19:08 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 11:19 |  | yes | no | no
1723 | 16322048203002282029898 | 5 | Goethe Ave | Seyburn St | Beals St | Asphalt | Yes | 2021-06-21 15:17 | 2021-07-08 17:23 | 2021-07-09 18:57 |  | 2021-08-03 19:15 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 11:41 |  | yes | no | no
1734 | 16322048203027982030129 | 5 | Goethe Ave | Townsend St | Baldwin St | Asphalt | Yes | 2021-06-21 17:20 | 2021-07-08 16:58 | 2021-07-09 18:31 |  | 2021-08-03 19:13 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 11:29 |  | yes | no | no
3134 | 15980038202306382022570 | 5 | Hague St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-16 10:48 | 2021-06-23 16:50 | 2021-06-29 13:23 |  | 2021-08-17 14:11 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 16:50 |  | yes | no | no
3135 | 15980038202306382022570 | 5 | Hague St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-16 10:48 | 2021-06-23 17:18 | 2021-06-29 13:11 |  | 2021-08-17 14:08 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 16:50 |  | yes | no | no
5380 | 16344098209778682030086 | 5 | Harding St | E Jefferson Ave | Lisette St | Asphalt | Yes | 2021-09-10 15:54 | 2021-10-05 20:51 | 2021-10-11 13:06 |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 15:54 |  | Yes | No | no
5381 | 16344098209778682030086 | 5 | Harding St | E Jefferson Ave | Lisette St | ASphalt | Yes | 2021-09-10 15:55 | 2021-10-05 21:27 | 2021-10-11 13:24 |  |  |  | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 15:55 |  | Yes | No | no
3262 | 16259048202702782026420 | 5 | Hazelwood St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 15:00 | 2021-07-14 18:44 | 2021-07-19 23:20 |  | 2021-08-13 19:12 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 14:40 |  | yes | no | no
3263 | 16259048202702782026420 | 5 | Hazelwood St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 14:56 | 2021-07-14 18:25 | 2021-07-19 23:40 |  | 2021-08-13 19:08 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 14:39 |  | yes | no | no
3338 | 16175068202913982028693 | 5 | Hazelwood St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 16:10 | 2021-07-12 22:29 | 2021-07-21 13:45 |  | 2021-08-14 18:36 | 2021-07-21 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 14:32 |  | yes | no | no
3339 | 16175068202913982028693 | 5 | Hazelwood St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-07-02 16:07 | 2021-08-27 15:32 | 2021-08-30 17:32 |  |  | 2021-08-31 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-08 14:32 |  | yes | no | no
3279 | 16259048202751382027027 | 5 | Hazelwood St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-07-02 15:09 | 2021-07-14 19:18 | 2021-08-16 21:38 |  |  | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 14:21 |  | yes | no | no
1647 | 16259048202637982025919 | 5 | Hazelwood St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 17:57 | 2021-07-14 18:05 | 2021-07-19 23:58 |  | 2021-08-14 12:33 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 15:05 |  | yes | no | no
4324 | 15877028203129282030238 | 5 | Helen St | Benson St | Mack Ave | Asphalt | Yes | 2021-06-21 18:58 | 2021-07-09 15:23 | 2021-07-10 13:08 |  | 2021-08-04 19:51 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 16:43 |  | yes | no | no
4325 | 15877028203129282030238 | 5 | Helen St | Benson St | Mack Ave | Asphalt | Yes | 2021-06-21 18:58 | 2021-07-09 15:54 | 2021-07-10 13:28 |  | 2021-08-04 19:51 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 16:43 |  | yes | no | no
4326 | 15877028203129282030238 | 5 | Helen St | Benson St | Mack Ave | Asphalt | Yes | 2021-06-21 16:46 | 2021-07-09 16:59 | 2021-07-10 14:55 |  | 2021-08-04 19:52 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 16:43 |  | yes | no | no
1768 | 15877028203182882031292 | 5 | Helen St | Charlevoix St | Benson St | Asphalt | Yes | 2021-06-21 18:31 | 2021-07-09 14:58 | 2021-07-09 10:25 |  | 2021-08-04 19:48 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 16:41 |  | yes | no | no
1685 | 47104938202849982028165 | 5 | Helen St | E Canfield St | Garfield St | Asphalt | Yes | 2021-09-10 17:37 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 17:36 |  | yes | no | no
1646 | 47104938202679482026458 | 5 | Helen St | E Warren Ave | Theodore St | Asphalt | Yes | 2021-06-21 14:56 | 2021-06-29 12:41 | 2021-07-02 19:19 |  | 2021-08-04 23:06 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 14:56 |  | yes | no | no
1677 | 47104938202816582027827 | 5 | Helen St | Garfield St | E Forest Ave | Asphalt | Yes | 2021-09-10 17:41 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 17:40 |  | yes | no | no
3534 | 15877028203350982032755 | 5 | Helen St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 18:31 | 2021-07-09 12:44 | 2021-07-10 12:58 |  | 2021-08-04 19:43 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 16:31 |  | yes | no | no
3535 | 15877028203350982032755 | 5 | Helen St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 18:31 | 2021-07-09 13:18 | 2021-07-14 15:07 |  | 2021-08-04 19:44 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 16:31 |  | yes | no | no
3376 | 15877028203023882092065 | 5 | Helen St | Mack Ave | Sylvester St | Asphalt | Yes | 2021-09-10 17:14 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 17:14 |  | yes | no | no
3377 | 15877028203023882092065 | 5 | Helen St | Mack Ave | Sylvester St | Asphalt | Yes | 2021-09-10 17:20 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 17:19 |  | yes | no | no
3559 | 15877028203418982033509 | 5 | Helen St | Saint Paul St | Kercheval St | Asphalt | Yes | 2021-06-21 16:52 | 2021-07-09 12:17 | 2021-07-10 12:33 |  | 2021-08-04 19:41 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 16:23 |  | yes | no | no
1699 | 47104938202898682028499 | 5 | Helen St | Stuart St | E Canfield St | Asphalt | Yes | 2021-09-10 17:31 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 17:31 |  | yes | no | no
1704 | 47104938202936982028986 | 5 | Helen St | Sylvester St | Stuart St | Asphalt | Yes | 2021-09-10 17:25 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 17:25 |  | yes | no | no
3006 | 16194048202036082019929 | 5 | Highland St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-10 22:55 | 2021-06-21 19:28 | 2021-06-24 17:10 |  | 2021-08-09 16:01 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:25 |  | yes | no | no
3007 | 16194048202036082019929 | 5 | Highland St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-10 22:55 | 2021-06-21 19:04 | 2021-06-24 16:53 |  | 2021-08-09 16:00 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:24 |  | yes | no | no
3518 | 55000988203226582031785 | 5 | Hogarth St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-11 17:18 | 2021-07-12 14:56 | 2021-07-15 14:57 |  | 2021-08-15 15:35 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 11:48 |  | yes | no | no
3519 | 55000988203226582031785 | 5 | Hogarth St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-11 18:21 | 2021-07-12 14:31 | 2021-07-15 14:34 |  | 2021-08-15 15:33 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 11:48 |  | yes | no | no
1816 | 55000988203257882032265 | 5 | Hogarth St | Holmur St | Dexter Ave | Asphalt | Yes | 2021-06-11 17:18 | 2021-07-10 17:27 | 2021-07-14 13:56 |  | 2021-08-15 14:38 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 18:55 |  | yes | no | no
3506 | 55000988203178582031361 | 5 | Hogarth St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-11 18:22 | 2021-07-12 13:38 | 2021-07-15 14:11 |  | 2021-08-15 15:31 | 2021-07-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:16 |  | yes | no | no
3507 | 55000988203178582031361 | 5 | Hogarth St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-11 18:22 | 2021-07-12 13:14 | 2021-07-15 13:54 |  | 2021-08-15 15:30 | 2021-07-16 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:16 |  | yes | no | no
5079 | 15879018202115082020330 | 5 | Holcomb Ave | Chapin St | Cairney St | Asphalt | Yes Round 2 | 2021-09-10 16:00 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:01 |  | no | yes | no
5080 | 15879018202115082020330 | 5 | Holcomb Ave | Chapin St | Cairney St | Asphalt | Yes Round 2 | 2021-09-10 16:08 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:08 |  | no | yes | no
1747 | 15839038203017282029936 | 5 | Holmur St | Blaine St | Carter St | Asphalt | Yes | 2021-06-11 16:32 | 2021-06-30 21:05 | 2021-07-14 16:45 |  | 2021-08-15 14:19 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 16:50 |  | yes | no | no
1720 | 15839038202941582029191 | 5 | Holmur St | Hazelwood St | Taylor St | Asphalt | Yes | 2021-06-11 16:27 | 2021-06-30 20:32 | 2021-07-14 14:22 |  | 2021-08-15 14:14 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 16:11 |  | yes | no | no
1789 | 15839038203178082031475 | 5 | Holmur St | Montgomery St | Vicksburg St | Asphalt | Yes | 2021-06-11 16:43 | 2021-07-10 14:51 | 2021-07-14 18:58 |  | 2021-08-15 14:24 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 16:56 |  | yes | no | no
1767 | 15839038203122982030956 | 5 | Holmur St | Virginia Park St | W Euclid St | Asphalt | Yes | 2021-06-11 16:38 | 2021-07-10 14:15 | 2021-07-14 17:12 |  | 2021-08-15 14:23 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 16:52 |  | yes | no | no
1759 | 15839038203065282030410 | 5 | Holmur St | W Philadelphia St | Pingree St | Asphalt | Yes | 2021-06-11 16:33 | 2021-06-30 21:49 | 2021-07-14 17:10 |  | 2021-08-15 14:21 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 16:52 |  | yes | no | no
1809 | 15839038203231082032067 | 5 | Holmur St | Whitney St | Columbus St | Asphalt | Yes | 2021-09-10 17:31 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 17:31 |  | yes | no | no
3282 | 16344048202823482027197 | 5 | Hurlbut St | Charlevoix St | Goethe Ave | Asphalt | Yes | 2021-06-21 13:48 | 2021-07-09 19:17 | 2021-07-14 13:05 |  | 2021-08-04 17:45 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-01 01:57 |  | yes | no | no
3283 | 16344048202823482027197 | 5 | Hurlbut St | Charlevoix St | Goethe Ave | Asphalt | Yes | 2021-06-21 13:48 | 2021-07-09 18:50 | 2021-07-14 12:52 |  | 2021-08-04 17:45 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-01 01:58 |  | yes | no | no
3250 | 16344048202719782092045 | 5 | Hurlbut St | Goethe Ave | Mack Ave | Asphalt | Yes | 2021-06-21 13:20 | 2021-07-09 18:21 | 2021-07-14 12:52 |  | 2021-08-04 17:41 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-01 01:58 |  | yes | no | no
3251 | 16344048202719782092045 | 5 | Hurlbut St | Goethe Ave | Mack Ave | Asphalt | Yes | 2021-06-21 13:20 | 2021-07-09 17:58 | 2021-07-14 12:12 |  | 2021-08-04 17:39 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 18:00 |  | yes | no | no
1806 | 16343038203291782032274 | 5 | Iroquois St | Agnes St | Saint Paul St | Asphalt | Yes | 2021-06-21 14:41 | 2021-07-06 18:43 | 2021-07-07 16:09 |  | 2021-08-04 15:38 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 14:00 |  | yes | no | no
3350 | 16343038202997982029172 | 5 | Iroquois St | Charlevoix St | Goethe Ave | Asphalt | Yes | 2021-06-21 14:32 | 2021-07-06 15:26 | 2021-07-07 13:31 |  | 2021-08-03 20:33 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:38 |  | yes | no | no
3351 | 16343038202997982029172 | 5 | Iroquois St | Charlevoix St | Goethe Ave | Asphalt | Yes | 2021-06-21 14:31 | 2021-07-06 15:02 | 2021-07-07 13:31 |  | 2021-08-03 20:32 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:38 |  | yes | no | no
1833 | 16343038203350282032917 | 5 | Iroquois St | E Lafayette St | Agnes St | Asphalt | Yes | 2021-06-21 14:42 | 2021-07-06 19:10 | 2021-07-07 16:23 |  | 2021-08-04 15:39 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 14:00 |  | yes | no | no
3404 | 16343038203080882029979 | 5 | Iroquois St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 14:35 | 2021-07-06 17:04 | 2021-07-07 15:05 |  | 2021-08-03 20:15 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:39 |  | yes | no | no
3405 | 16343038203080882029979 | 5 | Iroquois St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 14:34 | 2021-07-06 16:01 | 2021-07-07 13:44 |  | 2021-08-03 20:16 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:38 |  | yes | no | no
3154 | 15878048202422882023155 | 5 | Iroquois St | E Warren Ave | Moffat St | Asphalt | Yes | 2021-06-21 13:14 | 2021-07-01 20:04 | 2021-07-06 16:50 |  | 2021-08-03 12:51 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:14 |  | yes | no | no
3155 | 15878048202422882023155 | 5 | Iroquois St | E Warren Ave | Moffat St | Asphalt | Yes | 2021-06-21 13:14 | 2021-07-01 20:28 | 2021-07-06 16:40 |  | 2021-08-03 12:51 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:14 |  | yes | no | no
3308 | 16343038202917282028510 | 5 | Iroquois St | Goethe Ave | Mack Ave | Asphalt | Yes | 2021-06-21 14:23 | 2021-07-06 14:20 | 2021-07-07 13:07 |  | 2021-08-03 20:30 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:31 |  | yes | no | no
3309 | 16343038202917282028510 | 5 | Iroquois St | Goethe Ave | Mack Ave | Asphalt | Yes | 2021-06-21 14:22 | 2021-07-06 14:44 | 2021-07-07 13:07 |  | 2021-08-03 20:28 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:28 |  | yes | no | no
3462 | 16343038203156182030808 | 5 | Iroquois St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 14:38 | 2021-07-06 17:48 | 2021-07-07 15:29 |  | 2021-08-04 15:33 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:51 |  | yes | no | no
3463 | 16343038203156182030808 | 5 | Iroquois St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 14:37 | 2021-07-06 17:26 | 2021-07-07 15:28 |  | 2021-08-04 15:31 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:51 |  | yes | no | no
3118 | 15878048202315582022072 | 5 | Iroquois St | Moffat St | Gratiot Ave | Asphalt | Yes | 2021-06-21 12:39 | 2021-07-01 20:53 | 2021-07-06 16:40 |  | 2021-08-03 12:51 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 12:51 |  | yes | no | no
3119 | 15878048202315582022072 | 5 | Iroquois St | Moffat St | Gratiot Ave | Asphalt | Yes | 2021-06-21 12:35 | 2021-07-01 21:01 | 2021-07-06 16:10 |  | 2021-08-03 12:50 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 12:51 |  | yes | no | no
1786 | 16343038203227482031561 | 5 | Iroquois St | Saint Paul St | Kercheval St | Asphalt | Yes | 2021-06-21 14:39 | 2021-07-06 18:11 | 2021-07-07 15:47 |  | 2021-08-04 15:35 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 13:52 |  | yes | no | no
1781 | 47056988203195382031632 | 5 | Joseph Campau St | Leland St | E Alexandrine St | Asphalt | Yes | 2021-06-21 17:16 | 2021-06-29 18:41 | 2021-07-02 11:29 |  | 2021-08-04 22:52 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 17:16 |  | yes | no | no
2998 | 16311078202060882019775 | 5 | Klein St | Conant St | Farr St | Asphalt | Yes | 2021-06-10 14:09 | 2021-06-17 15:26 | 2021-06-22 22:45 |  | 2021-08-06 14:10 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 17:52 |  | yes | no | no
1678 | 16212088202788582027513 | 5 | La Salle Blvd | Gladstone St | Hazelwood St | Asphalt | Yes | 2021-07-02 14:43 | 2021-07-14 21:22 | 2021-07-19 20:14 |  | 2021-08-14 15:32 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 15:49 |  | yes | no | no
1774 | 16251078203146382031050 | 5 | La Salle Blvd | Grand Service Drive | Lothrop St | Asphalt | Yes | 2021-06-12 16:01 | 2021-07-19 13:05 | 2021-07-20 21:36 |  | 2021-08-14 14:42 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:37 |  | yes | no | no
1754 | 16251078203056482030173 | 5 | La Salle Blvd | Lamothe St | S La Salle Gdns | Asphalt | Yes | 2021-06-12 16:02 | 2021-07-19 12:19 | 2021-07-20 17:35 |  | 2021-08-14 14:46 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:37 |  | yes | no | no
1762 | 16251078203105082030564 | 5 | La Salle Blvd | Lothrop St | Lamothe St | Asphalt | Yes | 2021-06-12 16:02 | 2021-07-19 12:55 | 2021-07-20 20:29 |  | 2021-08-14 14:45 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:37 |  | yes | no | no
1696 | 16212088202839282028150 | 5 | La Salle Blvd | Pingree St | Blaine St | Asphalt | Yes | 2021-07-02 15:12 | 2021-07-14 11:07 | 2021-07-20 15:52 |  | 2021-08-14 15:30 | 2021-07-21 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 15:56 |  | yes | no | no
1658 | 16212088202710682026738 | 5 | La Salle Blvd | Taylor St | Clairmount St | Asphalt | Yes | 2021-07-02 14:40 | 2021-07-14 16:50 | 2021-07-15 21:01 |  | 2021-08-13 19:00 | 2021-07-17 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 13:03 |  | yes | no | no
1523 | 16155018201914182018889 | 5 | La Salle Blvd | W Buena Vista St | Tyler St | Asphalt | Yes | 2021-06-10 22:57 | 2021-06-18 13:04 | 2021-06-23 16:59 |  | 2021-08-09 15:11 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:00 |  | yes | no | no
1705 | 16212088202896482028683 | 5 | La Salle Blvd | W Euclid St | W Philadelphia St | Asphalt | Yes | 2021-07-02 15:14 | 2021-07-19 11:43 | 2021-07-20 16:33 |  | 2021-08-14 15:28 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 16:02 |  | yes | no | no
1753 | 16252038203056482030228 | 5 | Lamothe St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-12 16:46 | 2021-07-19 16:17 | 2021-07-20 17:51 |  | 2021-08-14 14:51 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 14:28 |  | yes | no | no
3464 | 16252038203101482030564 | 5 | Lamothe St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-12 16:45 | 2021-07-19 17:31 | 2021-07-20 19:28 |  | 2021-08-14 14:51 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 14:53 |  | yes | no | no
3465 | 16252038203101482030564 | 5 | Lamothe St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-12 16:46 | 2021-07-19 16:52 | 2021-07-20 20:02 |  | 2021-08-14 14:51 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 14:53 |  | yes | no | no
3096 | 16194088202211682021665 | 5 | Lawrence St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 13:32 | 2021-06-25 13:16 | 2021-07-02 13:51 |  | 2021-08-09 17:42 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 13:14 |  | yes | no | no
3097 | 16194088202211682021665 | 5 | Lawrence St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 13:43 | 2021-06-25 13:52 | 2021-07-02 14:57 |  | 2021-08-09 17:44 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 13:14 |  | yes | no | no
2972 | 15977108201975182019337 | 5 | Lawrence St | 2nd Blvd | Rosedale Ct & Woodward Ave | Asphalt | Yes | 2021-06-12 14:42 | 2021-06-21 17:56 | 2021-06-28 14:34 |  | 2021-08-16 13:34 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 13:34 |  | yes | no | no
2973 | 15977108201975182019337 | 5 | Lawrence St | 2nd Blvd | Rosedale Ct & Woodward Ave | Asphalt | Yes | 2021-06-12 14:42 | 2021-06-21 18:23 | 2021-06-28 14:51 |  | 2021-08-16 13:36 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 13:34 |  | yes | no | no
2986 | 15977108202015482019751 | 5 | Lawrence St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 14:42 | 2021-06-21 17:12 | 2021-06-28 12:34 |  | 2021-08-16 13:33 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 14:26 |  | yes | no | no
2987 | 15977108202015482019751 | 5 | Lawrence St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 14:42 | 2021-06-21 17:32 | 2021-06-28 12:49 |  | 2021-08-16 13:34 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 14:26 |  | yes | no | no
3214 | 16176048202501382024007 | 5 | Lawrence St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 19:50 | 2021-06-24 19:33 | 2021-07-09 17:31 |  | 2021-08-11 19:12 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 18:31 |  | yes | no | no
3215 | 16176048202501382024007 | 5 | Lawrence St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 20:11 | 2021-06-24 19:07 | 2021-07-09 17:13 |  | 2021-08-11 19:11 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 18:45 |  | yes | no | no
3008 | 15977108208787182020154 | 5 | Lawrence St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 14:36 | 2021-06-21 15:42 | 2021-06-28 12:07 |  | 2021-08-16 13:29 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 14:28 |  | yes | no | no
3009 | 15977108208787182020154 | 5 | Lawrence St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 14:41 | 2021-06-21 16:01 | 2021-06-28 12:17 |  | 2021-08-16 13:29 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 14:28 |  | yes | no | no
1585 | 16194088202237282022116 | 5 | Lawrence St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-11 13:32 | 2021-06-25 12:50 | 2021-07-02 13:35 |  | 2021-08-09 17:42 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 16:00 |  | yes | no | no
3193 | 16176048202400782023526 | 5 | Lawrence St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-10 20:11 | 2021-06-24 18:41 | 2021-07-09 17:12 |  | 2021-08-11 19:10 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:41 |  | yes | no | no
1604 | 16154108202323182022922 | 5 | Lawton St | Burlingame St | Webb St | Asphalt | Yes | 2021-06-10 20:11 | 2021-06-24 17:59 | 2021-07-02 13:10 |  | 2021-08-11 19:09 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:09 |  | yes | no | no
1620 | 16154108202387282023526 | 5 | Lawton St | Collingwood St | Lawrence St | Asphalt | Yes | 2021-06-10 20:11 | 2021-06-24 18:21 | 2021-07-02 13:10 |  | 2021-08-11 19:10 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:14 |  | yes | no | no
1579 | 16154108202126682020981 | 5 | Lawton St | Cortland St | Sturtevant St | Asphalt | Yes | 2021-06-10 14:35 | [5 empty] | HMA | No |  | Coordinate with DWSD - Sewer |  | No | Yes |  | 2021-06-11 13:59 |  | yes | no | no
1562 | 16154108202073382020467 | 5 | Lawton St | Fullerton St | Leslie St | Asphalt | Yes | 2021-06-10 15:01 | 2021-06-21 15:28 | 2021-06-24 00:42 |  | 2021-08-11 14:57 | 2021-06-24 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:15 |  | yes | no | no
1629 | 16154108202501882024414 | 5 | Lawton St | Glynn Ct | Calvert St | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  | Resurfacing is required | Yes | No | poor pavement |  |  | yes | no | no
1780 | 47113608203195382031803 | 5 | Leland St | Joseph Campau St | Mitchell St | Asphalt | Yes | [6 empty] | HMA | No |  |  | Resurfacing is required | No | No | poor pavement |  |  | yes | no | no
3208 | 16259078202495782024020 | 5 | Longfellow St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 14:20 | 2021-07-13 14:34 | 2021-07-19 13:53 |  | 2021-08-13 15:04 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 13:44 |  | yes | no | no
3209 | 16259078202495782024020 | 5 | Longfellow St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 14:18 | 2021-07-13 15:03 | 2021-07-19 13:23 |  | 2021-08-13 15:02 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 13:44 |  | yes | no | no
3062 | 15978088202163482021239 | 5 | Longfellow St | 2nd Blvd | Woodward Ave | Asphalt | Yes | 2021-06-12 15:46 | 2021-06-22 14:20 | 2021-06-28 17:26 |  | 2021-08-16 14:49 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:46 |  | yes | no | no
3063 | 15978088202163482021239 | 5 | Longfellow St | 2nd Blvd | Woodward Ave | Asphalt | Yes | 2021-06-12 15:46 | 2021-06-22 14:46 | 2021-06-28 16:06 |  | 2021-08-16 14:49 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:47 |  | yes | no | no
3090 | 15978088202214782021634 | 5 | Longfellow St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 15:46 | 2021-06-22 13:02 | 2021-06-28 17:51 |  | 2021-08-16 14:56 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:37 |  | yes | no | no
3091 | 15978088202214782021634 | 5 | Longfellow St | 3rd St | 2nd Blvd | Asphalt | Yes | 2021-06-12 15:46 | 2021-06-22 13:38 | 2021-06-28 17:36 |  | 2021-08-16 14:54 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:37 |  | yes | no | no
1601 | 16259078202307982022831 | 5 | Longfellow St | Byron St | S M 10 Service Drive | Asphalt | Yes | 2021-06-11 17:19 | 2021-06-29 18:33 | 2021-07-06 17:32 |  | 2021-08-13 16:04 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:35 |  | yes | no | no
3112 | 15978088208787882022147 | 5 | Longfellow St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 15:45 | 2021-06-22 12:19 | 2021-06-28 18:19 |  | 2021-08-16 14:56 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:32 |  | yes | no | no
3113 | 15978088208787882022147 | 5 | Longfellow St | Hamilton Ave | 3rd St | Asphalt | Yes | 2021-06-12 15:46 | 2021-06-22 12:40 | 2021-06-28 18:19 |  | 2021-08-16 14:56 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 15:31 |  | yes | no | no
3233 | 16259078202559882024957 | 5 | Longfellow St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-07-02 14:22 | 2021-07-13 14:08 | 2021-07-19 14:16 |  | 2021-08-13 15:08 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 13:27 |  | yes | no | no
3244 | 16259078202606482025598 | 5 | Longfellow St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 14:25 | 2021-07-13 13:15 | 2021-07-19 15:10 |  | 2021-08-13 15:13 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 13:16 |  | yes | no | no
3245 | 16259078202606482025598 | 5 | Longfellow St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 14:24 | 2021-07-13 13:42 | 2021-07-19 14:50 |  | 2021-08-13 15:09 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 13:19 |  | yes | no | no
3186 | 16259078202402082023478 | 5 | Longfellow St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-07-02 14:16 | 2021-07-13 15:25 | 2021-07-19 12:53 |  | 2021-08-13 14:59 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 14:17 |  | yes | no | no
3187 | 16259078202402082023478 | 5 | Longfellow St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-07-02 14:14 | 2021-07-13 15:47 | 2021-07-19 12:35 |  | 2021-08-13 15:55 | 2021-07-19 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-06 14:17 |  | yes | no | no
3152 | 16259078202347882023079 | 5 | Longfellow St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:19 | 2021-06-29 17:07 | 2021-07-06 19:55 |  | 2021-08-13 16:00 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 12:26 |  | yes | no | no
3153 | 16259078202347882023079 | 5 | Longfellow St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:19 | 2021-06-29 17:40 | 2021-07-06 18:39 |  | 2021-08-13 16:02 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 12:26 |  | yes | no | no
1749 | 16251068203042082092067 | 5 | Lothrop St | Dunedin St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-12 12:49 | 2021-07-19 15:30 | 2021-07-20 22:10 |  | 2021-08-14 14:38 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 15:10 |  | yes | no | no
1752 | 16251068203054982030420 | 5 | Lothrop St | Hanover St | Dunedin St | Asphalt | Yes | 2021-06-12 12:48 | 2021-07-19 15:15 | 2021-07-20 21:57 |  | 2021-08-14 14:38 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 15:06 |  | yes | no | no
1756 | 15838018203047782030027 | 5 | Mackinaw St | Arcadia St | Kimberly Ct | Asphalt | Yes | 2021-06-11 16:00 | 2021-06-30 19:51 | 2021-07-14 13:51 |  | 2021-08-15 16:09 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 15:33 |  | yes | no | no
3206 | 15980088202520582024207 | 5 | Marston St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-16 10:49 | 2021-06-24 12:22 | 2021-06-29 18:04 |  | 2021-08-17 14:36 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 19:30 |  | yes | no | no
3207 | 15980088202520582024207 | 5 | Marston St | Beaubien St | Oakland St | Asphalt | Yes | 2021-06-16 10:50 | 2021-06-24 11:51 | 2021-06-29 17:10 |  | 2021-08-17 14:37 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 07:26 |  | yes | no | no
1630 | 15980088202546382025205 | 5 | Marston St | Brush St | Beaubien St | Asphalt | Yes | 2021-06-16 10:50 | 2021-06-24 12:58 | 2021-06-29 18:43 |  | 2021-08-17 14:34 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 18:20 |  | yes | no | no
1637 | 15980088202586482025463 | 5 | Marston St | John R St | Brush St | Asphalt | Yes | 2021-06-16 10:50 | 2021-06-24 13:32 | 2021-06-29 18:43 |  | 2021-08-17 14:33 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 18:11 |  | yes | no | no
1631 | 15878028202598182025710 | 5 | Maxwell St | E Forest Ave | Willard St | Asphalt | Yes | 2021-06-21 14:13 | 2021-07-01 18:50 | 2021-07-06 15:06 |  | 2021-08-03 13:16 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 14:13 |  | yes | no | no
4315 | 15878028202883782027935 | 5 | Maxwell St | Mack Ave | Sylvester St | Asphalt | Yes | 2021-06-21 15:50 | 2021-07-01 16:03 | 2021-07-06 13:56 |  | 2021-08-03 15:05 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 14:54 |  | yes | no | no
4317 | 15878028202883782027935 | 5 | Maxwell St | Mack Ave | Sylvester St | Asphalt | Yes | 2021-06-21 15:47 | 2021-07-01 17:29 | 2021-07-06 13:56 |  | 2021-08-03 15:03 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 14:54 |  | yes | no | no
1639 | 15878028202662482026270 | 5 | Maxwell St | Norvell Ct | Manila St | Asphalt | Yes | 2021-09-07 20:01 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 20:01 |  | yes | no | no
1653 | 15878028202729182026926 | 5 | Maxwell St | Sprague Ave | E Canfield St | Asphalt | Yes | 2021-06-21 15:42 | 2021-07-01 18:20 | 2021-07-06 14:06 |  | 2021-08-03 15:01 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 14:55 |  | yes | no | no
1660 | 15878028202793582027690 | 5 | Maxwell St | Sylvester St | Ruedisale Ct | Asphalt | Yes | 2021-06-21 15:45 | 2021-07-01 17:55 | 2021-07-06 13:56 |  | 2021-08-03 15:02 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 14:55 |  | yes | no | no
1626 | 15878028202571082024826 | 5 | Maxwell St | Willard St | E Warren Ave & Maxwell Ave | Asphalt | Yes | 2021-06-21 14:13 | 2021-07-01 19:25 | 2021-07-06 15:33 |  | 2021-08-03 13:17 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 14:13 |  | yes | no | no
1615 | 15980058202406382023713 | 5 | Melbourne St | Beaubien St | Kingsley Ct | Asphalt | Yes | 2021-06-16 10:49 | 2021-06-23 19:03 | 2021-06-29 15:44 |  | 2021-08-17 14:21 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 17:29 |  | yes | no | no
1624 | 15980058202514182024381 | 5 | Melbourne St | John R St | Brush St | Asphalt | Yes | 2021-06-16 10:48 | 2021-06-23 18:26 | 2021-06-29 15:21 |  | 2021-08-17 14:19 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 17:19 |  | yes | no | no
1608 | 15980058202371382023456 | 5 | Melbourne St | Kingsley Ct | Oakland St | Asphalt | Yes | 2021-06-16 10:49 | 2021-06-23 20:12 | 2021-06-29 15:50 |  | 2021-08-17 14:24 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 17:29 |  | yes | no | no
1634 | 16285048202585682024920 | 5 | Melrose St | Custer St | Clay St | Asphalt | Yes | 2021-06-14 14:22 | 2021-06-24 18:18 | 2021-07-01 15:29 |  | 2021-08-17 15:48 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 13:38 |  | yes | no | no
3060 | 16194018208791782021037 | 5 | Monterey St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 22:55 | 2021-06-24 12:18 | 2021-07-02 11:54 |  | 2021-08-09 17:16 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:58 |  | yes | no | no
3061 | 16194018208791782021037 | 5 | Monterey St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 22:55 | 2021-06-24 12:31 | 2021-07-01 17:53 |  | 2021-08-09 17:19 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:58 |  | yes | no | no
1788 | 15838078203178082031426 | 5 | Montgomery St | Holmur St | Dexter Ave | Asphalt | Yes | 2021-06-11 16:41 | 2021-07-10 15:50 | 2021-07-14 17:50 |  | 2021-08-15 14:27 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 17:23 |  | yes | no | no
1799 | 15838078203210982031780 | 5 | Montgomery St | Radford St | Holmur St | Asphalt | Yes | 2021-06-11 16:44 | 2021-07-10 16:24 | 2021-07-14 19:46 |  | 2021-08-15 14:31 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 17:23 |  | yes | no | no
1522 | 16195058201915282090170 | 5 | Montville Pl | Glendale St | W Buena Vista St | Asphalt | Yes | 2021-06-10 22:57 | 2021-06-19 14:39 | 2021-06-23 17:00 |  | 2021-08-09 15:17 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:03 |  | yes | no | no
1519 | 16195058201888482018216 | 5 | Montville Pl | W Buena Vista St | Indiandale St | Asphalt | Yes | 2021-06-10 22:57 | 2021-06-19 15:04 | 2021-06-23 16:59 |  | 2021-08-09 15:06 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 11:59 |  | yes | no | no
1621 | 15980078202455182024168 | 5 | Mount Vernon St | Beaubien St | Kingsley Ct | Asphalt | Yes | 2021-06-16 10:49 | 2021-06-23 21:27 | 2021-06-29 16:18 |  | 2021-08-17 14:27 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 17:41 |  | yes | no | no
1617 | 15980078202416882023773 | 5 | Mount Vernon St | Kingsley Ct | Oakland St | Asphalt | Yes | 2021-06-16 10:49 | 2021-06-23 20:47 | 2021-06-29 16:08 |  | 2021-08-17 14:25 | 2021-06-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 17:41 |  | yes | no | no
4006 | 15837048203058782029300 | 5 | N Martindale St | Grand River Ave | Joy Rd | Asphalt | Yes | 2021-06-11 15:55 | 2021-06-30 19:11 | 2021-07-14 12:38 |  | 2021-08-15 16:39 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 15:16 |  | yes | no | no
4007 | 15837048203058782029300 | 5 | N Martindale St | Grand River Ave | Joy Rd | Asphalt | Yes | 2021-06-11 15:56 | 2021-06-30 18:53 | 2021-07-14 13:15 |  | 2021-08-15 16:39 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 15:15 |  | yes | no | no
4008 | 15837048203058782029300 | 5 | N Martindale St | Grand River Ave | Joy Rd | Asphalt | Yes | 2021-06-11 15:57 | 2021-06-30 18:22 | 2021-07-14 13:29 |  | 2021-08-15 16:32 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 15:15 |  | yes | no | no
3524 | 47047868203254482032090 | 5 | Northwestern St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-12 11:25 | 2021-07-12 11:59 | 2021-07-15 15:44 |  | 2021-08-15 15:37 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 11:59 |  | yes | no | no
3525 | 47047868203254482032090 | 5 | Northwestern St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-12 12:25 | 2021-07-12 12:37 | 2021-07-15 15:56 |  | 2021-08-15 15:38 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 11:36 |  | yes | no | no
1835 | 47047868203287082032544 | 5 | Northwestern St | Grand River Ave & Holmur St | Dexter Ave | Asphalt | Yes | [6 empty] | HMA | No |  |  | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
4285 | 16312068201878582018723 | 5 | Oliver St | City/Twp Line | Mount Elliott St | Asphalt | Yes | 2021-06-10 12:41 | 2021-06-17 17:20 | 2021-06-23 13:19 |  | 2021-08-06 14:21 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 17:14 |  | yes | no | no
4286 | 16312068201878582018723 | 5 | Oliver St | City/Twp Line | Mount Elliott St | Asphalt | Yes | 2021-06-10 13:18 | 2021-06-17 17:29 | 2021-06-23 13:35 |  | 2021-08-06 14:23 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 17:15 |  | yes | no | no
4287 | 16312068201878582018723 | 5 | Oliver St | City/Twp Line | Mount Elliott St | Asphalt | Yes | 2021-06-10 13:18 | 2021-06-17 18:06 | 2021-06-22 23:54 |  | 2021-08-06 14:25 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-10 17:15 |  | yes | no | no
1766 | 16389028203185582097664 | 5 | Parker St | Durand St | Vernor Hwy | Asphalt | Yes | 2021-06-21 16:45 | 2021-07-06 21:10 | 2021-07-07 18:54 |  | 2021-08-04 15:29 | 2021-07-08 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 13:13 |  | yes | no | no
3436 | 16389028203135282030454 | 5 | Parker St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 16:45 | 2021-07-07 11:50 | 2021-07-07 19:20 |  | 2021-08-03 20:38 | 2021-07-08 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 13:38 |  | yes | no | no
3437 | 16389028203135282030454 | 5 | Parker St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 16:46 | 2021-07-07 12:15 | 2021-07-07 19:20 |  | 2021-08-03 20:36 | 2021-07-08 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 13:37 |  | yes | no | no
1776 | 16389028203215482031855 | 5 | Parker St | Kercheval St | Durand St | Asphalt | Yes | 2021-06-21 15:01 | 2021-07-07 12:50 | 2021-07-07 18:37 |  | 2021-08-04 15:26 | 2021-07-08 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 13:13 |  | yes | no | no
1695 | 16254108202839282028098 | 5 | Pingree St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-07-02 15:23 | 2021-07-14 11:01 | 2021-07-20 15:11 |  | 2021-08-14 17:33 | 2021-07-21 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 16:08 |  | yes | no | no
3322 | 16254108202881082028392 | 5 | Pingree St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 15:19 | 2021-07-15 11:41 | 2021-07-20 13:56 |  | 2021-08-14 17:32 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 16:02 |  | yes | no | no
3323 | 16254108202881082028392 | 5 | Pingree St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-07-02 15:20 | 2021-07-15 12:04 | 2021-07-20 14:09 |  | 2021-08-14 17:32 | 2021-07-20 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 16:03 |  | yes | no | no
1674 | 47069978202771982027169 | 5 | Pingree St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 17:58 | 2021-07-15 13:29 | 2021-07-26 12:46 |  | 2021-08-14 13:01 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 15:17 |  | yes | no | no
1784 | 16317088203209782031642 | 5 | Preston St | Ellery St | Mount Elliott St | Asphalt | Yes | 2021-06-21 18:01 | 2021-06-29 15:37 | 2021-07-02 12:52 |  | 2021-08-04 21:10 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 18:01 |  | yes | no | no
3510 | 16317088203259382032097 | 5 | Preston St | Elmwood St | Ellery St | Asphalt | Yes | 2021-06-21 17:50 | 2021-06-29 17:07 | 2021-07-02 12:43 |  | 2021-08-04 21:06 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 17:50 |  | yes | no | no
3511 | 16317088203259382032097 | 5 | Preston St | Elmwood St | Ellery St | Asphalt | Yes | 2021-06-21 17:51 | 2021-06-29 16:00 | 2021-07-02 12:43 |  | 2021-08-04 21:08 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 17:51 |  | yes | no | no
3120 | 16176108202254482021945 | 5 | Richton St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 16:34 | 2021-06-23 16:38 | 2021-07-01 16:20 |  | 2021-08-11 17:41 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:08 |  | yes | no | no
3121 | 16176108202254482021945 | 5 | Richton St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 16:34 | 2021-06-23 17:40 | 2021-07-01 16:15 |  | 2021-08-11 17:40 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:08 |  | yes | no | no
3070 | 16176108202153782021163 | 5 | Richton St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 19:00 | 2021-06-24 11:19 | 2021-07-01 15:15 |  | 2021-08-11 17:37 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:23 |  | yes | no | no
3071 | 16176108202153782021163 | 5 | Richton St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 19:01 | 2021-06-24 11:36 | 2021-07-01 14:17 |  | 2021-08-11 17:35 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:23 |  | yes | no | no
3093 | 16176108202194582021537 | 5 | Richton St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-10 19:00 | 2021-06-24 11:03 | 2021-07-01 15:41 |  | 2021-08-11 17:38 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:38 |  | yes | no | no
4868 | 17126078203227482032054 | 5 | Saint Paul St | Iroquois St | Burns St | Asphalt | Yes Round 2 | 2021-09-10 16:02 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:02 |  | no | yes | no
1807 | 17126078203294582032735 | 5 | Saint Paul St | Van Dyke St | Parker St | Asphalt | Yes | 2021-06-21 14:58 | 2021-07-06 20:45 | 2021-07-07 18:28 |  | 2021-08-04 16:21 | 2021-07-08 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-22 14:55 |  | yes | no | no
3166 | 47110578202448882023293 | 5 | Seminole St | E Warren Ave | Moffat St | Asphalt | Yes | 2021-06-21 13:31 | 2021-07-02 16:42 | 2021-07-06 15:59 |  | 2021-08-03 12:54 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:31 |  | yes | no | no
3167 | 47110578202448882023293 | 5 | Seminole St | E Warren Ave | Moffat St | Asphalt | Yes | 2021-06-21 13:31 | 2021-07-02 15:06 | 2021-07-06 15:59 |  | 2021-08-03 12:54 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 13:31 |  | yes | no | no
2033 | 47110578202780782026730 | 5 | Seminole St | Sylvester St | E Canfield St | Asphalt | Yes | 2021-09-07 20:37 | [5 empty] | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 20:37 |  | yes | no | no
3786 | 47110578202780782026730 | 5 | Seminole St | Sylvester St | E Canfield St | Asphalt | Yes | 2021-09-07 20:37 | [5 empty] | HMA | No |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-07 20:37 |  | yes | no | no
5185 | 15878058202300882021962 | 5 | Seneca St | Moffat St | Chapin St | Asphalt | Yes Round 2 | 2021-09-10 16:16 | [5 empty] | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 16:16 |  | no | yes | no
5186 | 15878058202300882021962 | 5 | Seneca St | Moffat St | Chapin St | Asphalt | Yes Round 2 | 2021-09-10 16:14 | [5 empty] | HMA |  |  |  | Resurfacing Completed | Yes | Yes |  | 2021-09-10 16:14 |  | no | yes | no
3256 | 16393018202738482026336 | 5 | Seneca St | Sylvester St | E Canfield St | Asphalt | Yes | 2021-06-21 14:19 | 2021-07-02 21:23 | 2021-07-06 18:55 |  | 2021-08-03 15:46 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 15:39 |  | yes | no | no
3257 | 16393018202738482026336 | 5 | Seneca St | Sylvester St | E Canfield St | Asphalt | Yes | 2021-06-21 14:18 | 2021-07-06 11:38 | 2021-07-06 18:44 |  | 2021-08-03 15:45 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 15:39 |  | yes | no | no
1651 | 47056188202663682101281 | 5 | Seward St | 2nd Ave | Virginia Park Ct | Asphalt | Yes | 2021-06-12 13:12 | 2021-08-25 14:40 | 2021-08-30 20:00 |  |  | 2021-08-31 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-06-14 18:14 |  | yes | no | no
3264 | 47056188202717782026636 | 5 | Seward St | 3rd St | 2nd Ave | Asphalt | Yes | 2021-06-12 13:21 | 2021-08-26 15:30 | 2021-08-30 20:21 |  |  | 2021-08-31 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-06-14 18:13 |  | yes | no | no
3265 | 47056188202717782026636 | 5 | Seward St | 3rd St | 2nd Ave | Asphalt | Yes | 2021-06-12 13:21 | 2021-08-25 15:03 | 2021-08-30 20:09 |  |  | 2021-08-31 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-06-14 18:13 |  | yes | no | no
1682 | 47056188202801882027743 | 5 | Seward St | Merrill St | Hamilton | Asphalt | Yes | [6 empty] | HMA | No |  |  | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
1665 | 47056188202757582027177 | 5 | Seward St | N M 10 Service Drive | 3rd St | Asphalt | Yes | [6 empty] | HMA | No |  | No conflict | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
1690 | 47056188202828982028018 | 5 | Seward St | Poe St | Merrill St | Asphalt | Yes | [6 empty] | HMA | No |  |  | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | yes | no | no
1643 | 47056188210128182026073 | 5 | Seward St | Virginia Park Ct | Woodward Ave | Asphalt | Yes | 2021-06-12 13:12 | 2021-08-25 15:51 | 2021-08-30 18:37 |  |  | 2021-08-31 04:00 | HMA | No |  | No conflict |  | No | Yes |  | 2021-06-14 18:14 |  | yes | no | no
3240 | 15877098202653282025622 | 5 | Seyburn St | E Forest Ave | E Warren Ave | Asphalt | Yes | 2021-06-21 14:56 | 2021-07-01 14:15 | 2021-07-06 12:45 |  | 2021-08-03 13:13 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 14:56 |  | yes | no | no
3241 | 15877098202653282025622 | 5 | Seyburn St | E Forest Ave | E Warren Ave | Asphalt | Yes | 2021-06-21 14:56 | 2021-07-01 13:30 | 2021-07-02 20:32 |  | 2021-08-03 13:13 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 14:56 |  | yes | no | no
3476 | 16392038203176682030849 | 5 | Seyburn St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 15:22 | 2021-07-08 19:26 | 2021-07-09 21:20 |  |  | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-06-30 14:02 |  | yes | no | no
3477 | 16392038203176682030849 | 5 | Seyburn St | E Vernor Hwy | Charlevoix St | Asphalt | Yes | 2021-06-21 15:20 | 2021-07-08 18:34 | 2021-07-09 21:20 |  | 2021-08-03 21:21 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 14:02 |  | yes | no | no
3318 | 16392108202923282028517 | 5 | Seyburn St | Mack Ave | Sylvester St | Asphalt | Yes | 2021-06-21 16:40 | 2021-07-01 15:44 | 2021-07-06 12:52 |  | 2021-08-03 18:25 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 14:35 |  | yes | no | no
3319 | 16392108202923282028517 | 5 | Seyburn St | Mack Ave | Sylvester St | Asphalt | Yes | 2021-06-21 16:00 | 2021-07-01 14:56 | 2021-07-06 13:00 |  | 2021-08-03 18:26 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 14:35 |  | yes | no | no
1868 | 47057668203465682034341 | 5 | Seyburn St | Van Dyke Pl | E Lafayette St | Asphalt | Yes | 2021-06-21 15:35 | 2021-07-07 13:46 | 2021-07-09 12:27 |  | 2021-08-04 17:55 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 16:45 |  | yes | no | no
3276 | 15877068202803882027122 | 5 | Sheridan St | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-06-21 16:18 | 2021-07-01 11:33 | 2021-07-02 18:33 |  | 2021-08-03 18:33 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 11:51 |  | yes | no | no
3277 | 15877068202803882027122 | 5 | Sheridan St | E Canfield St | E Forest Ave | Asphalt | Yes | 2021-06-21 16:17 | 2021-06-30 20:28 | 2021-07-02 18:52 |  | 2021-08-03 18:33 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 11:51 |  | yes | no | no
1638 | 47055918202598482025762 | 5 | Smith St | Beaubien St | Saint Antoine St | Asphalt | Yes | 2021-06-14 15:10 | 2021-06-24 19:02 | 2021-07-01 12:31 |  | 2021-08-17 15:15 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 13:21 |  | yes | no | no
1640 | 47055918202616782025984 | 5 | Smith St | Brush St | Beaubien St | Asphalt | Yes | 2021-06-14 15:10 | 2021-06-24 19:23 | 2021-07-01 12:31 |  | 2021-08-17 15:16 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 13:21 |  | yes | no | no
1650 | 47055918202661882026167 | 5 | Smith St | John R St | Brush St | Asphalt | Yes | 2021-06-14 15:21 | 2021-06-24 20:13 | 2021-07-01 12:58 |  | 2021-08-17 15:03 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 13:21 |  | yes | no | no
5374 | 47055918202576282025490 | 5 | Smith St | Saint Antoine St | Oakland St | Asphalt | Yes Round 2 | 2021-09-10 16:53 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 16:54 |  | No | Yes | no
1536 | 16194058201969782019375 | 5 | Sturtevant St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-10 22:56 | 2021-06-21 21:54 | 2021-06-24 16:18 |  | 2021-08-09 15:59 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:23 |  | yes | no | no
3088 | 16177028202186282021336 | 5 | Sturtevant St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 15:29 | 2021-06-23 11:30 | 2021-06-25 14:06 |  | 2021-08-11 15:57 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:32 |  | yes | no | no
3089 | 16177028202186282021336 | 5 | Sturtevant St | Dexter Ave | Wildemere St | Asphalt | Yes | 2021-06-10 15:29 | 2021-06-23 11:51 | 2021-06-25 14:07 |  | 2021-08-11 15:59 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:32 |  | yes | no | no
2988 | 16194058202012982019697 | 5 | Sturtevant St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-10 22:56 | 2021-06-21 20:58 | 2021-06-24 18:23 |  | 2021-08-09 16:49 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:07 |  | yes | no | no
2989 | 16194058202012982019697 | 5 | Sturtevant St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-10 22:56 | 2021-06-21 21:26 | 2021-06-24 19:55 |  | 2021-08-09 16:22 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 15:07 |  | yes | no | no
3034 | 16177028202098182087800 | 5 | Sturtevant St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 15:55 | 2021-06-23 13:00 | 2021-06-24 20:56 |  | 2021-08-11 16:02 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:10 |  | yes | no | no
3035 | 16177028202098182087800 | 5 | Sturtevant St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 15:55 | 2021-06-23 13:25 | 2021-06-24 20:43 |  |  | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:10 |  | yes | no | no
3012 | 16194058202059682020129 | 5 | Sturtevant St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 22:55 | 2021-06-21 20:14 | 2021-06-24 17:52 |  | 2021-08-09 16:29 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:54 |  | yes | no | no
3013 | 16194058202059682020129 | 5 | Sturtevant St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-10 22:55 | 2021-06-21 20:31 | 2021-06-24 17:58 |  | 2021-08-09 16:30 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:54 |  | yes | no | no
3055 | 16177028202133682020981 | 5 | Sturtevant St | Wildemere St | Lawton St | Asphalt | Yes | 2021-06-10 15:29 | 2021-06-23 12:24 | 2021-06-25 14:07 |  | 2021-08-11 16:01 | 2021-06-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 14:22 |  | yes | no | no
3254 | 16175078202663782026058 | 5 | Taylor St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 15:02 | 2021-07-14 17:31 | 2021-07-15 18:59 |  | 2021-08-13 19:03 | 2021-07-17 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 13:47 |  | yes | no | no
3255 | 16175078202663782026058 | 5 | Taylor St | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-07-02 15:04 | 2021-07-13 21:42 | 2021-07-15 21:00 |  | 2021-08-13 19:05 | 2021-07-17 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 13:47 |  | yes | no | no
3267 | 16175078202710682026637 | 5 | Taylor St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-07-02 15:07 | 2021-07-14 17:16 | 2021-07-15 18:24 |  | 2021-08-13 19:01 | 2021-07-17 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-07-07 13:58 |  | yes | no | no
1681 | 47056908202811182028294 | 5 | Theodore St | Ellery St | Moran St | Asphalt | Yes | 2021-06-21 15:34 | 2021-06-28 20:31 | 2021-07-01 20:13 |  | 2021-08-04 22:40 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 15:34 |  | yes | no | no
1698 | 47056908202860182028816 | 5 | Theodore St | Elmwood St | McDougall St | Asphalt | Yes | 2021-06-21 15:57 | 2021-06-29 11:34 | 2021-07-01 20:00 |  | 2021-08-04 22:37 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 15:57 |  | yes | no | no
1676 | 47056908202777482028111 | 5 | Theodore St | Mount Elliott St | Ellery St | Asphalt | Yes | 2021-06-21 15:33 | 2021-06-28 20:08 | 2021-07-01 21:15 |  | 2021-08-04 22:43 | 2021-07-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-21 15:33 |  | yes | no | no
3380 | 47057648203027982029546 | 5 | Townsend St | Goethe Ave | Mack Ave | Asphalt | Yes | 2021-06-21 17:20 | 2021-07-08 15:50 | 2021-07-09 20:26 |  | 2021-08-03 19:10 | 2021-07-10 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-30 11:29 |  | yes | no | no
3516 | 47057648203285182032077 | 5 | Townsend St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 15:29 | 2021-07-07 15:52 | 2021-07-09 13:36 |  | 2021-08-04 20:30 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 17:09 |  | yes | no | no
3517 | 47057648203285182032077 | 5 | Townsend St | Kercheval St | E Vernor Hwy | Asphalt | Yes | 2021-06-21 15:29 | 2021-07-07 16:53 | 2021-07-09 13:36 |  | 2021-08-04 20:31 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-29 17:09 |  | yes | no | no
3158 | 16176078202347382023024 | 5 | Tuxedo St | Dexter | Wildemere St | Asphalt | Yes | 2021-06-10 19:13 | 2021-06-24 15:06 | 2021-07-09 14:41 |  | 2021-08-11 17:26 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:51 |  | yes | no | no
3159 | 16176078202347382023024 | 5 | Tuxedo St | Dexter | Wildemere St | Asphalt | Yes | 2021-06-10 19:32 | 2021-06-24 15:29 | 2021-07-09 15:16 |  | 2021-08-11 17:28 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 18:51 |  | yes | no | no
3124 | 16176078202260082022128 | 5 | Tuxedo St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 19:32 | 2021-06-24 16:05 | 2021-07-09 15:35 |  | 2021-08-11 17:30 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 19:04 |  | yes | no | no
3125 | 16176078202260082022128 | 5 | Tuxedo St | Lawton St | Linwood St | Asphalt | Yes | 2021-06-10 19:50 | 2021-06-24 16:34 | 2021-07-09 15:58 |  | 2021-08-11 17:31 | 2021-07-09 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 19:04 |  | yes | no | no
1783 | 15838068203147582031184 | 5 | Vicksburg St | Holmur St | Dexter Ave | Asphalt | Yes | 2021-06-11 16:38 | 2021-07-10 15:21 | 2021-07-14 17:50 |  | 2021-08-15 14:25 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 17:05 |  | yes | no | no
1921 | 47118578203603882035656 | 5 | Vinewood St | McGraw St | Milford St | Asphalt | Yes | 2021-06-28 12:45 | 2021-07-19 21:35 | 2021-07-26 14:16 |  | 2021-08-15 17:14 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 12:46 |  | yes | no | no
5251 | 16254018202891882028466 | 5 | Virginia Park St | 14th St | Rosa Parks Blvd | Asphalt | Yes Round 2 | 2021-09-10 17:09 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 17:09 |  | no | yes | no
5252 | 16254018202891882028466 | 5 | Virginia Park St | 14th St | Rosa Parks Blvd | Asphalt | Yes Round 2 | 2021-09-10 17:07 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-10 17:07 |  | no | yes | no
5738 | 16254018202773382027595 | 5 | Virginia Park St | Byron St | Merrill St | Asphalt | Yes | [6 empty] | HMA | [5 empty] | Yes |  |  |  | Yes | no | no
1714 | 16253108202927782028969 | 5 | Virginia Park St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-12 12:45 | 2021-07-15 13:00 | 2021-07-20 16:41 |  | 2021-08-14 15:25 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 13:53 |  | yes | no | no
1666 | 16254018202759582027282 | 5 | Virginia Park St | Merrill St | Virginia Park St | Asphalt | Yes | 2021-06-11 18:10 | 2021-07-15 16:26 | 2021-07-21 17:20 |  | 2021-08-14 13:07 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 16:44 |  | yes | no | no
1697 | 16254018202847582028139 | 5 | Virginia Park St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 18:09 | 2021-07-15 15:02 | 2021-07-21 18:16 |  | 2021-08-14 13:09 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 17:08 |  | yes | no | no
3298 | 16254018202813982027733 | 5 | Virginia Park St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 18:10 | 2021-07-15 16:06 | 2021-07-21 18:07 |  | 2021-08-14 13:08 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 17:14 |  | yes | no | no
3299 | 16254018202813982027733 | 5 | Virginia Park St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 18:10 | 2021-07-15 16:08 | 2021-07-21 17:34 |  | 2021-08-14 13:08 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 17:14 |  | yes | no | no
1722 | 16252058202953782029377 | 5 | W Bethune St | Churchill St | Woodrow Wilson St | Asphalt | Yes | 2021-06-12 13:01 | 2021-07-15 17:22 | 2021-07-21 20:19 |  | 2021-08-14 13:50 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 17:39 |  | yes | no | no
1712 | 16252058202923682029128 | 5 | W Bethune St | Kipling St | Poe St | Asphalt | Yes | 2021-06-12 13:01 | 2021-07-15 16:52 | 2021-07-21 21:19 |  | 2021-08-14 13:45 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 17:42 |  | yes | no | no
3156 | 47012828202356982023120 | 5 | W Boston Blvd | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 15:17 | 2021-06-29 14:06 | 2021-07-02 23:16 |  | 2021-08-13 14:12 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 16:08 |  | yes | no | no
3157 | 47012828202356982023120 | 5 | W Boston Blvd | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 15:17 | 2021-06-29 13:39 | 2021-07-02 22:58 |  | 2021-08-13 14:11 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 16:07 |  | yes | no | no
3162 | 16260018202361082023153 | 5 | W Boston Blvd | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 14:59 | 2021-06-28 20:10 | 2021-07-06 13:38 |  | 2021-08-13 13:59 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 17:16 |  | yes | no | no
3163 | 16260018202361082023153 | 5 | W Boston Blvd | 14th St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-11 14:59 | 2021-06-28 20:17 | 2021-07-06 14:09 |  | 2021-08-13 14:00 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 17:18 |  | yes | no | no
3190 | 47012828202407782023569 | 5 | W Boston Blvd | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-11 15:16 | 2021-06-29 14:35 | 2021-07-06 16:07 |  | 2021-08-13 14:14 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 16:23 |  | yes | no | no
3196 | 16260018202415782023610 | 5 | W Boston Blvd | La Salle Blvd | 14th St | Asphalt | Yes | 2021-06-11 14:49 | 2021-06-28 19:19 | 2021-07-06 13:28 |  | 2021-08-13 13:59 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 17:04 |  | yes | no | no
3210 | 47012828209137382024077 | 5 | W Boston Blvd | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-11 15:16 | 2021-06-29 15:40 | 2021-07-06 16:58 |  | 2021-08-13 14:16 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 16:47 |  | yes | no | no
3211 | 47012828209137382024077 | 5 | W Boston Blvd | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-11 15:16 | 2021-06-29 15:07 | 2021-07-06 16:37 |  | 2021-08-13 14:15 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 16:42 |  | yes | no | no
3212 | 16260018202487282024157 | 5 | W Boston Blvd | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-11 14:48 | 2021-06-28 17:39 | 2021-07-06 12:38 |  | 2021-08-13 13:58 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 16:52 |  | yes | no | no
3213 | 16260018202487282024157 | 5 | W Boston Blvd | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-06-11 14:49 | 2021-06-28 18:54 | 2021-07-06 13:28 |  | 2021-08-13 13:58 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 16:52 |  | yes | no | no
3140 | 47012828202312082022630 | 5 | W Boston Blvd | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 15:34 | 2021-06-29 13:28 | 2021-07-02 22:15 |  | 2021-08-13 14:11 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 15:56 |  | yes | no | no
3141 | 47012828202312082022630 | 5 | W Boston Blvd | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 15:34 | 2021-06-29 12:08 | 2021-07-02 21:58 |  | 2021-08-13 14:11 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 15:55 |  | yes | no | no
3142 | 16260018202315382022672 | 5 | W Boston Blvd | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 14:59 | 2021-06-28 20:53 | 2021-07-06 14:26 |  | 2021-08-13 14:02 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 17:24 |  | yes | no | no
3143 | 16260018202315382022672 | 5 | W Boston Blvd | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | 2021-06-11 14:59 | 2021-06-28 21:26 | 2021-07-06 14:39 |  | 2021-08-13 14:03 | 2021-07-06 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-16 17:45 |  | yes | no | no
1587 | 47012828202263082022356 | 5 | W Boston Blvd | Woodrow Wilson St | S M 10 Service Drive | Asphalt | Yes | 2021-06-11 15:34 | 2021-06-29 11:39 | 2021-07-02 21:45 |  | 2021-08-13 14:06 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 16:50 |  | yes | no | no
1589 | 16260018202267282098584 | 5 | W Boston Blvd | Woodrow Wilson St | S M 10 Service Drive | Asphalt | Yes | 2021-06-11 15:00 | 2021-06-28 22:11 | 2021-07-02 21:16 |  | 2021-08-13 14:04 | 2021-07-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 16:50 |  | yes | no | no
1516 | 16195028201865282018283 | 5 | W Buena Vista St | Ellen St | Rosa Parks Blvd | Asphalt | Yes | 2021-06-10 22:57 | 2021-08-24 20:24 | 2021-08-30 17:55 |  |  | 2021-08-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:10 |  | yes | no | no
3236 | 15980048202588182025383 | 5 | W Philadelphia St | 3rd St | 2nd Ave | Asphalt | Yes | 2021-06-12 13:41 | 2021-06-22 18:23 | 2021-06-28 20:49 |  | 2021-08-16 15:13 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 17:56 |  | yes | no | no
3237 | 15980048202588182025383 | 5 | W Philadelphia St | 3rd St | 2nd Ave | Asphalt | Yes | 2021-06-12 13:37 | 2021-06-22 18:58 | 2021-06-28 20:48 |  | 2021-08-16 15:15 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 17:56 |  | yes | no | no
1701 | 16254038202868382028352 | 5 | W Philadelphia St | La Salle Blvd | 14th St | Asphalt | Yes | 2021-09-10 17:15 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 17:15 |  | yes | no | no
3336 | 16254038202909782028683 | 5 | W Philadelphia St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-09-10 17:20 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 17:20 |  | yes | no | no
3337 | 16254038202909782028683 | 5 | W Philadelphia St | Linwood St | La Salle Blvd | Asphalt | Yes | 2021-09-10 17:18 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-10 17:18 |  | yes | no | no
1644 | 15980048202619482025881 | 5 | W Philadelphia St | N M 10 Service Drive | 3rd St | Asphalt | Yes | 2021-06-12 15:12 | 2021-06-22 17:54 | 2021-06-28 21:18 |  | 2021-08-16 15:13 | 2021-06-29 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 17:37 |  | yes | no | no
3272 | 16254078202749982026970 | 5 | W Philadelphia St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:58 | 2021-07-15 14:30 | 2021-07-21 12:12 |  | 2021-08-14 13:04 | 2021-07-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 15:47 |  | yes | no | no
3273 | 16254078202749982026970 | 5 | W Philadelphia St | Woodrow Wilson St | Byron St | Asphalt | Yes | 2021-06-11 17:58 | 2021-07-15 13:53 | 2021-07-21 12:12 |  | 2021-08-14 13:04 | 2021-07-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 15:56 |  | yes | no | no
1900 | 47002188203511582034848 | 5 | Wabash St | Bryant St | Merrick St | Asphalt | Yes | 2021-06-28 12:59 | 2021-07-19 20:55 | 2021-07-26 13:39 |  | 2021-08-15 17:48 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-28 13:00 |  | yes | no | no
5382 | 16263088201762382017312 | 5 | Waverly St | Rosa Parks Blvd | Woodrow Wilson St | Asphalt | Yes | [6 empty] | HMA |  |  |  | Coordinate with DPW Residential Resurfacing | Yes | No |  |  |  | Yes | No | no
1593 | 16130098202265382022338 | 5 | Wildemere St | Elmhurst St | Monterey St | Asphalt | Yes | 2021-06-10 19:03 | 2021-06-19 18:07 | 2021-07-01 17:20 |  | 2021-08-11 17:19 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:53 |  | yes | no | no
1565 | 16130098202082782020552 | 5 | Wildemere St | Leslie St | Glendale St | Asphalt | Yes | 2021-06-10 14:27 | 2021-06-19 15:46 | 2021-06-23 17:59 |  | 2021-08-11 14:47 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 12:51 |  | yes | no | no
1760 | 16178028203097282030660 | 5 | Wildemere St | Montgomery St | Vicksburg St | Asphalt | Yes | 2021-06-11 16:50 | 2021-07-12 16:52 | 2021-07-15 18:35 |  | 2021-08-15 15:25 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 18:39 |  | yes | no | no
1795 | 16178028203209082031785 | 5 | Wildemere St | Northwestern St | Hogarth St | Asphalt | Yes | 2021-06-12 12:22 | 2021-07-12 14:05 | 2021-07-15 16:03 |  | 2021-08-15 15:28 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 18:06 |  | yes | no | no
1582 | 16130098202194582021617 | 5 | Wildemere St | Richton St | Cortland St | Asphalt | Yes | 2021-06-10 14:45 | 2021-06-19 16:44 | 2021-07-01 13:06 |  | 2021-08-11 16:15 | 2021-07-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:52 |  | yes | no | no
1580 | 16130098202133682021050 | 5 | Wildemere St | Sturtevant St | Fullerton St | Asphalt | Yes | 2021-06-10 14:50 | 2021-06-19 16:14 | 2021-06-23 22:21 |  | 2021-08-11 15:08 | 2021-06-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 13:50 |  | yes | no | no
1822 | 16178028203275482032360 | 5 | Wildemere St | W Grand Blvd | Lothrop St | Asphalt | Yes | 2021-06-12 12:21 | [5 empty] | HMA | No |  |  | Resurfacing is required | No | No | poor pavement |  |  | yes | no | no
1778 | 16178028203148082031241 | 5 | Wildemere St | Whitney St | Columbus St | Asphalt | Yes | 2021-06-11 16:55 | 2021-07-12 15:27 | 2021-07-15 17:33 |  | 2021-08-15 15:27 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-23 18:08 |  | yes | no | no
2928 | 15776078201874682018256 | 5 | Woodland St | Woodward | John R St | Asphalt | Yes | 2021-06-12 14:14 | 2021-06-17 20:05 | 2021-06-24 17:26 |  | 2021-08-16 13:14 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 12:25 |  | yes | no | no
2929 | 15776078201874682018256 | 5 | Woodland St | Woodward | John R St | Asphalt | Yes | 2021-06-12 14:01 | 2021-06-17 19:34 | 2021-06-24 17:11 |  | 2021-08-16 13:15 | 2021-06-25 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-14 12:25 |  | yes | no | no
1622 | 47056178202441282023848 | 5 | Woodrow Wilson St | Atkinson St | Edison St | Asphalt | Yes | 2021-06-11 17:32 | 2021-06-30 13:41 | 2021-07-06 20:29 |  | 2021-08-13 16:10 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:40 |  | yes | no | no
1607 | 47056178202347882023161 | 5 | Woodrow Wilson St | Longfellow St | Chicago Blvd | Asphalt | Yes | 2021-06-11 13:57 | 2021-06-29 16:20 | 2021-07-06 20:19 |  | 2021-08-13 15:58 | 2021-07-07 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:32 |  | yes | no | no
1632 | 47056178202560682025142 | 5 | Woodrow Wilson St | Taylor St | Clairmount St | Asphalt | Yes | 2021-06-11 14:55 | 2021-06-30 16:45 | 2021-07-21 16:16 |  | 2021-08-14 12:41 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-11 17:42 |  | yes | no | no
3400 | 16252078203028382029377 | 5 | Woodrow Wilson St | W Grand Blvd | W Bethune St | Asphalt | Yes | 2021-06-12 16:46 | 2021-07-15 18:22 | 2021-07-21 21:48 |  | 2021-08-14 13:52 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 18:03 |  | yes | no | no
3401 | 16252078203028382029377 | 5 | Woodrow Wilson St | W Grand Blvd | W Bethune St | Asphalt | Yes | 2021-06-12 16:47 | 2021-07-15 17:58 | 2021-07-21 23:03 |  | 2021-08-14 13:52 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-06-17 18:03 |  | yes | no | no
1945 | 15840068203696482036367 | 6 | 16th St | W Forest Ave | W Hancock St | Asphalt | Yes | 2021-07-08 12:53 | 2021-07-12 14:34 | 2021-07-15 19:48 |  |  | 2021-07-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 15:48 |  | yes | no | no
2083 | 47055988204493482044511 | 6 | 17th St | Howard St | Porter St | Asphalt | Yes | 2021-07-08 17:09 | 2021-07-12 19:58 | 2021-07-15 13:29 |  | 2021-09-07 13:13 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 16:46 |  | yes | no | no
2077 | 47055988204438582043857 | 6 | 17th St | Porter St | Bagley St | Asphalt | Yes | 2021-07-08 17:09 | 2021-07-12 19:58 | 2021-07-15 13:10 |  | 2021-09-07 13:12 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 16:46 |  | yes | no | no
2084 | 15903028204500982044605 | 6 | 18th St | Howard St | Porter St | Asphalt | Yes | 2021-07-08 17:10 | 2021-07-12 20:40 | 2021-07-15 13:53 |  | 2021-09-07 13:12 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 17:14 |  | yes | no | no
2078 | 15903028204446682043940 | 6 | 18th St | Porter St | Bagley St | Asphalt | Yes | 2021-07-08 17:09 | 2021-07-12 20:41 | 2021-07-15 13:53 |  | 2021-09-07 13:11 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 17:08 |  | yes | no | no
2089 | 15903028204529282045009 | 6 | 18th St | W Lafayette Blvd | Howard St | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  |  |  | yes | no | no
1989 | 47055638204017982039675 | 6 | 24th St | Magnolia St | Selden St | Asphalt | Yes | 2021-07-10 14:18 | 2021-07-17 21:34 | 2021-07-19 18:57 |  | 2021-09-03 17:39 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 18:20 |  | yes | no | no
1998 | 47055638204066882040179 | 6 | 24th St | Martin Luther King Jr Blvd | Magnolia St | Asphalt | Yes | 2021-07-10 14:18 | 2021-07-19 12:15 | 2021-07-19 18:57 |  | 2021-09-03 17:42 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 18:31 |  | yes | no | no
2076 | 47055638204421782043912 | 6 | 24th St | Randall St | Ruskin St | Asphalt | Yes | 2021-07-10 14:33 | 2021-07-14 15:40 | 2021-07-15 20:39 |  | 2021-09-02 19:11 | 2021-07-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 12:53 |  | yes | no | no
2014 | 15813058204133182040804 | 6 | 25th St | Ash St | Martin Luther King Jr Blvd | Asphalt | Yes | 2021-07-10 14:26 | 2021-07-17 21:59 | 2021-07-19 19:23 |  | 2021-09-03 17:57 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 19:27 |  | yes | no | no
2029 | 15813058204195882041331 | 6 | 25th St | Michigan Ave | Ash St | Asphalt | Yes | 2021-07-10 14:25 | 2021-07-17 22:19 | 2021-07-19 19:29 |  | 2021-09-03 17:58 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 19:30 |  | yes | no | no
4330 | 16082018204455582043725 | 6 | 25th St | W Vernor Hwy | Toledo St | Asphalt | Yes | 2021-07-10 15:25 | 2021-07-14 16:05 | 2021-07-15 21:28 |  | 2021-09-02 18:38 | 2021-07-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 14:43 |  | yes | no | no
4331 | 16082018204455582043725 | 6 | 25th St | W Vernor Hwy | Toledo St | Asphalt | Yes | 2021-07-10 15:25 | 2021-07-14 17:03 | 2021-07-15 21:21 |  | 2021-09-02 18:36 | 2021-07-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 15:07 |  | yes | no | no
4332 | 16082018204455582043725 | 6 | 25th St | W Vernor Hwy | Toledo St | Asphalt | Yes | 2021-07-10 15:25 | 2021-07-14 17:27 | 2021-07-15 21:02 |  | 2021-09-02 18:34 | 2021-07-17 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 15:15 |  | yes | no | no
1975 | 15773028203900482038488 | 6 | 30th St | Horatio St | Herbert St | Asphalt | Yes | 2021-07-17 15:37 | 2021-07-19 17:49 | 2021-07-20 13:11 |  | 2021-09-03 16:46 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 15:09 |  | yes | no | no
3714 | 15812018204142982040607 | 6 | 33rd St | Jackson St | Buchanan St | Asphalt | Yes | 2021-07-17 15:37 | 2021-07-24 16:02 | 2021-07-27 15:38 |  | 2021-09-03 16:10 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 16:52 |  | yes | no | no
3715 | 15812018204142982040607 | 6 | 33rd St | Jackson St | Buchanan St | Asphalt | Yes | 2021-07-17 15:37 | 2021-07-24 15:19 | 2021-07-27 13:59 |  | 2021-09-03 16:08 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 16:52 |  | yes | no | no
4898 | 47055238204266882043007 | 6 | 51st St | Conrad St | Saint Stephens St | Asphalt | Yes Round 2 | 2021-09-17 18:08 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:40 |  | no | yes | no
4904 | 47055238204224682042668 | 6 | 51st St | Michigan Ave | Conrad St | Asphalt | Yes Round 2 | 2021-09-17 18:08 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:40 |  | no | yes | no
4252 | 15771098204234282041200 | 6 | Addison St | McGraw St | Dennison St | Asphalt | Yes | 2021-07-21 14:29 | 2021-07-28 12:31 | 2021-08-03 12:45 |  | 2021-08-19 13:26 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:33 |  | yes | no | no
4253 | 15771098204234282041200 | 6 | Addison St | McGraw St | Dennison St | Asphalt | Yes | 2021-07-21 14:27 | 2021-07-28 12:54 | 2021-08-02 22:27 |  | 2021-08-19 13:26 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:41 |  | yes | no | no
4254 | 15771098204234282041200 | 6 | Addison St | McGraw St | Dennison St | Asphalt | Yes | 2021-07-21 14:25 | 2021-07-28 13:43 | 2021-08-02 22:44 |  | 2021-08-19 13:26 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:50 |  | yes | no | no
3556 | 16184018203338882032569 | 6 | Alpine St | Mackenzie St | Joy Rd | Asphalt | Yes | 2021-07-12 18:44 | 2021-07-20 18:38 | 2021-07-26 21:39 |  | 2021-08-18 19:14 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 15:19 |  | yes | no | no
3557 | 16184018203338882032569 | 6 | Alpine St | Mackenzie St | Joy Rd | Asphalt | Yes | 2021-07-12 18:44 | 2021-07-20 17:49 | 2021-07-26 21:50 |  | 2021-08-18 19:13 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 15:19 |  | yes | no | no
3610 | 16171098203599182035118 | 6 | American St | Diversey | Tireman St | Asphalt | Yes | 2021-07-13 15:00 | 2021-07-21 12:21 | 2021-07-27 14:31 |  | 2021-08-18 13:14 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 16:44 |  | yes | no | no
3611 | 16171098203599182035118 | 6 | American St | Diversey | Tireman St | Asphalt | Yes | 2021-07-13 15:00 | 2021-07-21 12:48 | 2021-07-27 14:16 |  | 2021-08-18 13:11 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 16:44 |  | yes | no | no
3550 | 16183088203334382032524 | 6 | American St | Mackenzie St | Joy Rd | Asphalt | Yes | 2021-07-12 18:45 | 2021-07-20 19:21 | 2021-07-26 21:12 |  | 2021-08-18 19:06 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 15:02 |  | yes | no | no
3551 | 16183088203334382032524 | 6 | American St | Mackenzie St | Joy Rd | Asphalt | Yes | 2021-07-12 18:44 | 2021-07-20 19:39 | 2021-07-26 20:50 |  | 2021-08-18 19:09 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 15:02 |  | yes | no | no
3624 | 16171098203681482035991 | 6 | American St | Majestic St | Diversey | Asphalt | Yes | 2021-07-13 15:00 | 2021-07-21 13:53 | 2021-07-27 15:00 |  | 2021-08-18 13:17 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 17:21 |  | yes | no | no
3625 | 16171098203681482035991 | 6 | American St | Majestic St | Diversey | Asphalt | Yes | 2021-07-13 15:00 | 2021-07-21 13:15 | 2021-07-27 14:48 |  | 2021-08-18 13:16 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 17:21 |  | yes | no | no
3652 | 16171098203753582036814 | 6 | American St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 15:00 | 2021-07-21 15:07 | 2021-07-27 15:23 |  | 2021-08-18 13:20 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 17:22 |  | yes | no | no
3653 | 16171098203753582036814 | 6 | American St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 15:00 | 2021-07-21 14:41 | 2021-08-03 17:13 |  | 2021-08-18 13:19 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 17:21 |  | yes | no | no
1936 | 15841088203677482036516 | 6 | Avery St | Calumet St | W Canfield St | Asphalt | Yes | 2021-07-08 15:29 | 2021-07-10 16:58 | 2021-07-14 19:34 |  | 2021-08-17 18:31 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:29 |  | yes | no | no
1956 | 15841088203760482037296 | 6 | Avery St | Grand River Ave | W Alexandrine St | Asphalt | Yes | 2021-07-08 15:42 | 2021-07-10 15:24 | 2021-07-14 21:01 |  | 2021-08-17 18:33 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:45 |  | yes | no | no
1925 | 15841088203625782035871 | 6 | Avery St | Lysander St | W Forest Ave | Asphalt | Yes | 2021-07-08 14:11 | 2021-07-10 17:41 | 2021-07-14 19:13 |  | 2021-08-17 18:30 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:25 |  | yes | no | no
1881 | 15841088203471982034355 | 6 | Avery St | Putnam St | Merrick St | Asphalt | Yes | 2021-07-08 13:08 | 2021-07-09 10:41 | 2021-07-14 18:18 |  | 2021-08-17 18:21 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:05 |  | yes | no | no
1948 | 15841088203729682037018 | 6 | Avery St | W Alexandrine St | W Willis St | Asphalt | Yes | 2021-07-08 15:29 | 2021-07-10 15:58 | 2021-07-14 21:01 |  | 2021-08-17 18:31 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:36 |  | yes | no | no
1914 | 15841088203587182035487 | 6 | Avery St | W Forest Ave | W Hancock St | Asphalt | Yes | 2021-07-08 13:59 | 2021-07-12 11:42 | 2021-07-14 19:00 |  | 2021-08-17 18:26 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:20 |  | yes | no | no
1907 | 15841088203548782035110 | 6 | Avery St | W Hancock St | W Warren Ave | Asphalt | Yes | 2021-07-08 13:44 | 2021-07-10 18:22 | 2021-07-14 18:40 |  | 2021-08-17 18:24 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:13 |  | yes | no | no
1901 | 15841088203511082034719 | 6 | Avery St | W Warren Ave | Putnam St | Asphalt | Yes | 2021-07-08 13:11 | 2021-07-10 18:50 | 2021-07-14 18:24 |  | 2021-08-17 18:23 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:08 |  | yes | no | no
4906 | 16171018205013782049915 | 6 | Avis St | Woodmere St | Elsmere St | Asphalt | Yes Round 2 | 2021-09-17 17:46 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:39 |  | no | yes | no
2082 | 47122398204479582044639 | 6 | Bagley St | 25th St | 24th St | Asphalt | Yes | 2021-07-10 14:42 | 2021-07-14 18:12 | 2021-07-17 19:28 |  | 2021-09-02 16:10 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 14:28 |  | yes | no | no
2085 | 47122398204502282044905 | 6 | Bagley St | Vinewood St | W Grand Blvd | Asphalt | Yes | 2021-07-10 16:28 | 2021-07-14 18:49 | 2021-07-17 16:44 |  | 2021-09-02 16:12 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 15:23 |  | yes | no | no
3682 | 16107068203854082038067 | 6 | Barlum St | Martin St | Cicotte St | Asphalt | Yes | 2021-07-21 12:33 | 2021-07-26 17:18 | 2021-08-02 13:49 |  | 2021-08-19 20:39 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 18:02 |  | yes | no | no
3683 | 16107068203854082038067 | 6 | Barlum St | Martin St | Cicotte St | Asphalt | Yes | 2021-07-21 12:31 | 2021-07-26 16:42 | 2021-08-02 13:38 |  | 2021-08-19 20:38 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 18:02 |  | yes | no | no
3612 | 16108068203602182035555 | 6 | Barton St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 16:02 | 2021-07-23 12:34 | 2021-07-28 18:03 |  | 2021-08-18 15:58 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:17 |  | yes | no | no
3613 | 16108068203602182035555 | 6 | Barton St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 16:03 | 2021-08-24 16:54 | 2021-08-30 17:00 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:17 |  | yes | no | no
1327 | 16113048204840782048231 | 6 | Beard St | Chatfield St | Bostwick St | Asphalt | Yes | 2021-07-12 17:38 | 2021-07-20 20:22 | 2021-07-21 18:02 |  | 2021-09-02 14:03 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:16 |  | yes | no | no
1338 | 16113048204919982048988 | 6 | Beard St | Lexington St | Army St | Asphalt | Yes | 2021-07-12 17:41 | 2021-07-21 12:29 | 2021-07-21 18:39 |  | 2021-09-02 13:55 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:35 |  | yes | no | no
1334 | 16113048204878382048607 | 6 | Beard St | Lisbon St | Rowan St | Asphalt | Yes | 2021-07-12 17:41 | 2021-07-20 21:05 | 2021-07-21 18:15 |  | 2021-09-02 13:59 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:29 |  | yes | no | no
1751 | 16101058203028982030109 | 6 | Beechwood St | Greenway St | Ridgewood St | Asphalt | Yes | 2021-07-12 18:18 | 2021-07-20 14:42 | 2021-07-26 18:37 |  | 2021-08-26 12:46 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 12:25 |  | yes | no | no
1748 | 16101058203010982029883 | 6 | Beechwood St | Ridgewood St | Woodside | Asphalt | Yes | 2021-07-12 18:18 | 2021-07-20 15:08 | 2021-07-26 18:51 |  | 2021-08-26 12:46 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 12:29 |  | yes | no | no
1758 | 16101058203054582030394 | 6 | Beechwood St | Whitfield St | Underwood St | Asphalt | Yes | 2021-07-12 18:18 | 2021-07-20 13:54 | 2021-07-26 17:55 |  | 2021-08-26 12:50 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 12:22 |  | yes | no | no
3590 | 16108098203534682035345 | 6 | Belfast St | Rangoon St | Livernois Ave & Diversey | Asphalt | Yes | 2021-07-20 15:51 | 2021-07-23 13:19 | 2021-07-28 19:08 |  | 2021-08-18 15:58 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:04 |  | yes | no | no
3591 | 16108098203534682035345 | 6 | Belfast St | Rangoon St | Livernois Ave & Diversey | Asphalt | Yes | 2021-07-20 15:54 | 2021-07-23 13:02 | 2021-07-28 19:49 |  | 2021-08-18 15:58 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:04 |  | yes | no | no
2081 | 16095088204440582044198 | 6 | Brandon St | Clark St | Scotten St | Asphalt | Yes | 2021-07-10 15:16 | 2021-07-15 14:49 | 2021-07-19 16:43 |  | 2021-09-02 20:14 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:23 |  | yes | no | no
4339 | 16099018204499282044545 | 6 | Brandon St | Junction St | McKinstry St | Asphalt | Yes | 2021-07-10 17:59 | 2021-07-15 17:32 | 2021-07-19 15:44 |  | 2021-09-02 20:24 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:48 |  | yes | no | no
4340 | 16099018204499282044545 | 6 | Brandon St | Junction St | McKinstry St | Asphalt | Yes | 2021-07-10 17:59 | 2021-07-15 18:00 | 2021-07-19 15:44 |  | 2021-09-02 20:25 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:48 |  | yes | no | no
4341 | 16099018204499282044545 | 6 | Brandon St | Junction St | McKinstry St | Asphalt | Yes | 2021-07-10 17:59 | 2021-07-15 18:18 | 2021-07-26 15:43 |  | 2021-09-02 20:26 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:43 |  | yes | no | no
3744 | 16109168204354782043908 | 6 | Bulwer St | Martin St | Parkinson St | Asphalt | Yes | 2021-07-20 13:23 | 2021-07-22 15:19 | 2021-07-28 16:40 |  | 2021-08-26 19:22 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 12:22 |  | yes | no | no
3745 | 16109168204354782043908 | 6 | Bulwer St | Martin St | Parkinson St | Asphalt | Yes | 2021-07-20 13:19 | 2021-07-22 16:04 | 2021-07-28 16:56 |  | 2021-08-26 19:23 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 12:22 |  | yes | no | no
3602 | 16111088203595282035068 | 6 | Burnette St | Diversey | Tireman St | Asphalt | Yes | 2021-07-13 15:42 | 2021-07-21 22:10 | 2021-08-03 17:55 |  | 2021-08-18 14:23 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 16:27 |  | yes | no | no
3603 | 16111088203595282035068 | 6 | Burnette St | Diversey | Tireman St | Asphalt | Yes | 2021-07-13 15:41 | 2021-07-21 22:29 | 2021-07-27 18:49 |  | 2021-08-18 14:22 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 16:27 |  | yes | no | no
3620 | 16111088203677182035952 | 6 | Burnette St | Majestic St | Diversey | Asphalt | Yes | 2021-07-13 17:26 | 2021-07-21 21:16 | 2021-07-27 19:33 |  | 2021-08-18 14:24 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 17:07 |  | yes | no | no
3621 | 16111088203677182035952 | 6 | Burnette St | Majestic St | Diversey | Asphalt | Yes | 2021-07-13 15:47 | 2021-07-21 21:40 | 2021-07-27 19:06 |  | 2021-08-18 14:23 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 17:07 |  | yes | no | no
3646 | 16111088203750282036771 | 6 | Burnette St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 17:27 | 2021-07-21 20:52 | 2021-07-27 20:31 |  | 2021-08-18 14:30 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 17:33 |  | yes | no | no
3647 | 16111088203750282036771 | 6 | Burnette St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 17:26 | 2021-07-21 20:54 | 2021-07-27 20:16 |  | 2021-08-18 14:30 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 17:33 |  | yes | no | no
3460 | 16185078203068782087794 | 6 | Burnette St | Westfield St | W Chicago St | Asphalt | Yes | 2021-07-12 18:44 | 2021-07-20 15:39 | 2021-07-26 19:47 |  | 2021-08-18 19:22 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 13:58 |  | yes | no | no
3461 | 16185078203068782087794 | 6 | Burnette St | Westfield St | W Chicago St | Asphalt | Yes | 2021-07-12 18:43 | 2021-07-20 16:06 | 2021-07-26 19:28 |  | 2021-08-18 19:23 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 13:58 |  | yes | no | no
4258 | 15808028204378082042783 | 6 | Cabot St | Arnold St | Michigan Ave | Asphalt | Yes | 2021-07-20 14:37 | 2021-07-23 18:25 | 2021-07-29 17:35 |  | 2021-08-27 14:11 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:50 |  | yes | no | no
4259 | 15808028204378082042783 | 6 | Cabot St | Arnold St | Michigan Ave | Asphalt | Yes | 2021-07-20 14:41 | 2021-07-23 18:39 | 2021-07-29 17:14 |  | 2021-08-27 14:09 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:29 |  | yes | no | no
4260 | 15808028204378082042783 | 6 | Cabot St | Arnold St | Michigan Ave | Asphalt | Yes | 2021-07-20 14:44 | 2021-07-23 18:56 | 2021-07-29 17:14 |  | 2021-08-27 14:08 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:28 |  | yes | no | no
4264 | 15808028204554182044767 | 6 | Cabot St | John Kronk St | Saint John St | Asphalt | Yes | 2021-07-20 14:24 | 2021-07-23 17:13 | 2021-07-29 20:58 |  | 2021-08-27 14:21 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 19:02 |  | yes | no | no
4265 | 15808028204554182044767 | 6 | Cabot St | John Kronk St | Saint John St | Asphalt | Yes | 2021-07-20 14:27 | 2021-07-23 17:41 | 2021-07-29 20:48 |  | 2021-08-27 14:20 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 19:01 |  | yes | no | no
4266 | 15808028204554182044767 | 6 | Cabot St | John Kronk St | Saint John St | Asphalt | Yes | 2021-07-20 14:28 | 2021-07-23 17:40 | 2021-07-29 18:32 |  | 2021-08-27 14:20 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 19:01 |  | yes | no | no
4261 | 15808028204476782043780 | 6 | Cabot St | Saint John St | Arnold St | Asphalt | Yes | 2021-07-20 14:30 | 2021-07-23 17:11 | 2021-07-29 18:17 |  | 2021-08-27 14:20 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 19:01 |  | yes | no | no
4262 | 15808028204476782043780 | 6 | Cabot St | Saint John St | Arnold St | Asphalt | Yes | 2021-07-20 14:31 | 2021-07-23 18:05 | 2021-07-29 17:58 |  | 2021-08-27 14:12 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 19:01 |  | yes | no | no
4263 | 15808028204476782043780 | 6 | Cabot St | Saint John St | Arnold St | Asphalt | Yes | 2021-07-20 14:34 | 2021-07-24 12:03 | 2021-07-29 17:47 |  | 2021-08-27 14:11 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 19:01 |  | yes | no | no
1331 | 16168068204854182048029 | 6 | Cabot St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 14:18 | 2021-08-21 11:55 | 2021-08-27 15:41 |  | 2021-09-01 17:22 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:27 |  | yes | no | no
1308 | 16104078204745282047290 | 6 | Cadet St | Casgrain St | Infantry St | Asphalt | Yes | 2021-07-12 16:41 | 2021-07-20 19:38 | 2021-07-20 22:20 |  | 2021-09-02 14:15 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:08 |  | yes | no | no
1302 | 16104078204717582047033 | 6 | Cadet St | Livernois Ave | Dragoon St | Asphalt | Yes | 2021-07-12 16:41 | 2021-07-20 18:43 | 2021-07-20 22:05 |  | 2021-09-02 14:16 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:00 |  | yes | no | no
2734 | 47055068208680382048444 | 6 | Cahalan St | N Green St | Central St | Asphalt | Yes | 2021-08-17 15:35 | 2021-08-23 15:44 | 2021-08-28 19:02 |  | 2021-09-01 20:43 | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 13:30 |  | yes | no | no
2735 | 47055068208680382048444 | 6 | Cahalan St | N Green St | Central St | Asphalt | Yes | 2021-08-17 15:35 | 2021-08-23 16:56 | 2021-08-28 19:15 |  | 2021-09-01 20:45 | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 13:30 |  | yes | no | no
4887 | 15841048203695582036774 | 6 | Calumet St | Rosa Parks Blvd | Avery St | Asphalt | Yes Round 2 | 2021-09-17 18:22 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:41 |  | no | yes | no
2090 | 16091028204521782045005 | 6 | Campbell St | Brandon St | Plumer St | Asphalt | Yes | 2021-07-10 18:00 | 2021-07-15 20:54 | 2021-07-19 13:01 |  | 2021-09-02 20:32 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:52 |  | yes | no | no
1288 | 16091028204610382045898 | 6 | Campbell St | Newberry St | McMillan St | Asphalt | Yes | 2021-07-10 18:00 | 2021-07-20 11:59 | 2021-07-20 16:45 |  | 2021-09-02 20:44 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 18:52 |  | yes | no | no
2095 | 16091028204569782045451 | 6 | Campbell St | Romeyn St | Toledo St | Asphalt | Yes | 2021-07-10 15:37 | 2021-07-15 20:55 | 2021-07-19 13:00 |  | 2021-09-02 20:35 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 18:05 |  | yes | no | no
4018 | 16182088203462682033561 | 6 | Carbondale St | Vancouver St | Linsdale St | asphalt | Yes | 2021-07-12 18:56 | 2021-07-20 22:10 | 2021-07-28 13:08 |  | 2021-08-18 18:55 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 17:07 |  | yes | no | no
4019 | 16182088203462682033561 | 6 | Carbondale St | Vancouver St | Linsdale St | asphalt | Yes | 2021-07-12 18:56 | 2021-07-20 21:44 | 2021-07-28 12:56 |  | 2021-08-18 18:54 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 17:07 |  | yes | no | no
4020 | 16182088203462682033561 | 6 | Carbondale St | Vancouver St | Linsdale St | asphalt | Yes | 2021-07-12 18:55 | 2021-07-20 21:15 | 2021-07-28 12:20 |  | 2021-08-18 18:53 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 17:07 |  | yes | no | no
1317 | 16117018204783882047343 | 6 | Carson St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 13:52 | 2021-08-23 18:49 | 2021-08-28 12:45 |  | 2021-09-01 17:47 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:51 |  | yes | no | no
1326 | 16167058204840282047924 | 6 | Casgrain St | Army St | Regular St | Asphalt | Yes | 2021-07-12 16:41 | 2021-07-20 18:47 | 2021-07-21 20:29 |  | 2021-09-02 14:11 | 2021-07-23 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:36 |  | yes | no | no
1335 | 16167058204885382048402 | 6 | Casgrain St | W Lafayette Blvd | Army St | Asphalt | Yes | 2021-08-17 13:11 | 2021-08-24 17:44 | 2021-08-28 20:21 |  | 2021-09-02 14:09 | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:11 |  | yes | no | no
1293 | 16115068204667782046332 | 6 | Casper St | Belle St | Dix St | Asphalt | Yes | 2021-08-17 13:35 | 2021-08-27 14:44 | 2021-08-28 13:10 |  | 2021-09-01 19:03 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:35 |  | yes | no | no
2718 | 16115068204713682046677 | 6 | Casper St | Pitt St | Belle St | Asphalt | Yes | 2021-08-17 13:43 | 2021-08-24 12:14 | 2021-08-28 13:30 |  | 2021-09-01 19:07 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:43 |  | yes | no | no
2719 | 16115068204713682046677 | 6 | Casper St | Pitt St | Belle St | Asphalt | Yes | 2021-08-17 13:42 | 2021-08-21 18:33 | 2021-08-28 13:24 |  | 2021-09-01 19:05 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:42 |  | yes | no | no
1312 | 16115068204763682047136 | 6 | Casper St | W Vernor Hwy | Pitt St | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  |  |  | yes | no | no
1316 | 16091018204792782047744 | 6 | Cavalry St | Amherst St | Howard St | Asphalt | Yes | 2021-07-12 14:28 | 2021-07-20 18:10 | 2021-07-20 21:49 |  | 2021-09-02 14:27 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:57 |  | yes | no | no
1310 | 16091018204754682047308 | 6 | Cavalry St | Porter St | Rogers St | Asphalt | Yes | 2021-07-10 15:58 | 2021-07-20 14:12 | 2021-07-20 17:37 |  | 2021-09-02 14:32 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:48 |  | yes | no | no
1990 | 15772038204001282039474 | 6 | Cecil St | McGraw St | Wagner St | Asphalt | Yes | 2021-07-20 18:11 | 2021-07-23 21:58 | 2021-07-30 20:09 |  | 2021-08-19 18:30 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 13:44 |  | yes | no | no
3700 | 15772038203947482038729 | 6 | Cecil St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-20 18:13 | 2021-07-23 22:25 | 2021-07-30 20:25 |  | 2021-08-19 18:31 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 13:39 |  | yes | no | no
3701 | 15772038203947482038729 | 6 | Cecil St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-20 18:15 | 2021-07-23 22:49 | 2021-07-30 21:29 |  | 2021-08-19 18:31 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 13:38 |  | yes | no | no
1332 | 16113108204866782048407 | 6 | Chatfield St | N Green St | Beard St | Asphalt | Yes | 2021-07-12 17:38 | 2021-07-21 12:02 | 2021-07-21 18:02 |  | 2021-09-02 14:01 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 14:11 |  | yes | no | no
1992 | 16170078204019482039649 | 6 | Chopin St | McGraw St | Wagner St | Asphalt | Yes | 2021-07-20 18:04 | 2021-07-23 21:36 | 2021-07-30 19:44 |  | 2021-08-19 18:24 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 14:06 |  | yes | no | no
3702 | 16170078203964982038862 | 6 | Chopin St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-20 18:02 | 2021-07-23 21:11 | 2021-07-30 19:21 |  | 2021-08-19 18:24 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 14:14 |  | yes | no | no
3703 | 16170078203964982038862 | 6 | Chopin St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-20 18:01 | 2021-07-23 20:32 | 2021-07-30 19:02 |  | 2021-08-19 18:23 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 14:17 |  | yes | no | no
1296 | 16092048204694182046762 | 6 | Christiancy St | Campbell St | Junction St | Asphalt | Yes | 2021-07-10 15:52 | 2021-07-20 16:56 | 2021-07-20 21:15 |  | 2021-09-02 14:54 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:31 |  | yes | no | no
1300 | 16092048204710182046941 | 6 | Christiancy St | Cavalry St | Campbell St | Asphalt | Yes | 2021-07-10 15:52 | 2021-07-20 15:33 | 2021-07-20 21:14 |  | 2021-09-07 15:42 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-07-17 12:32 |  | yes | no | no
2043 | 15815078208729082042334 | 6 | Church St | Rosa Parks Blvd | Eleventh St | Asphalt | Yes | 2021-07-08 17:04 | 2021-07-12 16:04 | 2021-07-15 14:20 |  | 2021-09-07 14:12 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 14:17 |  | yes | no | no
1986 | 16107078203965482039351 | 6 | Cicotte St | Devereaux St | Gladys St | Asphalt | Yes | 2021-07-21 12:22 | 2021-07-26 15:36 | 2021-08-02 12:30 |  | 2021-08-19 19:56 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 18:27 |  | yes | no | no
1991 | 16107078204013782039865 | 6 | Cicotte St | W I 94 Service Drive | Hanson St | Asphalt | Yes | 2021-07-21 12:28 | 2021-07-26 15:59 | 2021-08-02 12:51 |  | 2021-08-19 19:57 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 19:00 |  | yes | no | no
3746 | 47112458209835182098350 | 6 | Clayton St | Parkinson St | Martin St | Asphalt | Yes | 2021-07-20 13:15 | 2021-07-22 17:39 | 2021-07-28 17:07 |  | 2021-08-26 19:18 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 12:32 |  | yes | no | no
3747 | 47112458209835182098350 | 6 | Clayton St | Parkinson St | Martin St | Asphalt | Yes | 2021-07-20 13:13 | 2021-07-24 14:40 | 2021-07-28 17:24 |  | 2021-08-26 19:19 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 12:32 |  | yes | no | no
3616 | 16108048203652282036091 | 6 | Clifton St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 17:02 | 2021-07-22 17:37 | 2021-07-28 15:33 |  | 2021-08-18 16:02 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 15:00 |  | yes | no | no
3617 | 16108048203652282036091 | 6 | Clifton St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 17:02 | 2021-07-22 18:46 | 2021-07-28 15:28 |  | 2021-08-18 16:03 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 15:00 |  | yes | no | no
4511 | 15810068204353082042917 | 6 | Clippert St | Clayton St | Edward | Asphalt | Yes | 2021-07-17 16:59 | 2021-07-21 19:28 | 2021-07-26 17:11 |  | 2021-09-03 13:51 | 2021-07-26 04:00 | HMA |  |  |  | Resurfaced on May 18, 2021 |  | Yes |  | 2021-07-19 12:31 |  | yes | No | no
4509 | 15810068204291782042184 | 6 | Clippert St | Edward | Michigan Ave | Asphalt | Yes | 2021-07-17 17:54 | 2021-07-21 20:07 | 2021-07-26 17:50 |  | 2021-09-03 13:54 | 2021-07-26 04:00 | HMA |  |  |  | Street Resurfaced on May 18, 2021 | No | Yes |  | 2021-07-19 12:45 |  | yes | No | no
4510 | 15810068204291782042184 | 6 | Clippert St | Edward | Michigan Ave | Asphalt | Yes | 2021-07-17 17:55 | 2021-07-21 20:29 | 2021-07-26 17:25 |  | 2021-09-03 13:54 | 2021-07-26 04:00 | HMA |  |  |  | Street Resurfaced on May 18, 2021 | No | Yes |  | 2021-07-19 12:45 |  | yes | No | no
2080 | 15810068204432982043925 | 6 | Clippert St | Otis St | Dennis St | Asphalt | Yes | 2021-07-17 16:55 | 2021-07-21 18:49 | 2021-07-26 16:50 |  | 2021-09-03 13:49 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 20:29 |  | yes | no | no
1935 | 15841098203663882036368 | 6 | Commonwealth St | Calumet St | W Canfield St | Asphalt | Yes | 2021-07-08 16:05 | 2021-07-14 11:33 | 2021-07-14 15:54 |  | 2021-08-17 19:13 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:58 |  | yes | no | no
1961 | 15841098203779482037556 | 6 | Commonwealth St | Grand River Ave | Selden St | Asphalt | Yes | 2021-07-08 16:05 | 2021-07-10 13:11 | 2021-07-14 15:08 |  | 2021-08-17 19:10 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:49 |  | yes | no | no
1919 | 15841098203612482035722 | 6 | Commonwealth St | Lysander St | W Forest Ave | Asphalt | Yes | 2021-07-08 15:44 | 2021-07-12 13:15 | 2021-07-14 15:54 |  | 2021-08-17 19:15 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 18:05 |  | yes | no | no
1879 | 15841098203457482034223 | 6 | Commonwealth St | Putnam St | Merrick St | Asphalt | Yes | 2021-07-08 15:42 | 2021-07-10 12:11 | 2021-07-14 17:12 |  | 2021-08-17 19:33 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 19:22 |  | yes | no | no
4892 | 15841098203755682037168 | 6 | Commonwealth St | Selden St | W Alexandrine St | Asphalt | Yes Round 2 | 2021-09-17 18:19 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:41 |  | no | yes | no
1911 | 15841098203572282035364 | 6 | Commonwealth St | W Forest Ave | W Hancock St | Asphalt | Yes | 2021-07-08 15:43 | 2021-07-14 12:07 | 2021-07-14 15:54 |  | 2021-08-17 19:17 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 18:13 |  | yes | no | no
1904 | 15841098203536482034942 | 6 | Commonwealth St | W Hancock St | W Warren Ave | Asphalt | Yes | 2021-07-08 15:43 | 2021-07-14 12:44 | 2021-07-14 16:27 |  | 2021-08-17 19:19 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 18:33 |  | yes | no | no
1895 | 15841098203494282034574 | 6 | Commonwealth St | W Warren Ave | Putnam St | Asphalt | Yes | 2021-07-08 15:42 | 2021-07-12 12:12 | 2021-07-14 16:27 |  | 2021-08-17 19:30 | 2021-07-14 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 19:12 |  | yes | no | no
3766 | 15938018205861882059015 | 6 | Conway St | N I 75 Service Drive | S Fort St | Asphalt | Yes | 2021-07-22 14:43 | 2021-07-26 13:23 | 2021-07-31 13:18 |  | 2021-08-28 13:57 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:00 |  | yes | no | no
3767 | 15938018205861882059015 | 6 | Conway St | N I 75 Service Drive | S Fort St | Asphalt | Yes | 2021-07-22 14:41 | 2021-07-26 14:41 | 2021-07-31 13:19 |  | 2021-08-28 13:58 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:01 |  | yes | no | no
3758 | 15938048205812482058533 | 6 | Corbin St | N I 75 Service Drive | S Fort St | Asphalt | Yes | 2021-07-22 14:39 | 2021-07-26 12:55 | 2021-07-31 13:18 |  | 2021-08-28 13:57 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:56 |  | yes | no | no
3759 | 15938048205812482058533 | 6 | Corbin St | N I 75 Service Drive | S Fort St | Asphalt | Yes | 2021-07-22 14:33 | 2021-07-26 12:24 | 2021-07-31 13:17 |  | 2021-08-28 13:56 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:56 |  | yes | no | no
2016 | 16174028204107682040940 | 6 | Dennison St | Cabot St | Lawndale St | Asphalt | Yes | 2021-07-21 14:24 | 2021-08-24 14:50 | 2021-08-30 14:46 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:51 |  | yes | no | no
2052 | 16106048204260082042354 | 6 | Edward | Gilbert St | Livernois Ave | Asphalt | Yes | 2021-07-17 16:55 | 2021-07-21 19:24 | 2021-07-26 19:26 |  | 2021-09-03 13:57 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 12:13 |  | yes | no | no
3734 | 16109078204371982043330 | 6 | Edward | Parkinson St | Martin St | Asphalt | Yes | 2021-07-17 18:56 | 2021-07-22 14:59 | 2021-07-26 22:16 |  | 2021-08-26 19:25 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:27 |  | yes | no | no
3735 | 16109078204371982043330 | 6 | Edward | Parkinson St | Martin St | Asphalt | Yes | 2021-07-17 18:56 | 2021-07-22 15:16 | 2021-07-27 21:18 |  | 2021-08-26 19:28 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:26 |  | yes | no | no
1292 | 16092098204677482046557 | 6 | Eldred St | Campbell St | Junction St | Asphalt | Yes | 2021-07-10 15:48 | 2021-07-20 17:41 | 2021-07-20 21:30 |  | 2021-09-02 14:56 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:00 |  | yes | no | no
1297 | 16092098204694482046774 | 6 | Eldred St | Cavalry St | Campbell St | Asphalt | Yes | 2021-07-10 15:50 | 2021-07-21 14:30 | 2021-07-21 21:06 |  | 2021-09-07 15:31 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:16 |  | yes | no | no
1980 | 16085078203947282039349 | 6 | Elm St | Rosa Parks Blvd | Harrison St | Asphalt | Yes | 2021-07-08 16:31 | 2021-07-12 15:19 | 2021-07-15 17:59 |  |  | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 14:10 |  | yes | no | no
2018 | 16173068204120482040677 | 6 | Elmer St | McGraw St | Wagner St | Asphalt | Yes | 2021-07-21 14:05 | 2021-07-27 13:05 | 2021-08-02 14:55 |  | 2021-08-19 14:43 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:27 |  | yes | no | no
5289 | 16173068204196482041204 | 6 | Elmer St | W I 94 Service Drive | McGraw St | Asphalt | Yes Round 2 | 2021-09-17 18:07 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:40 |  | no | yes | no
5290 | 16173068204196482041204 | 6 | Elmer St | W I 94 Service Drive | McGraw St | Asphalt | Yes Round 2 | 2021-09-17 18:07 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:40 |  | no | yes | no
3710 | 16173068204067782039837 | 6 | Elmer St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-21 14:06 | 2021-07-27 12:37 | 2021-08-02 15:13 |  | 2021-08-19 14:43 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:01 |  | yes | no | no
3711 | 16173068204067782039837 | 6 | Elmer St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-21 14:12 | 2021-07-27 12:14 | 2021-08-02 15:29 |  | 2021-08-19 14:43 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:02 |  | yes | no | no
2758 | 17110038205029282049994 | 6 | Falcon St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-09-17 19:39 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-17 17:42 |  | yes | no | no
2759 | 17110038205029282049994 | 6 | Falcon St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-09-17 17:44 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-17 17:44 |  | yes | no | no
1319 | 16168098204782882047420 | 6 | Ferris St | Pitt St | Woodmere St | Asphalt | Yes | 2021-09-21 18:48 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-21 18:47 |  | yes | no | no
4895 | 16168098204835482047828 | 6 | Ferris St | W Vernor Hwy | Pitt St | Asphalt | Yes Round 2 | 2021-09-17 17:39 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:39 |  | no | yes | no
2001 | 16170048204059182039997 | 6 | Florida St | McGraw St | Wagner St | Asphalt | Yes | 2021-07-21 12:46 | 2021-07-23 16:49 | 2021-07-30 13:47 |  | 2021-08-19 17:58 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:37 |  | yes | no | no
2015 | 16170048204110282040591 | 6 | Florida St | Panama St | McGraw St | Asphalt | Yes | 2021-07-21 12:44 | 2021-07-26 14:18 | 2021-07-30 13:35 |  | 2021-08-19 19:13 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:36 |  | yes | no | no
2026 | 16170048204159182041102 | 6 | Florida St | W I 94 Service Drive | Panama St | Asphalt | Yes | 2021-07-21 12:41 | 2021-07-26 13:44 | 2021-07-30 13:11 |  | 2021-08-19 19:12 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:36 |  | yes | no | no
3708 | 16170048203999782039198 | 6 | Florida St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-21 12:48 | 2021-07-23 17:17 | 2021-07-30 14:04 |  | 2021-08-19 17:59 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:55 |  | yes | no | no
3709 | 16170048203999782039198 | 6 | Florida St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-21 12:50 | 2021-07-23 18:21 | 2021-07-30 14:27 |  | 2021-08-19 18:00 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:56 |  | yes | no | no
3618 | 16108038203678682036357 | 6 | Floyd St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 17:07 | 2021-07-22 16:08 | 2021-07-28 14:43 |  | 2021-08-18 16:06 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 15:33 |  | yes | no | no
3619 | 16108038203678682036357 | 6 | Floyd St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 17:05 | 2021-07-22 15:45 | 2021-07-28 14:59 |  | 2021-08-18 16:06 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 15:33 |  | yes | no | no
3644 | 16108038203723082036786 | 6 | Floyd St | Wetherby St | Rangoon St | Asphalt | Yes | 2021-07-20 17:14 | 2021-07-22 17:08 | 2021-07-28 14:12 |  | 2021-08-18 16:10 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 16:33 |  | yes | no | no
3645 | 16108038203723082036786 | 6 | Floyd St | Wetherby St | Rangoon St | Asphalt | Yes | 2021-07-20 17:39 | 2021-07-22 16:34 | 2021-07-28 14:34 |  | 2021-08-18 16:09 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 16:33 |  | yes | no | no
2730 | 16114048204824682086806 | 6 | Gartner St | Central St | N Green St | Asphalt | Yes | 2021-08-10 18:51 | 2021-08-18 16:03 | 2021-08-20 18:28 |  | 2021-09-01 20:39 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 16:18 |  | yes | no | no
2731 | 16114048204824682086806 | 6 | Gartner St | Central St | N Green St | Asphalt | Yes | 2021-08-10 18:51 | 2021-08-18 16:03 | 2021-08-20 18:39 |  | 2021-09-01 20:41 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 16:22 |  | yes | no | no
1328 | 16114048204845082048246 | 6 | Gartner St | Evans St | Central St | Asphalt | Yes | 2021-08-10 18:50 | 2021-08-18 16:02 | 2021-08-20 17:15 |  | 2021-09-01 20:37 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 17:23 |  | yes | no | no
2742 | 16114048204911882048814 | 6 | Gartner St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-10 18:50 | 2021-08-18 12:59 | 2021-08-20 15:59 |  | 2021-09-01 20:29 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 16:51 |  | yes | no | no
2743 | 16114048204911882048814 | 6 | Gartner St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-10 18:50 | 2021-08-18 13:12 | 2021-08-20 16:14 |  | 2021-09-01 20:32 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 16:53 |  | yes | no | no
1336 | 16114048204881482048551 | 6 | Gartner St | Mullane St | Springwells St | Asphalt | Yes | 2021-08-10 18:50 | 2021-08-18 14:08 | 2021-08-20 16:46 |  | 2021-09-01 20:36 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 17:09 |  | yes | no | no
1330 | 16114048204855182048450 | 6 | Gartner St | Springwells St | Evans St | Asphalt | Yes | 2021-08-10 18:50 | 2021-08-19 12:03 | 2021-08-20 19:17 |  | 2021-09-01 20:37 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 17:18 |  | yes | no | no
1982 | 16107028203935182039154 | 6 | Gladys St | Cicotte St | Gilbert St | Asphalt | Yes | 2021-07-21 12:25 | 2021-07-26 15:07 | 2021-08-02 12:11 |  | 2021-08-19 19:55 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 18:11 |  | yes | no | no
1764 | 16181108203101082030289 | 6 | Greenway St | Northfield St | Beechwood St | Asphalt | Yes | 2021-07-12 18:19 | 2021-07-20 14:25 | 2021-07-26 18:36 |  | 2021-08-26 12:45 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 12:54 |  | yes | no | no
2019 | 16172058204123382041047 | 6 | Henderson St | Lonyo St | Saint Lawrence St | Asphalt | Yes | 2021-07-21 13:46 | 2021-07-27 16:12 | 2021-08-02 17:56 |  | 2021-08-19 14:38 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:20 |  | yes | no | no
1968 | 16111068203778982037771 | 6 | Holmes St | Central St | Proctor St | Asphalt | Yes | 2021-07-20 17:27 | 2021-07-23 15:39 | 2021-07-29 00:02 |  | 2021-08-19 18:52 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 17:13 |  | yes | no | no
4069 | 16111068203777182037741 | 6 | Holmes St | Proctor St | Sarena St & Wetherby St | Asphalt | Yes | 2021-07-20 17:24 | 2021-07-23 15:08 | 2021-07-28 23:30 |  | 2021-08-19 18:53 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 17:20 |  | yes | no | no
4071 | 16111068203777182037741 | 6 | Holmes St | Proctor St | Sarena St & Wetherby St | Asphalt | Yes | 2021-07-20 17:23 | 2021-07-23 14:39 | 2021-07-28 23:10 |  | 2021-08-19 18:53 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 17:20 |  | yes | no | no
2754 | 16116068205003882049757 | 6 | Homer St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-17 15:04 | 2021-08-20 12:07 | 2021-08-27 13:13 |  | 2021-08-30 16:15 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 17:22 |  | yes | no | no
2755 | 16116068205003882049757 | 6 | Homer St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-17 15:04 | 2021-08-20 17:16 | 2021-08-27 12:59 |  | 2021-08-30 16:14 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 17:22 |  | yes | no | no
2751 | 16116068204975782049527 | 6 | Homer St | Mullane St | Springwells St | Asphalt | Yes | 2021-08-17 15:04 | 2021-08-20 15:40 | 2021-08-21 18:39 |  | 2021-08-30 15:41 | 2021-08-27 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 17:41 |  | yes | no | no
2764 | 16116068205063482050322 | 6 | Homer St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 15:05 | 2021-08-19 19:22 | 2021-08-21 12:54 |  | 2021-08-30 16:10 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:43 |  | yes | no | no
2765 | 16116068205063482050322 | 6 | Homer St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 15:05 | 2021-08-19 19:39 | 2021-08-21 14:56 |  | 2021-08-30 16:11 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:43 |  | yes | no | no
2013 | 16105088204111982040806 | 6 | Horatio St | Daniels St | Cicotte St | Asphalt | Yes | 2021-07-17 18:11 | 2021-07-22 20:06 | 2021-07-27 18:49 |  | 2021-08-26 16:56 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 14:48 |  | yes | no | no
2002 | 16105088204066582040472 | 6 | Horatio St | Gilbert St | Livernois Ave | Asphalt | Yes | 2021-07-17 18:11 | 2021-07-22 19:51 | 2021-07-27 19:02 |  | 2021-08-26 16:59 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 15:41 |  | yes | no | no
2024 | 16110068204160582041437 | 6 | Horatio St | Larkins St | Braden St | Asphalt | Yes | 2021-07-17 18:12 | 2021-07-22 18:47 | 2021-07-27 20:13 |  | 2021-08-26 17:47 | 2021-07-28 04:00 | HMA | No |  |  | Resurfacing Completed | No | Yes |  | 2021-07-19 14:00 |  | yes | no | no
2017 | 16105088208684482041119 | 6 | Horatio St | Martin St | Daniels St | Asphalt | Yes | 2021-07-17 18:12 | 2021-07-22 19:34 | 2021-07-27 17:06 |  | 2021-08-26 16:55 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 14:35 |  | yes | no | no
4336 | 47055278204493582044172 | 6 | Hubbard St | W Vernor Hwy | Toledo St | Asphalt | Yes | 2021-07-10 16:28 | 2021-07-15 16:50 | 2021-07-17 15:48 |  | 2021-09-02 19:15 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 16:49 |  | yes | no | no
4337 | 47055278204493582044172 | 6 | Hubbard St | W Vernor Hwy | Toledo St | Asphalt | Yes | 2021-07-10 16:28 | 2021-07-15 14:08 | 2021-07-15 22:06 |  | 2021-09-02 19:17 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 16:59 |  | yes | no | no
4338 | 47055278204493582044172 | 6 | Hubbard St | W Vernor Hwy | Toledo St | Asphalt | Yes | 2021-07-10 16:28 | 2021-07-15 15:35 | 2021-07-15 21:53 |  | 2021-09-02 19:18 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:23 |  | yes | no | no
5287 | 16169038204746482046961 | 6 | Inglis St | Pitt St | Belle St | Asphalt | Yes Round 2 | 2021-09-17 17:40 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:39 |  | no | yes | no
5288 | 16169038204746482046961 | 6 | Inglis St | Pitt St | Belle St | Asphalt | Yes Round 2 | 2021-09-17 17:40 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:39 |  | no | yes | no
1322 | 16169038204795182047464 | 6 | Inglis St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 13:54 | 2021-08-21 17:33 | 2021-08-28 15:50 |  | 2021-09-01 17:43 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:22 |  | yes | no | no
2011 | 16095098204112382040961 | 6 | Jackson St | 30th St | 29th St | Asphalt | Yes | 2021-07-17 14:14 | 2021-07-19 18:24 | 2021-07-20 13:37 |  | 2021-09-03 16:14 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 16:33 |  | yes | no | no
3720 | 15811148204211082041337 | 6 | Joe St | Michigan Ave | Dead End or Start | Asphalt | Yes | 2021-07-17 16:46 | 2021-07-24 17:23 | 2021-07-27 12:06 |  | 2021-09-03 15:08 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 18:52 |  | yes | no | no
3721 | 15811148204211082041337 | 6 | Joe St | Michigan Ave | Dead End or Start | Asphalt | Yes | 2021-07-17 16:46 | 2021-07-24 17:56 | 2021-07-27 12:06 |  | 2021-09-03 15:06 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 18:52 |  | yes | no | no
3742 | 16100128204358382043838 | 6 | Konkel St | Junction St | Wesson St | Asphalt | Yes | 2021-07-17 16:46 | 2021-07-21 15:12 | 2021-07-26 12:28 |  | 2021-09-03 12:55 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 19:18 |  | yes | no | no
3743 | 16100128204358382043838 | 6 | Konkel St | Junction St | Wesson St | Asphalt | Yes | 2021-07-17 16:47 | 2021-07-21 15:53 | 2021-07-26 12:28 |  | 2021-09-03 12:57 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 19:29 |  | yes | no | no
2064 | 16097078204306982042768 | 6 | Kopernick St | Wesson St | Greusel St | Asphalt | Yes | 2021-07-17 16:47 | 2021-07-21 17:09 | 2021-07-26 13:20 |  | 2021-09-03 13:15 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 19:04 |  | yes | no | no
2045 | 16082078204262982042430 | 6 | Labrosse St | 8th St | Brooklyn St | Asphalt | Yes | 2021-07-08 17:09 | 2021-07-14 14:23 | 2021-07-15 17:25 |  |  | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 16:10 |  | yes | no | no
2041 | 16082078204243082042223 | 6 | Labrosse St | Brooklyn St | 6th St | Asphalt | Yes | 2021-07-08 17:09 | 2021-07-14 14:54 | 2021-07-15 17:42 |  | 2021-09-07 14:20 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 16:18 |  | yes | no | no
2047 | 16082078204279182042629 | 6 | Labrosse St | Trumbull St | 8th St | Asphalt | Yes | 2021-07-08 17:08 | 2021-07-14 13:37 | 2021-07-15 17:15 |  | 2021-09-07 14:14 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 15:38 |  | yes | no | no
2736 | 16116018204862682048286 | 6 | Lane St | Central St | N Green St | Asphalt | Yes | 2021-08-17 15:34 | 2021-08-23 17:31 | 2021-08-28 19:31 |  | 2021-09-01 20:48 | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 13:17 |  | yes | no | no
2737 | 16116018204862682048286 | 6 | Lane St | Central St | N Green St | Asphalt | Yes | 2021-08-17 15:34 | 2021-08-23 17:49 | 2021-08-28 19:57 |  | 2021-09-01 21:01 | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 13:17 |  | yes | no | no
5580 | 16171028204980182049454 | 6 | Lane St | Elsmere St | Lawndale St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5581 | 16171028204980182049454 | 6 | Lane St | Elsmere St | Lawndale St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2746 | 16116098208679282049161 | 6 | Lane St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-17 15:15 | 2021-08-19 14:45 | 2021-08-20 19:42 |  | 2021-08-30 17:27 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:03 |  | yes | no | no
2747 | 16116098208679282049161 | 6 | Lane St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-17 15:18 | 2021-08-19 15:03 | 2021-08-20 19:54 |  | 2021-08-30 17:28 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:03 |  | yes | no | no
5702 | 16116098204916182048902 | 6 | Lane St | Mullane St | Springwells St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2716 | 16091088204636382045707 | 6 | Lansing St | Christiancy St | W Vernor Hwy | Asphalt | Yes | 2021-07-10 17:58 | 2021-07-17 15:26 | 2021-07-17 20:30 |  | 2021-09-02 15:55 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:23 |  | yes | no | no
2717 | 16091088204636382045707 | 6 | Lansing St | Christiancy St | W Vernor Hwy | Asphalt | Yes | 2021-07-10 17:58 | 2021-07-17 15:07 | 2021-07-17 20:30 |  | 2021-09-02 15:54 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:23 |  | yes | no | no
2099 | 16091088204694682046737 | 6 | Lansing St | Howard St | Porter St | Asphalt | Yes | 2021-07-10 17:58 | 2021-07-17 16:43 | 2021-07-17 11:16 |  | 2021-09-02 16:38 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:24 |  | yes | no | no
2098 | 16091088204673782046363 | 6 | Lansing St | Porter St | Christiancy St | Asphalt | Yes | 2021-07-10 17:58 | 2021-07-17 15:47 | 2021-07-17 20:42 |  | 2021-09-02 16:42 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:23 |  | yes | no | no
2100 | 16091088204731682046946 | 6 | Lansing St | W Lafayette Blvd | Howard St | Asphalt | Yes | 2021-07-10 17:57 | 2021-07-17 17:05 | 2021-07-19 12:29 |  | 2021-09-02 16:38 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:24 |  | yes | no | no
4513 | 16091088204731682046946 | 6 | Lansing St | W Lafayette Blvd | Howard St | Asphalt | Yes | 2021-07-10 17:57 | 2021-07-17 17:19 | 2021-07-19 12:29 |  | 2021-09-02 13:18 | 2021-07-19 04:00 | HMA |  |  |  |  | No | Yes |  | 2021-07-16 12:24 |  | yes | No | no
2025 | 15810038204160582086840 | 6 | Larkins St | Horatio St | E I 94 Service Drive | Asphalt | Yes | 2021-07-17 18:12 | 2021-07-22 17:45 | 2021-07-27 20:09 |  | 2021-08-26 17:50 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 14:13 |  | yes | no | no
2044 | 15810038208525082041605 | 6 | Larkins St | Michigan Ave | Horatio St | Asphalt | Yes | 2021-07-17 18:13 | 2021-07-22 18:14 | 2021-07-27 20:26 |  | 2021-08-26 17:46 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 14:13 |  | yes | no | no
3722 | 15810028204286782042225 | 6 | Larkins St | Saint John St | Michigan Ave | Asphalt | Yes | 2021-07-17 18:54 | 2021-07-22 14:01 | 2021-07-26 19:52 |  | 2021-08-26 19:12 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:57 |  | yes | no | no
4249 | 16174038204206482040940 | 6 | Lawndale St | McGraw St | Dennison St | Asphalt | Yes | 2021-07-21 15:02 | 2021-07-28 15:34 | 2021-08-02 22:31 |  | 2021-08-19 13:38 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:28 |  | yes | no | no
4250 | 16174038204206482040940 | 6 | Lawndale St | McGraw St | Dennison St | Asphalt | Yes | 2021-07-21 15:00 | 2021-07-28 15:18 | 2021-08-03 13:41 |  | 2021-08-19 13:37 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:14 |  | yes | no | no
4251 | 16174038204206482040940 | 6 | Lawndale St | McGraw St | Dennison St | Asphalt | Yes | 2021-07-21 14:59 | 2021-07-28 14:38 | 2021-08-02 21:22 |  | 2021-08-19 13:37 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:00 |  | yes | no | no
1321 | 16168088204792982047665 | 6 | Lawndale St | Pitt St | Woodmere St | Asphalt | Yes | 2021-08-17 14:13 | 2021-08-21 12:24 | 2021-08-27 15:56 |  | 2021-09-01 17:24 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:10 |  | yes | no | no
1329 | 16168088204843982047929 | 6 | Lawndale St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 14:15 | 2021-08-21 12:38 | 2021-08-28 12:21 |  | 2021-09-01 17:24 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:12 |  | yes | no | no
2042 | 16082088204246882042261 | 6 | Leverette St | 10th St | Trumbull St | Asphalt | Yes | 2021-07-08 17:05 | 2021-07-12 18:10 | 2021-07-15 16:57 |  | 2021-09-07 14:10 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 15:17 |  | yes | no | no
2046 | 16082088204264582042468 | 6 | Leverette St | Eleventh St | 10th St | Asphalt | Yes | 2021-07-08 17:04 | 2021-07-12 17:37 | 2021-07-15 16:46 |  | 2021-09-07 14:10 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 14:34 |  | yes | no | no
2048 | 16082088208729182042645 | 6 | Leverette St | Rosa Parks Blvd | Eleventh St | Asphalt | Yes | 2021-07-08 17:04 | 2021-07-12 17:10 | 2021-07-15 14:35 |  | 2021-09-07 14:09 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 14:33 |  | yes | no | no
1857 | 16181018203361582033575 | 6 | Linsdale St | Burnette St | Livernois Ave | Asphalt | Yes | 2021-07-12 18:55 | 2021-08-24 17:24 | 2021-08-30 17:13 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 15:56 |  | yes | no | no
1859 | 16181018203364182033615 | 6 | Linsdale St | Prairie St | Burnette St | Asphalt | Yes | 2021-07-12 18:55 | 2021-07-20 20:29 | 2021-07-27 13:06 |  | 2021-08-18 19:03 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 15:56 |  | yes | no | no
1337 | 16113088204903982048783 | 6 | Lisbon St | N Green St | Beard St | Asphalt | Yes | 2021-07-12 17:41 | 2021-07-21 12:56 | 2021-07-21 18:26 |  | 2021-09-02 13:56 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:50 |  | yes | no | no
2756 | 17110028205016382049871 | 6 | Longworth St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 15:13 | 2021-08-19 18:02 | 2021-08-21 12:12 |  | 2021-08-30 15:49 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:04 |  | yes | no | no
2757 | 17110028205016382049871 | 6 | Longworth St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 15:14 | 2021-08-19 17:45 | 2021-08-27 13:29 |  | 2021-08-30 15:49 | 2021-08-27 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:04 |  | yes | no | no
2752 | 16116078204981482049545 | 6 | Longworth St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-17 15:14 | 2021-08-19 17:20 | 2021-08-21 11:54 |  | 2021-08-30 15:47 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:04 |  | yes | no | no
2753 | 16116078204981482049545 | 6 | Longworth St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-17 15:15 | 2021-08-19 16:57 | 2021-08-21 11:56 |  | 2021-08-30 15:46 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:04 |  | yes | no | no
2749 | 16116078204954582086790 | 6 | Longworth St | Mullane St | Springwells St | Asphalt | Yes | 2021-08-17 15:15 | 2021-08-19 15:44 | 2021-08-21 11:44 |  | 2021-08-30 15:45 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:03 |  | yes | no | no
2760 | 17110028205044982050163 | 6 | Longworth St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 15:13 | 2021-08-19 18:50 | 2021-08-21 12:39 |  | 2021-08-30 15:54 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:43 |  | yes | no | no
2761 | 17110028205044982050163 | 6 | Longworth St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 15:13 | 2021-08-19 18:26 | 2021-08-21 12:24 |  | 2021-08-30 15:50 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:42 |  | yes | no | no
1985 | 15812098203971182039453 | 6 | Lovett St | Buchanan St | Kinsman St | Asphalt | Yes | 2021-07-17 14:54 | 2021-07-19 14:42 | 2021-07-19 21:27 |  | 2021-09-03 16:20 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 16:33 |  | yes | no | no
1970 | 15812098203803582037617 | 6 | Lovett St | Herbert St | E I 94 Service Drive | Asphalt | Yes | 2021-07-17 13:59 | 2021-07-19 17:02 | 2021-07-19 22:11 |  | 2021-09-03 16:56 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 14:59 |  | yes | no | no
1983 | 15812098203945382039201 | 6 | Lovett St | Kinsman St | Rich St | Asphalt | Yes | 2021-07-17 14:54 | 2021-07-19 15:05 | 2021-07-19 21:43 |  | 2021-09-03 16:21 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 16:14 |  | yes | no | no
1979 | 15812098203920182038615 | 6 | Lovett St | Rich St | Horatio St | Asphalt | Yes | 2021-07-17 14:39 | 2021-07-19 15:54 | 2021-07-19 21:51 |  | 2021-09-03 16:52 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 15:37 |  | yes | no | no
2067 | 47055218204298882043495 | 6 | Lumley St | Cypress St | Jennie St | Asphalt | Yes | 2021-07-21 12:56 | 2021-07-23 14:39 | 2021-07-29 15:10 |  | 2021-08-27 15:46 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:44 |  | yes | no | no
2073 | 47055218204349582043699 | 6 | Lumley St | Jennie St | Saint Stephens St | Asphalt | Yes | 2021-07-20 13:40 | 2021-07-23 13:59 | 2021-07-28 22:33 |  | 2021-08-27 15:45 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:45 |  | yes | no | no
2061 | 47055218204228482042731 | 6 | Lumley St | Michigan Ave | Sumner | Asphalt | Yes | 2021-07-20 13:45 | 2021-07-23 13:55 | 2021-07-29 15:16 |  | 2021-08-27 15:47 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:28 |  | yes | no | no
4270 | 17109058205342382052922 | 6 | Lyon St | S Leigh St | Dearborn St | Asphalt | Yes | 2021-07-22 13:22 | 2021-07-26 14:42 | 2021-07-30 12:32 |  | 2021-08-30 12:48 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 13:45 |  | yes | no | no
4271 | 17109058205342382052922 | 6 | Lyon St | S Leigh St | Dearborn St | Asphalt | Yes | 2021-07-22 13:21 | 2021-07-26 14:42 | 2021-07-30 12:32 |  | 2021-08-30 12:47 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 13:48 |  | yes | no | no
4272 | 17109058205342382052922 | 6 | Lyon St | S Leigh St | Dearborn St | Asphalt | Yes | 2021-07-22 13:21 | 2021-07-26 13:24 | 2021-07-30 12:02 |  | 2021-08-30 12:47 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 13:51 |  | yes | no | no
3614 | 16108058203626982035835 | 6 | Majestic St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 16:10 | 2021-07-23 11:53 | 2021-07-28 17:19 |  | 2021-08-18 15:59 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:32 |  | yes | no | no
3615 | 16108058203626982035835 | 6 | Majestic St | Rangoon St | Livernois Ave | Asphalt | Yes | 2021-07-20 16:10 | 2021-07-23 11:31 | 2021-07-28 17:39 |  | 2021-08-18 15:59 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:32 |  | yes | no | no
1941 | 16108058203660582036269 | 6 | Majestic St | Wetherby St | Rangoon St | Asphalt | Yes | 2021-07-20 17:39 | 2021-07-23 12:13 | 2021-07-28 17:09 |  | 2021-08-18 15:59 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:33 |  | yes | no | no
1340 | 16170098204944582049304 | 6 | Mandale St | Elsmere St | Sharon St | Asphalt | Yes | 2021-08-17 14:28 | 2021-08-18 20:35 | 2021-08-20 15:14 |  | 2021-08-31 13:31 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:02 |  | yes | no | no
1339 | 16170098204921682049137 | 6 | Mandale St | Oakdale St | Cabot St | Asphalt | Yes | 2021-08-17 14:34 | 2021-08-18 19:57 | 2021-08-20 15:00 |  | 2021-08-31 13:32 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:02 |  | yes | no | no
1341 | 16170098204963382049445 | 6 | Mandale St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 14:27 | 2021-08-19 13:51 | 2021-08-20 15:26 |  | 2021-08-31 13:30 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:02 |  | yes | no | no
1801 | 15818088203204582031804 | 6 | Maplewood St | Beechwood St | Turner St | Asphalt | Yes | 2021-07-13 13:36 | 2021-07-19 22:12 | 2021-07-26 14:49 |  | 2021-08-26 14:06 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 18:38 |  | yes | no | no
1844 | 15818088203314782032879 | 6 | Maplewood St | Colfax St | Northfield St | Asphalt | Yes | 2021-07-13 13:20 | 2021-07-20 11:42 | 2021-07-26 16:06 |  | 2021-08-26 14:00 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 17:51 |  | yes | no | no
1812 | 15818088203232982032045 | 6 | Maplewood St | Ironwood St | Beechwood St | Asphalt | Yes | 2021-07-13 13:35 | 2021-07-19 22:40 | 2021-07-26 15:12 |  | 2021-08-26 14:04 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 18:38 |  | yes | no | no
4012 | 15818088203287982032329 | 6 | Maplewood St | Northfield St | Ironwood St | Asphalt | Yes | 2021-07-13 13:20 | 2021-07-20 12:04 | 2021-07-26 15:48 |  | 2021-08-26 14:01 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 18:08 |  | yes | no | no
4014 | 15818088203287982032329 | 6 | Maplewood St | Northfield St | Ironwood St | Asphalt | Yes | 2021-07-13 13:20 | 2021-07-20 11:15 | 2021-07-26 15:43 |  | 2021-08-26 14:02 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 18:08 |  | yes | no | no
1342 | 16171038204983882049622 | 6 | Mason | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 14:34 | 2021-08-19 14:14 | 2021-08-20 15:44 |  | 2021-08-30 17:46 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 16:02 |  | yes | no | no
2093 | 16091098204557082045244 | 6 | McKinstry St | W Vernor Hwy | Uthes St | Asphalt | Yes | 2021-07-10 15:12 | 2021-07-17 18:56 | 2021-07-19 16:22 |  | 2021-09-02 21:00 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:49 |  | yes | no | no
1284 | 16104098204589882045691 | 6 | McMillan St | Campbell St | Junction St | Asphalt | Yes | 2021-07-10 18:00 | 2021-07-19 20:28 | 2021-07-20 16:27 |  | 2021-09-02 21:11 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 18:43 |  | yes | no | no
1289 | 16104098204612182045898 | 6 | McMillan St | Cavalry St | Campbell St | Asphalt | Yes | 2021-07-10 18:00 | 2021-07-19 19:59 | 2021-07-20 14:27 |  | 2021-09-02 21:11 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 18:31 |  | yes | no | no
1290 | 16104098204625782046121 | 6 | McMillan St | Military St | Cavalry St | Asphalt | Yes | 2021-07-10 18:00 | 2021-07-19 19:36 | 2021-07-20 14:27 |  | 2021-09-02 21:07 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 18:21 |  | yes | no | no
2774 | 16288108205216082051820 | 6 | Melville St | S Yale | S Westend St | Asphalt | Yes | 2021-07-22 13:18 | 2021-07-26 12:56 | 2021-07-30 11:42 |  | 2021-08-30 13:15 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 13:35 |  | yes | no | no
2775 | 16288108205216082051820 | 6 | Melville St | S Yale | S Westend St | Asphalt | Yes | 2021-07-22 13:17 | 2021-07-26 11:35 | 2021-07-30 11:42 |  | 2021-08-30 13:15 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 13:37 |  | yes | no | no
1314 | 16105018204780082047314 | 6 | Military St | Army St | Regular St | Asphalt | Yes | 2021-07-12 15:23 | 2021-07-20 12:25 | 2021-07-20 18:14 |  | 2021-09-02 14:19 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:19 |  | yes | no | no
2088 | 15811028204502882044640 | 6 | Military St | Federal St | Ranspach St | Asphalt | Yes | 2021-07-21 15:37 | 2021-07-21 17:50 | 2021-07-26 16:05 |  | 2021-09-03 14:50 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 15:37 |  | yes | no | no
2092 | 15811028209842082045028 | 6 | Military St | Federal St | Plumer St | Asphalt | Yes | [6 empty] | HMA | No | DTE Coordination Needed (2022) |  | Coordinate with DPW 2020 Carryover Resurfacing | Yes | No |  |  |  | yes | no | no
2072 | 15811028204372382043275 | 6 | Military St | Otis St | Dennis St | Asphalt | Yes | 2021-07-17 16:48 | 2021-07-21 17:12 | 2021-08-28 21:10 |  | 2021-09-03 14:45 | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 19:39 |  | yes | no | no
1305 | 16105018204731482046936 | 6 | Military St | Regular St | Cadet St | Asphalt | Yes | 2021-07-12 15:23 | 2021-07-21 13:57 | 2021-07-21 20:42 |  | 2021-09-02 14:18 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:19 |  | yes | no | no
1291 | 16105018204667382046257 | 6 | Military St | W Vernor Hwy | McMillan St | Asphalt | Yes | [6 empty] | HMA | No | DTE Coordination Needed (2022) |  | Coordinate with DPW 2020 Carryover Resurfacing | Yes | No |  |  |  | yes | no | no
2094 | 16091068204556182045075 | 6 | Morrell St | McMillan St | Toledo St | Asphalt | Yes | 2021-07-10 17:58 | 2021-07-21 13:54 | 2021-07-21 22:30 |  | 2021-09-02 20:55 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:43 |  | yes | no | no
5285 | 16091068204759682046954 | 6 | Morrell St | W Lafayette Blvd | Porter St | Asphalt | Yes Round 2 | 2021-09-17 18:06 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:38 |  | no | yes | no
5286 | 16091068204759682046954 | 6 | Morrell St | W Lafayette Blvd | Porter St | Asphalt | Yes Round 2 | 2021-09-17 18:05 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:38 |  | no | yes | no
1286 | 16091068204595882045561 | 6 | Morrell St | W Vernor Hwy | McMillan St | Asphalt | Yes | 2021-07-10 17:58 | 2021-07-19 11:24 | 2021-07-19 16:05 |  | 2021-09-02 20:53 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-16 12:43 |  | yes | no | no
3718 | 15811078204183882040935 | 6 | N Campbell St | Jackson St | Buchanan St | Asphalt | Yes | 2021-07-17 16:00 | 2021-07-24 17:12 | 2021-07-27 13:29 |  | 2021-09-03 15:27 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 18:37 |  | yes | no | no
3719 | 15811078204183882040935 | 6 | N Campbell St | Jackson St | Buchanan St | Asphalt | Yes | 2021-07-17 16:00 | 2021-07-24 17:58 | 2021-07-27 13:34 |  | 2021-09-03 15:29 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 18:36 |  | yes | no | no
1303 | 16115018204713882046723 | 6 | N Green St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-09-17 17:56 | [5 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-09-17 17:56 |  | yes | no | no
1320 | 16113028204803282047588 | 6 | N Rademacher St | Regular St | Cadet St | Asphalt | Yes | 2021-07-12 16:41 | 2021-07-20 19:40 | 2021-07-21 20:11 |  | 2021-09-02 14:06 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:49 |  | yes | no | no
2728 | 47055048204805182047694 | 6 | Navy St | Central St | N Green St | Asphalt | Yes | 2021-08-10 17:31 | 2021-08-18 16:56 | 2021-08-20 12:11 |  | 2021-09-01 19:43 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-10 17:31 |  | yes | no | no
2729 | 47055048204805182047694 | 6 | Navy St | Central St | N Green St | Asphalt | Yes | 2021-08-10 17:00 | 2021-08-19 11:35 | 2021-08-20 18:58 |  | 2021-09-01 19:41 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-10 17:00 |  | yes | no | no
2740 | 16114058204893582048642 | 6 | Navy St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-10 18:02 | 2021-08-18 19:19 | 2021-08-20 13:19 |  | 2021-09-07 16:56 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 16:42 |  | yes | no | no
2741 | 16114058204893582048642 | 6 | Navy St | Lawndale St | Mullane St | Asphalt | Yes | 2021-08-10 18:02 | 2021-08-18 18:48 | 2021-08-20 13:13 |  | 2021-09-01 19:50 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 16:36 |  | yes | no | no
1333 | 16114058204864282086802 | 6 | Navy St | Mullane St | Springwells St | Asphalt | Yes | 2021-08-10 18:02 | 2021-08-18 18:09 | 2021-08-20 13:12 |  | 2021-09-01 19:49 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-16 16:33 |  | yes | no | no
1313 | 47055048204769482047438 | 6 | Navy St | N Green St | Beard St | Asphalt | Yes | 2021-08-10 17:00 | 2021-08-18 16:03 | 2021-08-20 11:52 |  | 2021-09-01 19:38 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-10 17:00 |  | yes | no | no
2732 | 47055048204837782048051 | 6 | Navy St | Springwells St | Central St | Asphalt | Yes | 2021-08-10 17:32 | 2021-08-18 17:46 | 2021-08-20 12:31 |  | 2021-09-01 19:46 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-10 17:32 |  | yes | no | no
2733 | 47055048204837782048051 | 6 | Navy St | Springwells St | Central St | Asphalt | Yes | 2021-08-10 17:32 | 2021-08-18 17:26 | 2021-08-20 12:30 |  | 2021-09-01 19:45 | 2021-08-23 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-10 17:32 |  | yes | no | no
1287 | 16104088204610382045878 | 6 | Newberry St | Campbell St | Junction St | Asphalt | Yes | 2021-07-10 18:00 | 2021-07-19 21:01 | 2021-07-20 16:27 |  | 2021-09-02 20:48 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 11:22 |  | yes | no | no
1301 | 16169028204703882046793 | 6 | Norman St | Belle St | Woodmere St | Asphalt | Yes | 2021-08-17 14:03 | 2021-08-21 16:01 | 2021-08-27 16:51 |  | 2021-09-01 17:38 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 11:15 |  | yes | no | no
2722 | 16169028204757082047038 | 6 | Norman St | Pitt St | Belle St | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  |  |  | yes | no | no
2723 | 16169028204757082047038 | 6 | Norman St | Pitt St | Belle St | Asphalt | Yes | [6 empty] | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  |  |  | yes | no | no
1323 | 16169028204806082047570 | 6 | Norman St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 13:56 | 2021-08-21 17:07 | 2021-08-27 17:05 |  | 2021-09-01 17:41 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:20 |  | yes | no | no
2744 | 16168058204921682048624 | 6 | Oakdale St | Mandale St | W Vernor Hwy | Asphalt | Yes | 2021-08-17 14:30 | 2021-08-19 13:49 | 2021-08-27 14:51 |  | 2021-08-31 13:34 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 14:27 |  | yes | no | no
2745 | 16168058204921682048624 | 6 | Oakdale St | Mandale St | W Vernor Hwy | Asphalt | Yes | 2021-08-17 14:31 | 2021-08-19 12:45 | 2021-08-27 14:51 |  | 2021-08-30 18:33 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 14:27 |  | yes | no | no
2738 | 16168048204863282048089 | 6 | Oakdale St | W Vernor Hwy | Woodmere St | Asphalt | Yes | 2021-08-17 14:21 | 2021-08-21 11:28 | 2021-08-27 15:25 |  | 2021-09-01 17:21 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:32 |  | yes | no | no
2739 | 16168048204863282048089 | 6 | Oakdale St | W Vernor Hwy | Woodmere St | Asphalt | Yes | 2021-08-17 14:21 | 2021-08-23 11:37 | 2021-08-27 15:13 |  | 2021-09-01 17:17 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:32 |  | yes | no | no
4243 | 16173108204147982040438 | 6 | Ogden St | Henderson St | Kirkwood St | Asphalt | Yes | 2021-07-21 15:15 | 2021-07-27 20:43 | 2021-08-02 20:20 |  | 2021-08-19 13:43 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:48 |  | yes | no | no
4244 | 16173108204147982040438 | 6 | Ogden St | Henderson St | Kirkwood St | Asphalt | Yes | 2021-07-21 15:13 | 2021-07-27 20:16 | 2021-08-02 19:58 |  | 2021-08-19 13:42 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:48 |  | yes | no | no
4245 | 16173108204147982040438 | 6 | Ogden St | Henderson St | Kirkwood St | Asphalt | Yes | 2021-07-21 15:12 | 2021-07-27 19:49 | 2021-08-02 19:51 |  | 2021-08-19 13:42 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:41 |  | yes | no | no
2035 | 16173108204179782041479 | 6 | Ogden St | McGraw St | Henderson St | Asphalt | Yes | 2021-07-21 15:17 | 2021-07-28 11:42 | 2021-08-02 20:36 |  | 2021-08-19 13:43 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:55 |  | yes | no | no
2770 | 17109108205112582050810 | 6 | Olivet St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 14:37 | 2021-08-20 17:47 | 2021-08-27 12:31 |  | 2021-08-30 14:44 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 11:47 |  | yes | no | no
2771 | 17109108205112582050810 | 6 | Olivet St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 14:39 | 2021-08-23 11:37 | 2021-08-27 12:46 |  | 2021-08-30 14:44 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 11:47 |  | yes | no | no
2079 | 16106018204432982044210 | 6 | Otis St | Clippert St | Cicotte St | Asphalt | Yes | 2021-07-17 16:50 | 2021-07-21 18:25 | 2021-07-26 16:28 |  | 2021-09-03 13:48 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 20:16 |  | yes | no | no
2075 | 16106018204404282043825 | 6 | Otis St | Gilbert St | Livernois Ave | Asphalt | Yes | 2021-07-17 16:49 | 2021-07-21 18:04 | 2021-07-26 15:21 |  | 2021-09-03 13:46 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 20:13 |  | yes | no | no
2068 | 16106018204352082043392 | 6 | Otis St | Hammond St | Wesson St | Asphalt | Yes | 2021-07-17 16:47 | 2021-07-21 15:55 | 2021-07-26 13:22 |  | 2021-09-03 13:13 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 19:30 |  | yes | no | no
2074 | 16106018204382582043723 | 6 | Otis St | Livernois Ave | Military St | Asphalt | Yes | 2021-07-17 16:49 | 2021-07-22 12:18 | 2021-07-26 13:51 |  | 2021-09-03 13:19 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 20:12 |  | yes | no | no
2066 | 16106018204339282043093 | 6 | Otis St | Wesson St | Greusel St | Asphalt | Yes | 2021-07-17 16:47 | 2021-07-21 15:06 | 2021-07-26 12:54 |  | 2021-09-03 13:12 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 19:18 |  | yes | no | no
3554 | 15818098203349682033035 | 6 | Pacific St | Beechwood St | Firwood St | Asphalt | Yes | 2021-07-13 14:31 | 2021-07-26 19:12 | 2021-07-28 21:20 |  | 2021-08-26 14:54 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:46 |  | yes | no | no
3555 | 15818098203349682033035 | 6 | Pacific St | Beechwood St | Firwood St | Asphalt | Yes | 2021-07-13 14:31 | 2021-07-26 19:44 | 2021-07-28 20:56 |  | 2021-08-26 14:55 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:47 |  | yes | no | no
1882 | 15818098203451882034265 | 6 | Pacific St | Colfax St | Northfield St | Asphalt | Yes | 2021-07-13 14:22 | 2021-07-26 18:41 | 2021-07-28 21:31 |  | 2021-08-26 14:50 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:52 |  | yes | no | no
1843 | 15818098203303582032787 | 6 | Pacific St | Firwood St | Turner St | Asphalt | Yes | 2021-07-13 14:31 | 2021-07-26 20:11 | 2021-07-28 20:28 |  | 2021-08-26 14:56 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:49 |  | yes | no | no
2087 | 16096028204505982044670 | 6 | Palms St | W Vernor Hwy | Wolff St | Asphalt | Yes | 2021-07-10 14:58 | 2021-07-15 13:11 | 2021-07-17 16:07 |  | 2021-09-02 19:21 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 16:39 |  | yes | no | no
2070 | 16112028204354682086860 | 6 | Parkwood St | Freer St | Parkinson St | Asphalt | Yes | 2021-07-20 13:30 | 2021-07-22 13:26 | 2021-07-26 20:50 |  | 2021-08-26 19:02 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 12:38 |  | yes | no | no
3726 | 16109098204327282042726 | 6 | Parkwood St | Parkinson St | Martin St | Asphalt | Yes | 2021-07-17 18:56 | 2021-07-22 12:26 | 2021-08-30 14:01 |  | 2021-09-07 18:28 | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:40 |  | yes | no | no
3727 | 16109098204327282042726 | 6 | Parkwood St | Parkinson St | Martin St | Asphalt | Yes | 2021-07-17 18:55 | 2021-07-21 21:06 | 2021-07-26 21:13 |  | 2021-08-26 19:04 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:40 |  | yes | no | no
4267 | 16169018204765882046975 | 6 | Pearl St | Pitt St | Woodmere St | Asphalt | Yes | 2021-08-17 13:59 | 2021-08-23 19:42 | 2021-08-28 12:02 |  | 2021-09-01 17:34 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 11:56 |  | yes | no | no
4269 | 16169018204765882046975 | 6 | Pearl St | Pitt St | Woodmere St | Asphalt | Yes | 2021-08-17 13:59 | 2021-08-21 15:23 | 2021-08-27 16:35 |  | 2021-09-01 17:35 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 11:46 |  | yes | no | no
1324 | 16169018204813582047658 | 6 | Pearl St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 13:57 | 2021-08-23 19:12 | 2021-08-28 15:51 |  | 2021-09-01 17:32 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 13:17 |  | yes | no | no
2012 | 16105078204106782040882 | 6 | Pelouze St | Cicotte St | Gilbert St | Asphalt | Yes | 2021-07-17 17:55 | 2021-07-22 18:36 | 2021-07-27 19:31 |  | 2021-08-26 17:22 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 16:02 |  | yes | no | no
2008 | 16105078204088282040698 | 6 | Pelouze St | Gilbert St | Livernois Ave | Asphalt | Yes | 2021-07-17 17:55 | 2021-07-22 19:17 | 2021-07-27 19:30 |  | 2021-08-26 17:20 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 16:23 |  | yes | no | no
2022 | 16105078204150982041186 | 6 | Pelouze St | Martin St | Burton St | Asphalt | Yes | 2021-07-17 18:11 | 2021-07-22 18:20 | 2021-07-27 19:59 |  | 2021-08-26 17:24 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 15:22 |  | yes | no | no
1318 | 16114108204782882047750 | 6 | Pitt St | Ferris St | Wendell St | Asphalt | Yes | 2021-08-17 14:09 | 2021-08-21 14:23 | 2021-08-27 16:08 |  | 2021-09-01 17:27 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 12:03 |  | yes | no | no
4333 | 16104048204482282044308 | 6 | Plumer St | Junction St | McKinstry St | Asphalt | Yes | 2021-07-10 17:59 | 2021-07-15 19:55 | 2021-07-19 13:33 |  |  | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-07-12 17:43 |  | yes | no | no
4334 | 16104048204482282044308 | 6 | Plumer St | Junction St | McKinstry St | Asphalt | Yes | 2021-07-10 17:59 | 2021-07-15 19:25 | 2021-07-19 13:53 |  | 2021-09-02 20:21 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:34 |  | yes | no | no
4335 | 16104048204482282044308 | 6 | Plumer St | Junction St | McKinstry St | Asphalt | Yes | 2021-07-10 17:59 | 2021-07-15 19:00 | 2021-07-19 13:53 |  | 2021-09-02 20:20 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 17:33 |  | yes | no | no
1309 | 16091048204754682047295 | 6 | Porter St | Cavalry St | Campbell St | Asphalt | Yes | 2021-07-10 15:58 | 2021-07-20 12:58 | 2021-07-20 17:52 |  | 2021-09-02 14:28 | 2021-07-21 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:57 |  | yes | no | no
2097 | 15820018204617282045955 | 6 | Porter St | Scotten St | Hubbard St | Asphalt | Yes | 2021-07-10 14:56 | 2021-07-15 12:31 | 2021-07-17 19:47 |  | 2021-09-02 16:25 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 16:34 |  | yes | no | no
4009 | 16185088203191882030706 | 6 | Prairie St | Dover St | Westfield St | Asphalt | Yes | 2021-07-12 18:44 | 2021-07-20 17:08 | 2021-07-26 20:32 |  | 2021-08-18 19:31 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 14:12 |  | yes | no | no
4011 | 16185088203191882030706 | 6 | Prairie St | Dover St | Westfield St | Asphalt | Yes | 2021-07-12 18:44 | 2021-07-20 16:37 | 2021-07-26 20:08 |  | 2021-08-18 19:29 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 14:12 |  | yes | no | no
1860 | 16183068203364182033335 | 6 | Prairie St | Linsdale St | Mackenzie St | Asphalt | Yes | 2021-07-12 18:54 | 2021-07-20 20:15 | 2021-07-27 12:55 |  | 2021-08-18 19:05 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 15:29 |  | yes | no | no
1905 | 16183068203508782034542 | 6 | Prairie St | Tireman St | Garden St | Asphalt | Yes | 2021-07-12 18:55 | 2021-07-22 12:37 | 2021-07-27 13:27 |  | 2021-08-18 18:21 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 15:07 |  | yes | no | no
3650 | 16171088203752582036797 | 6 | Prairie St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 15:18 | 2021-07-21 15:47 | 2021-07-27 15:48 |  | 2021-08-18 13:22 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 18:13 |  | yes | no | no
3651 | 16171088203752582036797 | 6 | Prairie St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 15:18 | 2021-07-21 16:13 | 2021-07-27 16:01 |  | 2021-08-18 13:24 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 18:13 |  | yes | no | no
1878 | 16088088203457482034434 | 6 | Putnam St | Commonwealth St | Trumbull St | Asphalt | Yes | 2021-07-08 15:43 | 2021-07-10 11:46 | 2021-07-15 12:42 |  | 2021-08-17 18:55 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 19:22 |  | yes | no | no
1893 | 16088088203492882034719 | 6 | Putnam St | Rosa Parks Blvd | Avery St | Asphalt | Yes | 2021-07-08 13:06 | 2021-07-09 20:35 | 2021-07-14 21:54 |  | 2021-08-17 18:59 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 16:49 |  | yes | no | no
1929 | 16107108203602182035761 | 6 | Rangoon St | Barton St | Diversey | Asphalt | Yes | 2021-07-20 16:00 | 2021-07-23 14:03 | 2021-07-28 18:09 |  | 2021-08-18 15:56 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:04 |  | yes | no | no
1916 | 16107108203559482035346 | 6 | Rangoon St | Eagle | Belfast St | Asphalt | Yes | 2021-07-20 15:59 | 2021-07-23 13:41 | 2021-07-28 18:53 |  | 2021-08-18 15:56 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 14:04 |  | yes | no | no
2762 | 16116048205049782050206 | 6 | Rathbone St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 14:46 | 2021-08-20 12:47 | 2021-08-21 17:30 |  | 2021-09-07 16:11 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 18:09 |  | yes | no | no
2763 | 16116048205049782050206 | 6 | Rathbone St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 14:46 | 2021-08-20 12:26 | 2021-08-21 17:31 |  | 2021-08-30 16:12 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 18:09 |  | yes | no | no
4358 | 16116048205020682049709 | 6 | Rathbone St | Lawndale St | Springwells St | Asphalt | Yes | 2021-08-17 14:49 | 2021-08-20 14:04 | 2021-08-21 17:54 |  | 2021-08-30 15:22 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 18:39 |  | yes | no | no
4359 | 16116048205020682049709 | 6 | Rathbone St | Lawndale St | Springwells St | Asphalt | Yes | 2021-08-17 14:52 | 2021-08-20 14:23 | 2021-08-21 17:54 |  | 2021-08-30 15:22 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 18:39 |  | yes | no | no
4360 | 16116048205020682049709 | 6 | Rathbone St | Lawndale St | Springwells St | Asphalt | Yes | 2021-08-17 14:53 | 2021-08-20 14:47 | 2021-08-21 18:01 |  | 2021-08-30 15:22 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 18:40 |  | yes | no | no
4361 | 16116048205020682049709 | 6 | Rathbone St | Lawndale St | Springwells St | Asphalt | Yes | 2021-08-17 14:53 | 2021-08-20 15:13 | 2021-08-21 18:18 |  | 2021-08-30 16:12 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 18:40 |  | yes | no | no
2766 | 16116048205080882050497 | 6 | Rathbone St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 14:44 | 2021-08-19 20:56 | 2021-08-21 16:53 |  | 2021-08-30 14:48 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 17:48 |  | yes | no | no
2767 | 16116048205080882050497 | 6 | Rathbone St | Woodmere St | Elsmere St | Asphalt | Yes | 2021-08-17 14:45 | 2021-08-20 13:10 | 2021-08-21 17:18 |  | 2021-08-30 14:48 | 2021-08-24 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-18 17:49 |  | yes | no | no
1325 | 16104068204833882048184 | 6 | Regular St | Lewerenz St | Waterman St | Asphalt | Yes | 2021-07-12 17:38 | 2021-07-20 20:24 | 2021-07-21 18:56 |  | 2021-09-02 14:05 | 2021-07-22 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 13:21 |  | yes | no | no
4237 | 16173088204135082040310 | 6 | Renville St | Henderson St | Kirkwood St | Asphalt | Yes | 2021-07-21 15:05 | 2021-07-27 17:20 | 2021-08-02 18:34 |  | 2021-08-19 13:56 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:11 |  | yes | no | no
4238 | 16173088204135082040310 | 6 | Renville St | Henderson St | Kirkwood St | Asphalt | Yes | 2021-07-21 15:08 | 2021-07-27 17:44 | 2021-08-03 15:24 |  | 2021-08-19 13:56 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:12 |  | yes | no | no
4239 | 16173088204135082040310 | 6 | Renville St | Henderson St | Kirkwood St | Asphalt | Yes | 2021-07-21 15:10 | 2021-07-27 18:14 | 2021-08-02 18:55 |  | 2021-08-19 13:56 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:12 |  | yes | no | no
2028 | 16173088204164782041350 | 6 | Renville St | McGraw St | Henderson St | Asphalt | Yes | 2021-07-21 15:04 | 2021-07-27 18:43 | 2021-08-03 14:47 |  | 2021-08-19 13:56 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:11 |  | yes | no | no
1981 | 16099058203937482039201 | 6 | Rich St | 28th St | Lovett St | Asphalt | Yes | 2021-07-17 14:54 | 2021-07-19 15:28 | 2021-07-20 12:56 |  | 2021-09-03 16:48 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 15:46 |  | yes | no | no
1993 | 16099058204031782040156 | 6 | Rich St | 35th St | Junction St | Asphalt | Yes | 2021-07-17 15:37 | 2021-07-24 14:46 | 2021-07-27 16:14 |  | 2021-09-03 15:17 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 17:16 |  | yes | no | no
1978 | 16099058203920182039042 | 6 | Rich St | Lovett St | Scotten St | Asphalt | Yes | 2021-07-17 14:39 | 2021-07-19 14:11 | 2021-07-20 12:56 |  | 2021-09-03 16:49 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 16:00 |  | yes | no | no
1999 | 16099058204060982040441 | 6 | Rich St | Wesson St | N Campbell St | Asphalt | Yes | 2021-07-17 15:59 | 2021-07-24 14:23 | 2021-07-27 16:15 |  | 2021-09-03 15:17 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 17:19 |  | yes | no | no
1298 | 16114098204702682046607 | 6 | Rieden St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 13:19 | 2021-08-23 13:28 | 2021-08-28 15:21 |  | 2021-09-01 19:19 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:19 |  | yes | no | no
1299 | 16091108204710782046935 | 6 | Rogers St | Campbell St | Junction St | Asphalt | Yes | 2021-07-10 15:58 | 2021-07-20 13:26 | 2021-07-20 17:18 |  | 2021-09-02 14:50 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:50 |  | yes | no | no
1304 | 16091108204730882047107 | 6 | Rogers St | Cavalry St | Campbell St | Asphalt | Yes | 2021-07-10 15:58 | 2021-07-20 14:45 | 2021-07-20 17:26 |  | 2021-09-02 14:50 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 12:51 |  | yes | no | no
1285 | 16104108204591582045697 | 6 | Romeyn St | Cavalry St | Campbell St | Asphalt | Yes | 2021-07-10 18:00 | 2021-07-19 19:13 | 2021-07-20 13:48 |  | 2021-09-02 20:37 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 18:11 |  | yes | no | no
2004 | 47055358204087582040417 | 6 | Roosevelt St | Martin Luther King Jr Blvd | Magnolia St | Asphalt | Yes | 2021-07-10 14:22 | 2021-07-19 13:10 | 2021-07-19 21:13 |  | 2021-09-03 17:36 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 19:00 |  | yes | no | no
2030 | 15813048204196782041442 | 6 | Roosevelt St | Michigan Ave | Ash St | Asphalt | Yes | 2021-07-10 14:24 | 2021-07-19 12:47 | 2021-07-19 21:07 |  | 2021-09-03 17:55 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 19:39 |  | yes | no | no
4902 | 16113098204886182048607 | 6 | Rowan St | N Green St | Beard St | Asphalt | Yes Round 2 | 2021-09-17 17:59 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:38 |  | no | yes | no
4901 | 47100988206025082059812 | 6 | S Annabelle St | Francis St | Visger St | Asphalt | Yes Round 2 | 2021-09-18 14:52 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-18 14:53 |  | no | yes | no
2115 | 47100988206146982061253 | 6 | S Annabelle St | Outer Dr | Salliotte St | Asphalt | Yes | 2021-07-22 14:20 | 2021-07-26 20:32 | 2021-07-30 17:30 |  | 2021-08-28 15:49 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:19 |  | yes | no | no
2101 | 16268078209826682057091 | 6 | S Annabelle St | Schaefer Hwy | Toronto St | Asphalt | Yes | 2021-07-22 13:47 | 2021-07-27 11:45 | 2021-07-30 14:14 |  | 2021-08-28 18:20 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:30 |  | yes | no | no
1345 | 16268078205709182056603 | 6 | S Annabelle St | Toronto St | Gilroy St | Asphalt | Yes | 2021-07-22 13:47 | 2021-07-27 12:08 | 2021-07-30 13:56 |  | 2021-08-28 18:21 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:30 |  | yes | no | no
3765 | 47100978205898582058397 | 6 | S Beatrice St | Downing St | Miami St | Asphalt | Yes | 2021-07-22 13:59 | [5 empty] | HMA | No |  |  |  |  | Yes |  | 2021-07-23 14:56 |  | yes | no | no
2103 | 47100978205776982057530 | 6 | S Beatrice St | Melvin St | Schaefer | Asphalt | Yes | 2021-07-22 13:53 | 2021-07-27 12:37 | 2021-07-30 14:47 |  | 2021-08-28 18:14 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:34 |  | yes | no | no
3756 | 47100978205839782057769 | 6 | S Beatrice St | Miami St | Melvin St | Asphalt | Yes | 2021-07-22 13:57 | 2021-07-27 11:48 | 2021-07-30 16:01 |  | 2021-08-28 18:19 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:45 |  | yes | no | no
3757 | 47100978205839782057769 | 6 | S Beatrice St | Miami St | Melvin St | Asphalt | Yes | 2021-07-22 13:54 | 2021-07-27 11:53 | 2021-07-30 15:26 |  | 2021-08-28 18:15 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:37 |  | yes | no | no
3773 | 47066598205954482059091 | 6 | S Dartmouth | Francis St | Visger St | Asphalt | Yes | 2021-07-22 15:07 | 2021-07-26 15:50 | 2021-07-31 14:29 |  | 2021-08-28 13:38 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:23 |  | yes | no | no
2105 | 47066598205992982059544 | 6 | S Dartmouth | Gleason St | Francis St | Asphalt | Yes | 2021-07-22 15:00 | 2021-07-26 15:29 | 2021-07-31 14:45 |  | 2021-08-28 13:38 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:32 |  | yes | no | no
2107 | 47066598206029382059929 | 6 | S Dartmouth | Outer Dr | Gleason St | Asphalt | Yes | 2021-07-22 14:58 | 2021-07-26 14:48 | 2021-07-31 14:59 |  | 2021-08-28 13:38 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:32 |  | yes | no | no
3779 | 16267058205990982059474 | 6 | S Edsel St | Francis St | Visger St | Asphalt | Yes | 2021-07-22 15:19 | 2021-07-26 19:02 | 2021-07-31 13:16 |  | 2021-08-28 15:03 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:56 |  | yes | no | no
2106 | 16267058206030082059909 | 6 | S Edsel St | Gleason St | Francis St | Asphalt | Yes | 2021-07-22 15:18 | 2021-07-26 18:33 | 2021-07-31 13:16 |  | 2021-08-28 15:03 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:51 |  | yes | no | no
3788 | 16267058206071182060300 | 6 | S Edsel St | Le Blanc St | Gleason St | Asphalt | Yes | 2021-07-22 15:14 | 2021-07-26 17:10 | 2021-07-31 15:35 |  | 2021-08-28 14:52 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:48 |  | yes | no | no
3789 | 16267058206071182060300 | 6 | S Edsel St | Le Blanc St | Gleason St | Asphalt | Yes | 2021-07-22 15:16 | 2021-07-26 18:16 | 2021-07-30 19:56 |  | 2021-08-28 15:02 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:48 |  | yes | no | no
2111 | 16267058206096382060711 | 6 | S Edsel St | Outer Dr | Le Blanc St | Asphalt | Yes | 2021-07-22 15:13 | 2021-07-26 16:41 | 2021-07-30 19:35 |  | 2021-08-28 14:51 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:42 |  | yes | no | no
3787 | 47100958206052382060118 | 6 | S Ethel St | Francis St | Visger St | Asphalt | Yes | 2021-09-18 14:41 | [5 empty] | HMA | No |  |  |  | No | Yes |  | 2021-09-18 14:41 |  | yes | no | no
2110 | 47100958206087682060523 | 6 | S Ethel St | Gleason St | Francis St | Asphalt | Yes | 2021-07-22 14:11 | 2021-07-26 19:36 | 2021-07-30 16:39 |  | 2021-08-28 15:59 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:40 |  | yes | no | no
2117 | 47100958206186282061539 | 6 | S Ethel St | Outer Dr | Salliotte St | Asphalt | Yes | 2021-07-22 14:18 | 2021-07-26 20:55 | 2021-07-30 17:09 |  | 2021-08-28 15:58 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:32 |  | yes | no | no
2113 | 47100958206120982060876 | 6 | S Ethel St | Peters St | Gleason St | Asphalt | Yes | 2021-07-22 14:12 | 2021-07-26 20:26 | 2021-07-30 16:40 |  | 2021-08-28 15:59 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:37 |  | yes | no | no
2116 | 47100958206153982061209 | 6 | S Ethel St | Salliotte St | Peters St | Asphalt | Yes | 2021-07-22 14:15 | 2021-07-26 21:04 | 2021-07-30 16:51 |  | 2021-08-28 15:58 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:32 |  | yes | no | no
2108 | 47044888206040682060002 | 6 | S Greyfriars St | Outer Dr | Gleason St | Asphalt | Yes | 2021-07-22 14:54 | 2021-07-26 15:20 | 2021-07-31 15:17 |  | 2021-08-28 14:28 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:35 |  | yes | no | no
3783 | 47100998206012982090730 | 6 | S Liddesdale St | Francis St | Visger St | Asphalt | Yes | 2021-07-22 14:28 | 2021-07-26 17:00 | 2021-07-30 19:11 |  | 2021-08-28 15:09 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:01 |  | yes | no | no
1343 | 16268068205653082056110 | 6 | S Liddesdale St | Gilroy St | Leonard St | Asphalt | Yes | 2021-07-22 13:34 | 2021-07-27 12:38 | 2021-07-30 13:41 |  | 2021-08-28 18:21 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:05 |  | yes | no | no
2109 | 47100998206049182060129 | 6 | S Liddesdale St | Gleason St | Francis St | Asphalt | Yes | 2021-07-22 14:25 | 2021-07-26 17:45 | 2021-07-30 19:04 |  | 2021-08-28 15:11 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:05 |  | yes | no | no
2114 | 47100998206136082061168 | 6 | S Liddesdale St | Outer Dr | Salliotte St | Asphalt | Yes | 2021-07-22 14:23 | 2021-07-26 18:41 | 2021-07-30 18:05 |  | 2021-08-28 15:13 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:19 |  | yes | no | no
2112 | 47100998206116882060846 | 6 | S Liddesdale St | Salliotte St | Peters St | Asphalt | Yes | 2021-07-22 14:24 | 2021-07-26 18:11 | 2021-07-30 18:05 |  | 2021-08-28 15:12 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 16:11 |  | yes | no | no
2102 | 16268068205748382056999 | 6 | S Liddesdale St | Schaefer | Toronto St | Asphalt | Yes | 2021-07-22 13:32 | 2021-07-27 12:54 | 2021-07-30 13:21 |  | 2021-08-28 18:19 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:07 |  | yes | no | no
1344 | 16268068205699982056530 | 6 | S Liddesdale St | Toronto St | Gilroy St | Asphalt | Yes | 2021-07-22 13:33 | 2021-07-27 13:12 | 2021-07-30 13:34 |  | 2021-08-28 18:20 | 2021-07-31 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:06 |  | yes | no | no
1814 | 16181068203235482032068 | 6 | S Martindale St | Colfax St | Northfield St | Asphalt | Yes | 2021-07-13 12:34 | 2021-07-20 12:42 | 2021-07-26 16:28 |  | 2021-08-26 13:23 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 17:29 |  | yes | no | no
3740 | 15808118204286282043643 | 6 | Saint James St | Michigan Ave | Dead End or Start | Asphalt | Yes | 2021-07-20 15:06 | 2021-07-24 12:03 | 2021-07-29 20:10 |  | 2021-08-27 14:06 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:25 |  | yes | no | no
3741 | 15808118204286282043643 | 6 | Saint James St | Michigan Ave | Dead End or Start | Asphalt | Yes | 2021-07-20 15:09 | 2021-07-24 12:20 | 2021-07-29 19:30 |  | 2021-08-27 14:05 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:28 |  | yes | no | no
2060 | 16112038204272282042544 | 6 | Saint John St | Apple St | Martin St | Asphalt | Yes | 2021-07-17 18:55 | 2021-07-21 20:03 | 2021-07-26 20:01 |  | 2021-08-26 19:08 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:51 |  | yes | no | no
2065 | 16112038204286782042722 | 6 | Saint John St | Apple St | Larkins St | Asphalt | Yes | 2021-07-17 18:55 | 2021-07-22 12:59 | 2021-07-28 15:54 |  | 2021-08-26 19:09 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:51 |  | yes | no | no
3736 | 16112038204373682043358 | 6 | Saint John St | Central St | Freer St | Asphalt | Yes | 2021-07-20 13:35 | 2021-07-23 12:02 | 2021-07-28 16:16 |  | 2021-08-26 19:40 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 12:46 |  | yes | no | no
3737 | 16112038204373682043358 | 6 | Saint John St | Central St | Freer St | Asphalt | Yes | 2021-07-20 13:33 | 2021-07-22 15:59 | 2021-07-26 20:32 |  | 2021-08-26 19:40 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 12:45 |  | yes | no | no
3739 | 16169078204371282042989 | 6 | Saint Lawrence St | Baubee St | Sumner Ave | Asphalt | Yes | 2021-07-20 14:18 | 2021-07-23 15:08 | 2021-07-29 22:38 |  | 2021-08-27 16:02 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:01 |  | yes | no | no
2020 | 16173078204132882041047 | 6 | Saint Lawrence St | McGraw St | Henderson St | Asphalt | Yes | 2021-07-21 13:50 | 2021-07-27 16:30 | 2021-08-02 16:56 |  | 2021-08-19 14:38 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:20 |  | yes | no | no
3748 | 16169078204427482043712 | 6 | Saint Lawrence St | Saint John St | Baubee St | Asphalt | Yes | 2021-07-21 13:00 | 2021-07-23 16:02 | 2021-07-29 15:54 |  | 2021-08-27 16:03 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:21 |  | yes | no | no
3749 | 16169078204427482043712 | 6 | Saint Lawrence St | Saint John St | Baubee St | Asphalt | Yes | 2021-07-20 14:15 | 2021-07-23 15:53 | 2021-07-29 15:57 |  | 2021-08-27 16:03 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 18:21 |  | yes | no | no
3712 | 16173078204079782039964 | 6 | Saint Lawrence St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-21 13:43 | 2021-07-27 15:41 | 2021-08-02 16:45 |  | 2021-08-19 14:36 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:15 |  | yes | no | no
3713 | 16173078204079782039964 | 6 | Saint Lawrence St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-21 13:32 | 2021-07-27 15:19 | 2021-08-02 16:20 |  | 2021-08-19 14:36 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:08 |  | yes | no | no
3572 | 16180048203407282033608 | 6 | Seebaldt St | Beechwood St | Firwood St | Asphalt | Yes | 2021-07-13 14:32 | 2021-07-26 21:14 | 2021-07-28 20:04 |  | 2021-08-26 15:03 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:59 |  | yes | no | no
3573 | 16180048203407282033608 | 6 | Seebaldt St | Beechwood St | Firwood St | Asphalt | Yes | 2021-07-13 14:32 | 2021-07-26 20:51 | 2021-07-28 20:10 |  | 2021-08-26 15:01 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 14:58 |  | yes | no | no
2726 | 16114068204785382047528 | 6 | Senator St | Central St | N Green St | Asphalt | Yes | 2021-08-17 15:36 | 2021-08-23 18:26 | 2021-08-28 18:25 |  | 2021-09-01 19:34 | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 13:56 |  | yes | no | no
2727 | 16114068204785382047528 | 6 | Senator St | Central St | N Green St | Asphalt | Yes | 2021-08-20 15:22 | 2021-08-23 15:22 | 2021-08-28 19:02 |  | 2021-09-01 19:35 | 2021-09-01 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 13:56 |  | yes | no | no
4896 | 16172068204068382040324 | 6 | Smart St | Addison St | Trenton St | Asphalt | Yes Round 2 | 2021-09-17 17:16 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:41 |  | no | yes | no
3706 | 16172068203992082039446 | 6 | Smart St | Lonyo St | McDonald St | Asphalt | Yes | 2021-07-21 13:24 | 2021-08-24 15:32 | 2021-08-30 15:11 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 13:12 |  | yes | no | no
3707 | 16172068203992082039446 | 6 | Smart St | Lonyo St | McDonald St | Asphalt | Yes | 2021-07-21 13:22 | 2021-07-27 14:49 | 2021-08-03 16:17 |  | 2021-08-19 15:15 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 13:03 |  | yes | no | no
1984 | 16172068203944682039103 | 6 | Smart St | McDonald St | Central St | Asphalt | Yes | 2021-07-21 13:19 | 2021-07-27 14:18 | 2021-08-03 15:56 |  | 2021-08-19 15:15 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 12:56 |  | yes | no | no
4897 | 16172068204032482039920 | 6 | Smart St | Trenton St | Lonyo St | Asphalt | Yes Round 2 | 2021-09-17 17:18 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:41 |  | no | yes | no
4028 | 16108028203736782037019 | 6 | Sparta St | Wetherby St | Rangoon St | Asphalt | Yes | 2021-07-20 17:18 | 2021-07-22 15:04 | 2021-07-28 13:27 |  | 2021-08-18 16:12 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 17:01 |  | yes | no | no
4029 | 16108028203736782037019 | 6 | Sparta St | Wetherby St | Rangoon St | Asphalt | Yes | 2021-07-20 17:19 | 2021-07-22 15:19 | 2021-07-28 14:25 |  | 2021-08-18 16:14 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 17:01 |  | yes | no | no
3732 | 47065328204284182043579 | 6 | Springwells St | Cypress St | Saint Stephens St | Asphalt | Yes | 2021-07-20 13:52 | 2021-07-23 13:37 | 2021-07-28 18:11 |  | 2021-08-27 16:00 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:18 |  | yes | no | no
2062 | 47065328204226882042841 | 6 | Springwells St | Michigan Ave | Cypress St | Asphalt | Yes | 2021-07-20 13:49 | 2021-07-23 15:28 | 2021-07-28 17:57 |  | 2021-08-27 15:59 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:11 |  | yes | no | no
1295 | 16115038204683582046430 | 6 | Stair St | Pitt St | Dix St | Asphalt | Yes | 2021-08-17 13:25 | 2021-08-23 12:56 | 2021-08-28 14:59 |  | 2021-09-01 19:12 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:25 |  | yes | no | no
1306 | 16115038204724382046835 | 6 | Stair St | W Vernor Hwy | Pitt St | Asphalt | Yes | 2021-08-17 13:25 | 2021-08-23 12:37 | 2021-08-28 14:14 |  | 2021-09-01 19:11 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-17 13:24 |  | yes | no | no
1973 | 16170068203845482038199 | 6 | Tarnow St | Burwell St | Sarena St | Asphalt | Yes | 2021-07-20 17:58 | 2021-07-23 20:08 | 2021-07-30 17:31 |  | 2021-08-19 18:07 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 13:29 |  | yes | no | no
1977 | 16170068203898882038454 | 6 | Tarnow St | Kirkwood St | Burwell St | Asphalt | Yes | 2021-07-20 17:56 | 2021-07-23 19:28 | 2021-07-30 17:00 |  | 2021-08-19 18:06 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 13:33 |  | yes | no | no
1996 | 16170068204036282039779 | 6 | Tarnow St | McGraw St | Wagner St | Asphalt | Yes | 2021-07-20 17:51 | 2021-07-26 12:15 | 2021-07-30 15:52 |  | 2021-08-19 18:03 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes | Car | 2021-07-22 14:46 |  | yes | no | no
2006 | 16170068204084682040586 | 6 | Tarnow St | Panama St | Gladys Ct | Asphalt | Yes | 2021-07-20 17:48 | 2021-07-26 13:13 | 2021-07-30 15:40 |  | 2021-08-19 19:10 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 14:46 |  | yes | no | no
2021 | 16170068204140082040846 | 6 | Tarnow St | W I 94 Service Drive | Panama St | Asphalt | Yes | 2021-07-20 17:38 | 2021-07-26 12:53 | 2021-07-30 15:17 |  | 2021-08-19 19:09 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:18 |  | yes | no | no
3704 | 16170068203977982038988 | 6 | Tarnow St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-20 17:53 | 2021-07-23 18:44 | 2021-07-30 16:19 |  | 2021-08-19 18:04 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 14:27 |  | yes | no | no
3705 | 16170068203977982038988 | 6 | Tarnow St | Wagner St | Kirkwood St | Asphalt | Yes | 2021-07-20 17:54 | 2021-07-23 19:00 | 2021-07-30 16:41 |  | 2021-08-19 18:04 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 14:22 |  | yes | no | no
2071 | 15808088204358882043188 | 6 | Ternes | Baubee St | Cypress St | Asphalt | Yes | 2021-07-20 14:02 | 2021-07-23 14:34 | 2021-07-29 15:30 |  | 2021-08-27 15:13 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:48 |  | yes | no | no
2063 | 15808088204283282042376 | 6 | Ternes | Sumner Ave | Elmer St & Michigan Ave | Asphalt | Yes | 2021-07-20 14:05 | 2021-08-24 13:06 | 2021-08-30 14:08 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:11 |  | yes | no | no
2003 | 15813078204096082040473 | 6 | Tillman St | Ash St | Martin Luther King Jr Blvd | Asphalt | Yes | 2021-07-10 14:14 | 2021-07-17 20:39 | 2021-07-19 18:27 |  | 2021-09-03 18:07 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 17:58 |  | yes | no | no
2009 | 16174018204081082040573 | 6 | Trenton St | Dennison St | Kirkwood St | Asphalt | Yes | 2021-07-21 14:36 | 2021-07-27 22:31 | 2021-08-02 20:58 |  | 2021-08-19 13:40 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:05 |  | yes | no | no
3716 | 16174018204161682040810 | 6 | Trenton St | Henderson St | Dennison St | Asphalt | Yes | 2021-07-21 14:32 | 2021-07-27 21:44 | 2021-08-03 13:53 |  | 2021-08-19 13:40 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:39 |  | yes | no | no
3717 | 16174018204161682040810 | 6 | Trenton St | Henderson St | Dennison St | Asphalt | Yes | 2021-07-21 14:33 | 2021-07-27 22:11 | 2021-08-03 14:24 |  | 2021-08-19 13:40 | 2021-08-04 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:00 |  | yes | no | no
1770 | 15818058203114382030394 | 6 | Underwood St | Northfield St | Beechwood St | Asphalt | Yes | 2021-07-12 18:19 | 2021-07-20 14:11 | 2021-07-26 18:03 |  | 2021-08-26 12:48 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 13:27 |  | yes | no | no
3538 | 16180078203293182032431 | 6 | Vancouver St | Beechwood St | Firwood St | Asphalt | Yes | 2021-07-13 14:22 | 2021-07-26 11:24 | 2021-08-03 18:41 |  |  | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:30 |  | yes | no | no
3539 | 16180078203293182032431 | 6 | Vancouver St | Beechwood St | Firwood St | Asphalt | Yes | 2021-07-13 14:22 | 2021-07-26 11:25 | 2021-08-03 19:11 |  | 2021-08-26 14:10 | 2021-08-05 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:29 |  | yes | no | no
1870 | 16180078203399182033704 | 6 | Vancouver St | Colfax St | Northfield St | Asphalt | Yes | 2021-07-13 14:01 | 2021-07-26 22:08 | 2021-07-28 22:02 |  | 2021-08-26 14:45 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:52 |  | yes | no | no
4015 | 16180078203370482033198 | 6 | Vancouver St | Northfield St | Ironwood St | Asphalt | Yes | 2021-07-13 14:01 | 2021-07-26 22:34 | 2021-07-28 22:20 |  | 2021-08-26 14:15 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:52 |  | yes | no | no
4017 | 16180078203370482033198 | 6 | Vancouver St | Northfield St | Ironwood St | Asphalt | Yes | 2021-07-13 14:01 | 2021-07-26 11:22 | 2021-07-28 22:45 |  | 2021-08-26 14:13 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:30 |  | yes | no | no
2086 | 16095058204502282044812 | 6 | Vinewood St | Bagley St | W Vernor Hwy | Asphalt | Yes | 2021-07-10 16:28 | 2021-07-14 19:21 | 2021-07-17 16:44 |  | 2021-09-02 16:14 | 2021-07-20 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 15:37 |  | yes | no | no
2096 | 16095058204576782045393 | 6 | Vinewood St | Porter St | Shady Ln | Asphalt | Yes | 2021-07-10 16:27 | 2021-07-14 20:19 | 2021-07-17 17:40 |  | 2021-09-02 16:17 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 15:59 |  | yes | no | no
2091 | 16095058204539382045022 | 6 | Vinewood St | Shady Ln | Bagley St | Asphalt | Yes | 2021-07-10 16:27 | 2021-07-14 19:46 | 2021-07-17 19:15 |  | 2021-09-02 16:16 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 15:38 |  | yes | no | no
3750 | 16095058204649382045767 | 6 | Vinewood St | W Lafayette Blvd | Porter St | Asphalt | Yes | 2021-07-10 15:59 | 2021-07-15 11:40 | 2021-07-17 17:11 |  | 2021-09-02 16:20 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 16:18 |  | yes | no | no
3751 | 16095058204649382045767 | 6 | Vinewood St | W Lafayette Blvd | Porter St | Asphalt | Yes | 2021-07-10 15:59 | 2021-07-14 20:53 | 2021-07-17 17:25 |  | 2021-09-02 16:19 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-12 16:04 |  | yes | no | no
2104 | 15937108205917682059281 | 6 | Visger St | S Greyfriars St | S Waring St | Asphalt | Yes | 2021-07-22 14:46 | 2021-07-26 15:02 | 2021-07-31 13:19 |  | 2021-08-28 13:37 | 2021-08-02 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-23 15:06 |  | yes | no | no
1946 | 15841078203716882037045 | 6 | W Alexandrine St | Commonwealth St | Trumbull St | Asphalt | Yes | 2021-07-08 16:05 | 2021-07-10 14:11 | 2021-07-14 21:13 |  | 2021-08-17 18:35 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:53 |  | yes | no | no
1952 | 15841078203740482037296 | 6 | W Alexandrine St | Grand River Ave | Avery St | Asphalt | Yes | 2021-07-08 15:42 | 2021-07-10 14:42 | 2021-07-14 21:39 |  | 2021-08-17 18:32 | 2021-07-15 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-08 17:38 |  | yes | no | no
4880 | 16087068203536482035211 | 6 | W Hancock St | Commonwealth St | Trumbull St | Asphalt | Yes Round 2 | 2021-09-17 18:25 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:42 |  | no | yes | no
4886 | 16086108203718782037018 | 6 | W Willis St | Rosa Parks Blvd | Avery St | Asphalt | Yes Round 2 | 2021-09-17 18:21 | [5 empty] | HMA | [5 empty] | Yes |  | 2021-09-17 19:41 |  | no | yes | no
1997 | 16107048204043382040268 | 6 | Wagner St | Springwells St | Casper St | Asphalt | Yes | 2021-07-21 13:12 | 2021-07-27 13:28 | 2021-08-02 14:14 |  | 2021-08-19 15:33 | 2021-08-03 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 17:56 |  | yes | no | no
3728 | 16109088204349682042979 | 6 | Waldo St | Parkinson St | Martin St | Asphalt | Yes | 2021-07-17 18:55 | 2021-07-22 14:37 | 2021-07-26 21:41 |  | 2021-08-26 19:33 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:27 |  | yes | no | no
3729 | 16109088204349682042979 | 6 | Waldo St | Parkinson St | Martin St | Asphalt | Yes | 2021-07-17 18:55 | 2021-07-22 14:39 | 2021-07-26 21:40 |  | 2021-08-26 19:32 | 2021-07-27 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 13:27 |  | yes | no | no
4246 | 15772098204210482041127 | 6 | Wesson St | Michigan Ave | Buchanan St | Asphalt | Yes | 2021-07-17 16:01 | 2021-07-24 16:01 | 2021-07-27 12:55 |  | 2021-09-03 15:10 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 18:36 |  | yes | no | no
4247 | 15772098204210482041127 | 6 | Wesson St | Michigan Ave | Buchanan St | Asphalt | Yes | 2021-07-17 16:01 | 2021-07-24 15:29 | 2021-07-27 12:55 |  | 2021-09-03 15:11 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 17:50 |  | yes | no | no
4248 | 15772098204210482041127 | 6 | Wesson St | Michigan Ave | Buchanan St | Asphalt | Yes | 2021-07-17 16:01 | 2021-07-24 15:25 | 2021-07-27 12:55 |  | 2021-09-03 15:16 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 17:36 |  | yes | no | no
2005 | 15772098208686982040609 | 6 | Wesson St | Vigo St | Rich St | Asphalt | Yes | 2021-07-17 16:00 | 2021-07-22 20:49 | 2021-07-27 16:35 |  | 2021-09-03 15:16 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-18 17:36 |  | yes | no | no
4382 | 15807078204482582086827 | 6 | Western St | Saint Stephens St | Michigan Ave | Asphalt | Yes | 2021-07-20 15:19 | 2021-07-24 13:17 | 2021-07-29 21:15 |  | 2021-08-27 13:57 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 16:01 |  | yes | no | no
4383 | 15807078204482582086827 | 6 | Western St | Saint Stephens St | Michigan Ave | Asphalt | Yes | 2021-07-20 15:17 | 2021-07-24 13:08 | 2021-07-29 21:47 |  | 2021-08-27 13:57 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:56 |  | yes | no | no
4384 | 15807078204482582086827 | 6 | Western St | Saint Stephens St | Michigan Ave | Asphalt | Yes | 2021-07-20 15:15 | 2021-07-24 12:56 | 2021-07-29 21:58 |  | 2021-08-27 13:58 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:50 |  | yes | no | no
4385 | 15807078204482582086827 | 6 | Western St | Saint Stephens St | Michigan Ave | Asphalt | Yes | 2021-07-20 15:13 | 2021-08-24 14:04 | 2021-08-30 14:26 |  |  | 2021-09-01 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:40 |  | yes | no | no
4386 | 15807078204482582086827 | 6 | Western St | Saint Stephens St | Michigan Ave | Asphalt | Yes | 2021-07-20 15:11 | 2021-07-24 12:31 | 2021-07-29 22:16 |  | 2021-08-27 13:59 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-22 15:28 |  | yes | no | no
1910 | 16111058203534982035062 | 6 | Wetherby St | Belfast St | Tireman St | Asphalt | Yes | 2021-07-13 17:27 | 2021-07-22 13:05 | 2021-07-27 21:55 |  | 2021-08-18 15:56 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 17:40 |  | yes | no | no
1926 | 16111058203593982035607 | 6 | Wetherby St | Diversey | Eagle | Asphalt | Yes | 2021-07-13 17:27 | 2021-07-22 13:32 | 2021-07-27 21:34 |  | 2021-08-18 15:55 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 18:11 |  | yes | no | no
1954 | 16111058203723082036933 | 6 | Wetherby St | Floyd St | Clifton St | Asphalt | Yes | 2021-07-13 17:27 | 2021-07-22 14:28 | 2021-07-27 20:53 |  | 2021-08-18 15:55 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 18:22 |  | yes | no | no
1942 | 16111058203660582036311 | 6 | Wetherby St | Majestic St | Barton St | Asphalt | Yes | 2021-07-13 17:27 | 2021-07-22 14:08 | 2021-07-27 21:13 |  | 2021-08-18 15:55 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 18:21 |  | yes | no | no
1972 | 16171068203800282037969 | 6 | Wheeler St | Proctor St | Sarena St | Asphalt | Yes | 2021-07-20 17:29 | 2021-07-23 16:07 | 2021-07-30 12:20 |  | 2021-08-19 18:50 | 2021-07-30 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-21 17:47 |  | yes | no | no
2000 | 16105098204058882040427 | 6 | Whitehead St | Cicotte St | Gilbert St | Asphalt | Yes | 2021-07-17 18:12 | 2021-07-22 20:44 | 2021-07-27 16:52 |  | 2021-08-26 16:50 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-19 15:11 |  | yes | no | no
1775 | 47056498203129982030545 | 6 | Whitfield St | Northfield St | Beechwood St | Asphalt | Yes | 2021-07-12 18:19 | 2021-07-20 13:47 | 2021-07-26 16:49 |  | 2021-08-26 12:55 | 2021-07-26 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 13:45 |  | yes | no | no
2724 | 16114088204768682047335 | 6 | Whittaker St | Central St | N Green St | Asphalt | Yes | 2021-08-17 15:37 | 2021-08-23 14:50 | 2021-08-28 17:35 |  | 2021-09-01 19:31 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 14:14 |  | yes | no | no
2725 | 16114088204768682047335 | 6 | Whittaker St | Central St | N Green St | Asphalt | Yes | 2021-08-17 15:37 | 2021-08-23 14:34 | 2021-08-28 17:31 |  | 2021-09-01 19:30 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 14:15 |  | yes | no | no
1307 | 16114088204733582047077 | 6 | Whittaker St | N Green St | Beard St | Asphalt | Yes | 2021-08-17 15:38 | 2021-08-23 14:12 | 2021-08-28 16:51 |  | 2021-09-01 19:28 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 14:15 |  | yes | no | no
5562 | 16107058203878282038371 | 6 | Willette St | Martin St | Cicotte St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
5563 | 16107058203878282038371 | 6 | Willette St | Martin St | Cicotte St | Asphalt | Yes Round 3 | [6 empty] | HMA | [5 empty] | Yes | [5 empty] | Yes
2027 | 15813088204191882041389 | 6 | Williams St | Michigan Ave | Butternut St | Asphalt | Yes | 2021-07-10 14:11 | 2021-07-17 20:06 | 2021-07-19 17:05 |  | 2021-09-03 18:04 | 2021-07-19 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-10 17:36 |  | yes | no | no
2772 | 17109098205129382050981 | 6 | Witt St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 14:41 | 2021-08-20 19:01 | 2021-08-27 12:31 |  | 2021-08-30 14:42 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 12:30 |  | yes | no | no
2773 | 17109098205129382050981 | 6 | Witt St | Elsmere St | Lawndale St | Asphalt | Yes | 2021-08-17 14:40 | 2021-08-20 18:11 | 2021-08-27 12:30 |  | 2021-08-30 14:43 | 2021-08-30 04:00 | HMA | No | Coordinate with DTE GRP |  |  | Yes | Yes |  | 2021-08-20 12:30 |  | yes | no | no
3606 | 16171078203596282035073 | 6 | Wykes St | Diversey | Tireman St | Asphalt | Yes | 2021-07-13 15:11 | 2021-07-21 17:19 | 2021-07-27 18:27 |  | 2021-08-18 13:33 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 15:47 |  | yes | no | no
3607 | 16171078203596282035073 | 6 | Wykes St | Diversey | Tireman St | Asphalt | Yes | 2021-07-13 15:11 | 2021-07-21 16:52 | 2021-07-27 18:30 |  | 2021-08-18 13:34 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 15:46 |  | yes | no | no
3622 | 16171078203678182035962 | 6 | Wykes St | Majestic St | Diversey | Asphalt | Yes | 2021-07-13 15:12 | 2021-07-21 19:13 | 2021-07-27 17:13 |  | 2021-08-18 13:30 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 16:04 |  | yes | no | no
3623 | 16171078203678182035962 | 6 | Wykes St | Majestic St | Diversey | Asphalt | Yes | 2021-07-13 15:12 | 2021-07-21 18:36 | 2021-07-27 18:01 |  | 2021-08-18 13:33 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-17 16:04 |  | yes | no | no
3648 | 16171078203751382036781 | 6 | Wykes St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 15:19 | 2021-07-21 20:00 | 2021-07-27 16:21 |  | 2021-08-18 13:27 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 18:28 |  | yes | no | no
3649 | 16171078203751382036781 | 6 | Wykes St | W Warren Ave | Majestic St | Asphalt | Yes | 2021-07-13 15:19 | 2021-07-21 19:35 | 2021-07-27 16:34 |  | 2021-08-18 13:29 | 2021-07-28 04:00 | HMA | No |  |  |  | No | Yes |  | 2021-07-13 18:28 |  | yes | no | no