## Final 2021 Residential Resurfac
Pave Order | Target_Year | Road Class | District Number | Project (1) | Street | From | To | Number of Speed Humps | Resurfacing Status | Resurfacing Completion Date | Speed Hump Status | Length | Material | Project Notes | Project Number | Utility Status | Class B Section
1 | 2021 | Class B | 6 | Patricia from Pleasant to Gilroy | Patricia | Pleasant | Gilroy |  | Completed | 2021-05-18 |  | 0.28 | Asp |  | PW-7019 |  | Pleasant to Gilroy-Fairchild
2 | 2021 | Class A | 6 | Clippert from Clayton to Michigan Ave | Clippert | Clayton | Michigan Ave |  | Completed | 2021-05-18 | Existing Speed Cushion | 0.28 | Asp |  | PW-7019
3 | 2021 | Class A | 6 | Horatio from Martin to Cecil | Horatio | Martin | Cecil |  | Completed | 2021-05-17 | Speed hump to be installed | 0.19 | Conc |  | PW-7019
4 | 2021 | Class A | 6 | Edsel Ford from Larkins to Braden | Edsel Ford | Larkins | Braden |  | Completed | 2021-05-19 |  | 0.06 | Asp |  | PW-7019
5 | 2021 | Class A | 6 | Torrey from 28th to Scotten | Torrey | 28th | Scotten |  | Completed | 2021-05-20 |  | 0.14 | Asp |  | PW-7019
6 | 2021 | Class A | 6 | 25th from Warren to Hancock | 25th | Warren | Hancock |  | Completed | 2021-05-19 |  | 0.10417 | Asp |  | PW-7019
7 | 2021 | Class A | 6 | Gilbert from Wagner to McGraw | Gilbert | Wagner | McGraw |  | Completed | 2021-05-15 |  | 0.13 | Asp |  | PW-7019
8 | 2021 | Class A | 6 | Beechton from Livernois to Warren | Beechton | Livernois | Warren |  | Completed | 2021-05-19 |  | 0.13 | Asp |  | PW-7019
9 | 2021 | Class A | 6 | Sharon from Edsel Ford to Dead End N. | Sharon | Edsel Ford | Dead End N. |  | Completed | 2021-05-19 |  | 0.037879 | Asp |  | PW-7019
10 | 2021 | Class A | 7 | Orangelawn From Wyoming to Mendota | Orangelawn | Wyoming | Mendota |  | Completed | 2021-05-15 |  | 0.31 | Asp |  | PW-7019
11 | 2021 | Class A | 7 | Lauder from Westfield to Chicago | Lauder | Westfield | Chicago |  | Completed | 2021-05-24 | Speed hump to be installed | 0.12 | Conc |  | PW-7019
12 | 2021 | Class A | 7 | Sussex from Chicago to Joy | Sussex | Chicago | Joy |  | Completed | 2021-05-21 | Speed hump to be installed | 0.32 | Asp |  | PW-7019
13 | 2021 | Class A | 7 | Winthrop from Ellis to Westfield | Winthrop | Ellis | Westfield |  | Completed | 2021-05-06 | Speed hump to be installed | 0.19 | Conc |  | PW-7019
14 | 2021 | Class A | 7 | Saint Marys from Joy to Cathedral | Saint Marys | Joy | Cathedral |  | Completed | 2021-05-07 |  | 0.24 | Conc |  | PW-7019
15 | 2021 | Class A | 7 | Mettetal from Cathedral to Ellis | Mettetal | Cathedral | Ellis |  | Completed | 2021-05-05 |  | 0.08 | Conc |  | PW-7019
16 | 2021 | Class A | 7 | Asbury Park from Joy to Ellis | Asbury Park | Joy | Ellis |  | Completed | 2021-05-24 | Speed hump to be installed | 0.16 | Asp |  | PW-7019
17 | 2021 | Class A | 7 | Memorial from Chicago to Dead End (S) | Memorial | Chicago | Dead End (S) |  | Completed | 2021-05-07 |  | 0.26 | Conc |  | PW-7019
18 | 2021 | Class A/Class B | 7 | Rutland from Chicago to Dead End (S) | Rutland | Chicago | Dead End (S) |  | Completed | 2021-05-07 |  | 0.14 | Conc |  | PW-7019 |  | Westfield to Dead End (S)
19 | 2021 | Class A/Class B | 7 | Mansfield From Chicago to Plymouth | Mansfield | Chicago | Plymouth |  | Completed | 2021-05-22 |  | 0.5 | Asp |  | PW-7019 |  | Chicago to Elmira
20 | 2021 | Class A | 7 | Tuller from Eaton to Lyndon | Tuller | Eaton | Lyndon |  |  |  |  | 0.18758 | Asp |  | PW-7019
21 | 2021 | Class A | 2 | Greenlawn from John C Lodge Fwy to Fenkell | Greenlawn | John C Lodge Fwy | Fenkell |  | Completed | 2021-08-04 |  | 0.1581 | Asp |  | PW-7019
22 | 2021 | Class A | 2 | Northlawn from Chalfonte to Lyndon | Northlawn | Chalfonte | Lyndon |  | Completed | 2021-06-08 |  | 0.34472 | Conc |  | PW-7019
23 | 2021 | Class B | 2 | Ohio from Chalfonte to Lyndon | Ohio | Chalfonte | Lyndon |  | Completed | 2021-05-26 |  | 0.34507 | Asp |  | PW-7019 |  | Chalfonte to Lyndon
24 | 2021 | Class A | 7 | Roselawn from Davison to Intervale | Roselawn | Davison | Intervale |  | Completed | 2021-08-04 | Speed hump to be installed | 0.38335 | Asp |  | PW-7019
25 | 2021 | Class A | 7 | Cloverlawn from Schoolcraft to Dead End (N) | Cloverlawn | Schoolcraft | Dead End (N) |  | Completed | 2021-06-04 |  | 0.31 | Asp |  | PW-7019
26 | 2021 | Class A | 7 | Northlawn from Schoolcraft to Davison | Northlawn | Schoolcraft | Davison |  | Completed | 2021-06-01 |  | 0.16 | Asp |  | PW-7019
27 | 2021 | Class A | 7 | Cherrylawn from Davison to Intervale | Cherrylawn | Davison | Intervale |  | Completed | 2021-06-09 |  | 0.39546 | Asp |  | PW-7019
28 | 2021 | Class A | 7 | Ohio from Intervale to Davison | Ohio | Intervale | Davison |  | Completed | 2021-06-02 | Speed hump to be installed | 0.36 | Asp |  | PW-7019
29 | 2021 | Class A | 7 | Intervale from Wyoming to Cloverlawn | Intervale | Wyoming | Cloverlawn |  | Completed | 2021-06-01 | Existing Speed Cushion | 0.52 | Asp |  | PW-7019
30 | 2021 | Class A | 7 | Washburn from Intervale to Kendall | Washburn | Intervale | Kendall |  | Completed | 2021-06-03 |  | 0.08 | Asp |  | PW-7019
31 | 2021 | Class A | 7 | Mendota from Kendall to Schoolcraft | Mendota | Kendall | Schoolcraft |  | Completed | 2021-06-03 |  | 0.12494 | Asp |  | PW-7019
32 | 2021 | Class A | 7 | Manor from Intervale to Jefferies Fwy | Manor | Intervale | Jefferies Fwy |  | Completed | 2021-06-03 |  | 0.3852 | Asp |  | PW-7019
33 | 2021 | Class A | 2 | Birwood from Fenkell to Lyndon | Birwood | Fenkell | Lyndon |  | Completed | 2021-06-08 | Speed hump to be installed | 0.50068 | Asp |  | PW-7019 | DTE Coordination Needed
34 | 2021 | Class A | 2 | Lesure From Keeler to Dead End (S) | Lesure | Keeler | Dead End (S) |  |  |  |  | 0.066288 | Asp |  | PW-7019
35 | 2021 | Class A | 1 | Freeland From Lyndon to Schoolcraft | Freeland | Lyndon | Schoolcraft |  | Completed | 2021-08-27 |  | 0.52 | Asp |  | PW-7033
36 | 2021 | Class A | 1 | Whitcomb from Schoolcraft to Fullerton | Whitcomb | Schoolcraft | Fullerton |  | Completed | 2021-08-03 |  | 0.26 | Conc |  | PW-7033
37 | 2021 | Class A | 1 | Chatham From Florence to Verne | Chatham | Florence | Verne |  |  |  |  | 0.13 | Conc |  | PW-7033
38 | 2021 | Class A | 1 | Redford from Lahser to Grand River | Redford | Lahser | Grand River |  |  |  |  | 0.08 | Asp |  | PW-7033 | DTE Coordination Needed and Coordination with the Lahser Streetscape Project
39 | 2021 | Class A | 1 | Greydale from Curtis to Pickford | Greydale | Curtis | Pickford |  |  |  |  | 0.15031 | Conc |  | PW-7033
40 | 2021 | Class A | 1 | Braile from Pembroke to Vassar | Braile | Pembroke | Vassar |  | Completed | 2021-06-11 | Existing Speed Cushion | 0.24913 | Conc |  | PW-7033
41 | 2021 | Class A | 1 | Fielding from Pembroke to 7 Mile | Fielding | Pembroke | 7 Mile |  | Completed | 2021-08-28 | Speed hump to be installed | 0.498 | Conc |  | PW-7033
42 | 2021 | Class A | 1 | Avon from 8 Mile to 7 Mile | Avon | 8 Mile | 7 Mile | 1 |  |  | Speed hump to be installed | 0.9251 | Conc |  | PW-7033
43 | 2021 | Class A | 2 | Fenmore from 8 Mile to Trojan | Fenmore | 8 Mile | Trojan |  | Completed | 2021-07-30 | Speed hump to be installed | 0.20607 | Conc |  | PW-7033
44 | 2021 | Class A | 2 | Archdale from 8 Mile to Pembroke | Archdale | 8 Mile | Pembroke |  | Completed | 2021-07-27 | Speed hump to be installed | 0.46831 | Conc |  | PW-7033
45 | 2021 | Class A | 2 | Oakfield from Pembroke to Eight Mile | Oakfield | Pembroke | Eight Mile |  | Completed | 2021-07-29 | Speed hump to be installed | 0.48056 | Conc |  | PW-7033
46 | 2021 | Class A | 2 | Oakfield from Pembroke to Seven Mile | Oakfield | Pembroke | Seven Mile |  | Completed | 2021-07-28 | Speed hump to be installed | 0.48 | Conc |  | PW-7033
47 | 2021 | Class A | 2 | Biltmore from 8 Mile to Pembroke | Biltmore | 8 Mile | Pembroke |  | Completed | 2021-07-30 | Speed hump to be installed | 0.48249 | Conc |  | PW-7033
48 | 2021 | Class A | 2 | Biltmore from Pembroke to Saint Martins | Biltmore | Pembroke | Saint Martins | 1 |  |  | Speed hump to be installed | 0.12376 | Conc |  | PW-7033
49 | 2021 | Class A | 2 | Winthrop from James Couzens Fwy to Saint Martins | Winthrop | James Couzens Fwy | Saint Martins |  | Completed | 2021-06-14 | Speed hump to be installed | 0.50739 | Asp |  | PW-7033
50 | 2021 | Class B | 2 | Gilchrist From Outer Drive to Curtis | Gilchrist | Outer Drive | Curtis |  |  |  |  | 0.24 | Asp |  | PW-7033 |  | Outer Drive to Curtis
51 | 2021 | Class A | 2 | Pinehurst From Santa Maria to Six Mile | Pinehurst | Santa Maria | Six Mile |  | Completed | 2021-07-30 | Speed hump to be installed | 0.12689 | Asp |  | PW-7033
52 | 2021 | Class A | 2 | Carmel From Woodward to Bauman | Carmel | Woodward | Bauman |  |  |  |  | 0.25 | Asp |  | PW-7033
53 | 2021 | Class A | 2 | Derby From Penrose to Dead End (N) | Derby | Penrose | Dead End (N) |  |  |  |  | 0.10038 | Asp |  | PW-7033
54 | 2021 | Class A/Class B | 3 | Andover From Eight Mile to Seven Mile | Andover | Eight Mile | Seven Mile |  |  |  |  | 1 | Asp |  | PW-7033 |  | Remington to Eight Mile
55 | 2021 | Class A | 3 | Yacama from Eight Mile to Seven Mile | Yacama | Eight Mile | Seven Mile |  |  |  |  | 1 | Asp |  | PW-7033
56 | 2021 | Class A | 3 | Omira From Eight Mile to Seven Mile | Omira | Eight Mile | Seven Mile | 2 |  |  | Speed hump to be installed | 1 | Asp |  | PW-7033
57 | 2021 | Class A | 3 | Cardoni From Emery to Seven Mile | Cardoni | Emery | Seven Mile |  |  |  |  | 0.18 | Asp |  | PW-7033
58 | 2021 | Class A | 3 | Keystone from E Outer Drive to Amrad | Keystone | E Outer Drive | Amrad | 2 |  |  | Speed hump to be installed | 0.25691 | Conc |  | PW-7033 | DTE Coordination Needed
59 | 2021 | Class A/Class B | 3 | Moenart from E Outer Drive to 8 Mile | Moenart | E Outer Drive | 8 Mile | 1 |  |  | Speed hump to be installed | 0.48398 | Conc/WPA |  | PW-7033 | DTE Coordination Needed | Chicago to Elmira
60 | 2021 | Class A | 3 | Bloom from E Outer Drive to 8 Mile | Bloom | E Outer Drive | 8 Mile |  |  |  |  | 0.48383 | Conc |  | PW-7033 | DTE Coordination Needed
61 | 2021 | Class A | 4 | Goulburn From Gratiot to McNichols | Goulburn | Gratiot | McNichols |  |  |  |  | 0.37 | Asp |  | PW-7033
62 | 2021 | Class A | 4 | Christy From Dresden to Bradford | Christy | Dresden | Bradford |  |  |  |  | 0.21023 | Asp |  | PW-7033
63 | 2021 | Class A | 4 | Mapleridge From Gratiot to Hayes | Mapleridge | Gratiot | Hayes |  |  |  |  | 0.83 | Asp |  | PW-7033
64 | 2021 | Class A | 4 | Payton From Morang to Dead End (W) | Payton | Morang | Dead End (W) |  |  |  |  | 0.10625 | Asp |  | PW-7033
65 | 2021 | Class A | 4 | Riad From Moross to Casino | Riad | Moross | Casino | 3 |  |  | Speed hump to be installed | 0.27917 | Asp |  | PW-7033
66 | 2021 | Class A | 4 | Nottingham From Morang to Grayton | Nottingham | Morang | Grayton |  | Completed | 2021-07-15 | Speed hump to be installed | 0.34432 | Asp |  | PW-7033
67 | 2021 | Class A | 4 | Bedford From McKinney to King Richard | Bedford | McKinney | King Richard |  |  |  |  | 0.13258 | Asp |  | PW-7033
68 | 2021 | Class A | 4 | Evanston From Berkshire to Devonshire | Evanston | Berkshire | Devonshire |  |  |  |  | 0.21212 | Asp |  | PW-7033
69 | 2021 | Class A | 4 | Rosemary From Dickerson to Chalmers | Rosemary | Dickerson | Chalmers |  | Completed | 2021-08-06 | Speed hump to be installed | 0.67 | Asp |  | PW-7033
70 | 2021 | Class A | 4 | Rosemary From Gratiot to Dickerson | Rosemary | Gratiot | Dickerson |  | Completed | 2021-08-06 | Speed hump to be installed | 0.67 | Asp |  | PW-7033
71 | 2021 | Class A | 3 | Longview From Conner to Chalmers | Longview | Conner | Chalmers |  | Completed | 2021-08-19 | Speed hump to be installed | 0.95701 | Asp |  | PW-7033
72 | 2021 | Class A | 3 | Wade from Connor to Ansbury | Wade | Connor | Ansbury |  | Completed | 2021-08-11 | Speed hump to be installed | 0.55 | Asp |  | PW-7033
73 | 2021 | Class A | 4 | Edsel Ford From Gunston to Norcross | Edsel Ford | Gunston | Norcross |  |  |  |  | 0.29 | Asp |  | PW-7033
74 | 2021 | Class A | 4 | Frankfort from Alter Rd to Dickerson | Frankfort | Alter Rd | Dickerson | 2 |  |  | Speed hump to be installed | 0.67 | Asp |  | PW-7033
75 | 2021 | Class A | 4 | Gray From Kercheval to Vernor | Gray | Kercheval | Vernor |  |  |  |  | 0.14489 | Asp |  | PW-7033
76 | 2021 | Class A | 4 | St. Clair from Shoemaker to Mack | St. Clair | Shoemaker | Mack | 9 |  |  | Existing Speed Cushion | 1.0038 | Asp |  | PW-7033
77 | 2021 | Class A | 4 | Garland From Canfield to Warren | Garland | Canfield | Warren |  |  |  |  | 0.3125 | Asp |  | PW-7033
78 | 2021 | Class A | 5 | Rohns From Goethe to Gratiot | Rohns | Goethe | Mack | 2 |  |  | Speed hump to be installed | 2 | Asp |  | PW-7033 | DTE Coordination Needed
79 | 2021 | Class A | 5 | David from Rohns to Crane | David | Rohns | Crane |  | Completed | 2021-08-26 |  | 0.1 | Asp |  | PW-7033
80 | 2021 | Class A | 5 | Burns From Forest to Mack | Burns | Forest | Mack |  | Completed | 2021-08-24 | Existing Speed Cushion | 0.55 | Asp |  | PW-7033
81 | 2021 | Class A | 5 | Seneca from Gratiot to Warren | Seneca | Gratiot | Warren |  | Completed | 2021-08-25 | Speed hump to be installed | 0.43 | Asp |  | PW-7033
82 | 2021 | Class A | 5 | Chapin from Seneca to Burns | Chapin | Seneca | Burns |  | Completed | 2021-08-25 |  | 0.1 | Asp |  | PW-7033
83 | 2021 | Class A | 5 | Fischer from Edsel Ford to Lambert | Fischer | Edsel Ford | Lambert |  |  |  |  | 0.08 | Asp |  | PW-7033
84 | 2021 | Class A | 5 | Parker from Gratiot to Hendrie | Parker | Gratiot | Hendrie |  |  |  |  | 0.24 | Asp |  | PW-7033
85 | 2021 | Class A | 5 | Maxwell from Forest to Canfield | Maxwell | Forest | Canfield |  | Completed | 2021-08-25 | Speed hump to be installed | 0.15 | Asp |  | PW-7033
86 | 2021 | Class A | 5 | Seminole from Sylvester to Canfield | Seminole | Sylvester | Canfield |  | Completed | 2021-08-26 | Existing Speed Cushion | 0.17 | Asp |  | PW-7033
87 | 2021 | Class A | 5 | Townsend from Canfield to Pulford | Townsend | Canfield | Pulford |  |  |  |  | 0.25 | Asp |  | PW-7033
88 | 2021 | Class A | 5 | Helen from Mack to Gratiot | Helen | Mack | Gratiot | 6 |  |  | Speed hump to be installed | 0.59 | Asp |  | PW-7033
89 | 2021 | Class A | 5 | Canton from Mack to Garfield | Canton | Mack | Garfield |  |  |  |  | 0.46 | Asp |  | PW-7033
90 | 2021 | Class A | 5 | Harding from Jefferson to Edlie | Harding | Jefferson | Edlie | 2 |  |  | Existing Speed Cushion | 0.17 | Conc |  | PW-7033
91 | 2021 | Class A | 5 | Belvidere from Jefferson to Kercheval | Belvidere | Jefferson | Kercheval |  |  |  |  | 0.34 | Asp |  | PW-7033
92 | 2021 | Class A | 5 | Crane from Jefferson to Vernor | Crane | Jefferson | Vernor |  |  |  |  | 0.4 | Asp |  | PW-7033
93 | 2021 | Class A | 6 | Temple from Cass to Woodward | Temple | Cass | Woodward |  |  |  |  | 0.20315 | Asp |  | PW-7033
94 | 2021 | Class A | 6 | Brainard from 3rd to Dead End (W) | Brainard | 3rd | Dead End (W) |  |  |  |  | 0.05 | Asp |  | PW-7033
95 | 2021 | Class A | 6 | Ash from 14th to Wabash | Ash | 14th | Wabash |  |  |  |  | 0.06 | Asp |  | PW-7033
96 | 2021 | Class A | 6 | Hazel from Wabash to Vermont | Hazel | Wabash | Vermont |  |  |  |  | 0.07 | Asp |  | PW-7033
97 | 2021 | Class A | 6 | Selden from Vermont to 14th | Selden | Vermont | 14th |  |  |  |  | 0.14 | Asp |  | PW-7033
98 | 2021 | Class A | 5 | 15th from Warren to Edsel Ford Fwy | 15th | Warren | Edsel Ford Fwy |  |  |  |  | 0.25 | Asp |  | PW-7033
99 | 2021 | Class A | 5 | Stanton from Grand River to Edsel Ford Fwy | Stanton | Grand River | Edsel Ford Fwy |  |  |  |  | 0.18 | Asp |  | PW-7033
100 | 2021 | Class A | 5 | Lorraine from Grand River to Edsel Ford Fwy | Lorraine | Grand River | Edsel Ford Fwy |  |  |  |  | 0.02 | Asp |  | PW-7033
101 | 2021 | Class A | 5 | Northwestern from Grand River to Dexter | Northwestern | Grand River | Dexter | 1 |  |  | Speed hump to be installed | 0.1361 | Asp |  | PW-7033
102 | 2021 | Class A | 5 | Hanover from LaSalle Garden to W Grand Blvd | Hanover | LaSalle Garden | W Grand Blvd |  |  |  |  | 0.2831 | Asp |  | PW-7033
103 | 2021 | Class A | 5 | Poe from W Grand Blvd to Seward | Poe | W Grand Blvd | Seward |  |  |  |  | 0.50927 | Asp |  | PW-7033
104 | 2021 | Class A | 5 | Seward from John C Lodge Fwy to Poe | Seward | John C Lodge Fwy | Poe | 2 |  |  | Speed hump to be installed | 0.26683 | Asp |  | PW-7033
105 | 2021 | Class A | 5 | Seward from 3rd to John C Lodge Fwy | Seward | 3rd | John C Lodge Fwy | 1 |  |  | Speed hump to be installed | 0.14958 | Asp |  | PW-7033 | DWSD Coordination Required
106 | 2021 | Class A | 5 | Glynn from McQuade to Dexter | Glynn | McQuade | Dexter |  |  |  |  | 0.09 | Asp |  | PW-7033 | DTE Coordination Needed
107 | 2021 | Class A | 2 | Buena Vista from Lawton to Linwood | Buena Vista | Lawton | Linwood |  |  |  |  | 0.15 | Asp |  | PW-7033
108 | 2021 | Class A | 5 | Waverly from 12th to Woodrow Wilson | Waverly | 12th | Woodrow Wilson | 1 |  |  | Existing Speed Cushion | 0.16 | Asp |  | PW-7033
109 | 2021 | Class A | 6 | 8th from Lafayette to Fort | 8th | Lafayette | Fort |  |  |  |  | 0.06 | Brick |  | PW-7033
110 | 2021 | Class A | 4 | Riverside from Korte to Dead End (S). | Riverside | Korte | Dead End (S). | 2 |  |  | Speed hump to be installed | 0.22 | Asp |  | PW-7033 | DWSD Coordination Required
111 | 2021 | Class B | 4 | Guilford From Harper to Southampton | Guilford | Harper | Southampton | 2 |  |  | Speed hump to be installed | 0.56818 | Asp |  | PW-7033 | DWSD Coordination Required | Harper to Southampton
112 | 2021 | Class B | 4 | Bishop From Waveney to Mack | Bishop | Waveney | Mack | 6 |  |  | Speed hump to be installed | 0.5 | Asp |  | PW-7033 | DTE Coordination Needed | Waveney to Mack
113 | 2021 | Class A | 4 | Yorkshire from Mack to Warren | Yorkshire | Mack | Warren | 7 |  |  | Speed hump to be installed | 0.88 | Asp |  | PW-7033 | DTE Coordination Needed
114 | 2021 | Class A | 4 | Audubon From Warren to Wallingford St | Audubon | Warren | Wallingford St | 6 |  |  | Speed hump to be installed | 0.55 | Asp |  | PW-7033 | DTE Coordination Needed
115 | 2021 | Class A | 4 | Bedford From Warren to Munich | Bedford | Warren | Munich | 2 |  |  | Speed hump to be installed | 0.25 | Asp |  | PW-7033 | DTE Coordination Needed
116 | 2021 | Class A | 4 | Devonshire from Warren to Cornwall | Devonshire | Warren | Cornwall | 1 |  |  | Speed hump to be installed | 0.13 | Asp |  | PW-7033 | DTE Coordination Needed
117 | 2021 | Class A | 4 | Berkshire from Warren to Cornwall | Berkshire | Warren | Cornwall |  |  |  |  | 0.13 | Asp |  | PW-7033 | DTE Coordination Needed
118 | 2021 | Class A | 4 | Buckingham From Mack to Waveney | Buckingham | Mack | Waveney | 1 |  |  | Existing Speed Cushion | 0.5 | Asp |  | PW-7033 | DTE Coordination Needed
119 | 2021 | Class A | 4 | Somerset from Mack to Breman | Somerset | Mack | Breman | 3 |  |  | Speed hump to be installed | 0.35 | Asp |  | PW-7033 | DTE Coordination Needed
120 | 2021 | Class A | 4 | Lozier from Alter Rd to Barham | Lozier | Alter Rd | Barham |  |  |  |  | 0.18 | Asp |  | PW-7033 | DTE Coordination Needed
121 | 2021 | Class A | 4 | Wayburn from Waveney to Warren | Wayburn | Waveney | Warren | 4 |  |  | Speed hump to be installed | 0.7 | Asp |  | PW-7033 | DTE Coordination Needed
122 | 2021 | Class A | 3 | College From Conner to Gunston | College | Conner | Gunston | 1 |  |  | Speed hump to be installed | 0.42652 | Asp |  | PW-7033 | DTE Coordination Needed
| 2021 | Class C | 6 | Gilroy from Deacon to Beatrice | Gilroy | Deacon | Beatrice |  |  |  |  | 0.05 |  | 2019/2020 Carryover | PW-7020
| 2021 | Class C | 6 | Panama from Springwells to Cecil | Panama | Springwells | Cecil |  |  |  |  | 0.27 |  | 2019/2020 Carryover | PW-7020
| 2021 | Class C | 1 | Curtis from Berg to Redfern | Curtis | Berg | Redfern |  |  |  |  | 0.13 |  | 2020 Carryover | PW-7020
| 2021 | Class C | 4 | Abington from Joy to Dead End | Abington | Joy | Dead End |  |  |  |  | 0.02 |  |  | PW-7020
| 2021 | Class C | 3 | Barrett from Harper to Maiden | Barrett | Harper | Maiden | 2 |  |  | Existing Speed Cushion | 0.2 |  |  | PW-7020
| 2021 | Class C | 5 | Bremen from Buckingham to Chatsworth | Bremen | Buckingham | Chatsworth | 1 |  |  | Speed hump to be installed | 0.13 |  |  | PW-7020 | DTE Coordination Needed
| 2021 | Class C | 1 | Brinkett from Crane to Holcomb | Brinkett | Crane | Holcomb |  |  |  |  | 0.1 |  |  | PW-7020
| 2021 | Class C | 1 | Cambridge from Fielding to Burt | Cambridge | Fielding | Burt |  |  |  |  | 0.12 |  |  | PW-7020
| 2021 | Class C | 5 | Cambridge from Shaftsbury to Grandville | Cambridge | Shaftsbury | Grandville |  |  |  |  | 0.06 |  |  | PW-7020
| 2021 | Class C | 6 | Fargo from Southfield to Stahelin | Fargo | Southfield | Stahelin |  |  |  |  | 0.34 |  |  | PW-7020
| 2021 | Class C | 1 | Heyden from Vassar to Pembroke | Heyden | Vassar | Pembroke |  |  |  |  | 0.24 |  |  | PW-7020
| 2021 | Class C | 7 | Longacre From Chicago to Dead End | Longacre | Chicago | Dead End |  |  |  |  | 0.05 |  |  | PW-7020
| 2021 | Class C | 2 | Milbank from Sherwood to Concord | Milbank | Sherwood | Concord |  |  |  |  | 0.05 |  |  | PW-7020
| 2021 | Class C | 6 | Monica from Fenkell to Chalfonte | Monica | Fenkell | Chalfonte |  |  |  |  | 0.12 |  |  | PW-7020
| 2021 | Class C | 6 | Omaha from Electric to Bassett | Omaha | Electric | Bassett |  |  |  |  | 0.32 |  |  | PW-7020
| 2021 | Class C | 4 | Pilgrim from Meyers to Appoline | Pilgrim | Meyers | Appoline |  |  |  |  | 0.04 |  |  | PW-7020
| 2021 | Class C | 2 | Rosewood from Cadieux to Grayton | Rosewood | Cadieux | Grayton | 1 |  |  | Speed hump to be installed | 0.11 |  |  | PW-7020 | DTE Coordination Needed
| 2021 | Class C | 1 | Santa Maria from Schaefer to Snowden | Santa Maria | Schaefer | Snowden | 1 |  |  | Speed hump to be installed | 0.1 |  |  | PW-7020
| 2021 | Class C | 1 | St. Martins from Greenview to Sunderland | St. Martins | Greenview | Sunderland | 1 |  |  | Speed hump to be installed | 0.02 |  |  | PW-7020
| 2021 | Class C | 1 | St. Martins from Pierson to Evergreen | St. Martins | Pierson | Evergreen |  |  |  |  | 0.37 |  |  | PW-7020
| 2021 | Class C | 1 | Trinity from Puritan to Fenkell | Trinity | Puritan | Fenkell |  |  |  |  | 0.5 |  |  | PW-7020
| 2021 | Class C | 2 | Trojan from Rosemont to Southfield | Trojan | Rosemont | Southfield |  |  |  |  | 0.1 |  |  | PW-7020
| 2021 | Class C | 1 | Tuller from Fenkell to Chalfonte | Tuller | Fenkell | Chalfonte |  |  |  |  | 0.13 |  |  | PW-7020
| 2021 | Class C | 1 | Vassar from Pierson to Westmoreland | Vassar | Pierson | Westmoreland |  |  |  |  | 0.48 |  |  | PW-7020
| 2021 | Class C | 1 | Vaughan from Pembroke to Vassar | Vaughan | Pembroke | Vassar | 1 |  |  | Speed hump to be installed | 0.25 |  |  | PW-7020
| 2021 | Class C | 4 | Verne from Huntington to Evergreen | Verne | Huntington | Evergreen | 2 |  |  | Speed hump to be installed | 0.2 |  |  | PW-7020
| 2021 | Class C | 4 | Voight from Barham to Alter Rd | Voight | Barham | Alter Rd |  |  |  |  | 0.19 |  |  | PW-7020 | DTE Coordination Needed
| 2021 | Class C | 1 | Waveney from Alter Rd to Somerset | Waveney | Alter Rd | Somerset |  |  |  |  | 0.34 |  |  | PW-7020 | DTE Coordination Needed
| 2023 | Class A | 5 | Beverly Ct from Grand River to Joy | Beverly Ct | Grand River | Joy |  |  |  |  | 0.16 |  | 2020 Carryover |  | DTE Coordination Needed (2023)
| 2022 | Class B | 6 | Clark Ct from Scotten to Fairbanks | Clark Ct | Scotten | Fairbanks |  |  |  |  | 0.07 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 6 | Federal from Military to Livernois | Federal | Military | Livernois |  |  |  |  | 0.05 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 7 | Leslie from Dexter to Livernois | Leslie | Dexter | Livernois | 3 |  |  | Speed hump to be installed | 0.59 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 7 | Mansfield from Tireman to Dead End (N) | Mansfield | Tireman | Dead End (N) |  |  |  |  | 0.17 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 7 | Mettetal from Tireman to Dead End (N) | Mettetal | Tireman | Dead End (N) |  |  |  |  | 0.36 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 6 | Military from Plumer to Federal | Military | Plumer | Federal | 1 |  |  | Speed hump to be installed | 0.12 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 6 | Military from Toledo to Cadet | Military | Toledo | Cadet | 1 |  |  | Speed hump to be installed | 0.3 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 6 | Porter from Clark to Lansing | Porter | Clark | Lansing |  |  |  |  | 0.13 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2021 | Class C | 1 | Beaverland from Grand River to Curtis | Beaverland | Grand River | Curtis |  |  |  |  | 0.14 |  |  | PW-7012
| 2021 | Class C | 1 | Burgess from Karl to Pickford | Burgess | Karl | Pickford |  |  |  |  | 0.07 |  |  | PW-7012
| 2021 | Class C | 1 | Burgess from Margareta to Clarita | Burgess | Margareta | Clarita |  |  |  |  | 0.08 |  |  | PW-7012
| 2021 | Class C | 1 | Burgess from Santa Clara to Glenco | Burgess | Santa Clara | Glenco |  |  |  |  | 0.17 |  |  | PW-7012
| 2021 | Class C | 1 | Margareta from Lahser to Northrop | Margareta | Lahser | Northrop |  |  |  |  | 0.16 |  |  | PW-7012
| 2021 | Class C | 1 | Santa Clara from Lahser to Bentler | Santa Clara | Lahser | Bentler |  |  |  |  | 0.24 |  |  | PW-7012
| 2021 | Class C | 1 | Willmarth from Lahser to Curtis | Willmarth | Lahser | Curtis |  |  |  |  | 0.4 |  |  | PW-7012
|  | Class A | 5 |  | Benson | McDougall | Ellery
|  | Class A | 3 |  | Eureka | Outer Drive | Lantz
|  | Class A | 5 |  | Superior | Joseph Campau | Mitchell
|  | Class B |  |  | E Winchester | Hanna/Hull | Greeley
|  | Class C |  |  | Lantz | Coventry | Keating
|  | Class C |  |  | Healy | Hildale | Stockton
|  | Class C |  |  | Lantz | Fenelon | Conley
[5 empty] | Park Grove St | Dresden St | Waltham