## Final 2021 Residential Resurfac
Pave Order | Target_Year | Road Class | District Number | Project (1) | Street | From | To | Resurfacing Status | Resurfacing Completion Date | Speed Hump Status | Length | Material | Project Notes | Project Number | Utility Status | Class B Section
42 | 2021 | Class A | 1 | Avon from 8 Mile to 7 Mile | Avon | 8 Mile | 7 Mile |  |  | Speed hump to be installed | 0.9251 | Conc |  | PW-7033
48 | 2021 | Class A | 2 | Biltmore from Pembroke to Saint Martins | Biltmore | Pembroke | Saint Martins |  |  | Speed hump to be installed | 0.12376 | Conc |  | PW-7033
56 | 2021 | Class A | 3 | Omira From Eight Mile to Seven Mile | Omira | Eight Mile | Seven Mile |  |  | Speed hump to be installed | 1 | Asp |  | PW-7033
58 | 2021 | Class A | 3 | Keystone from E Outer Drive to Amrad | Keystone | E Outer Drive | Amrad |  |  | Speed hump to be installed | 0.25691 | Conc |  | PW-7033 | DTE Coordination Needed
59 | 2021 | Class A/Class B | 3 | Moenart from E Outer Drive to 8 Mile | Moenart | E Outer Drive | 8 Mile |  |  | Speed hump to be installed | 0.48398 | Conc/WPA |  | PW-7033 | DTE Coordination Needed | Chicago to Elmira
65 | 2021 | Class A | 4 | Riad From Moross to Casino | Riad | Moross | Casino |  |  | Speed hump to be installed | 0.27917 | Asp |  | PW-7033
74 | 2021 | Class A | 4 | Frankfort from Alter Rd to Dickerson | Frankfort | Alter Rd | Dickerson |  |  | Speed hump to be installed | 0.67 | Asp |  | PW-7033
76 | 2021 | Class A | 4 | St. Clair from Shoemaker to Mack | St. Clair | Shoemaker | Mack |  |  | Existing Speed Cushion | 1.0038 | Asp |  | PW-7033
78 | 2021 | Class A | 5 | Rohns From Goethe to Gratiot | Rohns | Goethe | Mack |  |  | Speed hump to be installed | 2 | Asp |  | PW-7033 | DTE Coordination Needed
88 | 2021 | Class A | 5 | Helen from Mack to Gratiot | Helen | Mack | Gratiot |  |  | Speed hump to be installed | 0.59 | Asp |  | PW-7033
90 | 2021 | Class A | 5 | Harding from Jefferson to Edlie | Harding | Jefferson | Edlie |  |  | Existing Speed Cushion | 0.17 | Conc |  | PW-7033
101 | 2021 | Class A | 5 | Northwestern from Grand River to Dexter | Northwestern | Grand River | Dexter |  |  | Speed hump to be installed | 0.1361 | Asp |  | PW-7033
104 | 2021 | Class A | 5 | Seward from John C Lodge Fwy to Poe | Seward | John C Lodge Fwy | Poe |  |  | Speed hump to be installed | 0.26683 | Asp |  | PW-7033
105 | 2021 | Class A | 5 | Seward from 3rd to John C Lodge Fwy | Seward | 3rd | John C Lodge Fwy |  |  | Speed hump to be installed | 0.14958 | Asp |  | PW-7033 | DWSD Coordination Required
108 | 2021 | Class A | 5 | Waverly from 12th to Woodrow Wilson | Waverly | 12th | Woodrow Wilson |  |  | Existing Speed Cushion | 0.16 | Asp |  | PW-7033
110 | 2021 | Class A | 4 | Riverside from Korte to Dead End (S). | Riverside | Korte | Dead End (S). |  |  | Speed hump to be installed | 0.22 | Asp |  | PW-7033 | DWSD Coordination Required
111 | 2021 | Class B | 4 | Guilford From Harper to Southampton | Guilford | Harper | Southampton |  |  | Speed hump to be installed | 0.56818 | Asp |  | PW-7033 | DWSD Coordination Required | Harper to Southampton
112 | 2021 | Class B | 4 | Bishop From Waveney to Mack | Bishop | Waveney | Mack |  |  | Speed hump to be installed | 0.5 | Asp |  | PW-7033 | DTE Coordination Needed | Waveney to Mack
113 | 2021 | Class A | 4 | Yorkshire from Mack to Warren | Yorkshire | Mack | Warren |  |  | Speed hump to be installed | 0.88 | Asp |  | PW-7033 | DTE Coordination Needed
114 | 2021 | Class A | 4 | Audubon From Warren to Wallingford St | Audubon | Warren | Wallingford St |  |  | Speed hump to be installed | 0.55 | Asp |  | PW-7033 | DTE Coordination Needed
115 | 2021 | Class A | 4 | Bedford From Warren to Munich | Bedford | Warren | Munich |  |  | Speed hump to be installed | 0.25 | Asp |  | PW-7033 | DTE Coordination Needed
116 | 2021 | Class A | 4 | Devonshire from Warren to Cornwall | Devonshire | Warren | Cornwall |  |  | Speed hump to be installed | 0.13 | Asp |  | PW-7033 | DTE Coordination Needed
118 | 2021 | Class A | 4 | Buckingham From Mack to Waveney | Buckingham | Mack | Waveney |  |  | Existing Speed Cushion | 0.5 | Asp |  | PW-7033 | DTE Coordination Needed
119 | 2021 | Class A | 4 | Somerset from Mack to Breman | Somerset | Mack | Breman |  |  | Speed hump to be installed | 0.35 | Asp |  | PW-7033 | DTE Coordination Needed
121 | 2021 | Class A | 4 | Wayburn from Waveney to Warren | Wayburn | Waveney | Warren |  |  | Speed hump to be installed | 0.7 | Asp |  | PW-7033 | DTE Coordination Needed
122 | 2021 | Class A | 3 | College From Conner to Gunston | College | Conner | Gunston |  |  | Speed hump to be installed | 0.42652 | Asp |  | PW-7033 | DTE Coordination Needed
| 2021 | Class C | 3 | Barrett from Harper to Maiden | Barrett | Harper | Maiden |  |  | Existing Speed Cushion | 0.2 |  |  | PW-7020
| 2021 | Class C | 5 | Bremen from Buckingham to Chatsworth | Bremen | Buckingham | Chatsworth |  |  | Speed hump to be installed | 0.13 |  |  | PW-7020 | DTE Coordination Needed
| 2021 | Class C | 2 | Rosewood from Cadieux to Grayton | Rosewood | Cadieux | Grayton |  |  | Speed hump to be installed | 0.11 |  |  | PW-7020 | DTE Coordination Needed
| 2021 | Class C | 1 | Santa Maria from Schaefer to Snowden | Santa Maria | Schaefer | Snowden |  |  | Speed hump to be installed | 0.1 |  |  | PW-7020
| 2021 | Class C | 1 | St. Martins from Greenview to Sunderland | St. Martins | Greenview | Sunderland |  |  | Speed hump to be installed | 0.02 |  |  | PW-7020
| 2021 | Class C | 1 | Vaughan from Pembroke to Vassar | Vaughan | Pembroke | Vassar |  |  | Speed hump to be installed | 0.25 |  |  | PW-7020
| 2021 | Class C | 4 | Verne from Huntington to Evergreen | Verne | Huntington | Evergreen |  |  | Speed hump to be installed | 0.2 |  |  | PW-7020
| 2022 | Class A | 7 | Leslie from Dexter to Livernois | Leslie | Dexter | Livernois |  |  | Speed hump to be installed | 0.59 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 6 | Military from Plumer to Federal | Military | Plumer | Federal |  |  | Speed hump to be installed | 0.12 |  | 2020 Carryover |  | DTE Coordination Needed (2022)
| 2022 | Class A | 6 | Military from Toledo to Cadet | Military | Toledo | Cadet |  |  | Speed hump to be installed | 0.3 |  | 2020 Carryover |  | DTE Coordination Needed (2022)