## 2021 Class A
Target Year | Road Type | Project | Street | From | To | District Number | Length | Project Notes | Utility Status
2021 | Class A | 15th from Warren to Edsel Ford Fwy | 15th | Warren | Edsel Ford Fwy | 5 | 0.25 | 2020 Carryover
2021 | Class A | 8th from Lafayette to Fort | 8th | Lafayette | Fort | 6 | 0.06 | 2020 Carryover
2021 | Class A | Asbury Park from Joy to Ellis | Asbury Park | Joy | Ellis | 7 | 0.16 | 2020 Carryover
2021 | Class A | Ash from 14th to Wabash | Ash | 14th | Wabash | 6 | 0.06 | 2020 Carryover
2021 | Class A | Beechton from Livernois to Warren | Beechton | Livernois | Warren | 6 | 0.13 | 2020 Carryover
2021 | Class A | Belvidere from Jefferson to Kercheval | Belvidere | Jefferson | Kercheval | 5 | 0.34 | 2020 Carryover
2021 | Class A | Brainard from 3rd to Dead End (W) | Brainard | 3rd | Dead End (W) | 6 | 0.05 | 2020 Carryover
2021 | Class A | Buena Vista from Lawton to Linwood | Buena Vista | Lawton | Linwood | 2 | 0.15 | 2020 Carryover
2021 | Class A | Clippert from Clayton to Michigan Ave | Clippert | Clayton | Michigan Ave | 6 | 0.28 | 2020 Carryover
2021 | Class A | Cloverlawn from Schoolcraft to Dead End (N) | Cloverlawn | Schoolcraft | Dead End (N) | 7 | 0.31 | 2020 Carryover
2021 | Class A | Crane from Jefferson to Vernor | Crane | Jefferson | Vernor | 5 | 0.4 | 2020 Carryover
2021 | Class A | Edsel Ford from Larkins to Braden | Edsel Ford | Larkins | Braden | 6 | 0.06 | 2020 Carryover
2021 | Class A | Hazel from Wabash to Vermont | Hazel | Wabash | Vermont | 6 | 0.07 | 2020 Carryover
2021 | Class A | Horatio from Martin to Cecil | Horatio | Martin | Cecil | 6 | 0.19 | 2020 Carryover
2021 | Class A | Intervale from Wyoming to Cloverlawn | Intervale | Wyoming | Cloverlawn | 7 | 0.52 | 2020 Carryover
2021 | Class A | Lauder from Westfield to Chicago | Lauder | Westfield | Chicago | 7 | 0.12 | 2020 Carryover
2021 | Class A | Lorraine from Grand River to Edsel Ford Fwy | Lorraine | Grand River | Edsel Ford Fwy | 6 | 0.02 | 2020 Carryover
2021 | Class A | Memorial from Chicago to Dead End (S) | Memorial | Chicago | Dead End (S) | 7 | 0.26 | 2020 Carryover
2021 | Class A | Mettetal from Cathedral to Ellis | Mettetal | Cathedral | Ellis | 7 | 0.08 | 2020 Carryover
2021 | Class A | Northlawn from Schoolcraft to Davison | Northlawn | Schoolcraft | Davison | 7 | 0.16 | 2020 Carryover
2021 | Class A | Ohio from Intervale to Davison | Ohio | Intervale | Davison | 7 | 0.36 | 2020 Carryover
2021 | Class B | Patricia from Pleasant to Gilroy | Patricia | Pleasant | Gilroy | 6 | 0.28 | 2020 Carryover
2021 | Class A | Redford from Lahser to Grand River | Redford | Lahser | Grand River | 1 | 0.08 | 2020 Carryover | DTE Coordination Needed
2021 | Class A | Rutland from Chicago to Dead End (S) | Rutland | Chicago | Dead End (S) | 7 | 0.14 | 2020 Carryover
2021 | Class A | Saint Marys from Joy to Cathedral | Saint Marys | Joy | Cathedral | 7 | 0.24 | 2020 Carryover
2021 | Class A | Selden from Vermont to 14th | Selden | Vermont | 14th | 6 | 0.14 | 2020 Carryover
2021 | Class A | Stanton from Grand River to Edsel Ford Fwy | Stanton | Grand River | Edsel Ford Fwy | 6 | 0.18 | 2020 Carryover
2021 | Class A | Sussex from Chicago to Joy | Sussex | Chicago | Joy | 7 | 0.32 | 2020 Carryover
2021 | Class A | Torrey from 28th to Scotten | Torrey | 28th | Scotten | 6 | 0.14 | 2020 Carryover
2021 | Class A | Washburn from Intervale to Kendall | Washburn | Intervale | Kendall | 7 | 0.08 | 2020 Carryover
2021 | Class A | Whitcomb from Schoolcraft to Fullerton | Whitcomb | Schoolcraft | Fullerton | 1 | 0.26 | 2020 Carryover
2021 | Class A | Winthrop from Ellis to Westfield | Winthrop | Ellis | Westfield | 7 | 0.19 | 2020 Carryover
2021 | Class A | 25th from Warren to Hancock | 25th | Warren | Hancock | 6 | 0.10417
2021 | Class A Class B | Andover From Eight Mile to Seven Mile | Andover | Eight Mile | Seven Mile | 3 | 1
2021 | Class A | Archdale from 8 Mile to Pembroke | Archdale | 8 Mile | Pembroke | 2 | 0.46831
2021 | Class A | Audubon From Warren to Wallingford St | Audubon | Warren | Wallingford St | 4 | 0.55 |  | DTE Coordination Needed
2021 | Class A | Avon from 8 Mile to 7 Mile | Avon | 8 Mile | 7 Mile | 1 | 0.9251
2021 | Class A | Bedford From McKinney to King Richard | Bedford | McKinney | King Richard | 4 | 0.13258
2021 | Class A | Bedford From Warren to Munich | Bedford | Warren | Munich | 4 | 0.25 |  | DTE Coordination Needed
2021 | Class A | Berkshire from Warren to Cornwall | Berkshire | Warren | Cornwall | 4 | 0.13 |  | DTE Coordination Needed
2021 | Class A | Biltmore from 8 Mile to Pembroke | Biltmore | 8 Mile | Pembroke | 2 | 0.48249
2021 | Class A | Biltmore from Pembroke to Saint Martins | Biltmore | Pembroke | Saint Martins | 2 | 0.12376
2021 | Class A | Birwood from Fenkell to Lyndon | Birwood | Fenkell | Lyndon | 2 | 0.50068
2021 | Class B | Bishop From Waveney to Mack | Bishop | Waveney | Mack | 4 | 0.5 |  | DTE Coordination Needed
2021 | Class A | Bloom from E Outer Drive to 8 Mile | Bloom | E Outer Drive | 8 Mile | 3 | 0.48383 |  | DTE Coordination Needed
2021 | Class A | Braile from Pembroke to Vassar | Braile | Pembroke | Vassar | 1 | 0.24913
2021 | Class A | Buckingham From Mack to Waveney | Buckingham | Mack | Waveney | 4 | 0.5 |  | DTE Coordination Needed
2021 | Class A | Burns From Forest to Mack | Burns | Forest | Mack | 5 | 0.55
2021 | Class A | Canton from Mack to Garfield | Canton | Mack | Garfield | 5 | 0.46
2021 | Class A | Cardoni From Emery to Seven Mile | Cardoni | Emery | Seven Mile | 3 | 0.18
2021 | Class A | Carmel From Woodward to Bauman | Carmel | Woodward | Bauman | 2 | 0.25
2021 | Class A | Chapin from Seneca to Burns | Chapin | Seneca | Burns | 5 | 0.1
2021 | Class A | Chatham From Florence to Verne | Chatham | Florence | Verne | 1 | 0.13
2021 | Class A | Cherrylawn from Davison to Intervale | Cherrylawn | Davison | Intervale | 7 | 0.39546
2021 | Class A | Christy From Dresden to Bradford | Christy | Dresden | Bradford | 4 | 0.21023
2021 | Class A | College From Conner to Gunston | College | Conner | Gunston | 3 | 0.42652 |  | DTE Coordination Needed
2021 | Class A | David from Rohns to Crane | David | Rohns | Crane | 1 | 0.1
2021 | Class A | Derby From Penrose to Dead End (N) | Derby | Penrose | Dead End (N) | 2 | 0.10038
2021 | Class A | Devonshire from Warren to Cornwall | Devonshire | Warren | Cornwall | 4 | 0.13 |  | DTE Coordination Needed
2021 | Class A | Edsel Ford From Gunston to Norcross | Edsel Ford | Gunston | Norcross | 4 | 0.29
2021 | Class A | Evanston From Berkshire to Devonshire | Evanston | Berkshire | Devonshire | 4 | 0.21212
2021 | Class A | Fenmore from 8 Mile to Trojan | Fenmore | 8 Mile | Trojan | 2 | 0.20607
2021 | Class A | Fielding from Pembroke to 7 Mile | Fielding | Pembroke | 7 Mile | 1 | 0.498
2021 | Class A | Fischer from Edsel Ford to Lambert | Fischer | Edsel Ford | Lambert | 5 | 0.08
2021 | Class A | Frankfort from Alter Rd to Dickerson | Frankfort | Alter Rd | Dickerson | 4 | 0.67
2021 | Class A | Freeland From Lyndon to Schoolcraft | Freeland | Lyndon | Schoolcraft | 1 | 0.52
2021 | Class A | Garland From Canfield to Warren | Garland | Canfield | Warren | 4 | 0.3125
2021 | Class A | Gilbert from Wagner to McGraw | Gilbert | Wagner | McGraw | 6 | 0.1
2021 | Class B | Gilchrist From Outer Drive to Curtis | Gilchrist | Outer Drive | Curtis | 2 | 0.24
2021 | Class A | Glynn from McQuade to Dexter | Glynn | McQuade | Dexter | 5 | 0.09 |  | DTE Coordination Needed
2021 | Class A | Goulburn From Gratiot to McNichols | Goulburn | Gratiot | McNichols | 4 | 0.37
2021 | Class A | Gray From Kercheval to Vernor | Gray | Kercheval | Vernor | 4 | 0.14489
2021 | Class A | Greenlawn from John C Lodge Fwy to Fenkell | Greenlawn | John C Lodge Fwy | Fenkell | 2 | 0.1581
2021 | Class A | Greydale from Curtis to Pickford | Greydale | Curtis | Pickford | 1 | 0.15031
2021 | Class B | Guilford From Harper to Southampton | Guilford | Harper | Southampton | 4 | 0.56818 |  | DWSD Coordination Required
2021 | Class A | Hanover from LaSalle Garden to W Grand Blvd | Hanover | LaSalle Garden | W Grand Blvd | 5 | 0.2831
2021 | Class A | Harding from Jefferson to Edlie | Harding | Jefferson | Edlie | 5 | 0.17
2021 | Class A | Helen from Mack to Gratiot | Helen | Mack | Gratiot | 5 | 0.59
2021 | Class A | Keystone from E Outer Drive to Amrad | Keystone | E Outer Drive | Amrad | 3 | 0.25691 |  | DTE Coordination Needed
2021 | Class A | Lesure From Keeler to Dead End (S) | Lesure | Keeler | Dead End (S) | 2 | 0.066288
2021 | Class A | Longview From Conner to Chalmers | Longview | Conner | Chalmers | 3 | 0.95701
2021 | Class A | Lozier from Alter Rd to Barham | Lozier | Alter Rd | Barham | 6 | 0.18 |  | DTE Coordination Needed
2021 | Class A | Manor from Intervale to Jefferies Fwy | Manor | Intervale | Jefferies Fwy | 7 | 0.3852
2021 | Class A Class B | Mansfield From Chicago to Plymouth | Mansfield | Chicago | Plymouth | 7 | 0.5
2021 | Class A | Mapleridge From Gratiot to Hayes | Mapleridge | Gratiot | Hayes | 4 | 0.83
2021 | Class A | Maxwell from Forest to Canfield | Maxwell | Forest | Canfield | 5 | 0.15
2021 | Class A | Mendota from Kendall to Schoolcraft | Mendota | Kendall | Schoolcraft | 7 | 0.12494
2021 | Class A Class B | Moenart from E Outer Drive to 8 Mile | Moenart | E Outer Drive | 8 Mile | 3 | 0.48398 |  | DTE Coordination Needed
2021 | Class A | Northlawn from Chalfonte to Lyndon | Northlawn | Chalfonte | Lyndon | 2 | 0.34472
2021 | Class A | Northwestern from Grand River to Dexter | Northwestern | Grand River | Dexter | 5 | 0.1361
2021 | Class A | Nottingham From Morang to Grayton | Nottingham | Morang | Grayton | 4 | 0.34432
2021 | Class A | Oakfield from Pembroke to Eight Mile | Oakfield | Pembroke | Eight Mile | 2 | 0.48056
2021 | Class A | Oakfield from Pembroke to Seven Mile | Oakfield | Pembroke | Seven Mile | 2 | 0.48
2021 | Class B | Ohio from Chalfonte to Lyndon | Ohio | Chalfonte | Lyndon | 2 | 0.34507
2021 | Class A | Omira From Eight Mile to Seven Mile | Omira | Eight Mile | Seven Mile | 3 | 1
2021 | Class A | Orangelawn From Wyoming to Mendota | Orangelawn | Wyoming | Mendota | 7 | 0.31
2021 | Class A | Parker from Gratiot to Hendrie | Parker | Gratiot | Hendrie | 5 | 0.24
2021 | Class A | Payton From Morang to Dead End (W) | Payton | Morang | Dead End (W) | 4 | 0.10625
2021 | Class A | Pinehurst From Santa Maria to Six Mile | Pinehurst | Santa Maria | Six Mile | 2 | 0.12689
2021 | Class A | Poe from W Grand Blvd to Seward | Poe | W Grand Blvd | Seward | 5 | 0.50927
2021 | Class A | Riad From Moross to Casino | Riad | Moross | Casino | 4 | 0.27917
2021 | Class A | Riverside from Korte to Dead End (S). | Riverside | Korte | Dead End (S). | 4 | 0.22 |  | DWSD Coordination Required
2021 | Class A | Rohns From Goethe to Mack | Rohns | Goethe | Mack | 5 | 0.1 |  | DTE Coordination Needed
2021 | Class A | Roselawn from Davison to Intervale | Roselawn | Davison | Intervale | 7 | 0.38335
2021 | Class A | Rosemary From Dickerson to Chalmers | Rosemary | Dickerson | Chalmers | 4 | 0.67
2021 | Class A | Rosemary From Gratiot to Dickerson | Rosemary | Gratiot | Dickerson | 4 | 0.67
2021 | Class A | Seminole from Sylvester to Canfield | Seminole | Sylvester | Canfield | 5 | 0.17
2021 | Class A | Seneca from Gratiot to Warren | Seneca | Gratiot | Warren | 5 | 0.43
2021 | Class A | Seward from 3rd to John C Lodge Fwy | Seward | 3rd | John C Lodge Fwy | 5 | 0.14958 |  | DWSD Coordination Required
2021 | Class A | Seward from John C Lodge Fwy to Poe | Seward | John C Lodge Fwy | Poe | 5 | 0.26683
2021 | Class A | Sharon from Edsel Ford to Dead End N. | Sharon | Edsel Ford | Dead End N. | 6 | 0.037879
2021 | Class A | Somerset from Mack to Breman | Somerset | Mack | Breman | 4 | 0.35 |  | DTE Coordination Needed
2021 | Class A | St. Clair from Shoemaker to Mack | St. Clair | Shoemaker | Mack | 4 | 1.0038
2021 | Class A | Temple from Cass to Woodward | Temple | Cass | Woodward | 6 | 0.20315
2021 | Class A | Townsend from Canfield to Pulford | Townsend | Canfield | Pulford | 5 | 0.25
2021 | Class A | Tuller from Eaton to Lyndon | Tuller | Eaton | Lyndon | 7 | 0.18758
2021 | Class A | Wade from Connor to Ansbury | Wade | Connor | Ansbury | 3 | 0.55
2021 | Class A | Waverly from 12th to Woodrow Wilson | Waverly | 12th | Woodrow Wilson | 5 | 0.16
2021 | Class A | Wayburn from Waveney to Warren | Wayburn | Waveney | Warren | 4 | 0.7 |  | DTE Coordination Needed
2021 | Class A | Winthrop from James Couzens Fwy to Saint Martins | Winthrop | James Couzens Fwy | Saint Martins | 2 | 0.50739
2021 | Class A | Yacama from Eight Mile to Seven Mile | Yacama | Eight Mile | Seven Mile | 3 | 1
2021 | Class A | Yorkshire from Mack to Warren | Yorkshire | Mack | Warren | 4 | 0.88 |  | DTE Coordination Needed

## 2021 Class C
Target Year | Road Type | Project | Street | From | To | District Number | Length | Project Notes | Utility Status
2021 | Class C | Gilroy from Deacon to Beatrice | Gilroy | Deacon | Beatrice | 6 | 0.049 | 2019/2020 Carryover
2021 | Class C | Panama from Springwells to Cecil | Panama | Springwells | Cecil | 6 | 0.27 | 2019/2020 Carryover
2021 | Class C | Curtis from Berg to Redfern | Curtis | Berg | Redfern | 1 | 0.13 | 2020 Carryover
2021 | Class C | Abington from Joy to Dead End | Abington | Joy | Dead End | 4 | 0.02
2021 | Class C | Barrett from Harper to Maiden | Barrett | Harper | Maiden | 3 | 0.2
2021 | Class C | Bremen from Buckingham to Chatsworth | Bremen | Buckingham | Chatsworth | 5 | 0.13 |  | DTE Coordination Needed
2021 | Class C | Brinkett from Crane to Holcomb | Brinkett | Crane | Holcomb | 1 | 0.099
2021 | Class C | Cambridge from Fielding to Burt | Cambridge | Fielding | Burt | 1 | 0.12
2021 | Class C | Cambridge from Shaftsbury to Grandville | Cambridge | Shaftsbury | Grandville | 5 | 0.055
2021 | Class C | Fargo from Southfield to Stahelin | Fargo | Southfield | Stahelin | 6 | 0.342
2021 | Class C | Heyden from Vassar to Pembroke | Heyden | Vassar | Pembroke | 1 | 0.239
2021 | Class C | Longacre From Chicago to Dead End | Longacre | Chicago | Dead End | 7 | 0.05
2021 | Class C | Milbank from Sherwood to Concord | Milbank | Sherwood | Concord | 2 | 0.048
2021 | Class C | Monica from Fenkell to Chalfonte | Monica | Fenkell | Chalfonte | 6 | 0.121
2021 | Class C | Omaha from Electric to Bassett | Omaha | Electric | Bassett | 6 | 0.323
2021 | Class C | Pilgrim from Meyers to Appoline | Pilgrim | Meyers | Appoline | 4 | 0.044
2021 | Class C | Rosewood from Cadieux to Grayton | Rosewood | Cadieux | Grayton | 2 | 0.107 |  | DTE Coordination Needed
2021 | Class C | Santa Maria from Schaefer to Snowden | Santa Maria | Schaefer | Snowden | 1 | 0.095
2021 | Class C | St. Martins from Greenview to Sunderland | St. Martins | Greenview | Sunderland | 1 | 0.0155
2021 | Class C | St. Martins from Pierson to Evergreen | St. Martins | Pierson | Evergreen | 1 | 0.371
2021 | Class C | Trinity from Puritan to Fenkell | Trinity | Puritan | Fenkell | 1 | 0.5
2021 | Class C | Trojan from Rosemont to Southfield | Trojan | Rosemont | Southfield | 2 | 0.097
2021 | Class C | Tuller from Fenkell to Chalfonte | Tuller | Fenkell | Chalfonte | 1 | 0.128
2021 | Class C | Vassar from Pierson to Westmoreland | Vassar | Pierson | Westmoreland | 1 | 0.477
2021 | Class C | Vaughan from Pembroke to Vassar | Vaughan | Pembroke | Vassar | 1 | 0.248
2021 | Class C | Verne from Huntington to Evergreen | Verne | Huntington | Evergreen | 4 | 0.197
2021 | Class C | Voight from Barham to Alter Rd | Voight | Barham | Alter Rd | 4 | 0.194 |  | DTE Coordination Needed
2021 | Class C | Waveney from Alter Rd to Somerset | Waveney | Alter Rd | Somerset | 1 | 0.343 |  | DTE Coordination Needed

## 2020 Carryover Deferred
Target Year | Road Type | Project | Street | From | To | District Number | Length | Project Notes | Utility Status
2023+ | Class A | Beverly Ct from Grand River to Joy | Beverly Ct | Grand River | Joy | 5 | 0.16 | 2020 Carryover | DTE Coordination Needed (2023)
2022+ | Class B | Clark Ct from Scotten to Fairbanks | Clark Ct | Scotten | Fairbanks | 6 | 0.07 | 2020 Carryover | DTE Coordination Needed (2022)
2022+ | Class A | Federal from Military to Livernois | Federal | Military | Livernois | 6 | 0.05 | 2020 Carryover | DTE Coordination Needed (2022)
2022+ | Class A | Leslie from Dexter to Livernois | Leslie | Dexter | Livernois | 7 | 0.59 | 2020 Carryover | DTE Coordination Needed (2022)
2022+ | Class A | Mansfield from Tireman to Dead End (N) | Mansfield | Tireman | Dead End (N) | 7 | 0.17 | 2020 Carryover | DTE Coordination Needed (2022)
2022+ | Class A | Mettetal from Tireman to Dead End (N) | Mettetal | Tireman | Dead End (N) | 7 | 0.36 | 2020 Carryover | DTE Coordination Needed (2022)
2022+ | Class A | Military from Plumer to Federal | Military | Plumer | Federal | 6 | 0.12 | 2020 Carryover | DTE Coordination Needed (2022)
2022+ | Class A | Military from Toledo to Cadet | Military | Toledo | Cadet | 6 | 0.3 | 2020 Carryover | DTE Coordination Needed (2022)
2022+ | Class A | Porter from Clark to Lansing | Porter | Clark | Lansing | 6 | 0.13 | 2020 Carryover | DTE Coordination Needed (2022)