## Sheet1
PW7035A - HMA Speed Hump Locations on Hold
** UPDATED on 09/08/21 **
Location | [5 empty] | Start Date | Resolution Date | Main in Road or Berm | Notes
|  |  |  | DWSD - Water | DWSD - Sewer
District No. | Street | From | To
4 | Drexel | Averhill | Korte | 2 |  |  |  |  | Water - procurement?
4 | Farmbrook | Warren | Frankfort | 1 |  |  | 2021-10-15 |  | Water main replacement
4 | Farmbrook | Berden | Chandler Park | 2 |  |  | 2021-10-15 |  | Water main replacement
4 | Guilford | Cornwall | Warren | 1 |  |  |  |  | Road sewer repair?
4 | Guilford | Harper | Chandler Park | 2 |  |  | 2021-11-15 |  | Water main replacement
4 | Hereford | Chester | Minerva | 1 |  |  |  |  | Easement sewer repair?
4 | Hereford | Minerva | Chandler Park | 3 |  |  | 2021-12-15 |  | Water main replacement
4 | Hereford | Chandler Park | Munich | 7 |  |  |  |  | Easment sewer repair?
4 | Oldtown | Harper | Linville | 3 |  |  |  |  | Easement sewer repair?
4 | Oldtown | Linville | Chandler Park | 1 |  |  |  |  | Road sewer repair?
4 | Piper | Averhill | Scripps | 4 |  |  |  |  | Water - procurement?
4 | Riverside | Scripps | Korte | 2 |  |  |  |  | Water - procurement?
4 | Scripps | Eastlawn | Newport | 1 |  |  |  |  | Water - procurement?
5 | Delaware | Bethune | Third | 1 |  |  | 2021-10-15 |  | Water main replacement
5 | Lawton | Cortland | Sturtevant |  | 1 |  |  |  | nothing on GIS
|  |  |  | 31 | 1
32