## Sheet1
PW7035A - HMA Speed Hump Locations on Hold
** UPDATED on 09/09/21 **
Location | [5 empty] | Start Date | Resolution Date | Main in Road or Berm | Notes
|  |  |  | DWSD - Water | DWSD - Sewer
District No. | Street | From | To | [6 empty] | DWSD contract number
4 | Drexel | Averhill | Korte | 2 |  |  |  |  | Water - procurement? | WS-713: Jefferson-Chalmers Neighborhood water main work
4 | Farmbrook | Warren | Frankfort | 1 |  |  | 2021-10-15 |  | Water main replacement | WS-712: Cornerstone Village Water main work
4 | Farmbrook | Berden | Chandler Park | 2 |  |  | 2021-10-15 |  | Water main replacement | WS-712: Cornerstone Village Water main work
4 | Guilford | Cornwall | Warren |  | 1 |  |  |  | Road sewer repair? | DWS-908: Sewer work in Cornerstone Village
4 | Guilford | Harper | Chandler Park | 2 |  |  | 2021-11-15 |  | Water main replacement | WS-712: Cornerstone Village Water main work
4 | Hereford | Chester | Minerva |  | 1 |  |  |  | Easement sewer repair? | DWS-908: Sewer work in Cornerstone Village
4 | Hereford | Minerva | Chandler Park | 3 |  |  | 2021-12-15 |  | Water main replacement | WS-712: Cornerstone Village Water main work
4 | Hereford | Chandler Park | Munich |  | 7 |  |  |  | Easement sewer repair? | DWS-908: Sewer work in Cornerstone Village
4 | Oldtown | Harper | Linville |  | 3 |  |  |  | Easement sewer repair? | DWS-908: Sewer work in Cornerstone Village
4 | Oldtown | Linville | Chandler Park |  | 1 |  |  |  | Road sewer repair? | DWS-908: Sewer work in Cornerstone Village
4 | Piper | Averhill | Scripps | 4 |  |  |  |  | Water - procurement? | WS-713: Jefferson-Chalmers Neighborhood water main work
4 | Riverside | Scripps | Korte | 2 |  |  |  |  | Water - procurement? | WS-713: Jefferson-Chalmers Neighborhood water main work
4 | Scripps | Eastlawn | Newport | 1 |  |  |  |  | Water - procurement? | WS-713: Jefferson-Chalmers Neighborhood water main work
5 | Delaware | Woodward | Third | 1 |  |  | 2021-10-15 |  | Water main replacement | WS-718 Water main work
|  |  |  | 18 | 13
31