## Sheet1
PW7035A - 2021 HMA Speed Hump Installation
Forecasting Location Requirements to Reach Contract Value
Quantities Through Date: | 2021-08-16
Totals
Locations Currently in Contract | 1825
Locations Required to reach 2000 | 175
Additional Locations Required to achieve 50,000 LFT @ Current Contract Value | 67
Additional Locations Available Due to Max Contractor OT of $52,500 | 26
Calculations
Description of Speed Hump | LFT/Hump | Average LFT/Hump | Number of Humps
Estimated | 50000 | 25 | 2000
Installed Through Date | 36189.629 | 24.1909 | 1496
Projected Footage to Install 2000 Speed Humps | 12192.228 | 24.1909 | 504
Projected Footage after 2000 Speed Humps Installed | 48381.857 | 24.1909 | 2000
Remaining Footage Available | 1618.143 | 24.1909 | 66.8905
Projected Footage to Install 2000 Speed Humps
Number of Locations Estimated | 2000
Number of Locations in Contract | 1825
Number of Locations Available | 1655
Number of Locations Completed | 1496 | LFT/Hump | LFT
Number of Locations Pending Installation | 159 | 24.1909 | 3846.3576
Number of Locations on Hold | 170 | 24.1909 | 4112.4578
Number of Locations Missing from Contract | 175 | 24.1909 | 4233.4125
12192.228
Additional Humps due to Max Contractor OT Reclamation = $52,500
Original Contract Amount | 4118500
Current Contract Amount | 4066000
Contractor OT Reclamation | 52500
Cost of Hump Per PavtMrkg | $139.50/Ea | 2 Ea/Hump | $279.00/Hump
Cost of Hump Per Linear Foot | $71.21/Ft | 24 Ft/Hump | $1722.57/Hump
Cost to Install One Speed Hump |  |  | $2001.57/Hump
Number of Speed Humps Able to Install with $52,500 = 26 Locations