## ALL Parties
PW7035A - HMA Speed Hump Locations on Hold
** UPDATED on 09/17/21 **
Location | [9 empty] | Affected Speed Humps | [9 empty] | Resolution Date | Resolution Date
[7 empty] | Resto |  | Abandonment | DTE GRP | Residential Milling Project | Class C Streets Project | DPW 2020 Carryover | DWSD - Water | DWSD - Sewer | Residential Rejection | 2022? Resurfacing | Vacancy | Concrete Blocks
District No. | Street | From | To | Activity Name | Start | Finish | Start | Finish
3 | Binder | E Lantz | Outer Drive | [15 empty] | 1 | Speed Cushion
3 | Buffalo | 7 Mile | Emery | [15 empty] | 2 | Speed Cushion
3 | Buffalo | Amrad | Hamlet | [15 empty] | 1 | Speed Cushion
3 | E Lantz | Coventry | Keating | [13 empty] | 1 |  |  | Poor Pavement
3 | E Lantz | Fenelon | Conley | [13 empty] | 1 |  |  | Poor Pavement
3 | E Lantz | Syracuse | Albany | [14 empty] | 1 |  | N/A
3 | E Winchester | Hull | Greeley | [13 empty] | 1 |  |  | Poor Pavement
3 | Eureka | E Lantz | E Outer Drive | [13 empty] | 2 |  |  | Poor Pavement
3 | Healy | Stockton | Hilldale | [13 empty] | 1 |  |  | Poor Pavement
3 | Keystone | Amrad | E Outer Drive | [7 empty] | 2 | [8 empty] | not started
3 | Omira | Emery | 7 Mile | [7 empty] | 2 | [8 empty] | conditioning
3 | Shields | E Lantz | Outer Drive | [15 empty] | 2 | Speed Cushion
3 | Sparling | Rupert | Luce | [12 empty] | 1 |  |  |  | Pending TED
3 | St Louis | Hildale | 7 Mile | [15 empty] | 1 | Speed Cushion
4 | Audubon | Warren | Wallinford | [7 empty] | 6 | [8 empty] | Leveled
4 | College | Algonac | Elmo | Install Services - College (Conner & Gunston) | 08-30-21 A | 09-01-21 A | 2021-09-20 | 2021-09-22 | Done | 1 | 1 | [8 empty] | Leveled | 8/30 Lead - 9/15 Rest
4 | Corbett | Ansbury | Park | [6 empty] | 1 | [9 empty] | 10/19 Lead - 11/16 Rest
4 | Drexel | Averhill | Korte | [10 empty] | 2 | [5 empty] | 2022
4 | Farmbrook | Warren | Frankfort | [10 empty] | 1 | [5 empty] | 2021-10-15
4 | Farmbrook | Berden | Chandler Park | [10 empty] | 2 | [5 empty] | 2021-10-15
4 | Guilford | Cornwall | Warren | [11 empty] | 1 |  |  |  |  | TBD
4 | Guilford | Harper | Chandler Park | [7 empty] | 2 |  |  | 2 | [5 empty] | 2021-11-15 | not started
4 | Hereford | Chester | Southhampton | [10 empty] | 3 | 2 |  |  |  |  | 2021-12-15
4 | Hereford | Southhampton | Munich | [6 empty] | 6 |  |  |  |  | 6 |  |  |  |  | TBD | 9/16 Rest
4 | Hurlbut | Moffat | Warren | [13 empty] | 2 |  |  | Poor Pavement
4 | Oldtown | Harper | Chandler Park | [11 empty] | 4 |  |  |  |  | TBD
4 | Piper | Averhill | Scripps | [10 empty] | 4 | [5 empty] | 2022
4 | Riverside | Scripps | Korte | [7 empty] | 2 |  |  | 2 | [5 empty] | 2022 | not started
4 | Saint Patrick | Gunston | Bradford | [13 empty] | 2 |  |  | Poor Pavement
4 | Scripps | Eastlawn | Newport | [10 empty] | 1 | [5 empty] | 2022
4 | Somerset | Bremen | Mack | [7 empty] | 3 | [8 empty] | leveled
5 | Atkinson | Linwood | La Salle | [12 empty] | 1 |  |  |  | Pending TED
5 | Delaware | Bethune | Third | [10 empty] | 1 | [5 empty] | 2021-10-15
5 | Eliot | John R | Brush | [15 empty] | 1 | Speed Cushion
5 | Lawton | Glynn | Calvert | [13 empty] | 1 |  |  | Poor Pavement
5 | Leland | Joseph | Mitchell | [13 empty] | 1 |  |  | Poor Pavement
5 | Northwestern | Grand River | Holmur | [7 empty] | 1 | [8 empty] | not started
5 | Seward | Poe | Third | [7 empty] | 3 | [8 empty] | not started
5 | Wildemere | W Grand Blvd | Lothrop | [13 empty] | 1 |  |  | Poor Pavement
6 | 18th | W Lafayette | Howard | [6 empty] | 1 | [9 empty] | Main? 12/10 - 12/15 Rest
6 | Casper | Pitt | W Vernor | [6 empty] | 1 | [9 empty] | 9/7 Lead - 9/21 Rest
6 | Military | Federal | Plumer | [6 empty] | 1 |  |  | 1 | [6 empty] | on hold | 2022 Coord
6 | Military | W Vernor | McMillan | [6 empty] | 1 |  |  | 1 | [6 empty] | on hold | 2022 Coord
6 | New Town | Victoria Park N | Victoria Park S | [15 empty] | 1 | Speed Cushion
6 | Norman | Belle | Pitt | [6 empty] | 2 | [9 empty] | 11/12 Lead - 11/17 Rest
6 | Radcliffe | Mather | Central | [12 empty] | 1 |  |  |  | Pending TED
[10 empty] | 14 | 22 | 0 | 2 | 18 | 13 | 3 | 13 | 1 | 9
[11 empty] | 24 |  |  | 31 |  | 13
68

## Sheet1
|  |  |  | Services |  |  | Restoration |  | Abandon
District No. | Street | From | To | Activity Name | Services Start | Services Finish | Resto Start | Resto Finish
4 | College | Algonac | Elmo | Install Services - College (Conner & Gunston) | 08-30-21 A | 09-01-21 A | 2021-09-20 | 2021-09-22 | Done
4 | Corbett | Ansbury | Park | Install Services - Corbett 1 (Annsbury & Coplin) | 2021-10-19 | 2021-11-05 | 2021-11-08 | 2021-11-10 | 11/85/21
4 | Hereford | Southhampton | Munich | We don’t have work in this are
6 | 18th | W Lafayette | Howard | We don’t have services in this are, Main install will be at 10/13/2021 | 2021-10-13 | 2021-10-14 | 2021-12-09 | 2021-12-12 | 2021-12-06
6 | Casper | Pitt | W Vernor | Out work off of this segements, only tie in in W Vernor in 11/2/2021
6 | Military | Federal | Plumer | We don’t have any work in this area
6 | Military | W Vernor | McMillan | We don’t have any work in this area
6 | Norman | Belle | Pitt | Only tie in at W Vernor